## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
81 | Erection And Completion Of Maternity Wing At Myanga Dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Bumula | Kimaeti | 0.56714/34.38875 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 4000000 | 3435280 | 3435280 | CGB |  | 3435280 | 0 | 1435300 | 41.78% | 1435300 |  | 1999980 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Waiting bay not completed
150 | Construction Of Nakhwana Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti | 0.580498/34.403357 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2896320 | 2896320 | CGB |  | 2896320 | 0 | 2896320 | 100% | 2896320 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project needs fencing
165 | Construction Of Bitobo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti | 0.624082/34.388964 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3034408 | 2898643 | 2898643 | CGB |  | 2898643 | 0 | 1020359 | 35.2% | 1020359 |  | 1878284 | Oongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Slow progress
193 | Construction Of Bitobo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3034408 | 2898643 | 2898643 | CGB |  | 2898643 | 0 | 1020359 | 35.2% | 1020359 |  | 1878284 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
229 | Completion Of Maternity Wing At Kimaeti Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Bumula | Kimaeti | 0.60416/34.40745 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1900000 | 4593250 | 4593250 | CGB |  | 4593250 | 0 | 4523414.2 | 98.48% | 4523414.2 |  | 69835.8 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | Ceiling board not in good use
230 | Construction Of Myanga Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti | 0.56714/34.38775 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 3000000 | 0 | 0 | CGB |  | 0 | 0 |  | #DIV/0! |  |  | 0 | [7 empty] | No | complete | Financial | Yes | [5 empty] | Needs septic tank
264 | Purchase of one acre of land and Construction of Bitobo Dispensary | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services in the area | acres of land purchased |  |  | Bumula | Kimaeti | 0.624082/34.388964 | [10 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | [7 empty] | No | complete | Financial | Yes | [5 empty] | Land purchased by cdf
265 | Purchase of 1 acre land and Construction of Myanga dispensary | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Bumula | Kimaeti | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Ongoing | [6 empty] | No | complete | Financial | Yes
78 | Upgrading of Lunakwe Mkt-Lumboka Mkt-Mulukoba Pri | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41663 | 41780 |  | 4298322 | 4298322 | 4298322 | County Government of Bungoma |  | 4298322 |  | 4298322 | 100% | 4298322 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
199 | Periodic Maintenance of Kimwanga - Tabala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.59539/34.44149 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43233 |  | 4086877 | 4086877 | 4086877 | County Government of Bungoma |  | 4086877 |  | 4086877 |  | 4086877 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Drainage to be improved
200 | Periodic Maintenance of Myanga - Apokori Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.56714/34.392261 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43231 |  | 4086877 | 4086877 | 4086877 | County Government of Bungoma |  | 4086877 |  | 4086877 |  | 4086877 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Drainage to be improved
201 | Periodic Maintenance of Moses Mayubani Wamalwa | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43123 | 43239 |  | 10177641460 | 10177641460 | 10177641460 | County Government of Bungoma |  | 10177641460 |  | 10177641460 |  | 10177641460 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
202 | Periodic Maintenance of Roads In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43235 |  | 4086877 | 4086877 | 4086877 | County Government of Bungoma |  | 4086877 |  | 4086877 | 95.45% | 4086877 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
369 | Grading of Lelekwe - Syombe - Kimaeti Secondary Road | Grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43602 |  | 7497776 | 7497776 | 7497776 | County Government of Bungoma |  | 7497776 |  | 7497776 |  | 7497776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
370 | Periodic Maintenance of Syombe - Tulukuyi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.592714/34.393492 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43480 | 43609 |  | 7497776 | 7497776 | 7497776 | County Government of Bungoma |  | 7497776 |  | 7497776 |  | 7497776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Drainage to be improved
371 | Periodic Maintenance of Raods In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43598 |  | 7497776 | 7497776 | 7497776 | County Government of Bungoma |  | 7497776 |  | 7497776 | 99.9% | 7497776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
372 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
548 | Upgrading of Tabala-Nakhwana Bridge | Road improvement works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.579568/34.425752 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
549 | Construction of Kitingia - Sihilila Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Bumula | Kimaeti | 0.603849/34.389250 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10177641460 | 10177641460 | 10177641460 | County Government of Bungoma |  | 10177641460 |  | 10177641460 |  | 10177641460 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Refilling was poorly done
574 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
801 | Periodic Maintenance of Carmel View - Tabala - Mayanja Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti | 0.59795/34.42866 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44338 | 44369 | 9991743.38 | 9991743.38 | 9991743.38 | County Government of Bungoma |  | 9991743.38 |  | 9991743.38 |  | 9991743.38 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Drainage to be improved
802 | Periodic Maintenance of Myanga - Syombe - Sichekeni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.58071/34.41133 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44333 |  | 6886572 | 6886572 | 6886572 | County Government of Bungoma |  | 6886572 |  | 6886572 |  | 6886572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Improve draianage
803 | Periodic Maintenance of Masielo Sec - Napara Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.630835/34.433598 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44329 |  | 6886572 | 6886572 | 6886572 | County Government of Bungoma |  | 6886572 |  | 6886572 |  | 6886572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintenance to be enhanced
804 | Construction of Tabala - Nakhwana Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44330 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
805 | Periodic Maintenance of Roads In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44339 |  | 6886572 | 6886572 | 6886572 | County Government of Bungoma |  | 6886572 |  | 6886572 | 99.98% | 6886572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
806 | Periodic Maintenance of Carmel View - Tabala - Mayanja Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44335 |  | 9991743.38 | 9991743.38 | 9991743.38 | County Government of Bungoma |  | 9991743.38 |  | 9991743.38 | 89.43% | 9991743.38 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1132 | Periodic Maintenance of Wambu - Maseno Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.55859/34.38533 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44698 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Drainage to be improved
1133 | Periodic Maintenance of Kimaeti - Syombe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44694 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1134 | Periodic Maintenance of Kitingia - Sihilila Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.598059/34.380258 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44705 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs culverts and enhanced drainage
1135 | Periodic Maintenance of Kitabisi - Wekelekha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44702 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1136 | Periodic Maintenance of Japhesa - Masafwa - Nakhwana - Santos Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti | 0.60349/34.40752 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44699 | 44730 | 8979023.5 | 8979023.5 | 8979023.5 | County Government of Bungoma |  | 8979023.5 |  | 8979023.5 |  | 8979023.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The bridge at Nakhwana needs repair
1137 | Construction of Kimwanga - Wakafura (Road) Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.59688/34.44246 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44696 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs repair and maintenance
1138 | Periodic Maintenance of Roads In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44700 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 | 88.31% | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1139 | Routine Maintenance Of Japhesa - Masafwa - Nakhwana - Santos Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44697 |  | 8979023.5 | 8979023.5 | 8979023.5 | County Government of Bungoma |  | 8979023.5 |  | 8979023.5 | 98.97% | 8979023.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1424 | Periodic Maintenance of Myanga - Tulienge Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45067 |  | 5801375 | 5801375 | 5801375 | County Government of Bungoma |  | 5801375 |  | 5801375 |  | 5801375 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1425 | Periodic Maintenance of Mt. Carmel - Myanga Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45056 |  | 4697826 | 4697826 | 4697826 | County Government of Bungoma |  | 4697826 |  | 4697826 |  | 4697826 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1426 | Upgrading of Nakhwana - Syombe Drift | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.58118/34.41133 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45067 |  | 9974337.72 | 9974337.72 | 9974337.72 | County Government of Bungoma |  | 9974337.72 |  | 9974337.72 |  | 9974337.72 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Drainage to be improved
1427 | Construction of Khasolo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45059 |  | 10177641460 | 10177641460 | 10177641460 | County Government of Bungoma |  | 10177641460 |  | 10177641460 |  | 10177641460 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1428 | Periodic Maintenance of Myanga - Tulienge Bridge Road In Kimaeti Ward |  | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.57005/34.39261 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45066 |  | 5801375 | 5801375 | 5801375 | County Government of Bungoma |  | 5801375 |  | 5801375 | 99.31% | 5801375 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | There's no bridge
1429 | Periodic Maintenance of Mt. Carmel - Myanga Mkt Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.55962/34.412272 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45061 |  | 4697826 | 4697826 | 4697826 | County Government of Bungoma |  | 4697826 |  | 4697826 | 98.87% | 4697826 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No work done
1430 | Framework Contracts For Maintenance Of Roads In Kanduyi And Bumula Sub Counties | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45070 |  | 9974337.72 | 9974337.72 | 9974337.72 | County Government of Bungoma |  | 9974337.72 |  | 9974337.72 | 99.48% | 9974337.72 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1671 | Periodic Maintenance of Nambuchi - Miyanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.59795/34.42866 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45435 |  | 6131760 | 6131760 | 6131760 | County Government of Bungoma |  | 6131760 |  | 6131760 |  | 6131760 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The road needs drainage
1672 | Periodic Maintenance of Chief Naulikha - Nakalila - Wakafura - Masielo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.606700/34.422848 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45426 |  | 3740478 | 3740478 | 3740478 | County Government of Bungoma |  | 3740478 |  | 3740478 |  | 3740478 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintenance to be enhanced
1673 | Periodic Maintenance of Nambuchi - Miyanga Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45428 |  | 6131760 | 6131760 | 6131760 | County Government of Bungoma |  | 6131760 |  | 6131760 | 100% | 6131760 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1674 | Periodic Maintenance of Impreza - Bitobo Dispensary - Tunduli Junction Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.609398/34.390078 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45430 |  | 6002304 | 6002304 | 6002304 | County Government of Bungoma |  | 6002304 |  | 6002304 | 98.35% | 6002304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The road needs culvert
1675 | Periodic Maintenance of Chief Naulikha - Nakalila - Wakafura - Masielo Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti | 0.606700/34.432848 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45434 |  | 3740478 | 3740478 | 3740478 | County Government of Bungoma |  | 3740478 |  | 3740478 | 99.97% | 3740478 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Routine maintenance needed
55 | Proposed Renovation and refurbishment of 5 units county staff quarters. | Renovation and refurbishment | To enhance revenue collection | Five units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2021/22 | 44594 | 31/3/2022 | 20/4/2022 | 3000000 | 2494800 | 2494800 | CGB |  | 2494800 |  | 2494800 | 100% | 2494800 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
120 | Purchase Of One Acre For Kambini Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Kambini Dispensary Purchased | 3110599 | Ward based projects | Bumula | Kimaeti |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42959 | 43376 | 13/5/2018 | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
21 | Construction of 1 NO. ECDE classroom at Syombe primary school and renovation Works at Masielo, Tulukuyi, Bukirimo, Miyanga, Kimaeti, Nakhwana and Kimwanga primary schools. | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti | 0.592120/34.437247-0.590302/34.378641-0.620869/34.436064 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 6000000 | 5998960 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 5998960 | 100% | 5998960 | 0 | 0 | Completed | [15 empty] | Needs pit latrines
82 | CONSTRUCTION OF ECDE CLASSROOM AT Nakwana,Bitobo.Kitabisi | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti | 0.623225/34.387510 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3600000 | 3596750 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 2864480 | 79.64% | 2864480 | 732270 | 732270 | Complete and in use | 1
114 | Construction Of 1 No. Ecde Classroom At Khasolo, Radi And Mwiyenga Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti | 0.58216/34.41029-0.628073/34.392041 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3600000 | 1075304 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 0 | 0% | 0 | 1075304 | 1075304 | complete and in use | 1 | [14 empty] | Needs extra class
145 | Proposed Erection And Completion Of 1 No. Ecde At Kimaeti, Myanga And Kimwanga Primary Schools In Kimaeti Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti | 0.59323/34.43906-0.660828/34.430462 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3600000 | 3562000 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3562000 | 100% | 3562000 | 0 | 0 | complete and in use | 1 | [14 empty] | Needs extra class
172 | Construction Of 1 Ecde Classroom At Napara, Silila And Bukirimo Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti | 0.640471/34.410254-0.665096/34.431386-0.56061/34.377 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 3600000 | 3582010 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3582010 | 100% | 3582010 | 0 |  | complete and in use | 1 | [14 empty] | Needs extra class
198 | The Proposed And Completion Of 1 N0 Classroom At Masielo And Tulukuyi Primary School In Kimaeti Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti | 0.57371/34.39434 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2000000 | 2373810 | 2000000 | County Government of Bungoma | N/A | 2000000 |  | 2373810 | 100% | 2373810 | 0 |  | complete and in use | 1
17 | Upgrading of Mwiyenga Primary and Matokho Boreholes in Kimaeti/Bumula wards | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45544 | 45546 | 45546 | 6000000 | 5777960 | 5777960 | FLLOCA | N/A | 5777960 | 0 | 0 | 100% | 5777960 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
62 | Upgrading of Kimaeti Market Borehole in Kimaeti In Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | 0.60332/34.40717 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4988406 | 4988406 | CGB | N/A | 4988406 | 0 | 4988406 | 100% | 4988406 | 0 | 0 | Complete | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | The project needs piping
95 | Drilling and Equipping of Kitingia Primary Borehole and Rehabilitation of Tabara Primary Water Project | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and equipped | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | Tabala-0.580146/34.431003, Kitingia 0.625662/34.391901 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4954502 | 4954502 | CGB | N/A | 4954502 | 0 | 4954502 | 100% | 4954502 | 0 | 0 | Complete | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
105 | Upgrading of Nakhwana primary borehole and drilling of Nambuchi borehole in kimaeti ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points;site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 1 borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | 0.588303/34.417372 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4000000 | 3976132 | 3976132 |  | N/A | 3976132 | 0 | 3976132 | 100% | 3976132 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
166 | Rehabilitation and upgrading of Khulwanda and Syombe boreholes | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 3000000 | 2939788 | 2939788 |  | N/A | 2939788 | 0 | 2939788 | 100% | 2939788 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
167 | DRILLING AND EQUIPPING OF SIHILILA PRIMARY BOREHOLE IN KIMAETI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2000000 | 1991720 | 1991720 |  | N/A | 1991720 | 0 | 1991720 | 100% | 1991720 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
195 | DRILLING AND EQUIPING OF BITOBO BOREHOLE AND PROTECTION 2 NO. WATER SPRINGS IN KIMAETI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 2 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | 0.64082/34.388964 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2500000 | 2233009 | 2233009 |  | N/A | 2233009 | 0 | 2233009 | 100% | 2233009 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Needs piping
196 | EXTENSION OF MYANGA WATER PROJECT | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | 0.56639/34.39087 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2700000 | 2573692 | 2573692 |  | N/A | 2573692 | 0 | 2573692 | 100% | 2573692 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | The storage tank burst
219 | REHABILITATION OF BUNJAKU SHALLOW WELL IN KIMAETI WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 well upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 500000 | 489520 | 489520 |  | N/A | 489520 | 0 | 489520 | 100% | 489520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
237 | DRILLING OF SYOMBE AND KIMAETI BOREHOLES IN KIMAETI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | 0.60131/34.39261 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 3800000 | 3780206 | 3780206 |  | N/A | 3780206 | 0 | 3780206 | 100% | 3780206 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | The project is not functioning due to mechanical problem
308 | ST. JUDE NAPARA GIRLS WATER PROJECT | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | 0.640323/34.422712 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 2000000 | 2000000 |  | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Need water kiosk
430 | Extension of nzowasco pipeline to kimaeti market | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3300000 | 3051900 | 3051900 |  | N/A | 3051900 | 0 | 3051900 | 100% | 3051900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
528 | with 6 Springs, 2 Shallow wells and 1 borehole | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump; Site identification; geological survey, drilling development, construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled, 2 wells constructed and 6 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3800000 | 3529200 | 3529200 |  | N/A | 3529200 | 0 | 3529200 | 100% | 3529200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
609 | Drilling and equip Kibabii TTC borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti | 0.57916/34.39668 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3480000 | 3480000 |  | N/A | 3480000 | 0 | 3480000 | 100% | 3480000 | 0 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | There was no enough water
17 | Construction of Kimaeti ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Kimaeti ward office constructed | 3111504 | Construction of non- residential buildings | Bumula | Kimaeti | 0.62513/34.403357 | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2023/24 | 45300 | 45415 | 45467 | 9500000 | 9453590 | 9500000 | County Government of Bungoma | - | 9453590 | - | 9453590 | 100% | 5875156 | 3578156 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Rehabilitation of cattle dips | Rehabilitation of cattle dips in Luuya, Kibisi, Bukembe, Lutaso, Tulumba, and Myanga Cattle Dips | To improve animal health and productivity | 6 Cattle dips rehabiliatated | 3110504 | Other infrastructure and civil works | Bumula | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44136 | 44139 | 14/3/2020 | 5000000 | 3486950 | 3548016 | County Government of Bungoma |  | 3486950 | 0 | 3486950 | 100% | 3486950 | 0 | 0 | Completed
| Construction of ablution block, fence and gate at Bumula Dairy FCS in Kimaeti Ward | Construction of ablution block, fence and gate at Bumula Dairy FCS in Kimaeti Ward | To enhance income generation among dairy farmers | 1 Ablution block constructed | 3110504 | Other infrastructure and civil works | Bumula | Kimaeti | 0.630835/34.433596 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 20/1/2024 | 24/5/2024 | 15/7/2024 | 8000000 | 5600000 | 5000000 | County Government of Bungoma |  | 5600000 | 0 | 4900000 | 88% | 4900000 | 700000 | 700000 | Completed
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Kimaeti |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
135 | Renovation of Myanga market | [6 empty] | Kimaeti | 0.566639/34.39087 |  |  | Kanduyi Enterprises | 2016/17 |  | Complete |  | 16692817.6 |  |  | CGG | [8 empty] | Complete | [15 empty] | Security lights,gates broken,draiange system needed
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti | 0.595737/34.403467 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti | 0.595737/34.403467 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti | 0.595737/34.403467 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti | 0.60448/34.40544 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
101 | Construction Of Fuchani And Napong'o Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensries constructed |  |  | Kanduyi | East Sang'alo | 0.469976/34.631480 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 7000000 | 6949440 | 6949440 | CGB |  | 6949440 | 0 | 6949440 | 100% | 6949440 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Needs equipments and expansion
151 | Construction Of Pit Latrines At Mechimeru Market | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | pit latrines constructed |  |  | Kanduyi | East Sang'alo | 0.501448/34.649801 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 1000000 | 969340 | 969340 | CGB |  | 969340 | 0 | 826613 | 85.28% | 826613 |  | 142727 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | Needs renovation
200 | Completion of Of Mechi Meru Matenity Wing | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | maternity wings completed |  |  | Kanduyi | East Sang'alo | 0.510021/34.663213 |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 2000000 | 2151145 | 2151145 | CGB |  | 2151145 | 0 | 2151145 | 100% | 2151145 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project is in use
201 | Construction Of Mumbule Matenity Wing | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings constructed |  |  | Kanduyi | East Sang'alo | 0.459187/34.607228 |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 2000000 | 2386421.6 | 2386421.6 | CGB |  | 2386421.6 | 0 | 2237978.1 | 93.78% | 2237978.1 |  | 148443.5 | Complete and not use | [6 empty] | No | complete | Financial | Yes | [5 empty] | The projec requires equipments
305 | Purchase of 1-acre land for Napong’o Dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Kanduyi | East Sang'alo |  |  | Ward Based | Health & Sanitation | 2015/16 | 42491 | 42705 | 42705 |  | 800000 | 800000 | CGB |  | 800000 | 0 | 800000 | 100% | 800000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
306 | Completion of mechimeru dispensary | Walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries completed |  |  | Kanduyi | East Sang'alo | o.510021/34.663213 |  | Ward Fund | Health & Sanitation | 2014/15 |  | 41883 | 42185 |  | 2360420 | 2360420 | CGB |  | 2360420 | 0 | 2148848 | 91.04% | 2148848 |  | 211572 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | Commissioned and in use
307 | Completion of Mechanical Works of Bulondo Dispensary | Mechanical works | To provide access and affordable health services within the community | dispensaries completed |  |  | Kanduyi | East Sang'alo |  |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42185 |  |  | 915147.2 | 915147.2 | CGB |  | 915147.2 | 0 | 915147.2 | 100% | 915147.2 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
309 | Construction of public toilet at Dorofu | Digging of 20ft deep fit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities within the market | Public toilets constructed |  |  | Kanduyi | East Sang'alo | 0.451142/34.615558 |  | Ward Based | Health & Sanitation | 2015/16 |  | 42467 | 42725 |  | 1197053 | 1197053 | CGB |  | 1197053 | 0 | 1197053 | 100% | 1197053 |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | Poorly managed and needs a committee in place
310 | Construction of Pit latrines | Digging of 20ft deep fit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities within the market | pit latrines constructed |  |  | Kanduyi | East Sang'alo |  |  | CEF | Health & Sanitation | 2016/17 | 42788 | 42877 | 42846 |  | 1255829 | 1255829 | CGB |  | 1255829 | 0 | 1255829 | 100% | 1255829 |  | 0 | complete and not in use | [6 empty] | No | complete | Financial | Yes
9 | Completion of Sang'alo Multipurpose Hall | Construction of multi-purpose hall | To promote and preserve culture and heritage. | Multipurpose hall constructed | 3110504 | other ifrastructure and civil works | Kanduyi | East Sang'alo |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Gender and Culture | 2022/23 | 27/11/2023 | 27/06/2024 |  | 21440351 | 20895126.4 | 5500000 | County Government of Bungoma | n/a | n/a | n/a | 5500000 | 26.32% | 5500000 | 15395126 | 15395126.4 | Completed | 0.9
163 | Construction of Khakula Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43243 |  | 13308964 | 13308964 | 13308964 | County Government of Bungoma |  | 13308964 |  | 13308964 |  | 13308964 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
164 | Periodic Maintenance of Wanjugu Junction - Chwele River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo | 0.425398/34.595670 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43112 | 43236 |  | 13308964 | 13308964 | 13308964 | County Government of Bungoma |  | 13308964 |  | 13308964 |  | 13308964 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs maintenance
S/No. | Periodic Maintenance of Dorofu - Lukhuna Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo | 0.453738/34.613573 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43238 |  | 13308964 | 13308964 | 13308964 | County Government of Bungoma |  | 13308964 |  | 13308964 |  | 13308964 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs periodic mainenance
166 | Periodic Maintenance of Roads In East Sangalo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43232 |  | 13308964 | 13308964 | 13308964 | County Government of Bungoma |  | 13308964 |  | 13308964 | 11.54% | 13308964 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
318 | Upgrading of Tungele Drift | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43484 | 43601 |  | 10071340 | 10071340 | 10071340 | County Government of Bungoma |  | 10071340 |  | 10071340 |  | 10071340 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
319 | Periodic Maintenance of Lutungu - Stephen Wanjitala - Tungele Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43489 | 43609 |  | 10071340 | 10071340 | 10071340 | County Government of Bungoma |  | 10071340 |  | 10071340 |  | 10071340 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs periodic maintenance
320 | Periodic Maintenance of Nuclear - Wekhima Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo | 0.522860/34.669860 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43607 |  | 10071340 | 10071340 | 10071340 | County Government of Bungoma |  | 10071340 |  | 10071340 |  | 10071340 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Requires periodic maintenance
321 | Periodic Maintenance of Roads I N East Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43597 |  | 10071340 | 10071340 | 10071340 | County Government of Bungoma |  | 10071340 |  | 10071340 | 97.03% | 10071340 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
322 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
509 | Periodic Maintenance of Koyabe - Lusaka - Bigshow - Nabutola - Ondele Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo | 0.500741/34.646524 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43973 |  | 7665772 | 7665772 | 7665772 | County Government of Bungoma |  | 7665772 |  | 7665772 |  | 7665772 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs periodic maintenance
510 | Upgrading of Mechimeru - Kimugui Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | East Sang'alo | 0.503431/34.650914 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43962 |  | 2949822 | 2949822 | 2949822 | County Government of Bungoma |  | 2949822 |  | 2949822 |  | 2949822 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs gravelling and grading
511 | Upgrading of Spot Improvement Of Mechimeru - Kimugui Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43969 |  | 2949822 | 2949822 | 2949822 | County Government of Bungoma |  | 2949822 |  | 2949822 | 95.54% | 2949822 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
512 | Periodic Maintenance of Roads In East Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43962 |  | 7665772 | 7665772 | 7665772 | County Government of Bungoma |  | 7665772 |  | 7665772 | 90.98% | 7665772 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
742 | Periodic Maintenance of Sirira Annex - St. Martins Catholic Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44334 |  | 9198684 | 9198684 | 9198684 | County Government of Bungoma |  | 9198684 |  | 9198684 |  | 9198684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
743 | Periodic Maintenance of Elima - Fuchani Stream | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44335 |  | 9198684 | 9198684 | 9198684 | County Government of Bungoma |  | 9198684 |  | 9198684 |  | 9198684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Requires graveling and grading
744 | Upgrading of Roads In East Sang'Alo Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
745 | Periodic Maintenance of Roads In East Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44335 |  | 9198684 | 9198684 | 9198684 | County Government of Bungoma |  | 9198684 |  | 9198684 | 99.94% | 9198684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1067 | Periodic Maintenance of Elima - Fuchani Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44701 |  | 3870073 | 3870073 | 3870073 | County Government of Bungoma |  | 3870073 |  | 3870073 |  | 3870073 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs grading and gravelling
1068 | Periodic Maintenance of Mabuusi Junction - Mechimeru Mkt - Sikalame Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.3KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | East Sang'alo | 0.510021/34.663213 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44703 |  | 5256603.8 | 5256603.8 | 5256603.8 | County Government of Bungoma |  | 5256603.8 |  | 5256603.8 |  | 5256603.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | rRequires gravelling and grading
1069 | Periodic Maintenance of Roads In East Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44701 |  | 3870073 | 3870073 | 3870073 | County Government of Bungoma |  | 3870073 |  | 3870073 | 100% | 3870073 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1070 | Periodic Maintenance of Mabuusi Junction - Mechimeru Mkt - Sikalame Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.3KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44701 |  | 5256603.8 | 5256603.8 | 5256603.8 | County Government of Bungoma |  | 5256603.8 |  | 5256603.8 | 97.11% | 5256603.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1381 | Construction of Fuchani Stream Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45062 |  | 8650618 | 8650618 | 8650618 | County Government of Bungoma |  | 8650618 |  | 8650618 |  | 8650618 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs periodic maintenance
1382 | Periodic Maintenance of Nabutola - Fuchani Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45065 |  | 8650618 | 8650618 | 8650618 | County Government of Bungoma |  | 8650618 |  | 8650618 |  | 8650618 | 0 | 0 | Incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Ieeds periodic maintenane
1383 | Periodic Maintenance of St. Pauls Lwandanyi - Namundi Tarmac Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45058 |  | 8650618 | 8650618 | 8650618 | County Government of Bungoma |  | 8650618 |  | 8650618 | 99.74% | 8650618 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1638 | Periodic Maintenance of Khakula - Sunrise Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45436 |  | 4840332 | 4840332 | 4840332 | County Government of Bungoma |  | 4840332 |  | 4840332 |  | 4840332 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Requires periodic maintenance
1639 | Periodic Maintenance of Mabusi - Mufule Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo | 0.498626/34.641530 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45436 |  | 6530000 | 6530000 | 6530000 | County Government of Bungoma |  | 6530000 |  | 6530000 |  | 6530000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Requires gravelling and grading
1640 | Periodic Maintenance of Mutomolo - Lukongo - Mabusi - Mufule Road In East Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo | 0.498626/34.641530,0.529002/34.648638 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45434 |  | 6530000 | 6530000 | 6530000 | County Government of Bungoma |  | 6530000 |  | 6530000 | 96.29% | 6530000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Requires grading and gravelling
1641 | Periodic Maintenance of Mwibale P.A.G Church - River Chwele - Khakula - Sunrise Road In East Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | East Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45422 |  | 4840332 | 4840332 | 4840332 | County Government of Bungoma |  | 4840332 |  | 4840332 | 99.6% | 4840332 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
8 | Purchase of 1 Acre for Wacheka VTC | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new VTC | One acre of Land Purchased for construction of Wacheka VTC | 3110599 | Ward based projects | Kanduyi | East Sang'alo | 0.458197/34.608110 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45352 | 45444 |  | 800000 | - | 800000 | CGB | N/A | 800000 | 0 | 800000 | 100% | 0 |  |  | Complete | 0.5 |  |  |  |  | 0 | No | [8 empty] | Payment was done
11 | Construction of 1 NO. ECDE classroom and 2 NO. Door Pit Latrines at Dorofu and Mabusi primary Schools in East Sang'alo Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | East Sang'alo | 0.514007/34.637885,0.43068/34.613135 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 4200000 | 4030860 | 4200000 | County Government of Bungoma | N/A | 4200000 | 0 |  | 0% |  | 4030860 | 4030860 | Stalled | At substructure (15%) | [14 empty] | The project is incomplete and not in use
39 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Khaweli,Watwang’a And Mwikhupo Primary Schools In East Sang’alo Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | East Sang'alo | 0.4464819/34.621314 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 4200000 | 4035150 | 4200000 | County Government of Bungoma | N/A | 4200000 | 0 | 0 | 0% | 0 | 4035150 | 4035150 | Complete and in use | 1 | [14 empty] | The project needs renovation
74 | Construction of 2 no ecde classrooms at nabutola pr and sango primary school | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | East Sang'alo | 0.492729/34.661814 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3000000 | 2999400 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 1993749.55 | 66.47% | 1993749.55 | 1005650.45 | 1005650.45 | Stalled | 0.2 | [14 empty] | Needs completion
107 | Construction Of 1 No. Ecde Classroom At Kimugui, Wacheka, Fuchani, Mufule And Nabichakha Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | East Sang'alo | 0.460254/34.610178,,0.453698/34.600346 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 6500000 | 6300000 | 6500000 | County Government of Bungoma | N/A | 6500000 | 0 | 6300000 | 100% | 6300000 | 0 | 0 | complete | 0.9 | [14 empty] | The project is in use
136 | Construction Of 1 No.Ecde Classroom At Luntungu And Mwibale Primary Schools In East Sang’alo Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | East Sang'alo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 2400000 | 2280000 | 2400000 | County Government of Bungoma | N/A | 2400000 | 0 | 1790721.57 | 78.54% | 1790721.57 | 489278.43 | 489278.43 | Incomplete | 1 | [14 empty] | Needs renovation annd construction of pit latrines
190 | Construction Of 1 No.Ecde Classroom At Khakula And Musakasa Primary Schools In East Sang’alo Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | East Sang'alo | 0.518797/34.67104 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3000000 | 2427200 | 3000000 | County Government of Bungoma | N/A | 3000000 |  | 2427200 | 100% | 2427200 | 0 |  | complete and in use | 1 | [14 empty] | The project is in use
10 | Upgrading of Dorof Borehole in East Sangalo ward | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 5000000 | 4892992.5 | 4892992.5 | FLLOCA | N/A | 4892992.5 | 0 | 0 | 100% | 4892992.5 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
81 | Upgrading and Extension of Napong'o Water Project in East Sangalo Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | Water project extended and upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5500000 | 5390520 | 5390520 | CGB | N/A | 5390520 | 0 | 5390520 | 100% | 0 | 5390520 | 0 | Work in progress | 50% complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
102 | Upgrading of kimugui primary borehole and drilling of 1no. Borehole in east sangalo ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points;site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 1 borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 6000000 | 5909852 | 5909852 |  | N/A | 5909852 | 0 | 5909852 | 100% | 5909852 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | BOREHOLE DRILLED .FABRICATION OF STAND AND TANK INSTALLATION COMPLETE.SOLAR SYSTEMS INSTALLED. PIPE LAYING REMAINING
145 | Upgrading of boreholes at dorofu and sigalame market | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo | 0.552971/34.613413 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4897520 | 4897520 |  | N/A | 4897520 | 0 | 4897520 | 100% | 4897520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | There is need for a committee to be formed
185 | DRILLING OF 2 NO. BOREHOLES at Dorofu and Kimugui markets and upgrading of Mwibale borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 5500000 | 5227358 | 5227358 |  | N/A | 5227358 | 0 | 5227358 | 100% | 5227358 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
252 | DRILLING OF 3NO. BOREHOLES IN EAST SANG'ALO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 4400000 | 4294320 | 4294320 |  | N/A | 4294320 | 0 | 4294320 | 100% | 4294320 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
330 | PROTECTION OF 5 WATER SPRINGS IN EAST SANG’ALO WARD. | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 1200000 | 1100000 | 1100000 |  | N/A | 1100000 | 0 | 1100000 | 100% | 1100000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Commissioned but requires repair
348 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 200000 | 160813 | 160813 |  | N/A | 160813 | 0 | 160813 | 100% | 160813 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
499 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1536200 | 1536200 |  | N/A | 1536200 | 0 | 1536200 | 100% | 1536200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Commissioned but requires repair
500 | Construction of 5 Roof Catchment,Construction of 50m3 Masonry tank at Mechimeru Health. | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1533656.61 | 1533656.61 |  | N/A | 1533656.61 | 0 | 1533656.61 | 100% | 1533656.61 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | The project was commissioned and in use
501 | Construction of East Bukusu Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 5000000 | 4900440 | 4900440 |  | N/A | 4900440 | 0 | 4900440 | 100% | 4900440 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
570 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1608137 | 1608137 |  | N/A | 1608137 | 0 | 1608137 | 100% | 1608137 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
571 | East Bukusu Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | East Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2240800 | 2240800 |  | N/A | 2240800 | 0 | 2240800 | 100% | 2240800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
44 | Proposed construction of auction ring at Dorofu market | construction Dorofu auction ring | promotion of MSMEs | Auction ring constructed | 1357862/2023-24 |  |  | East Sang'alo | 0.453155/34.613346 | Trade, Energy and Industrialization | Dept of Trade | BEFRA VENTURES LIMITED | 2023/2024 |  |  |  | 1500000 | 1473000 |  | CGB | [8 empty] | Stalled |  | 1 | [13 empty] | The site was abandoned
113 | Construction of Boda Boda Sheds at Sikalame market, Mechimeru, Mwibale and Dorofu | of Sheds market Sikalame market, Mechimeru | [5 empty] | East Sang'alo | o.452977/34.613475 |  |  | Befra Ventures Ltd | 2019/20 |  |  |  | 1412600 |  |  | CGG | [8 empty] | Complete | [15 empty] | The project is in use
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | East Sang'alo | 0.490196/34.640036 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed | [15 empty] | The project failed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | East Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | East Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
15 | Erection and completion works for maternity wing at khalala dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings erected and completed |  |  | Webuye West | SITIKHO | 0.46622/34.65578 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 28-2-2024 |  |  | 3000000 | 2807857 | 2807857 | CGB |  | 2807857 | 0 | 0 | 0% | 0 | 1904200 | 2807857 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Slow progress contractor needs to be sorted to speed up works
62 | proposed erection and completion of maternity wing at mang'ana dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Webuye West | SITIKHO | 0.524639/34.691484 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 20/2/24 |  |  | 5000000 | 4709460 | 4709460 | CGB |  | 4709460 | 0 | 0 | 0% | 0 |  | 4709460 | On-going | 57 | [5 empty] | No | complete | Financial | Yes |  |  |  | No |  | Slow progress contractor needs to be sorted to speed up works
87 | Erection And Completion Works Of Maternity Wing At Sitikho Dispensary. | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Webuye West | SITIKHO | 0.49963/34.684339 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 3000000 | 2777780 | 2777780 | CGB |  | 2777780 | 0 | 2669254.35 | 96.09% | 2669254.35 |  | 108525.65 | Completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Needs equipping
117 | Equiping Of Ngwelo And Mang'ana Dispensaries | Equipping with drugs and medical equipment |  | maternity wing equipped |  |  | Webuye West | SITIKHO | 0.524639/34.691484 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2000000 | 2250116 | 2250116 | CGB |  | 2250116 | 0 | 0 | 0% | 0 |  | 2250116 | Completed | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project is in use
143 | Purchase Of Medicl Equipments For Sitikho Dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Webuye West | SITIKHO | 0.499963/34.684339 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 500000 |  |  | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Completed | [6 empty] | No | complete | Financial | Yes | [5 empty] | More equipments needed
144 | Construction Of 3 Pit Door Latrines And Urinal At Mang'ana Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 3No. Door pit latrines constructed |  |  | Webuye West | SITIKHO | 0.5113866/34.691946 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 500000 | 648740 | 648740 | CGB |  | 648740 | 0 | 643168.68 | 99.14% | 643168.68 |  | 5571.32 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project is in use
178 | Proposed Erection And Completion Of Ngwelo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Webuye West | SITIKHO | 0.594240/34.711586 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3200000 | 2926370 | 2926370 | CGB |  | 2926370 | 0 | 677790 | 23.16% | 677790 |  | 2248580 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Needs fencing and construction septic tank
250 | Construction Mangana Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Webuye West | SITIKHO | 0.524528/34.691517 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 3000000 | 3671063.6 | 3671063.6 | CGB |  | 3671063.6 | 0 | 3671063.6 | 100% | 3671063.6 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project is in use
343 | Purchase of one acre piece of land for Mangana Dispensary. | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Webuye West | SITIKHO | 0.524528/34.694517 | [10 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Ongoing | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project is in use
344 | Construction of 3-door pit latrine | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To enhance access to sanitary facilities at the school | 3No. Door pit latrines constructed |  |  | Webuye West | SITIKHO | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
345 | Construction of Public Toilets. | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To enhance access to sanitary facilities at the market | Public toilets constructed |  |  | Webuye West | SITIKHO | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete, not in use. | [6 empty] | No | complete | Financial | Yes
21 | Upgrading of Yalusi Pr-Little Angel Academy-Chiefs Centre-Sda Nambalayi-Mayila Mkt | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.540998/34.703484-0.536918/34.773339 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41650 | 41777 |  | 4065684 | 4065684 | 4065684 | County Government of Bungoma |  | 4065684 |  | 4065684 | 100% | 4065684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs more culverts
246 | Periodic Maintenance of Chiefs Centre - Sda Church - Nambalai Primary - Maila Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43244 |  | 10336800 | 10336800 | 10336800 | County Government of Bungoma |  | 10336800 |  | 10336800 |  | 10336800 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
247 | Periodic Maintenance of Ngwelo Primary - Mangoli Road - Kwabubi River | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.60200/34.708055 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43240 |  | 10336800 | 10336800 | 10336800 | County Government of Bungoma |  | 10336800 |  | 10336800 |  | 10336800 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs repair of floor and more clasrooms due to high population enrolment
248 | Periodic Maintenance of Khalala Friends Church - Musabale Road - Sitkho Market | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.4697/34.65153-0.46743/34.708055 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43236 |  | 10336800 | 10336800 | 10336800 | County Government of Bungoma |  | 10336800 |  | 10336800 |  | 10336800 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs repair
249 | Periodic Maintenance of Roads In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43112 | 43234 |  | 10336800 | 10336800 | 10336800 | County Government of Bungoma |  | 10336800 |  | 10336800 | 99.45% | 10336800 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
427 | Periodic Maintenance of Periodic Maintenance Roads In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43486 | 43596 |  | 9512580 | 9512580 | 9512580 | County Government of Bungoma |  | 9512580 |  | 9512580 | 99.89% | 9512580 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintenance needed
428 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
429 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye West | SITIKHO | 0.590358/34.712031-0.599894/34.698544 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs repair
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
645 | Periodic Maintenance of Milo Secondary - Alice Wabwoba - Mzee Sanga - Wanyembi Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.532999/34.723345-0.53310/34.7333 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43973 |  | 6365759 | 6365759 | 6365759 | County Government of Bungoma |  | 6365759 |  | 6365759 |  | 6365759 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs repair and maintenance
646 | Periodic Maintenance of Roads In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43973 |  | 6365759 | 6365759 | 6365759 | County Government of Bungoma |  | 6365759 |  | 6365759 | 99.71% | 6365759 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
942 | Periodic Maintenance of Lumbwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.546970/34.739169-0.534172/34.741664 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44339 |  | 10856034 | 10856034 | 10856034 | County Government of Bungoma |  | 10856034 |  | 10856034 |  | 10856034 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Need more repair and periodic mantenance
943 | Periodic Maintenance of Ngwelo Sec - Philipo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.589670/34.692964 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44338 |  | 10856034 | 10856034 | 10856034 | County Government of Bungoma |  | 10856034 |  | 10856034 |  | 10856034 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs periodic mantenance
944 | Periodic Maintenance of Sundukwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.597371/34.693586-0.602278/34.690267 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44330 |  | 10856034 | 10856034 | 10856034 | County Government of Bungoma |  | 10856034 |  | 10856034 |  | 10856034 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs periodic maintenance
945 | Periodic Maintenance of Roads In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44331 |  | 10856034 | 10856034 | 10856034 | County Government of Bungoma |  | 10856034 |  | 10856034 | 92.73% | 10856034 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1272 | Periodic Maintenance of Chiefs Centre - Sda Church - Nambalayi Primary - Maila Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.51246/34.705278-0.52799/34.719835 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44692 |  | 10481620.8 | 10481620.8 | 10481620.8 | County Government of Bungoma |  | 10481620.8 |  | 10481620.8 |  | 10481620.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs more culverts
1273 | Periodic Maintenance of Mang'Oli Road - Khababwi Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44702 | 44733 | 10481620.8 | 10481620.8 | 10481620.8 | County Government of Bungoma |  | 10481620.8 |  | 10481620.8 |  | 10481620.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1274 | Periodic Maintenance of Mulukhu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.519255/34.688377 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44692 | 44723 | 10481620.8 | 10481620.8 | 10481620.8 | County Government of Bungoma |  | 10481620.8 |  | 10481620.8 |  | 10481620.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs repair and maintenance
1275 | Periodic Maintenance of Mzee Nathan Makokha - Ngachi Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.556855/34.710189 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44701 | 44732 | 10481620.8 | 10481620.8 | 10481620.8 | County Government of Bungoma |  | 10481620.8 |  | 10481620.8 |  | 10481620.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs routine maintenance and repair
1276 | Periodic Maintenance of Mzee Francis Kundu - Ngwelo Catholic Church Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.46385/34.65228-0.46976/34.66024 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44696 | 44727 | 10481620.8 | 10481620.8 | 10481620.8 | County Government of Bungoma |  | 10481620.8 |  | 10481620.8 |  | 10481620.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs maintenance
1277 | Periodic Maintenance of Roads In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44693 |  | 10481620.8 | 10481620.8 | 10481620.8 | County Government of Bungoma |  | 10481620.8 |  | 10481620.8 | 99.28% | 10481620.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1531 | Periodic Maintenance of Kaviiki Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.493932/34.680358-0.492656/34.688751 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45056 | 45087 | 4499657 | 4499657 | 4499657 | County Government of Bungoma |  | 4499657 |  | 4499657 |  | 4499657 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | In good condition
1532 | Construction of Chi Box Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45061 |  | 5116400 | 5116400 | 5116400 | County Government of Bungoma |  | 5116400 |  | 5116400 |  | 5116400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1533 | Construction of Little Lucky Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Webuye West | SITIKHO | 0.536940/34.713316 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45058 |  | 10177641460 | 10177641460 | 10177641460 | County Government of Bungoma |  | 10177641460 |  | 10177641460 |  | 10177641460 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1534 | Periodic Maintenance of Kiviiki Road In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45056 |  | 4499657 | 4499657 | 4499657 | County Government of Bungoma |  | 4499657 |  | 4499657 | 93.33% | 4499657 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1535 | Installation Of Chi-Box Culvert In Sitikho Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45069 |  | 5116400 | 5116400 | 5116400 | County Government of Bungoma |  | 5116400 |  | 5116400 | 100% | 5116400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1778 | Periodic Maintenance of Khalala Friends Church - Spaki Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.46385/34.65228,0.46976/34.66024 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45436 | 45467 | 6573546 | 6573546 | 6573546 | County Government of Bungoma |  | 6573546 |  | 6573546 |  | 6573546 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintenance needed
1779 | Periodic Maintenance of Mwalimu Emmanuel Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45428 | 45459 | 3124535 | 3124535 | 3124535 | County Government of Bungoma |  | 3124535 |  | 3124535 |  | 3124535 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1780 | Periodic Maintenance of Kilwake - Silungi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.546635/34.729415,0.553483/34.721826 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45435 |  | 3992604 | 3992604 | 3992604 | County Government of Bungoma |  | 3992604 |  | 3992604 |  | 3992604 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs culverts for drainage
1781 | Periodic Maintenance of Milo Secondary - Kwanusu - Soita Khisa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.532997/34.723345,0.538585/34.723345 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45431 |  | 2879352 | 2879352 | 2879352 | County Government of Bungoma |  | 2879352 |  | 2879352 |  | 2879352 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1782 | Periodic Maintenance of Khalala Friends Church - Spaki Road In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45434 |  | 6573546 | 6573546 | 6573546 | County Government of Bungoma |  | 6573546 |  | 6573546 | 99.96% | 6573546 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1783 | Periodic Maintenance of Mwalimu Emmanuel Road In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO | 0.524339/34.692166 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45423 |  | 3124535 | 3124535 | 3124535 | County Government of Bungoma |  | 3124535 |  | 3124535 | 99.92% | 3124535 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintenance needed
1784 | Periodic Maintenance of Kilwake - Silungi Road In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45427 |  | 3992604 | 3992604 | 3992604 | County Government of Bungoma |  | 3992604 |  | 3992604 | 99.64% | 3992604 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1785 | Periodic Maintenance of Milo Secondary - Kwanusu - Soita Khisa Road In Sitikho Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | SITIKHO |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45431 |  | 2879352 | 2879352 | 2879352 | County Government of Bungoma |  | 2879352 |  | 2879352 | 99.9% | 2879352 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
100 | Purchase of land for Ngwelo dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land for Ngwelo dispensary Purchased | 3110599 | Ward based projects | Webuye West | SITIKHO |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 27/5/2019 | 30/6/2019 | 30/6/2019 | 1000000 | 900000 | 900000 | CGB |  | 900000 |  | 900000 |  | 900000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
101 | Purchase of land for Mang'ana dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land for Mang'ana dispensary Purchased | 3110599 | Ward based projects | Webuye West | SITIKHO | 0.524528/34.691517 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 43231 | 18/4/2019 | 30/6/2019 | 700000 | 500000 | 500000 | CGB |  | 500000 |  | 500000 |  | 500000 |  |  | Completed | 1 | [14 empty] | The project is in use
126 | Purchase Of 1 Acre For Ngwelo Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Ngwelo Dispensary Purchased | 3110599 | Ward based projects | Webuye West | SITIKHO | 0.594240/34.711586 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42892 | 43077 | 43079 | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 100% | 500000 | 0 |  | Completed | 1 | [14 empty] | Needs fencing and construction septic tank
61 | Proposed Erection And Completion Works For 1no. Ecde Classroom At Bituyu And Nambalai Primary Schools In Sitikho Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | SITIKHO | Bituyu,0.5189/34.708980-Nambalayi,0.525489/34.714275 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2880000 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 | 0% | 0 | 2880000 | 2880000 | Complete and not in use | 1 | [14 empty] | Routine maintenance needed
92 | Proposed erection and completion works for 1no. ECDE Classroom at Khalala and Bukanjangabo primary schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | SITIKHO | Khalala,0.46711/34.65574-Bukunjangabo,0.545078/34.729306 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 2800000 | 2795000 | 2800000 | County Government of Bungoma | N/A | 2800000 | 0 | 2272845.05 | 81.32% | 2272845.05 | 522154.95 | 522154.95 | 3 complete and 2 ongoing and not in use | 0.7 | [14 empty] | Floor damaged needs repair
126 | Construction Of 1 No. Ecde Classroom At Mwembula And Khalumuli Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | SITIKHO | Mwembula,0.48652/34.67595-Khalumuli,0.583428/34.717958 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 2400000 | 2400240 | 2400000 | County Government of Bungoma | N/A | 2400000 | 0 | 2400240 | 100% | 2400240 | 0 | 0 | complete and in use | 1 | [14 empty] | Needs periodic maintenance
180 | Construction Of 1no. Ecde At Ngachi Primary School | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | SITIKHO | 0.559243/34711354 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 1200000 | 1250675 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 1250675 | 100% | 1250675 | 0 |  | complete and in use | 1 | [14 empty] | Needs repair of floor and more clasrooms due to high population enrolment
213 | Construction Of 1no. Ecde Classroom At Mukite Primary School In Sitikho Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | SITIKHO | 0.45773/34.64333 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 1200000 | 1287120 | 1200000 | County Government of Bungoma | N/A | 1200000 |  | 1287120 | 100% | 1287120 | 0 |  | complete and in use | 1 | [14 empty] | Floor needs repair
|  |  | To enhance access to clean and safe drinking water | 1 Borehole upgraded |  |  | Webuye West | SITIKHO | [11 empty] | FLLOCA | N/A | [5 empty] | 0 | 0 | [10 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
73 | Drilling and Upgrading of Mang'ana Dispensary Borehole in Sitikho Ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | SITIKHO | 0.5244545/34.691785 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2990480 | 2990480 | CGB | N/A | 2990480 | 0 | 2990480 | 100% | 2990480 | 0 | 0 | Complete | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Needs upgrading by piping to more households
111 | Protection of 8no. Water springs in Sitikho ward | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye West | SITIKHO |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1500000 | 1356678 | 1356678 |  | N/A | 1356678 | 0 | 1356678 | 100% | 1356678 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
171 | Upgrading of Sitikho Secondary School borehole | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | SITIKHO | Lunja-0.594532/34.6999-Luombo,0.59241/34.71600 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2000000 | 1998000 | 1998000 |  | N/A | 1998000 | 0 | 1998000 | 100% | 1998000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Erection of new tank and pipe extension needed
207 | PROTECTION OF 8 NO. WATER SPRINGS IN SITIKHO WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | SITIKHO | Welemba-0.476265/34.6691-Sipaki,0.47279/34.65451-Naluyenje,0.502979/34.67878-Festo,0.595393/34.70597-Japheth,0.595379/34.71059-Kimatia,0.58539/34.69169 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1500000 | 1384000 | 1384000 |  | N/A | 1384000 | 0 | 1384000 | 100% | 1384000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
208 | DRILLING OF 2NO. BOREHOLES AT KAKIMANYI DISPENSARY AND MANG’ANA DISPENSARY IN SITIKHO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | SITIKHO | Kakimanyi,0.54833/34.6674-Mang'ana,0.52445/34.69178 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 3500000 | 3390360 | 3390360 |  | N/A | 3390360 | 0 | 3390360 | 100% | 3390360 | 0 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Needs to be revived
294 | SITIKHO WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Webuye West | SITIKHO |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 18000000 | 17435000 | 17435000 |  | N/A | 17435000 | 0 | 17435000 | 100% | 17435000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
295 | CONSTRUCTION OF 5NO.WATER SPRINGS IN SITIKHO WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | SITIKHO | Wambani,0.578134/34.718665-Tunguta,0.53736/34.712119 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 1000000 | 996700 | 996700 |  | N/A | 996700 | 0 | 996700 | 100% | 996700 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Periodic maintanance needed
451 | Drilling of Borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works |  | SITIKHO |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1589070 | 1589070 |  | N/A | 1589070 | 0 | 1589070 | 100% | 1589070 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
35 | Proposed construction of 3 NO. bodaboda sheds | sheds construction of | promotion of MSMEs | Bodaboda sheds constructed | 1363225/2023-24 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Trade | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Completed | Complete and in use | 1000000 |  |  | CGB | [8 empty] | Complete | 100 | 3
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye | [5 empty] | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
98 | Installation of 1 No high mast flood light solar poered | of mast light mast flood | [5 empty] | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Ms Gaussian Solutions Limited | 2021/22 |  | Complete and in use |  | 1353000 |  |  | CGB
104 | Proposed installation of 35 no. Grid powered street lights in Webuye East, Webuye West, Kimilili and Bumula Sub Counties | installation Grid lights East Kimilili street Kimilili and | [5 empty] | SITIKHO |  |  |  | M/S Rygeo Tech Solution | 2020/21 |  | Complete |  | 3232265 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | SITIKHO |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed | [15 empty] | To increase slots to capture more beneficiaries in the ward
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed | [15 empty] | To increase slots to capture more beneficiaries in the ward
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | SITIKHO |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | SITIKHO |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
34 | Purchase of medical equipment for Savana dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Webuye East | MIHUU | 0.673721/34.758023 |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 1000000 | 1017100 | 1017100 | CGB |  | 1017100 | 0 | 0 | 0% | 0 |  | 1017100 | Complete | [6 empty] | No | complete | Financial | Yes
174 | Completion Of Maternity Wing At Lukusi Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Webuye East | MIHUU | 0.652996/34.813016 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1851620 | 1851620 | CGB |  | 1851620 | 0 | 1851620 | 100% | 1851620 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
237 | Construction Of A Maternity Wing At Mihuu Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Webuye East | MIHUU | 0.637090/34.787025 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 3400000 | 3373560 | 3373560 | CGB |  | 3373560 | 0 | 1718760.8 | 50.95% | 1718760.8 |  | 1654799.2 | Complete | [6 empty] | No | complete | Financial | Yes
238 | Construction Of 2 No.Door Pit Latrines At Lukusi,Lugulu, Furoyi Markets | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 2No. Door pit latrines constructed |  |  | Webuye East | MIHUU | 0.655366/34.815364 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1400000 | 1392210 | 1392210 | CGB |  | 1392210 | 0 | 1392210 | 100% | 1392210 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
46 | Construction of Mihuu-Froi With Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.620870/34.808109 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41658 | 41769 |  | 11460162 | 11460162 | 11460162 | County Government of Bungoma |  | 11460162 |  | 11460162 | 100% | 11460162 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
213 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43239 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
397 | Upgrading of Roads In Mihuu Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.672538/34.750148 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43478 | 43600 |  | 6485397 | 6485397 | 6485397 | County Government of Bungoma |  | 6485397 |  | 6485397 | 100% | 6485397 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
398 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | MIHUU | 0.628469/34.773792 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
399 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
400 | Periodic Maitenance Of Rural Roads Through West Kenya Sugar Mou | Grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye East | MIHUU | 0.657334/34.756489 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43600 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
583 | Periodic Maintenance of Lukusi - Bakisa - Froi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | MIHUU | 0.641471/34.791512 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43967 |  | 10036624 | 10036624 | 10036624 | County Government of Bungoma |  | 10036624 |  | 10036624 |  | 10036624 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
584 | Periodic Maintenance of Froi - Nabuyole Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | MIHUU | 0.579321/34.807045 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43970 |  | 11739206 | 11739206 | 11739206 | County Government of Bungoma |  | 11739206 |  | 11739206 |  | 11739206 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
585 | Periodic Maintenance of Totolela - Bakisa River - Makhendu River - Misimo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.647612/34.816565 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43963 | 43994 | 14559823 | 14559823 | 14559823 | County Government of Bungoma |  | 14559823 |  | 14559823 |  | 14559823 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
586 | Construction of Toili Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 3.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.633736/34.382727 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43962 |  | 14559823 | 14559823 | 14559823 | County Government of Bungoma |  | 14559823 |  | 14559823 |  | 14559823 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
587 | Periodic Maintenance of Roads In Mihuu Ward With A Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 3.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.620870/34.808109 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43969 |  | 14559823 | 14559823 | 14559823 | County Government of Bungoma |  | 14559823 |  | 14559823 | 99.99% | 14559823 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
588 | Periodic Maintenance of Lukusi-Bakisa Froi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43969 |  | 10036624 | 10036624 | 10036624 | County Government of Bungoma |  | 10036624 |  | 10036624 | 98.17% | 10036624 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
589 | Periodic Maintenance of Froi-Nabuyole Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43969 |  | 11739206 | 11739206 | 11739206 | County Government of Bungoma |  | 11739206 |  | 11739206 | 99.26% | 11739206 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
637 | Routine Maintenance Of Roads In Webuye East And Webuye West Sub- Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
877 | Periodic Maintenance of Jagery - Sipala - Mukolongolo - Kangale - Mulach S.A Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.642012/34.764573 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44336 |  | 10935204 | 10935204 | 10935204 | County Government of Bungoma |  | 10935204 |  | 10935204 |  | 10935204 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
878 | Periodic Maintenance of Muslim Estate Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.617731/34.766525 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44336 |  | 10935204 | 10935204 | 10935204 | County Government of Bungoma |  | 10935204 |  | 10935204 |  | 10935204 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
879 | Periodic Maintenance of Deliverance - Mzee Sunguri Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44340 |  | 10935204 | 10935204 | 10935204 | County Government of Bungoma |  | 10935204 |  | 10935204 |  | 10935204 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
880 | Periodic Maintenance of Lugulu - Lugulu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44329 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
881 | Upgrading of Mihuu Road At Nabuyole River | Road improvement works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.711152/34.796057 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44331 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
882 | Periodic Maintenance of Roads In Mihuu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44332 |  | 10935204 | 10935204 | 10935204 | County Government of Bungoma |  | 10935204 |  | 10935204 | 99.86% | 10935204 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1183 | Periodic Maintenance of Koyana - Misiebebe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.673721/34.758025 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44700 |  | 17145298.8 | 17145298.8 | 17145298.8 | County Government of Bungoma |  | 17145298.8 |  | 17145298.8 |  | 17145298.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1184 | Periodic Maintenance of Savanna Primary - Baptist Church - Savanna Dispensary | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.672538/34.758023 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44703 |  | 17145298.8 | 17145298.8 | 17145298.8 | County Government of Bungoma |  | 17145298.8 |  | 17145298.8 |  | 17145298.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1185 | Periodic Maintenance of John Maasai - Lukorito - Situni - Wanyama - Nandasaba Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.648507/34.763203 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44703 |  | 17145298.8 | 17145298.8 | 17145298.8 | County Government of Bungoma |  | 17145298.8 |  | 17145298.8 |  | 17145298.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1186 | Periodic Maintenance of Nabuyole School - Abigael - Railway Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.777064/34.576330 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44701 |  | 17145298.8 | 17145298.8 | 17145298.8 | County Government of Bungoma |  | 17145298.8 |  | 17145298.8 |  | 17145298.8 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1187 | Periodic Maintenance of Barasa Sibuchi - Lasaro - Kutukhulu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.621174/34.774106 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44692 |  | 17145298.8 | 17145298.8 | 17145298.8 | County Government of Bungoma |  | 17145298.8 |  | 17145298.8 |  | 17145298.8 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1188 | Periodic Maintenance of Misimo Sec - Bakhwami - Maraka Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | MIHUU | 0.655449/34.815302 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44698 | 44729 | 5109006 | 5109006 | 5109006 | County Government of Bungoma |  | 5109006 |  | 5109006 |  | 5109006 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1189 | Periodic Maintenance of Roads In Mihuu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44698 |  | 17145298.8 | 17145298.8 | 17145298.8 | County Government of Bungoma |  | 17145298.8 |  | 17145298.8 | 100% | 17145298.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1190 | Routine Maintenance Of Misimo Secondary - Bakhwami - Maraka Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | MIHUU | 0.655449/34.815302 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44704 |  | 5109006 | 5109006 | 5109006 | County Government of Bungoma |  | 5109006 |  | 5109006 | 100% | 5109006 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1479 | Periodic Maintenance of Makona Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.651020/34.700545 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45058 |  | 6200000 | 6200000 | 6200000 | County Government of Bungoma |  | 6200000 |  | 6200000 |  | 6200000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1480 | Periodic Maintenance of Njomo - Mukanda - Mzee Were - Jimmy Tori - Sunguti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.629386/34.828123 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45058 |  | 8889196 | 8889196 | 8889196 | County Government of Bungoma |  | 8889196 |  | 8889196 |  | 8889196 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1481 | Periodic Maintenance of Makanyaka - Masivayi - Musumba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.539480/34.832870 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45064 |  | 8889196 | 8889196 | 8889196 | County Government of Bungoma |  | 8889196 |  | 8889196 |  | 8889196 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1482 | Periodic Maintenance of Walwanda - Khasabuli - Vuyela Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.670987/34.763548 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45062 |  | 8889196 | 8889196 | 8889196 | County Government of Bungoma |  | 8889196 |  | 8889196 |  | 8889196 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1483 | Periodic Maintenance of Makona Box Culvert In Mihuu Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45061 |  | 6200000 | 6200000 | 6200000 | County Government of Bungoma |  | 6200000 |  | 6200000 | 99.97% | 6200000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1484 | Periodic Maintenance of Njomo - Mukanda - Mzee Were Jimmy Tori - Sunguti Road, Makanyaka - Masibayi - Musumba Walwanda - Khasabuli - Buyela In Mihuu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.629386/34.82123 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45066 |  | 8889196 | 8889196 | 8889196 | County Government of Bungoma |  | 8889196 |  | 8889196 | 99.92% | 8889196 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1727 | Periodic Maintenance of Mihuu Polytechnic - Toili - Omondi - Lukusi - Mihuu Mosque - Sango Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.629357/34.791085 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45429 | 45460 | 7549860 | 7549860 | 7549860 | County Government of Bungoma |  | 7549860 |  | 7549860 |  | 7549860 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1728 | Periodic Maintenance of Lugulu Deliverance - Mzee Sunguri Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.660332/34.785537 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45425 | 45456 | 6259667 | 6259667 | 6259667 | County Government of Bungoma |  | 6259667 |  | 6259667 |  | 6259667 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1729 | Periodic Maintenance of Sipala Market - Jaggary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.642012/34.764573 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45428 | 45459 | 6259667 | 6259667 | 6259667 | County Government of Bungoma |  | 6259667 |  | 6259667 |  | 6259667 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1730 | Periodic Maintenance of Mulachi Sa - Makona Bridge - Wangila Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | MIHUU | 0.652001/34.70054 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45435 |  | 3273520 | 3273520 | 3273520 | County Government of Bungoma |  | 3273520 |  | 3273520 |  | 3273520 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1731 | Periodic Maintenance of Mihuu Polytechnic - Toili - Omondi - Lukusi - Mihuu Mosque - Sango Road In Mihuu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45423 |  | 7549860 | 7549860 | 7549860 | County Government of Bungoma |  | 7549860 |  | 7549860 | 41.89% | 7549860 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1732 | Periodic Maintenance of Lugulu Deliverance - Mzee Sangura Road And Sipala Market - Jagarry Road In Mihuu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45423 |  | 6259667 | 6259667 | 6259667 | County Government of Bungoma |  | 6259667 |  | 6259667 | 99.99% | 6259667 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1733 | Periodic Maintenance of Mulachi Sa - Makona Bridge - Wangira Road In Mihuu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | MIHUU |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45428 |  | 3273520 | 3273520 | 3273520 | County Government of Bungoma |  | 3273520 |  | 3273520 | 100% | 3273520 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
125 | Purchase Of 1 Acre For Mang'ana Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Mang'ana Dispensary Purchased | 3110599 | Ward based projects | Webuye East | MIHUU |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 13/1/2018 | 13/3/2018 | 30/6/2018 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 100% | 0 | 0 |  | Stalled | 0
152 | purchase of 1 acre land for Bakisa youth polytechnic | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new polytechnic | One acres of Land for Bakisa youth polytechnic Purchased | 3110599 | Ward based projects | Webuye East | MIHUU | 0.647608/34.816566 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/01/2017 | 21/03/2017 | 30/06/2017 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 100% | 700000 |  |  | Completed | 1
153 | Purchase of land for Savana Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Savana Dispensary Purchased | 3110599 | Ward based projects | Webuye East | MIHUU | 0.673721/34.758023 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 100% |  |  |  | Complete | 0
22 | Construction of 1 NO. ECDE Classroom at Siilila and 1NO. Workshop at Bakisa Polytechnic in Mihuu Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | MIHUU | 0.647608/34.816561 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3200000 | 2798300 | 3200000 | County Government of Bungoma | N/A | 3200000 | 0 |  | 0% |  | 2798300 | 2798300 | Stalled | Contractor declined (0%) | 0 | Contractor declined
55 | Proposed Erection And Completion Works Of 1no. Ecde Classroom Lumuli And Sirende S.A Primary Schools In Mihuu Ward | Consturction oo VTC | To complete VTC providing learning environment | VTC completed | 3110599 | Construction and Civil works | Webuye East | MIHUU | 0.672538/34.758023 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 2400000 | 2814550 | 2400000 | County Government of Bungoma | N/A | 2400000 | 0 | 826246.35 | 29.36% | 826246.35 | 1988303.65 | 1988303.65 | Complete and not in use | 1
120 | Construction Of 1 No. Ecde Classroom At Mahanga Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | MIHUU | 0.619715/34.771807 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 1200000 | 4364390 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 949635.45 | 21.76% | 949635.45 | 3414754.55 | 3414754.55 | complete and in use | 1
152 | Proposed Erection And Completion Of 1 No. Ecde At Minyali Primary School In Mihuu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | MIHUU | 0.673721//34.758023 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1200000 | 1195723 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 1195723 | 100% | 1195723 | 0 | 0 | complete and in use | 1
203 | Construction Of 1no. Ecde Classroom At Froy Lugulu, Pag Primary And Murumba Primary Schools In Mihuu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | MIHUU | 0.619442/34.778084 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4000000 | 4140960 | 4000000 | County Government of Bungoma | N/A | 4000000 |  | 4140960 | 100% | 4140960 | 0 |  | complete and in use | 1
39 | Proposed Tree Growing Within Institutions In Luuya/Bwake, Matulo, Mihuu, Kamukuywa, And Naitiri/Kabuyefwe Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Webuye East | MIHUU |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45452 | 45455 | 45455 | 5917500 | 5910500 | 5910500 | FLLOCA | IDA | 0 | 5910500 | 0 | 100% | 0 | 0 |  | Re-tendered | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
87 | Drilling and Equipping of Sirende Borehole and Solarisation of Savana Dispensary Borehole in Mihuu Ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and equipped | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.673721/34.758023 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3600000 | 3429416 | 3429416 | CGB | N/A | 3429416 | 0 | 3429416 | 100% | 0 | 3429416 | 0 | Stalled | 60% complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
169 | Rehabilitation of water project in Mihuu ward | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.626529/34.795654 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 3200000 | 3095112 | 3095112 |  | N/A | 3095112 | 0 | 3095112 | 100% | 3095112 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
201 | UPGRADING OF NABUYOLE BOREHOLE TO SOLAR PUMPING | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.557352/34.686194 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2000000 | 1844690 | 1844690 |  | N/A | 1844690 | 0 | 1844690 | 100% | 1844690 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
233 | DRILLING AND EQUIPPING OF MUSLIM ESTATE BOREHOLE IN MIHUU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.617281/34.763529 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2000000 | 1968520 | 1968520 |  | N/A | 1968520 | 0 | 1968520 | 100% | 1968520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
292 | CONSTRUCTION OF MISIMO SUBLOCATION 6 WATER SPRINGS AND BOREHOLE PROJECT IN MIHUU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 2 Boreholes drilled and 6 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works |  | MIHUU | 0.6556961/34.829751 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3891875 | 3891875 |  | N/A | 3891875 | 0 | 3891875 | 100% | 3891875 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
293 | CONSTRUCTION OF MITUKUYU SUBLOCATION WATER SPRINGS AND BOREHOLE DRILLING IN MIHUU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 2 Boreholes drilled and 2 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works |  | MIHUU | 0.950908/36.057765 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3500000 | 3436776 | 3436776 |  | N/A | 3436776 | 0 | 3436776 | 100% | 3436776 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
390 | Lukusi water project | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | MIHUU | 0.652996/34.813016 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1000000 | 919325 | 919325 |  | N/A | 919325 | 0 | 919325 | 100% | 919325 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
397 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.616758/34.776095 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1653900 | 1653900 |  | N/A | 1653900 | 0 | 1653900 | 100% | 1653900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
399 | Mihuu sec. sch. Borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works |  | MIHUU | 0.717626/34.739972 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1714900 | 1714900 |  | N/A | 1714900 | 0 | 1714900 | 100% | 1714900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
524 | Construction of mihuu Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.625740/34.798002 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 4200000 | 4111580 | 4111580 |  | N/A | 4111580 | 0 | 4111580 | 100% | 4111580 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
525 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1460320 | 1460320 |  | N/A | 1460320 | 0 | 1460320 | 100% | 1460320 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
589 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 of water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1653900 | 1653900 |  | N/A | 1653900 | 0 | 1653900 | 100% | 1653900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
590 | Drilling of Mihuu Borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.625740/34.798002 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1714900 | 1714900 |  | N/A | 1714900 | 0 | 1714900 | 100% | 1714900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
591 | Construction of Lukusi water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | MIHUU | 0.652996/34.813016 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1000000 | 919325 | 919325 |  | N/A | 919325 | 0 | 919325 | 100% | 919325 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions
1 | Construction of Mihuu ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Mihuu ward office constructed | 3111504 | Construction of non- residential buildings | Webuye East | MIHUU | 0.626781/34.7146180 | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 42382 | 9500000 | 12365776 | 9500000 | County Government of Bungoma | - | 12365776 | - | 12365776 | 100% | 12365776 | 0 | 0 | Incomplete | - | - | - | - | - | - | - |  | - | No | - | No | -
| Supply and delivery of young dairy animals(Heifers) 18 to 24 months $ young dairy goats 12 to 18 months old | Supply and delivery of young dairy animals(Heifers) 18 to 24 months $ young dairy goats 12 to 18 months old | To enhance dairy production, value addition and income generation | 58 Dairy animals (heifers) supplied and delivered to farmer groups | 3110599 | Ward Based projects | Tongaren/Webuye East/Kanduyi | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 6800000 | 6800000 | 6800000 | County Government of Bungoma |  | 6800000 | 0 | 6800000 | 100% | 6800000 | 0 | 0
104 | Proposed installation of 35 no. Grid powered street lights in Webuye East, Webuye West, Kimilili and Bumula Sub Counties | installation Grid lights East Kimilili street Kimilili and | [5 empty] | MIHUU |  |  |  | M/S Rygeo Tech Solution | 2020/21 |  | Complete |  | 3232265 |  |  | CGG
116 | Installation of 2 no. Solar Powered High Mast Flood lights at Mihuu and Froyi markets | of Powered Flood Mast at Mihuu | [5 empty] | MIHUU |  |  |  | Go Solar Systems Ltd | 2019/20 |  | Complete |  | 2026000 | 0 |  | CGG | [8 empty] | Complete
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | MIHUU |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628915/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Incomplete
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.650265/34.757333 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Not delivered
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.650265/34.757333 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.650265/34.757333 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | MIHUU | 0.650265/34.757333 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.650265/34.757333 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.650265/34.757333 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | MIHUU |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | MIHUU | 0.650265/34.757333 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | MIHUU | 0.628715/34.797035 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | MIHUU |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
113 | Completion Of Misikhu Maternity Wing | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | maternity wing completed |  |  | Webuye West | Misikhu | 0.7099817/34.7489433 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1000000 | 989317 | 989317 | CGB |  | 989317 | 0 | 0 | 0% | 0 |  | 989317 | stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | To be completed and equiped
114 | Completion Of Kituni Maternitywing | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | maternity wing completed |  |  | Webuye West | Misikhu | 0.661188/34.732078 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1000000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Waiting handing over
115 | Construction Of Out Patient Room At Bunjosi Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | outpatient room constructed |  |  | Webuye West | Misikhu | 0.698902/34.76410 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1500000 | 1493000 | 1493000 | CGB |  | 1493000 | 0 | 0 | 0% | 0 |  | 1493000 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | The site was handed over
137 | Construction Of Maternity Wing At Kituni Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Webuye West | Misikhu |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2000000 | 2053374 | 2053374 | CGB |  | 2053374 | 0 |  | 0% |  |  | 2053374 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
138 | Construction Of Maternity Wing At Misikhu Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Webuye West | Misikhu | 0.7099817/34.7489433 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2000000 | 1939276.4 | 1939276.4 | CGB |  | 1939276.4 | 0 | 1000000 | 51.57% | 1000000 |  | 939276.4 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Needs to be completed
240 | Construction Of 1pit Latrine At Sirisia Vocational Centre | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 1No. Door pit latrines constructed |  |  | Webuye West | Misikhu | 0.678844/34.722324 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 300000 | 0 | 0 | CGB |  | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | In use but excavation was shallow
241 | Construction Of 1pit Latrine At Sirisia Vocational Centre | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 1No. Door pit latrines constructed |  |  | Webuye West | Misikhu |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 300000 | 0 | 0 | CGB |  | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | Budget relocated to kituni dispensary for complettion of dispensary | [6 empty] | No | complete | Financial | Yes |  |  |  | No
346 | Renovation of Kituni Dispensary | Excavation of trenches for foundation,construction of 150mm thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible affordable health services within the community | Dispensaries renovated |  |  | Webuye West | Misikhu | 0.660775/34.7323317 |  | CEF | Health & Sanitation | 2016/2017 |  | 42705 |  |  | 1612465 | 1612465 | CGB |  | 1612465 | 0 | 1612464 | 100% | 1612464 |  | 1 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project is in use
129 | Upgrading of Bunang'Eni Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.705643/34.684605 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42750 | 42877 |  | 20697553.34 | 20697553.34 | 20697553.34 | County Government of Bungoma |  | 20697553.34 |  | 20697553.34 | 100% | 20697553.34 | 0 | 0 | Complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
214 | Periodic Maintenance of Daraja Mbili - Simwenyi Makalama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.6851333/34.02072310-0.6936333/34.7373617 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43237 |  | 8681792.2 | 8681792.2 | 8681792.2 | County Government of Bungoma |  | 8681792.2 |  | 8681792.2 |  | 8681792.2 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs opening and gravelling
215 | Periodic Maintenance of Makhese - Lazaro - Tuty Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.676006/34.748517 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43117 | 43231 |  | 8681792.2 | 8681792.2 | 8681792.2 | County Government of Bungoma |  | 8681792.2 |  | 8681792.2 |  | 8681792.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintenance to be done
216 | Periodic Maintenance of Misikhu Ward Roads | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43230 |  | 8681792.2 | 8681792.2 | 8681792.2 | County Government of Bungoma |  | 8681792.2 |  | 8681792.2 | 97.71% | 8681792.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
400 | Periodic Maitenance Of Rural Roads Through West Kenya Sugar Mou | Grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43600 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
402 | Periodic Maintenance of Roads In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43479 | 43602 |  | 5353400 | 5353400 | 5353400 | County Government of Bungoma |  | 5353400 |  | 5353400 | 100% | 5353400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
403 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
404 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
592 | Periodic Maintenance of Daraja Mbili - Friends High School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43970 |  | 7589662 | 7589662 | 7589662 | County Government of Bungoma |  | 7589662 |  | 7589662 |  | 7589662 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
593 | Upgrading of Kituni - Sirisia - Bunjosi - Kibingei Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43969 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 |  | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
594 | Periodic Maintenance of Lugulu - Kituni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.66363678/34.742732-0.663925/34.729710 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43970 | 44001 | 6038670 | 6038670 | 6038670 | County Government of Bungoma |  | 6038670 |  | 6038670 |  | 6038670 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The road is in bad state hence needs maintenance
595 | Periodic Maintenance of Roads In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43962 |  | 6038670 | 6038670 | 6038670 | County Government of Bungoma |  | 6038670 |  | 6038670 | 99.99% | 6038670 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
596 | Periodic Maintenance of Daraja Mbili-Misikhu Friends High School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu | 0.706339/34.722685 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43970 |  | 7589662 | 7589662 | 7589662 | County Government of Bungoma |  | 7589662 |  | 7589662 | 98.21% | 7589662 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
599 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
638 | Drainage Works In Webuye East And Webuye West Sub-Counties(Lot 4) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43966 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 | 88.12% | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
885 | Periodic Maintenance of Makhese - Sirisia - R. Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.675950/34748502 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44328 | 44359 | 9912693 | 9912693 | 9912693 | County Government of Bungoma |  | 9912693 |  | 9912693 |  | 9912693 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The road needs regular periodic maintenance
886 | Periodic Maintenance of Bunjosi - Fanuel - Nambami Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.695012/34.7023469 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44333 | 44364 | 9912693 | 9912693 | 9912693 | County Government of Bungoma |  | 9912693 |  | 9912693 |  | 9912693 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs maintenance
887 | Periodic Maintenance of Roadsin Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44337 |  | 9912693 | 9912693 | 9912693 | County Government of Bungoma |  | 9912693 |  | 9912693 | 99.96% | 9912693 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1198 | Periodic Maintenance of Mitoto Mbili - Meshack Namukhweso - Mukoro Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.662766/34.754328 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44701 |  | 11327400 | 11327400 | 11327400 | County Government of Bungoma |  | 11327400 |  | 11327400 |  | 11327400 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | To be completed and equiped
1199 | Periodic Maintenance of Kituni Sec - School - Chilison Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.665224/34.71764-0.668654/34.739212 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44698 |  | 11327400 | 11327400 | 11327400 | County Government of Bungoma |  | 11327400 |  | 11327400 |  | 11327400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs maintenance
1200 | Periodic Maintenance of Kofia - Silila Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.650462/34.731882-0.645267/34.722708 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44703 |  | 11327400 | 11327400 | 11327400 | County Government of Bungoma |  | 11327400 |  | 11327400 |  | 11327400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | In good condition and serving the community well
1201 | Periodic Maintenance of Mauso - Bunang'Eni Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu | 0.705643/34.684605 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44694 | 44725 | 3162392 | 3162392 | 3162392 | County Government of Bungoma |  | 3162392 |  | 3162392 |  | 3162392 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1202 | Periodic Maintenance of Misikhu Friends - Elgon Hotel Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44692 |  | 5570738.4 | 5570738.4 | 5570738.4 | County Government of Bungoma |  | 5570738.4 |  | 5570738.4 |  | 5570738.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1203 | Periodic Maintenance of Roads In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.66266778/34.732732/0.652039-34.717247 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44694 |  | 11327400 | 11327400 | 11327400 | County Government of Bungoma |  | 11327400 |  | 11327400 | 98.92% | 11327400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1204 | Periodic Maintenance of Mauso - Bunang'Eni Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu | 0.705643/34.684605 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44703 |  | 3162392 | 3162392 | 3162392 | County Government of Bungoma |  | 3162392 |  | 3162392 | 96.87% | 3162392 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1205 | Routine Maintenance Of Misikhu Friends - Elgon Hotel Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Misikhu | 0.6984917/34.7337183-0.7099573/34.7534385 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44697 |  | 5570738.4 | 5570738.4 | 5570738.4 | County Government of Bungoma |  | 5570738.4 |  | 5570738.4 | 96.69% | 5570738.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs maintenance
1485 | Periodic Maintenance of Cheng'Oli Primary - Wakhumicha - Wengila Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.660528/34.738960-0.653887/34.730798 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45068 |  | 6156198 | 6156198 | 6156198 | County Government of Bungoma |  | 6156198 |  | 6156198 |  | 6156198 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1486 | Periodic Maintenance of Bunjosi Primary - River Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.692803/34.785541 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45062 |  | 3634633 | 3634633 | 3634633 | County Government of Bungoma |  | 3634633 |  | 3634633 |  | 3634633 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The road needs regular periodic maintenance
1487 | Periodic Maintenance of Cheng'Oli Primary - Wakhumicha - Wengila Mkt In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.680528/34.738960-0.653887/34.730798 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45056 |  | 6156198 | 6156198 | 6156198 | County Government of Bungoma |  | 6156198 |  | 6156198 | 99.95% | 6156198 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1488 | Periodic Maintenance of Bunjosi Pri - R. Kuywa Road In Miskhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45067 |  | 3634633 | 3634633 | 3634633 | County Government of Bungoma |  | 3634633 |  | 3634633 | 100% | 3634633 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1739 | Periodic Maintenance of Wenyila - Sub Chief - Namundi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.651940/34.729452/0.638828/34.719101 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45422 |  | 4445091 | 4445091 | 4445091 | County Government of Bungoma |  | 4445091 |  | 4445091 |  | 4445091 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1740 | Periodic Maintenance of Bunang¦Eni - Masakhalia - Kuywa Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.707398/34.685542 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45432 | 45463 | 4149726 | 4149726 | 4149726 | County Government of Bungoma |  | 4149726 |  | 4149726 |  | 4149726 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1741 | Periodic Maintenance of Kituni - Makhanu - Salvation Army Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.658753/34.714975-0.660060/34.729410 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45436 |  | 2507703 | 2507703 | 2507703 | County Government of Bungoma |  | 2507703 |  | 2507703 |  | 2507703 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The road needs murraming
1742 | Periodic Maintenance of Nambami Primary - Estate Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45427 |  | 1851360 | 1851360 | 1851360 | County Government of Bungoma |  | 1851360 |  | 1851360 |  | 1851360 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1743 | Periodic Maintenance of Nambami Primary - Estate Road In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45431 |  | 1851360 | 1851360 | 1851360 | County Government of Bungoma |  | 1851360 |  | 1851360 | 99.94% | 1851360 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1744 | Periodic Maintenance of Kituni - Makhanu - Salvation Army Road In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.6909213/34.7337183-0.695795/34.7507767 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45435 |  | 2507703 | 2507703 | 2507703 | County Government of Bungoma |  | 2507703 |  | 2507703 | 99.94% | 2507703 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs gravelling and drainage
1745 | Periodic Maintenance of Wenyila - Sub Chief - Namundi Road In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45426 |  | 4445091 | 4445091 | 4445091 | County Government of Bungoma |  | 4445091 |  | 4445091 | 99.94% | 4445091 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1746 | Periodic Maintenance of Bunang'Eni - Masakhalia - Kuywa Bridge Road In Misikhu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Misikhu | 0.71932/34.683525 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45424 |  | 4149726 | 4149726 | 4149726 | County Government of Bungoma |  | 4149726 |  | 4149726 | 99.64% | 4149726 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
12 | Purchase of 1 Acre for extension of sibembe E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of of ECDE centre | One acre of Land Purchased for extension of Sibembe ECDE | 3110599 | Ward based projects | Webuye West | Misikhu | 0.646225/34.722838 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45323 | 45809 |  | 500000 | 1000000 | 500000 | CGB | N/A | 500000 | 0 | 500000 | 100% | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | Purchased
66 | Purchase Of 1 Acre For Sibembe E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land For Sibembe E.C.D.E Purchased | 3110599 | Ward based projects | Webuye West | Misikhu | 0.646238/34.723052 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 | 44055 | 22/6/2021 | 30/6/2021 | 1000000 | 1000000 | 1000000 | CGB |  | 1000000 |  | 1000000 | 100% | 700000 |  |  | Completed | 1 | [14 empty] | Purchased
27 | Construction of 1 NO. ECDE Classroom at Manani primary schools in Misikhu Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Misikhu | 0.766356/34.721413 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 2500000 | 2498300 | 2500000 | County Government of Bungoma | N/A | 2500000 | 0 | 1787210 | 71.54% | 1787210 | 711090 | 711090 | complete | At roofing (90%) | [14 empty] | Not handed over
57 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Sibembe And Misikhu Friends Schools In Misikhu Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Misikhu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2817100 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 | 0% | 0 | 2817100 | 2817100 | Complete and not in use | 1
88 | construction of 1 no ecde at bunangeni primary sch. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Misikhu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1200000 | 1196900 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 |  | 0% |  | 1196900 | 1196900 | Complete and in use | 1
155 | Proposed Erection And Completion Of 1 No. Ecde At Mungakha And Lugulu Day Primary Schools In Misikhu Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Misikhu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 2465311.05 | 2391446 | 2465311.05 | County Government of Bungoma | N/A | 2465311.05 | 0 | 2391446 | 100% | 2391446 | 0 | 0 | complete and in use | 1
205 | Construction Of 1no. Ecde Classroom And 1no. Pit Latrine At Sirisia, Chengoli And Misikhu Rc Primary Schools And Sirisia Vocational Training Centre In Misikhu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Misikhu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 6000000 | 5891400 | 6000000 | County Government of Bungoma | N/A | 6000000 |  | 5891400 | 100% | 5891400 | 0 |  | complete and in use | 1
1 | Upgrading of Bunjosi Primary and Kakimanyi Dispensdary Boreholes Borehole in Misikhu/Sitikho Ward | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45547 | 45547 | 7000000 | 6584160 | 6584160 | FLLOCA | N/A | 6584160 | 0 | 0 | 100% | 6584160 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
68 | Drilling and Upgrading of Kituni Dispensary and Mukhe dispensary Boreholes in Misikhu Ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu | 0.736671/34.723831 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 6000000 | 5937344 | 5937344 | CGB | N/A | 5937344 | 0 | 5937344 | 100% | 5937344 | 0 | 0 | Complete | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Not in use
124 | Drilling of 3no. Boreholes in Misikhu ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 5300000 | 5264080 | 5264080 |  | N/A | 5264080 | 0 | 5264080 | 100% | 5264080 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
155 | construction and protection of 6no water springs | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 6 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 1200000 | 1160160 | 1160160 |  | N/A | 1160160 | 0 | 1160160 | 100% | 0 | 1160160 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
273 | DRILLING OF KITUNI AND MISIKHU DISPENSARY IN MISIKHU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 4000000 | 3900000 | 3900000 |  | N/A | 3900000 | 0 | 3900000 | 100% | 3900000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
296 | CONSTRUCTION AND PROTECTION OF MISIKHU WATER SPRINGS IN MISIKHU WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 1000000 | 918256 | 918256 |  | N/A | 918256 | 0 | 918256 | 100% | 918256 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
343 | Protection of 22 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 22 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu | 0.674784/34.747664 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 3500000 | 3336265 | 3336265 |  | N/A | 3336265 | 0 | 3336265 | 100% | 3336265 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | In good condition and serving the community well
425 | Protection of 10 water Springs and Construction of 1Shallow wells | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed and 1 well constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu | 0.709745/34.692009 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2000000 | 1735879.5 | 1735879.5 |  | N/A | 1735879.5 | 0 | 1735879.5 | 100% | 1735879.5 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | To be protected
440 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works |  | Misikhu | 0.663078/34.743883 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 600000 | 550500 | 550500 |  | N/A | 550500 | 0 | 550500 | 100% | 550500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | In good condition and serving the community well
453 | Construction of 6 Roof catchments | Construction of Roof catchments | To enhance access to clean and safe drinking water | 6 roof catchments constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 800000 | 636031 | 636031 |  | N/A | 636031 | 0 | 636031 | 100% | 636031 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
521 | Protection of 22 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 22 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3500000 | 3336265 | 3336265 |  | N/A | 3336265 | 0 | 3336265 | 100% | 3336265 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
522 | Construction of 6 Roof catchments | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 6 roof catchments constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 636031 | 636031 |  | N/A | 636031 | 0 | 636031 | 100% | 636031 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
597 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1350500 | 1350500 |  | N/A | 1350500 | 0 | 1350500 | 100% | 1350500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
598 | Construction of 4 Shallow wells | Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 4 shallow wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Misikhu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2000000 | 1870230 | 1870230 |  | N/A | 1870230 | 0 | 1870230 | 100% | 1870230 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Rehabilitation Of Magemo Dam | Rehabilitation Of Magemo Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Ndivisi | Misikhu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43009 | 43014 | 17/5/2017 | 15000000 | 9707680 | 10000000 | County Government of Bungoma |  | 9707680 | 0 | 9707680 | 100% | 9707680 | 0 | 0 | Completed
| Supply and delivery of 2 months old chicks and Feeds | Supply and delivery of 2 months old chicks and Feeds | To enhance poultry production and increase household incomes | Poultry birds supplied | 3110599 | Ward Based projects | Webuye East | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 19/12/2021 | 19/3/2022 | 44595 | 1000000 | 12450840 | 12500000 | County Government of Bungoma |  | 12450840 | 0 | 12450840 | 100% | 12450840 | 0 | 0 | Completed | [15 empty] | Groups benefited successfully
| Construction of Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | Construction of 20 Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | To support growth of coffee farmers and enhance income generation | 20 Coffee drying tables constructed | 3110504 | Other infrastructure and civil works | Kimilili/Webuye West, Mt. Elgon | Misikhu |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44900 | 44838 | 10000000 | 3087863.88 | 3100000 | County Government of Bungoma |  | 3087863.88 | 0 | 3087863.88 | 100% | 3087863.88 | 0 | 0 | Completed
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye | [5 empty] | Misikhu | 071471/34.75247380 | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB | [24 empty] | The project is in use
104 | Proposed installation of 35 no. Grid powered street lights in Webuye East, Webuye West, Kimilili and Bumula Sub Counties | installation Grid lights East Kimilili street Kimilili and | [5 empty] | Misikhu |  |  |  | M/S Rygeo Tech Solution | 2020/21 |  | Complete |  | 3232265 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed | [15 empty] | Received and distributed from agric
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Misikhu | 0.721150/34.701354 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed | [15 empty] | Not in use after being vandalized
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed | [15 empty] | Received and distributed at the ward agric office
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed | [15 empty] | Were issued out to groups
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Misikhu | 0.7172467/34.7457367 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Misikhu | 0.67639/34.748006 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed | [15 empty] | Distributed at the agric office as received
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Misikhu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Misikhu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
58 | construction of 4NO.Door pit latrines with urinal at kayaya dispensay | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Webuye West | Matulo | 0.640648/34.72927 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 20/2/24 |  |  | 800000 | 760507 | 760507 | CGB |  | 760507 | 0 | 0 | 0% | 0 |  | 760507 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | In good condition and in use
342 | Renovation of Matulo Dispensary | dispensaries renovated | To provide accessible,affordable health services within the community | Dispensaries renovated |  |  | Webuye West | Matulo | 0.616223/34.70552 |  | Ward Based | Health & Sanitation | 2015/16 |  |  |  |  | 1604536 | 1604536 | CGB |  | 1604536 | 0 | 1604536 | 100% | 1604536 |  | 0 | Ongoing for maternity wing | [6 empty] | No | complete | Financial | Yes | [5 empty] | Low pace foundation storage
347 | Renovation of Kayaya Dispensary. | Excavation of trenches for foundation,construction of 150mm thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible affordable health services within the community | Dispensaries renovated |  |  | Webuye West | Matulo | 0.640640/34.72920 |  | Ward Fund | Health & Sanitation | 2014/2015 |  | 42185 |  |  | 1334638 | 1334638 | CGB |  | 1334638 | 0 | 1334638 | 100% | 1334638 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
41 | Upgrading of Nalondo-Mabanga | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41653 | 41776 |  | 11692800 | 11692800 | 11692800 | County Government of Bungoma |  | 11692800 |  | 11692800 | 100% | 11692800 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
211 | Periodic Maintenance of Kona Mbaya Road -Malaha - Kayaya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.634818/34.720148 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43244 |  | 11381601 | 11381601 | 11381601 | County Government of Bungoma |  | 11381601 |  | 11381601 |  | 11381601 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
212 | Periodic Maintenance of Roads In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43233 |  | 11381601 | 11381601 | 11381601 | County Government of Bungoma |  | 11381601 |  | 11381601 | 56.66% | 11381601 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
394 | Periodic Maintenance of Roads In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43489 | 43606 |  | 10741368 | 10741368 | 10741368 | County Government of Bungoma |  | 10741368 |  | 10741368 | 84% | 10741368 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
395 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
575 | Periodic Maintenance of Dina - Kombo - Mang'Ana Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.606132/34.756540 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43968 |  | 6910688.4 | 6910688.4 | 6910688.4 | County Government of Bungoma |  | 6910688.4 |  | 6910688.4 |  | 6910688.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs maintenance
576 | Periodic Maintenance of Matisi - Wamang'Oli Primary - Ad Church - Ndemaki Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.629142/34.702939 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43975 |  | 6910688.4 | 6910688.4 | 6910688.4 | County Government of Bungoma |  | 6910688.4 |  | 6910688.4 |  | 6910688.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs renovation
577 | Periodic Maintenance of Mulati-Flyover-Pag-Molo Roads | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo | 58.71888/57.04944-31.470/36.06192 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43975 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Road was murramed
578 | Upgrading of Minata - Malaha Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Matulo | 0.603321/34.749920 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43964 |  | 6373040 | 6373040 | 6373040 | County Government of Bungoma |  | 6373040 |  | 6373040 |  | 6373040 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs maintenance
579 | Upgrading of Spot Improvement Of Minata - Malaha Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Matulo | 0.611139/34.749550 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43969 |  | 6373040 | 6373040 | 6373040 | County Government of Bungoma |  | 6373040 |  | 6373040 | 98.08% | 6373040 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Movable but needs culverts
580 | Periodic Maintenance of Roads In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43969 |  | 6910688.4 | 6910688.4 | 6910688.4 | County Government of Bungoma |  | 6910688.4 |  | 6910688.4 | 99.71% | 6910688.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
637 | Routine Maintenance Of Roads In Webuye East And Webuye West Sub- Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
864 | Periodic Maintenance of Pag - Murram - Jagary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.639113/34.756820 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44340 |  | 15198325.8 | 15198325.8 | 15198325.8 | County Government of Bungoma |  | 15198325.8 |  | 15198325.8 |  | 15198325.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs rehabilitation and draiange
865 | Periodic Maintenance of Weighbridge - Sikhitimi - Water Spring - Malaha - Minata Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.606132/34.756540 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44336 |  | 15198325.8 | 15198325.8 | 15198325.8 | County Government of Bungoma |  | 15198325.8 |  | 15198325.8 |  | 15198325.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
866 | Periodic Maintenance of Matulo - Uwanja Ndege Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.628085/34.757579 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44329 |  | 15198325.8 | 15198325.8 | 15198325.8 | County Government of Bungoma |  | 15198325.8 |  | 15198325.8 |  | 15198325.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
867 | Periodic Maintenance of Wepukhulu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.606880/34.723719 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44327 |  | 15198325.8 | 15198325.8 | 15198325.8 | County Government of Bungoma |  | 15198325.8 |  | 15198325.8 |  | 15198325.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
868 | Periodic Maintenance of Nato Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.604546/34.732367 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44328 |  | 15198325.8 | 15198325.8 | 15198325.8 | County Government of Bungoma |  | 15198325.8 |  | 15198325.8 |  | 15198325.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs maintenance
869 | Periodic Maintenance of Satelite - Munyikana Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.619422/34.762214 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44327 |  | 15198325.8 | 15198325.8 | 15198325.8 | County Government of Bungoma |  | 15198325.8 |  | 15198325.8 |  | 15198325.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
870 | Upgrading of Sweet Waters - S.A Pri. Road | Road improvement works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo | 957324/44.69941-49.815/38.51532 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs renovation
871 | Upgrading of Minata - Malaha Road | Road improvement works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44335 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
872 | Upgrading of Matulo - Kibu House Road | Road improvement works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44332 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
873 | Upgrading of Lugulu - Mayi Bilongo Road | Road improvement works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.650774/34.75764 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44333 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Not accesible needs construction
874 | Periodic Maintenance of Roads In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44327 |  | 15198325.8 | 15198325.8 | 15198325.8 | County Government of Bungoma |  | 15198325.8 |  | 15198325.8 | 99.9% | 15198325.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1172 | Periodic Maintenance of Chebosi Church - Pcu Church Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.616272/34.749960 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44702 |  | 15334305 | 15334305 | 15334305 | County Government of Bungoma |  | 15334305 |  | 15334305 |  | 15334305 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity
1173 | Periodic Maintenance of Matulo Corner - Juma Game Park - Matulongwelo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.611634/34.711662 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44693 |  | 15334305 | 15334305 | 15334305 | County Government of Bungoma |  | 15334305 |  | 15334305 |  | 15334305 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1174 | Periodic Maintenance of Simala Bandu - Musekese - Wanyama - R. Muji Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.589667/34.730679 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44704 |  | 15334305 | 15334305 | 15334305 | County Government of Bungoma |  | 15334305 |  | 15334305 |  | 15334305 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project was poorly done needs renovation
1175 | Periodic Maintenance of Nalianya Wamang'Oli Pri - Ndemaki Water Spring - Assistant Chief Office - Bilongo Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.625783/34.724833 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44703 |  | 15334305 | 15334305 | 15334305 | County Government of Bungoma |  | 15334305 |  | 15334305 |  | 15334305 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is working well
1176 | Periodic Maintenance of Kmtc - Jovena - Sda Flyover - Malaha Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Matulo | 0.15608/18.5472-44.6994/9.57324 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44702 | 44733 | 2770085.8 | 2770085.8 | 2770085.8 | County Government of Bungoma |  | 2770085.8 |  | 2770085.8 |  | 2770085.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1177 | Periodic Maintenance of Roads In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44698 |  | 15334305 | 15334305 | 15334305 | County Government of Bungoma |  | 15334305 |  | 15334305 | 99.3% | 15334305 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Completed and in use
1178 | Routine Maintenance Of Kmtc - Jovenah - Sda - Flyover - Malaha Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Matulo | 19.5472/15.60869-44.6994/9.57324 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44700 |  | 2770085.8 | 2770085.8 | 2770085.8 | County Government of Bungoma |  | 2770085.8 |  | 2770085.8 | 95.73% | 2770085.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs renovation
1471 | Periodic Maintenance of Salvation Army - Mwanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.63KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45067 |  | 2297757 | 2297757 | 2297757 | County Government of Bungoma |  | 2297757 |  | 2297757 |  | 2297757 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1472 | Periodic Maintenance of Masaba - Panda Miti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.0605169/34.735422 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45056 |  | 4748738 | 4748738 | 4748738 | County Government of Bungoma |  | 4748738 |  | 4748738 |  | 4748738 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1473 | Periodic Maintenance of Minata - Malaha - Pefa - Mupeli - Kayaya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.634818/34.720148 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45064 | 45095 | 7225882 | 7225882 | 7225882 | County Government of Bungoma |  | 7225882 |  | 7225882 |  | 7225882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No culves renovation done
1474 | Periodic Maintenance of Masaba - Panda Miti Road In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45070 |  | 4748738 | 4748738 | 4748738 | County Government of Bungoma |  | 4748738 |  | 4748738 | 80.87% | 4748738 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1475 | Periodic Maintenance of Minata - Malaha - Pefa - Mupeli - Kayaya Road In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45067 |  | 7225882 | 7225882 | 7225882 | County Government of Bungoma |  | 7225882 |  | 7225882 | 99.19% | 7225882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1476 | Periodic Maintenance of Salvation Army Mwanja Road In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.63KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45056 |  | 2297757 | 2297757 | 2297757 | County Government of Bungoma |  | 2297757 |  | 2297757 | 100% | 2297757 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project needs rehabilitation
1713 | Periodic Maintenance of Cameroon - Mara Moja - Late Councilor Khaemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.613354/34.754355 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45428 |  | 3365334 | 3365334 | 3365334 | County Government of Bungoma |  | 3365334 |  | 3365334 |  | 3365334 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs maintenance
1714 | Periodic Maintenance of Flyover P.A.G - Mulati And Satellite - Munyikana Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45424 |  | 5158250 | 5158250 | 5158250 | County Government of Bungoma |  | 5158250 |  | 5158250 |  | 5158250 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1715 | Periodic Maintenance of Transformer - Matulo Corner - Mwalimu Titus - Chindoboli Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.608028/34.717946 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45435 |  | 4956042 | 4956042 | 4956042 | County Government of Bungoma |  | 4956042 |  | 4956042 |  | 4956042 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Work needs culverts
1716 | Construction of Kayaya - Bilongo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.638715/34.719352 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45428 |  | 7537140 | 7537140 | 7537140 | County Government of Bungoma |  | 7537140 |  | 7537140 |  | 7537140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1717 | Periodic Maintenance of Cameroon - Mara Moja - Late Councilor Khaemba Road In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45435 |  | 3365334 | 3365334 | 3365334 | County Government of Bungoma |  | 3365334 |  | 3365334 | 99.51% | 3365334 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1718 | Periodic Maintenance of Fly Over - P.A.G - Mulati Road And Satellite - Munyikana Road In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo | 0.362999556/34.45569284 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45431 |  | 5158250 | 5158250 | 5158250 | County Government of Bungoma |  | 5158250 |  | 5158250 | 99.96% | 5158250 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1719 | Periodic Maintenance of Transformer - Matulo Corner - Mwalimu Titus - Chindoboli Road In Matulo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45431 |  | 4956042 | 4956042 | 4956042 | County Government of Bungoma |  | 4956042 |  | 4956042 | 97.49% | 4956042 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1720 | Proposed Kayaya - Bilongo Box Culvert In Matulo Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45427 |  | 7537140 | 7537140 | 7537140 | County Government of Bungoma |  | 7537140 |  | 7537140 | 99.76% | 7537140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1 | Review of Physical and development plan for Webuye Urban Area | Document review,Desktop research, Gaps analysis, Report Writing and formulation of new maps, Stakeholder engagement for new vision and direction of the urban area | To guide sustainable and inclusive growth of urban areas through land use,infrastructure development and improved service delivery | One Physical and land use plan for Webuye Urban Area developed | 2211311 | Development/Physical Planning | Webuye West | Matulo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 15/5/2024 | 15/11/2024 | 15/11/2024 | 2600000 | 2567080 | 2567080 | CGB | N/A | 2567080 | 0 | 2567080 | 100% | 513416 | 2053664 | 0 | Completed | 1 | N/A | N/A | N/A | N/A | 0 | No |  |  | No |  | No |  |  |  | The project is 100% complete and in use
52 | Purchase of 1/4 Acre land for Webuye S.A E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of ECDE centre | One quater acre of Land for Webuye S.A ECDE Purchased | 3110599 | Ward based projects | Webuye West | Matulo | 30.75084/34.32292 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2021/22 | 45078 | 45413 | 45597 | 2000000 | 1500000 | 1500000 | CGB |  | 1500000 |  | 1500000 | 100% | 1500000 |  |  | Completed | 1 | [14 empty] | The land is available but not completed
67 | Purchase of land for Matulo ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of expansion of ECDE centre | One acre of land for Matulo ECDE Purchased | 3110599 | Ward based projects | Webuye West | Matulo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 | 23/12/2020 | 23/03/2021 | 30/4/2021 | 2000000 | 1500000 | 1500000 | CGB |  | 1500000 |  | 1500000 | 100% | 1500000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
108 | Proposed replacement of roof covering of Webuye Medical staff Quarters flats. | Replacement of roof | To enhance revenue collection | Two storey County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Webuye West | Matulo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2018/19 | 43740 | 43803 | 25/4/2019 | 3500000 | 3442000 | 3442000 | CGB | N/A | 3422000 | 0 | 3422000 | 100% | 3422000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
10 | Construction of 1 No. ECDE classroom at Wenyela primary school in Matulo Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Matulo | 0.646984/34.737939 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 1500000 | 1489610 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 |  | 0% |  | 1489610 | 1489610 | ongoing | At substructure (15%)
220 | Construction of classrooms at webuye DEB and Matulo primary schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Matulo | 0.2328408/46.1363476 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2000000 | 1997989 | 2000000 | County Government of Bungoma | N/A | 2000000 |  |  | 0% | 0 | 1997989 |  | Complete | 0.5
39 | Proposed Tree Growing Within Institutions In Luuya/Bwake, Matulo, Mihuu, Kamukuywa, And Naitiri/Kabuyefwe Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Webuye West | Matulo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45452 | 45455 | 45455 | 5917500 | 5910500 | 5910500 | FLLOCA | IDA | 0 | 5910500 | 0 | 100% | 0 | 0 |  | Re-tendered | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | The project is in use
67 | Protection of 10no. Water Springs in Matulo Ward | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo | 0.637025/34.730984 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2000000 | 1957616 | 1957616 | CGB | N/A | 1957616 | 0 | 1957616 | 100% | 1957616 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
84 | Drilling and Equipping of Webuye S.A Primary Borehole in Matulo Ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo | 36.23284/34.46136347 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2500000 | 2297624 | 2297624 | CGB | N/A | 2297624 | 0 | 2297624 | 100% | 0 | 2297624 | 0 | Work in progress | 40%complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
107 | Protection of 4no. Water springs in matulo ward | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo | 03489114/34.45584683 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1000000 | 932992 | 932992 |  | N/A | 932992 | 0 | 932992 | 100% | 932992 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
236 | DRILLING OF 2NO. BOREHOLES AND PIPELINE EXTENSION IN MATULO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 4000000 | 3993532 | 3993532 |  | N/A | 3993532 | 0 | 3993532 | 100% | 3993532 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
298 | CONSTRUCTION OF MATULO-WAMANG’OLI PIPELINE WATER PROJECT IN MATULO WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2700000 | 2537191 | 2537191 |  | N/A | 2537191 | 0 | 2537191 | 100% | 2537191 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
364 | Nzowasco pipeline extension to Matulo | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo | 0.605926/34.727057 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 3800000 | 3569066 | 3569066 |  | N/A | 3569066 | 0 | 3569066 | 100% | 3569066 | 0 | 0 | Ongoing | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Increase pressure
391 | Protection of 10 water Springs and Construction of 4 Shallow wells | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed; 4 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo | 0.36089114/34.455846832 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 400000 | 360573 | 360573 |  | N/A | 360573 | 0 | 360573 | 100% | 360573 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
407 | Protection of 3 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo | 0.363075/34. | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 500000 | 449370 | 449370 |  | N/A | 449370 | 0 | 449370 | 100% | 449370 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
443 | Protection of 10 water Springs and Construction of 4 Shallow wells | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs Constructed and 4 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1000000 | 841337 | 841337 |  | N/A | 841337 | 0 | 841337 | 100% | 841337 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
514 | Protection of 3 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 of water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 500000 | 449370 | 449370 |  | N/A | 449370 | 0 | 449370 | 100% | 449370 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
515 | Nzowasco pipeline extension to Matulo | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo | 0.608013/34.759960 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3700000 | 3569066 | 3569066 |  | N/A | 3569066 | 0 | 3569066 | 100% | 3569066 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
592 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Matulo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1400000 | 1201910 | 1201910 |  | N/A | 1201910 | 0 | 1201910 | 100% | 1201910 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
32 | Proposed installation and commissioning of 3 NO. 15M high powered floodlights | installation of NO M | promotion of MSMEs and security | High powered flood light installed | 1358576/2023-24 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 3000000 |  |  | CGB | [8 empty] | Complete | 100 | 3
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye | [5 empty] | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
104 | Proposed installation of 35 no. Grid powered street lights in Webuye East, Webuye West, Kimilili and Bumula Sub Counties | installation Grid lights East Kimilili street Kimilili and | [5 empty] | Matulo |  |  |  | M/S Rygeo Tech Solution | 2020/21 |  | Complete |  | 3232265 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Matulo |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Matulo | 0.641512/34.749475 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed | [15 empty] | Died but calves are there
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Matulo | 0.634818/34.720148 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed | [15 empty] | Is in use
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo | 0.593763/34.734967 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed | [15 empty] | Not found
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Matulo | 0.632377/34.717090 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed | [15 empty] | Was sold
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Matulo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Matulo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
50 | Erection and completion works for female, male and children's ward at kimalewa Health Centre. | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Female, male and children wards erected and completed |  |  | Kabuchai | Mukuyuni | 0.817787,34.663714 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 13/2/2024 |  |  | 5000000 | 4999800 | 4999800 | CGB |  | 4999800 | 0 | 4084800 | 0.81699 | 4084800 |  | 915000 | stalled | 92 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
242 | Completion Of Sikulu Health Centre | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | health centres completed |  |  | Kabuchai | Mukuyuni | 0.751121,34.632529 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1000000 | 0 | 0 | CGB |  | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No
23 | Upgrading of Bondeni-Lukokwe Lower Mukuyuni | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41649 | 41779 |  | 3805525 | 3805525 | 3805525 | County Government of Bungoma |  | 3805525 |  | 3805525 | 100.0% | 3805525 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
221 | Periodic Maintenance of Kuywa Junction - Sikulu School - Njimbwakale - Lukhuna A School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43231 |  | 8867405.4 | 8867405.4 | 8867405.4 | County Government of Bungoma |  | 8867405.4 |  | 8867405.4 |  | 8867405.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
222 | Periodic Maintenance of Milembe - Buyanji Area Kapkateny | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.7864861,34.626954 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43232 |  | 8867405.4 | 8867405.4 | 8867405.4 | County Government of Bungoma |  | 8867405.4 |  | 8867405.4 |  | 8867405.4 | 0 | 0 | complete and in use but culverts needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
223 | Periodic Maintenance of Roads In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43238 |  | 8867405.4 | 8867405.4 | 8867405.4 | County Government of Bungoma |  | 8867405.4 |  | 8867405.4 | 100.0% | 8867405.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
408 | Periodic Maintenance of Roads In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43484 | 43603 |  | 9485784 | 9485784 | 9485784 | County Government of Bungoma |  | 9485784 |  | 9485784 | 99.65% | 9485784 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
409 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
603 | Periodic Maintenance of Sichei -Primary - Chengeni - Samita Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43965 |  | 7477360 | 7477360 | 7477360 | County Government of Bungoma |  | 7477360 |  | 7477360 |  | 7477360 | 0 | 0 | complete and in use but culverts needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
604 | Grading of Sichei-Kibichori Road | Grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.74748,34.692846 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | completed but periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
605 | Upgrading of Chebukaka - Lukhome - Mpakani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | Mukuyuni | 0.790314,34.596163 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43961 |  | 6099976 | 6099976 | 6099976 | County Government of Bungoma |  | 6099976 |  | 6099976 |  | 6099976 | 0 | 0 | completed but periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
606 | Upgrading of Spot Improvement Of Chebukaka - Lukhome - Mpakani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | Mukuyuni | 0.790314,34.596163 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43969 |  | 6099976 | 6099976 | 6099976 | County Government of Bungoma |  | 6099976 |  | 6099976 | 95.72% | 6099976 | 0 | 0 | completed but periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
607 | Periodic Maintenance of Roads In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43963 |  | 7477360 | 7477360 | 7477360 | County Government of Bungoma |  | 7477360 |  | 7477360 | 99.98% | 7477360 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
911 | Periodic Maintenance of Namarare - Chepsitati - Lukhome Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.763834,34.598038 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44330 |  | 10259701.2 | 10259701.2 | 10259701.2 | County Government of Bungoma |  | 10259701.2 |  | 10259701.2 |  | 10259701.2 | 0 | 0 | completed but periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
912 | Periodic Maintenance of Sikhana - Mbako - Makhonge Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.764456,34.576780 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44326 |  | 10259701.2 | 10259701.2 | 10259701.2 | County Government of Bungoma |  | 10259701.2 |  | 10259701.2 |  | 10259701.2 | 0 | 0 | completed and in use but culverts needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
913 | Periodic Maintenance of Roads In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44337 |  | 10259701.2 | 10259701.2 | 10259701.2 | County Government of Bungoma |  | 10259701.2 |  | 10259701.2 | 99.98% | 10259701.2 | 0 | 0 | completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1216 | Periodic Maintenance of Ap Camp - Teremi Primary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.771427,34.611703 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44705 |  | 18977049 | 18977049 | 18977049 | County Government of Bungoma |  | 18977049 |  | 18977049 |  | 18977049 | 0 | 0 | completed and in use but periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1217 | Periodic Maintenance of Kuywa Market - Sikulu - Lukhuna Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.750486,34.649066 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44699 |  | 18977049 | 18977049 | 18977049 | County Government of Bungoma |  | 18977049 |  | 18977049 |  | 18977049 | 0 | 0 | completed, periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1218 | Periodic Maintenance of Chebusitati Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.750486,34.655631 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44705 |  | 18977049 | 18977049 | 18977049 | County Government of Bungoma |  | 18977049 |  | 18977049 |  | 18977049 | 0 | 0 | completed, periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1219 | Periodic Maintenance of Sichei Cattle Dip - Chwele River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.742997,34.605224 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44703 |  | 18977049 | 18977049 | 18977049 | County Government of Bungoma |  | 18977049 |  | 18977049 |  | 18977049 | 0 | 0 | completed, periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1220 | Periodic Maintenance of Chebukaka - Kimalewa - R. Kibisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.2KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Mukuyuni | 0.751911,34.613740 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44693 | 44724 | 4654053.4 | 4654053.4 | 4654053.4 | County Government of Bungoma |  | 4654053.4 |  | 4654053.4 |  | 4654053.4 | 0 | 0 | completed and in use but culverts needed& periodic maintainance | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1221 | Periodic Maintenance of Roads In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.750929,34.649703 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44695 |  | 18977049 | 18977049 | 18977049 | County Government of Bungoma |  | 18977049 |  | 18977049 | 100.0% | 18977049 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1222 | Spot Improvement Of Chebukaka - Kimalewa - R. Kibisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.2KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Mukuyuni | 0.752310,34.649213 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44705 |  | 4654053.4 | 4654053.4 | 4654053.4 | County Government of Bungoma |  | 4654053.4 |  | 4654053.4 | 100.0% | 4654053.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1503 | Periodic Maintenance of Milembe Justimore Church - Ex Chief - Kibisi Factory - Believers - Cattle Dip - Chwele River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45066 |  | 18803057 | 18803057 | 18803057 | County Government of Bungoma |  | 18803057 |  | 18803057 |  | 18803057 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1504 | Periodic Maintenance of Chebukaka - Lukhome Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.755898,34.609157 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45064 |  | 2994540 | 2994540 | 2994540 | County Government of Bungoma |  | 2994540 |  | 2994540 |  | 2994540 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1505 | Periodic Maintenance of Milembe Jastimo Church - Ex Chief - Kibisi Factory - Believers - Cattle Dip - Chwele River Road In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45059 |  | 18803057 | 18803057 | 18803057 | County Government of Bungoma |  | 18803057 |  | 18803057 | 99.95% | 18803057 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1506 | Framework Contracts For Maintenance Of Roads In Kabuchai And Sirisia Sub Counties | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45060 |  | 2994540 | 2994540 | 2994540 | County Government of Bungoma |  | 2994540 |  | 2994540 | 98.28% | 2994540 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1754 | Periodic Maintenance of Chepsitati - Chepkpongoi - Nalyanya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45436 |  | 5073840 | 5073840 | 5073840 | County Government of Bungoma |  | 5073840 |  | 5073840 |  | 5073840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1755 | Periodic Maintenance of Namasaka - Njibwakale - Catholic - Friends Schurch - Nakitari Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45432 |  | 6030318 | 6030318 | 6030318 | County Government of Bungoma |  | 6030318 |  | 6030318 |  | 6030318 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1756 | Periodic Maintenance of Kimalewa - Milembe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.784662,34.640468 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45426 |  | 3030384 | 3030384 | 3030384 | County Government of Bungoma |  | 3030384 |  | 3030384 |  | 3030384 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1757 | Periodic Maintenance of Milembe-Lukhome Road In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.786486,34.621529 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45434 |  | 4831400 | 4831400 | 4831400 | County Government of Bungoma |  | 4831400 |  | 4831400 | 100.0% | 4831400 | 0 | 0 | completed, periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1758 | Periodic Maintenance of Namasaka - Njibwakale - Catholic - Friends Church - Nakitari Road In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.734200,34.657108 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45425 |  | 6030318 | 6030318 | 6030318 | County Government of Bungoma |  | 6030318 |  | 6030318 | 100.0% | 6030318 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1759 | Periodic Maintenance of Periodic Maintenance Of Chekwanda Market - Wasike - Mabonga - Pcu Church Road In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45427 |  | 5519976 | 5519976 | 5519976 | County Government of Bungoma |  | 5519976 |  | 5519976 | 99.99% | 5519976 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1760 | Periodic Maintenance of Chepsitati - Chepkongoi - Nalyanya Road In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.7668820,34.691201 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45426 |  | 5073840 | 5073840 | 5073840 | County Government of Bungoma |  | 5073840 |  | 5073840 | 82.21% | 5073840 | 0 | 0 | completed, periodic maintainance needed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1761 | Periodic Maintenance of Kimalewa - Milembe Road In Mukuyuni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Mukuyuni | 0.784662,34.613269 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45426 |  | 3030384 | 3030384 | 3030384 | County Government of Bungoma |  | 3030384 |  | 3030384 | 99.95% | 3030384 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
141 | Purchase of land for chekwanda ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for chekwanda ECDE Purchased | 3110599 | Ward based projects | Kabuchai | Mukuyuni |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 42497 | 42499 | 20/10/2016 | 400000 | 400000 | 400000 | CGB | N/A | 400000 |  | 400000 | 1 | 400000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
142 | Purchase of Land for Buyanji ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Buyanji ECDE Purchased | 3110599 | Ward based projects | Kabuchai | Mukuyuni | 0.793964,34.613269 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 19/1/2017 | 19/3/2017 | 20/5/2017 | 400000 | 400000 | 400000 | CGB | N/A | 400000 |  | 400000 | 1 | 400000 |  |  | completed with onlu one building | 1 | [14 empty] | The project is 100% complete and not in use
187 | Purchase of land for Buyanji ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Buyanji ECDE Purchased | 3110599 | Ward based projects | Kabuchai | Mukuyuni | 0.793964,34.613269 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42616 | 42619 | 9/04//2016 | 400000 | 400000 | 400000 | CGB | N/A | 400000 |  | 400000 |  | 400000 |  |  | completed with onlu one building | 1 | [14 empty] | The project is 100% complete and in use
13 | Construction of 1 No. ECDE Classroom at Sichei and Matisi Primary Schools in Mukuyuni Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Mukuyuni | 0.15571,34.59453 0.717721,34.626382 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3000000 | 2911520 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0 |  | 2911520 | 2911520 | completed with onlu one building | At substructure (15%)
89 | Construction of 1No ECDE Classroom in Chebukaka Boys and St Walumoli primary schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Mukuyuni | 0.753428,34.612074 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3000000 | 2999600 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0 |  | 2999600 | 2999600 | completed with onlu one building | 1
122 | Construction Of 1 No. Ecde And 2 No. Door Pit Latrine At Lukhome And Kuywa Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Mukuyuni | kuywa ecde(0.772617,34.641416) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 5500000 | 3441960 | 5500000 | County Government of Bungoma | N/A | 5500000 | 0 | 3441960 | 1 | 3441960 | 0 | 0 | completed with onlu one building | 1
156 | Proposed Erection And Completionof 1 No. Ecde At Milembe, Hon. Wetangula Sango And Lukhuna Primary Schools In Mukuyuni Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Mukuyuni | 0.732787,34.657096 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3600000 | 3586960 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3586960 | 1 | 3586960 | 0 | 0 | completed with onlu one building | 1
206 | Construction Of 1no. Ecde Classroom At St.Charles Buyanji And Makhomge Primary Schools And Renovation Of Mukuyuni Vocational Training Centre In Mukuyuni Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Mukuyuni | 0.758196,34.605155 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3800000 | 3745396.4 | 3800000 | County Government of Bungoma | N/A | 3800000 |  | 3745396.4 | 1 | 3745396.4 | 0 |  | completed with onlu one building | 100.0%
13 | Upgrading of Chenjeni Primary and Tabani Boreholes in Mukuyuni/Chwele Kabuchai Wards | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kabuchai | Mukuyuni | 0.750537,34.631540 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 6000000 | 5820416 | 5820416 | FLLOCA | N/A | 5820416 | 0 | 0 | 1 | 5820416 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
69 | Pipeline Extension on KOICA Sichei Sub-location | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2915544 | 2915544 | CGB | N/A | 2915544 | 0 | 2915544 | 1 | 2915544 | 0 | 0 | completed with onlu one building | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
178 | rehabilitation of lukhome-chebukaka water piping in mukuyuni ward | Trenching ; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4100000 | 4060000 | 4060000 |  | N/A | 4060000 | 0 | 4060000 | 1 | 4060000 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
228 | DRILLING OF 3NO. BOREHOLES IN MUKUYUNI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni | 0.745226,34.652652 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 4100000 | 4015920 | 4015920 |  | N/A | 4015920 | 0 | 4015920 | 1 | 4015920 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
279 | CONSTRUCTION OF MUKUYUNI WATER SPRINGS AND BOREHOLE DRILLING PROJECT IN MUKUYUNI WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection; site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 1 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni | 0.751136,34.640222 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3000000 | 2883237.5 | 2883237.5 |  | N/A | 2883237.5 | 0 | 2883237.5 | 1 | 2883237.5 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
345 | Construction of Kibichori – Bokoli Water Supply including 100m3 tank. | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | KM of pipeline constructed and 1 storage tank erected | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 6500000 | 6211331.75 | 6211331.75 |  | N/A | 6211331.75 | 0 | 6211331.75 | 1 | 6211331.75 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
427 | Construction of Kibichori – Bokoli Water Supply including 100m3 tank. | erection of storage tank; pipeline extension and provision of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed; and erection of 1 storage tank | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 10000000 | 9316997.85 | 9316997.85 |  | N/A | 9316997.85 | 0 | 9316997.85 | 1 | 9316997.85 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
446 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs. constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni | 0.735127,34.640439 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1480759.8 | 1480759.8 |  | N/A | 1480759.8 | 0 | 1480759.8 | 1 | 1480759.8 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
493 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni | 0.735127,34.640439 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1480760 | 1480760 |  | N/A | 1480760 | 0 | 1480760 | 1 | 1480760 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
494 | Construction of 5Roof catchment and 1 Storage tank at chepsitati primary school | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni | 0.65208,34.565621 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1368750 | 1368750 |  | N/A | 1368750 | 0 | 1368750 | 1 | 1368750 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
495 | Construction of Kibichori – Bokoli Water Supply including 100m3 tank. | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed and tank constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 16000000 | 15528329.75 | 15528329.75 |  | N/A | 15528329.75 | 0 | 15528329.75 | 1 | 15528329.75 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
567 | Construction of Nakoyonjo W/s | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Mukuyuni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3447044 | 3447044 |  | N/A | 3447044 | 0 | 3447044 | 1 | 3447044 | 0 | 0 | completed with onlu one building | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Construction of Coffee Drying Table at Sichei, Chenjeni, and Kibisi | Construction of 10 Coffee Drying Table at Sichei, Chenjeni, and Kibisi | To support growth of coffee farmers and enhance income generation | 10 Coffee Drying tables constructed at Nanjikobe FCS | 3110504 | Other infrastructure and civil works | Kabuchai | Mukuyuni | 0.746229,34.639965 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44479 | 44837 | 23/5/2022 | 6000000 | 1450000 | 1500000 | County Government of Bungoma |  | 1450000 | 0 | 1450000 | 1 | 1450000 | 0 | 0 | completed with onlu one building
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Mukuyuni |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Mukuyuni |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Mukuyuni | 0.785314,34.602243 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | completed,migrated and project stalled
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Mukuyuni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Mukuyuni | 0.750312,34.613442 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Mukuyuni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Bikoti spring | [5 empty] | Kabuchai | Mukuyuni |  | water & irrigation |  |  | 2017/2018 | [15 empty] | completed and in use
| Street lights kimalewa shopping centre | [5 empty] | Kabuchai | Mukuyuni | 0.780912,34.640812 | Trade, Energy and Industrialization |  |  | 2022/23 | [15 empty] | completed, needs more street lights
| Baraki Primary ecde | [5 empty] | Kabuchai | Mukuyuni | 0.760181,34.640149 | Education and Vocational Training |  |  | 2024/25 | [15 empty] | ongoing
| Green house(NEEMA DISABILITY GROUND KUYWA) | [5 empty] | Kabuchai | Mukuyuni | 0.751098,34.640401 | Agriculture |  |  | 2024/25 | [15 empty] | ongoing
| Street lights Kuywa market | [5 empty] | Kabuchai | Mukuyuni | 0.750888,34.644898 | Trade, Energy and Industrialization |  |  | 2020/21 | [15 empty] | completed, more needed
| Solar light Kuywa market | [5 empty] | Kabuchai | Mukuyuni | 0.750888,34.644898 | Trade, Energy and Industrialization |  |  | 2014/15 | [15 empty] | completed, needs repair
| Boda boda shade Kuywa | [5 empty] | Kabuchai | Mukuyuni | 0.750888,34.644898 | Trade, Energy and Industrialization |  |  | 2017/18 | [15 empty] | completed and in use
| Baraki Vocational Training Centre | [5 empty] | Kabuchai | Mukuyuni | 0.770910,34.641398 | Education |  |  | 2016/17 | [15 empty] | completed
| Sisenda-Mutaki Road Namawanga | [5 empty] | Kabuchai | Mukuyuni | 0.764054,34.636066 | Roads |  |  | 2024/25 | [15 empty] | completed
| Bikoti spring | [5 empty] | Kabuchai | Mukuyuni |  |  |  |  | 2017/18 | [15 empty] | completed
18 | construction of Binyenya dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Tongaren | Tongaren |  |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 2000000 |  |  | CGB |  |  | 0 | 535000 | #DIV/0! | 535000 | 165742.7 | -535000 | yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No
118 | Construction Of Binyenya Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Tongaren | Tongaren |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1500000 |  |  | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No
152 | Construction Of 2no. Door Toilets At Lukhuna And Ambichi Markets | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 2no door toilets constructed |  |  | Tongaren | Tongaren | 0.790138,34.993377 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 800000 | 799280 | 799280 | CGB |  | 799280 | 0 | 0 | 0 | 0 |  | 799280 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
317 | Construction of 4-door public toilet | Digging of 20ft deep fit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the market. | 4no.door public toilets constructed |  |  | Tongaren | Tongaren |  |  | CEF | Health & Sanitation | 2016/17 | 22nd/Feb/2017 |  | 22nd /May/2017 |  | 1194540 | 1194540 | CGB |  | 1194540 | 0 | 0 | 0 | 0 |  | 1194540 | completed | [6 empty] | No | complete | Financial | Yes
96 | Periodic Maintenance of Soysambu - Brigadier - R. Nzoia | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2014/2015 | 42026 | 42141 |  | 26427248.12 | 26427248.12 | 26427248.12 | County Government of Bungoma |  | 26427248.12 |  | 26427248.12 | 100.0% | 26427248.12 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
109 | Periodic Maintenance of Rehabilitation Of Mutoto Junction Tongaren (Mkt Access) Roads | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.779515,34.963224 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42381 | 42513 |  | 4085752 | 4085752 | 4085752 | County Government of Bungoma |  | 4085752 |  | 4085752 | 100.0% | 4085752 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
110 | Periodic Maintenance of Periodic Maintenance - Lunao - Karani Roads | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42391 | 42506 |  | 5475316 | 5475316 | 5475316 | County Government of Bungoma |  | 5475316 |  | 5475316 | 97.22% | 5475316 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
140 | Upgrading of Misikhu Brigadier Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.783621,34.993180 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42756 | 42865 |  | 1115939198 | 1115939198 | 1115939198 | County Government of Bungoma |  | 1115939198 |  | 1115939198 | 97.47% | 1115939198 | 0 | 0 | ongoing | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
141 | Periodic Maintenance of Milele Primary-Makololwe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.806894,34.998540 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42757 | 42878 |  | 6491940 | 6491940 | 6491940 | County Government of Bungoma |  | 6491940 |  | 6491940 | 100.0% | 6491940 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
258 | Construction of Box Culvert At Milimani - Binyenya And Namungu Road | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.842256,34.949468 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43241 |  | 8386295.4 | 8386295.4 | 8386295.4 | County Government of Bungoma |  | 8386295.4 |  | 8386295.4 |  | 8386295.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
259 | Periodic Maintenance of Lukhuna Friends - Bunambo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.8088041,34.9470448 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43236 |  | 8386295.4 | 8386295.4 | 8386295.4 | County Government of Bungoma |  | 8386295.4 |  | 8386295.4 |  | 8386295.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
260 | Periodic Maintenance of Roads In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.782809,34.963489 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43241 |  | 8386295.4 | 8386295.4 | 8386295.4 | County Government of Bungoma |  | 8386295.4 |  | 8386295.4 | 99.77% | 8386295.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
261 | Periodic Maintenance of Maintenance Of Makunga Mkt - Karima Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43243 |  | 10500000 | 10500000 | 10500000 | County Government of Bungoma |  | 10500000 |  | 10500000 | 99.52% | 10500000 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
262 | Periodic Maintenance of Andere-Katasi-Justice Nambuye-Mfunje | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.783271,34.963036 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43231 |  | 7012896 | 7012896 | 7012896 | County Government of Bungoma |  | 7012896 |  | 7012896 | 99.82% | 7012896 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
263 | Periodic Maintenance of Naitiri-Mukhuyu Junct-Lunyu | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43235 |  | 14907508 | 14907508 | 14907508 | County Government of Bungoma |  | 14907508 |  | 14907508 | 97.45% | 14907508 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
434 | Construction of Njiwa Box Culvert In Tongaren Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.797474,34.979287 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43604 |  | 8661441.6 | 8661441.6 | 8661441.6 | County Government of Bungoma |  | 8661441.6 |  | 8661441.6 | 99.67% | 8661441.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
435 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.782237,34.965273 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
436 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
437 | Periodic Maintenance of Mfupi -Musembe-Margaret Kakai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43489 | 43596 |  | 7916304 | 7916304 | 7916304 | County Government of Bungoma |  | 7916304 |  | 7916304 | 99.98% | 7916304 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
438 | Periodic Maintenance of St Kizito Jnt-Bunambo Fym Pri. Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43603 |  | 12251253 | 12251253 | 12251253 | County Government of Bungoma |  | 12251253 |  | 12251253 | 99.98% | 12251253 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
492 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
598 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
656 | Periodic Maintenance of Jeshi La Wokovu - Njiwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.781820,34.969089 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43973 |  | 6888764 | 6888764 | 6888764 | County Government of Bungoma |  | 6888764 |  | 6888764 |  | 6888764 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
657 | Periodic Maintenance of Roads In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.780335,34.963496 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43964 |  | 6888764 | 6888764 | 6888764 | County Government of Bungoma |  | 6888764 |  | 6888764 | 94.7% | 6888764 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
658 | Periodic Maintenance of Binyenya - Ndalu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.87647,34.987081 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43965 |  | 10702566 | 10702566 | 10702566 | County Government of Bungoma |  | 10702566 |  | 10702566 |  | 10702566 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
659 | Periodic Maintenance of Binyenya - Ndalu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.87647,34.987081 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43964 |  | 10702566 | 10702566 | 10702566 | County Government of Bungoma |  | 10702566 |  | 10702566 |  | 10702566 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
660 | Periodic Maintenance of Kibisi-Karima-River Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43970 |  | 10881916 | 10881916 | 10881916 | County Government of Bungoma |  | 10881916 |  | 10881916 | 95.57% | 10881916 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
661 | Periodic Maintenance of Binyenya-Ndalu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.87647,34.987081 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43971 |  | 10702566 | 10702566 | 10702566 | County Government of Bungoma |  | 10702566 |  | 10702566 | 98.83% | 10702566 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
969 | Periodic Maintenance of Vtc - Juspas - Opala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.769074,34.971130 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44338 |  | 8287492.4 | 8287492.4 | 8287492.4 | County Government of Bungoma |  | 8287492.4 |  | 8287492.4 |  | 8287492.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
970 | Periodic Maintenance of Lukhuna - Malala - Narwenyi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.8670715,34.8843143 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44338 |  | 8287492.4 | 8287492.4 | 8287492.4 | County Government of Bungoma |  | 8287492.4 |  | 8287492.4 |  | 8287492.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
971 | Periodic Maintenance of Tongaren Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.781666,34.962487 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
972 | Periodic Maintenance of Kakamwe - Mfunje Saliwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.782711,34.981674 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
973 | Periodic Maintenance of Roads In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.783312,34.962393 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44340 |  | 8287492.4 | 8287492.4 | 8287492.4 | County Government of Bungoma |  | 8287492.4 |  | 8287492.4 | 100.0% | 8287492.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
974 | Periodic Maintenance of Mawe Moja - Mapera - Minyali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44336 |  | 7311784 | 7311784 | 7311784 | County Government of Bungoma |  | 7311784 |  | 7311784 |  | 7311784 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
975 | Periodic Maintenance of Naitiri Junction - Wangusi - Lungai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44339 |  | 6077878 | 6077878 | 6077878 | County Government of Bungoma |  | 6077878 |  | 6077878 |  | 6077878 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
976 | Periodic Maintenance of Mitelwa - Lunyu - Kibisi -Nzoia River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44339 |  | 7757587 | 7757587 | 7757587 | County Government of Bungoma |  | 7757587 |  | 7757587 |  | 7757587 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
977 | Spot Improvement Of Mawe Moja - Mapera - Minyali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44331 |  | 7311784 | 7311784 | 7311784 | County Government of Bungoma |  | 7311784 |  | 7311784 | 97.57% | 7311784 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
978 | Periodic Maintenance of Naitiri Junction - Wangusi - Lungai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44340 |  | 6077878 | 6077878 | 6077878 | County Government of Bungoma |  | 6077878 |  | 6077878 | 95.01% | 6077878 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
979 | Spot Improvement Of Mitelwa - Lunyu - Kibisi - Nzoia River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44330 |  | 7757587 | 7757587 | 7757587 | County Government of Bungoma |  | 7757587 |  | 7757587 | 99.63% | 7757587 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
980 | Drainage Works In Kimilili And Tongaren | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44326 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | not done | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1305 | Periodic Maintenance of Makololwe - Kikwamet - Mona Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.794501,35.000108 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44701 | 44732 | 16131995.88 | 16131995.88 | 16131995.88 | County Government of Bungoma |  | 16131995.88 |  | 16131995.88 |  | 16131995.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1306 | Periodic Maintenance of Manyasa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.8063686,34.9456769 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 | 44733 | 16131995.88 | 16131995.88 | 16131995.88 | County Government of Bungoma |  | 16131995.88 |  | 16131995.88 |  | 16131995.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1307 | Periodic Maintenance of Wekulo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.7768002,34.8884517 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44698 | 44729 | 16131995.88 | 16131995.88 | 16131995.88 | County Government of Bungoma |  | 16131995.88 |  | 16131995.88 |  | 16131995.88 | 0 | 0 | not done | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1308 | Periodic Maintenance of Okech Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.821853,34.988894 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44700 | 44731 | 16131995.88 | 16131995.88 | 16131995.88 | County Government of Bungoma |  | 16131995.88 |  | 16131995.88 |  | 16131995.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1309 | Periodic Maintenance of Adagala - Kedego Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.867877,34.982838 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44697 | 44728 | 16131995.88 | 16131995.88 | 16131995.88 | County Government of Bungoma |  | 16131995.88 |  | 16131995.88 |  | 16131995.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1310 | Periodic Maintenance of Tongaren - Oruko - Wamukota Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.782979,34.962211 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44702 | 44733 | 16131995.88 | 16131995.88 | 16131995.88 | County Government of Bungoma |  | 16131995.88 |  | 16131995.88 |  | 16131995.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1311 | Periodic Maintenance of Roads In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.782809,34.963489 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44700 |  | 16131995.88 | 16131995.88 | 16131995.88 | County Government of Bungoma |  | 16131995.88 |  | 16131995.88 | 99.94% | 16131995.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1312 | Periodic Maintenance of Pwani Mkt - Mitua - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44693 | 44724 | 6489886.8 | 6489886.8 | 6489886.8 | County Government of Bungoma |  | 6489886.8 |  | 6489886.8 |  | 6489886.8 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1313 | Periodic Maintenance of Pwani Mkt - Mitua - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44702 | 44733 | 6489886.8 | 6489886.8 | 6489886.8 | County Government of Bungoma |  | 6489886.8 |  | 6489886.8 |  | 6489886.8 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1314 | Routine Maintenance Of Pwani Market - Mitua - R. Nzoia | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44695 |  | 6489886.8 | 6489886.8 | 6489886.8 | County Government of Bungoma |  | 6489886.8 |  | 6489886.8 | 98.42% | 6489886.8 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1552 | Periodic Maintenance of Olunga - Chief Namunyiri Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.782711,34.981674 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45058 |  | 7146903 | 7146903 | 7146903 | County Government of Bungoma |  | 7146903 |  | 7146903 |  | 7146903 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1553 | Periodic Maintenance of Safania - Makololwe Check Point - Wachilonga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.824132,34.989876 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45059 |  | 7146903 | 7146903 | 7146903 | County Government of Bungoma |  | 7146903 |  | 7146903 |  | 7146903 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1554 | Periodic Maintenance of Kiminini River - Lukhuna Jehovah Witness Junction | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.7750481,34.9184426 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45068 |  | 7146903 | 7146903 | 7146903 | County Government of Bungoma |  | 7146903 |  | 7146903 |  | 7146903 | 0 | 0 | completed and in bad state | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1555 | Periodic Maintenance of Nalondo - Sinoko Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.7740244,34.949112 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45062 |  | 7146903 | 7146903 | 7146903 | County Government of Bungoma |  | 7146903 |  | 7146903 |  | 7146903 | 0 | 0 | completed and fair | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1556 | Periodic Maintenance of Olunga - Chief Namunyiri, Safania Makololwe Checkpoint Wachilonga Road In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.782711,34.981674 (0.824132,34.989876) | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45066 |  | 7146903 | 7146903 | 7146903 | County Government of Bungoma |  | 7146903 |  | 7146903 | 87.05% | 7146903 | 0 | 0 | completed and in good state | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1557 | Periodic Maintenance of Kiminini River - Lukhuna Jehovah Witness Junction, Nalondo - Sinoko Road In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.7750481,34.9184426 (0.7740244,34.949112) | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45066 |  | 7146903 | 7146903 | 7146903 | County Government of Bungoma |  | 7146903 |  | 7146903 | 99.94% | 7146903 | 0 | 0 | completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1558 | Routine Maintenance Of Topstar-Sasaka Maresi Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45067 |  | 3707765 | 3707765 | 3707765 | County Government of Bungoma |  | 3707765 |  | 3707765 | 100.0% | 3707765 | 0 | 0 | N/A | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1803 | Periodic Maintenance of Mufunje - Musalaba Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.783271,34.963036 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45422 | 45453 | 7220608 | 7220608 | 7220608 | County Government of Bungoma |  | 7220608 |  | 7220608 |  | 7220608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1804 | Periodic Maintenance of Salvation Army - Grace Way Acedemy - Milele Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.797927,34.987156 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45422 | 45453 | 7220608 | 7220608 | 7220608 | County Government of Bungoma |  | 7220608 |  | 7220608 |  | 7220608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1805 | Periodic Maintenance of Lukhuna Junction - Machakha - Nabongolo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.801776,34.974903 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45426 | 45457 | 7843615 | 7843615 | 7843615 | County Government of Bungoma |  | 7843615 |  | 7843615 |  | 7843615 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1806 | Periodic Maintenance of Lukhuna Friends - Bunambo Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.8088041,34.9470448 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45423 | 45454 | 7843615 | 7843615 | 7843615 | County Government of Bungoma |  | 7843615 |  | 7843615 |  | 7843615 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1807 | Periodic Maintenance of Bituyu - Bidii - Julius Bridge Broad | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.8356763,34.9616456 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45423 | 45454 | 7843615 | 7843615 | 7843615 | County Government of Bungoma |  | 7843615 |  | 7843615 |  | 7843615 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1808 | Periodic Maintenance of Mabusi Junction - Namakhele Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.7734766,34.9553135 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45432 |  | 2864736 | 2864736 | 2864736 | County Government of Bungoma |  | 2864736 |  | 2864736 |  | 2864736 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1809 | Periodic Maintenance of S.A - Graceway Academy - Milele Primary Road And Mufunje - Musalaba Market Road In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.797927,34.987156 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45423 |  | 7220608 | 7220608 | 7220608 | County Government of Bungoma |  | 7220608 |  | 7220608 | 100.0% | 7220608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1810 | Periodic Maintenance of Bituyu - Bidii - Julius Bridge Road, Lukhuna Friends - Bunambo Market And Lukhuna Junction - Machakha - Nabongolo Road In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.8356763,34.9616456 (0.794779,34.971723) | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45435 |  | 7843615 | 7843615 | 7843615 | County Government of Bungoma |  | 7843615 |  | 7843615 | 100.0% | 7843615 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1811 | Periodic Maintenance of Mabusi Junction - Namakhele Road In Tongaren Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Tongaren | 0.7734766,34.9553135 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45435 |  | 2864736 | 2864736 | 2864736 | County Government of Bungoma |  | 2864736 |  | 2864736 | 100.0% | 2864736 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
37 | Purchase of 1 acre for Jerusa E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land for Jerusa ECDE purchased. | 3110599 | Ward based projects | Tongaren | Tongaren |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | - |  |  | 3000000 | 2000000 | 2000000 | CGB |  | 2000000 |  | 2000000 | 1 | 0 |  |  | N/A | 0 | 0 | Lack of documentations(Title deed) | 2022/23 |  |  | No | Compete | [7 empty] | The project is staled due Lack of documentations(Title deed)
38 | Purchase of 1 Acre for Makhonge D.E.B. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of expansion of ECDE centre | One acre of Land for Makhonge D.E.B. purchased | 3110599 | Ward based projects | Tongaren | Tongaren |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | - | - |  | 2000000 | 1300000 | 1300000 | CGB |  | 1300000 |  | 1300000 | 1 | 0 |  |  | N/A | 0 | 0 | Lack of documentations(Title deed) | 2022/23 |  |  | No | Compete | [7 empty] | The project is staled due Lack of documentations(Title deed)
39 | Purchase of 1 Acre for Makumu primary E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land for Makumu primary E.C.D.E Purchased | 3110599 | Ward based projects | Tongaren | Tongaren |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 |  |  |  | 2500000 | 1500000 | 1500000 | CGB |  | 1500000 |  | 1500000 | 1 | 0 |  |  | N/A | 0 | 0 | [13 empty] | The project is staled due Lack of documentations(Title deed)
82 | Purchase of land for Binyenya Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land for Binyenya Dispensary Purchased | 3110599 | Ward based projects | Tongaren | Tongaren |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 |  |  |  | 1500000 | 1200000 | 1200000 | CGB |  | 1200000 |  | 1200000 | 1 | 0 |  |  | not done | 0 | [14 empty] | The project is staled due Lack of documentations(Title deed)
181 | Purchase of land for Milele primary ECDE centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One and half acres of Land for Milele primary ECDE Purchased | 3110599 | Ward based projects | Tongaren | Tongaren | 0.791555,34.990389 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42528 | 42531 | 42468 | 1200000 | 1200000 | 1200000 | CGB | N/A | 1200000 |  | 1200000 |  | 1200000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
26 | Renovation and completion of ECDE classroom at Milele and Binyenya in Tongaren Ward | To repair class floors, paint walls and complete a classroom | To renovate and complete ECDE classroom providing a conducive learning environment | ECDE classroom repaired and classroom completed | 3110599 | Construction and Civil works | Tongaren | Tongaren | binyenya(0.186772,34.98334) milele(0.791555,34.990389) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 1500000 | 1455400 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 |  | 0 |  | 1455400 | 1455400 | completed and in use | At roofing (90%)
64 | Proposed Renovation And Completion Works Of 1no. Ecde Classroom At Makololwe, Mufunje And Primary Schools In Tongaren Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Tongaren | makololwe(0.806976,35.001710) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 1000000 | 997632 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 0 | 0 | 0 | 997632 | 997632 | completed | 1
216 | The Proposed Erection And Completion Of 1 N0 Classroom And Pit Latrine At Makololwe, Mabusi, Milimani Youth Polytechnic In Tongaren Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Tongaren | makololwe(0.806976,35.001710) milimani vtc(0.802061,34.970967) mabusi(0.762553216,34.94714313) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 6000000 | 5891900 | 6000000 | County Government of Bungoma | N/A | 6000000 |  | 5891900 | 1 | 5891900 | 0 |  | completed | 100.0%
5 | Upgrading of Ambich Market Borehole in Tongaren ward | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Tongaren | Tongaren | 0.790138,34.993377 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 6000000 | 5850380 | 5850380 | FLLOCA | N/A | 5850380 | 0 | 0 | 1 | 5850380 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
23 | Hass Avocado Fruit Tree Production In Tongaren, Webuye West And Webuye East Sub Counties | Supply and distribution of certified and grafted Hass avocado seedlings, Provision of manure, pegging, holing , training of nursery operators and maintanance of the orchard for 3 months | To promote climate change mitigation and adaptation | Hass avocado fruit trees planted | 2640599 | Other Capital Grants and Transfers |  | Tongaren |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7020500 | 6539100 | 6539100 | FLLOCA | KFW | 0 | 6539100 | 0 | 1 | 0 | 0 |  | not done | 0.7 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
29 | Proposed Establishment And Maintenance Of Tree Nurseries In Tongaren And Webuye East Sub-County Under The Flloca Programme | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Tree nurseries established and maintained | 2640599 | Other Capital Grants and Transfers | Tongaren,Webuye West | Tongaren |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7308000 | 7068330 | 7068330 | FLLOCA | IDA | 0 | 7068330 | 0 | 1 | 0 | 0 |  | completed | 0.32 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
93 | Ambichi-Soysambu-Tongaren Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 1 Water project constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 1850000 | 1850000 | 1850000 | CGB | N/A | 1850000 | 0 | 1850000 | 1 | 0 | 1850000 | 0 | not started | NOT AWARDED | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
136 | Upgrading of Lukhuna Market and Binyenya market Boreholes in Tongaren Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.8254742,34.9215445 binyenya(0.790138,34.993377) | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 3000000 | 2927840 | 2927840 |  | N/A | 2927840 | 0 | 2927840 | 1 | 2927840 | 0 | 0 | completed not working | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
159 | Protection of 2 no .water springs in tongaren ward | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 2 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 500000 | 460636 | 460636 |  | N/A | 460636 | 0 | 460636 | 1 | 460636 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
212 | DRILLING AND EQUIPPING OF 2NO. BOREHOLES AND CONSTRUCTION OF 4NO. WATER SPRINGS IN TONGAREN WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.790138,34.993377 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 3800000 | 3583986 | 3583986 |  | N/A | 3583986 | 0 | 3583986 | 1 | 3583986 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
246 | DRILLING OF 3NO BOREHOLES IN TONGAREN WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | sokomoko(0.7750481,34.9184426) | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 4500000 | 4369720 | 4369720 |  | N/A | 4369720 | 0 | 4369720 | 1 | 4369720 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
318 | EXTENSION OF CENTRAL NAITIRI WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3800000 | 3649167 | 3649167 |  | N/A | 3649167 | 0 | 3649167 | 1 | 3649167 | 0 | 0 | N/A | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
321 | DRILLING AND CONSTRUCTION OF MILIMANI BOREHOLE AND 3NO.SPRINGS IN TONGAREN WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 3 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.802018,34.977902 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3000000 | 2988450 | 2988450 |  | N/A | 2988450 | 0 | 2988450 | 1 | 2988450 | 0 | 0 | completed not working | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
366 | Installation of solar pumping system in Tongaren water project | Installation of solar pannels and solar pumps; installation of steel stand and plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended and upgraded | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.779792,34.963022 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1700000 | 1600054 | 1600054 |  | N/A | 1600054 | 0 | 1600054 | 1 | 1600054 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
381 | Construction & Protection of 10 No. Water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | nalianya(0.798726,34.996365) makololwe(0.806894,34.998540) sahani(0.804726,34.988729) kachinja(0.804726,34.988729) nandoicha(0.803864,34.984098) scholar(0.793608,35.000118) kalihu(0.797085,34.990872) | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1500000 | 1487935 | 1487935 |  | N/A | 1487935 | 0 | 1487935 | 1 | 1487935 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
438 | Installation of solar pumping system in Tongaren water project | Improvement of a standard drainage tunnel and replacement of 1 Afrdev hand pump with solar pump | To enhance access to clean and safe drinking water | 1 Borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.779792,34.963022 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2500000 | 2400080.4 | 2400080.4 |  | N/A | 2400080.4 | 0 | 2400080.4 | 1 | 2400080.4 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
464 | Drilling of 1 borehole at Ambichi Market equip with hand pump. | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.790138,34.993377 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2000000 | 1788150 | 1788150 |  | N/A | 1788150 | 0 | 1788150 | 1 | 1788150 | 0 | 0 | completed and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
470 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1487935 | 1487935 |  | N/A | 1487935 | 0 | 1487935 | 1 | 1487935 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
471 | Drilling of 1 borehole at Ambichi Market equip with hand pump. | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.790138,34.993377 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1788150 | 1788150 |  | N/A | 1788150 | 0 | 1788150 | 1 | 1788150 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
472 | Installation of solar pumping system in Tongaren water project | Pipeline extension, rehabilitation of spillway; solarization and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed and solarised | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.779792,34.963022 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 4200000 | 4000134 | 4000134 |  | N/A | 4000134 | 0 | 4000134 | 1 | 4000134 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
552 | Protection of 10 water springs and drilling of 2 boreholes at Mabusi and Birunda Secondary and equip with hand pumps | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protectionsite identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 boreholes drilled and 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Tongaren | 0.7750481,34.9184426 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 4500000 | 4235800 | 4235800 |  | N/A | 4235800 | 0 | 4235800 | 1 | 4235800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
5 | Construction of Tongaren ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Tongaren ward office constructed | 3111504 | Construction of non- residential buildings | Tongaren | Tongaren | 0.783633,34.959087 | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43671 | 9500000 | 9674539 | 9500000 | County Government of Bungoma | - | 9674539 | - | 9674539 | 1 | 9674539 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
1 | Supply and Delivery, testing and commissioning of 10No. car washing machines Across ward. | Purchase and supply of car washing machines | youth empowerment | Carwashing machines machines delivered, tested and commisioned | BGM/CNTY/TEI/18/OT/2024-2025 1667861-2024-2025 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Trade | BRAMFORD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 500000 |  |  | CGB | [8 empty] | not done |  | 10
31 | Proposed Supply and Installation of 7NO.Solar Powered streetlight | Supply of Solar of 7NO | promotion of MSMEs and security | solar powered street lights installed | 1363470-2023-24 |  |  | Tongaren | ambichi(0.789402,34.992728 0.788906,34.992207 0.789740,34.992381 0.789030,34.991773) sokomoko(0.7740244,34.949112) sango(0.769074,34.971130) kakamwe(0.780752,34.977246) machakha(0.816882,34.964084) milimani(0.801282,34.974166) binyenya(0.814564,34.987891 0.8144629,34.987354 0.815685,34.987924 0.816214,34.988722) tongaren market solar(0.782300,34.963269) highmast solar tongaren market(0.782237,34.962985) | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE LIMITED | 2023/2024 |  | Completed | Complete and in use | 2130000 |  |  | CGB | [8 empty] | Complete | 100 | 7
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Tongaren |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Tongaren |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Tongaren | 0.780698,34.963784 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Tongaren | 0.783874,34.965192 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Tongaren | 0.783874,34.965192 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Tongaren | 0.783874,34.965192 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | N/A
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Tongaren | 0.783874,34.965192 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Tongaren | 0.783874,34.965192 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | N/A
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | N/A
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Tongaren | 0.783874,34.965192 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tongaren |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Tongaren |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
12 | Erection and completion works for maternity and completion of staff quarters at Chepkutumi dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Staff quarters erected and completed |  |  | Sirisia | Malakisi/Kulisiru | 0.717216,34.482811 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 27-2-2024 |  |  | 5000000 | 4652680 | 4652680 | CGB |  | 4652680 | 0 | 0 | 0 | 0 | 0 | 4652680 | stalled | 88 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
40 | Purchase of hospital beds with beddings in Lwakhakha dispensary in Lwandanyi ward | [5 empty] | Sirisia | Malakisi/Kulisiru |  |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 1000000 | 1000000 | 1000000 | CGB |  | 1000000 | 0 | 1000000 | 1 | 1000000 | 0 | 0 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
83 | Erection And Completion Works For Maternity Wards Phase 1 At Bukokholo Dispensary. | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wards erected and completed |  |  | Sirisia | Malakisi/Kulisiru | 0.696410,34.466153 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2500000 | 0 | 0 | CGB |  | 0 | 0 | 1423500 | #DIV/0! | 1423500 |  | -1423500 | stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
111 | Erection Of Waiting Bay At Sirisia Sub-County Hospital |  |  | Waiting bay erected |  |  | Sirisia | Malakisi/Kulisiru |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1000000 | 996350 | 996350 | CGB |  | 996350 | 0 | 0 | 0 | 0 |  | 996350 | Complete and in use | [6 empty] | No | complete | Financial | Yes
205 | Contruction Of Maternity Wing At Bisunu Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings constructed |  |  | Sirisia | Malakisi/Kulisiru |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 2136500 | 2114400 | 2114400 | CGB |  | 2114400 | 0 | 2114400 | 1 | 2114400 |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes
211 | Construction of a Maternity wing at Bisunu Dispensary. | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings constructed |  |  | Sirisia | Malakisi/Kulisiru |  |  | WBPSPCU | Health & Sanitation | 2018-2019 | [6 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
336 | Construction of Ecosan pit latrine at Sirisia market | Digging of 20ft deep pit,flooring,walling,painting,roofinganfd fitting doors | To enhance access to sanitary facilities at the market | Ecosan pit latrines constructed |  |  | Sirisia | Malakisi/Kulisiru |  |  | CEF | Health & Sanitation | 2016/2017 |  | 42675 |  |  | 1153788 | 1153788 | CGB |  | 1153788 | 0 |  | 0 |  |  | 1153788 | Complete and in use | [6 empty] | No | complete | Financial | Yes
337 | Construction of 4 door public toilet. | Construction of 4 door public toilet at Bisunu market | Digging of 20ft deep pit,flooring,walling,painting,roofinganfd fitting doors | 4no.door public toilets constructed |  |  | Sirisia | Malakisi/Kulisiru | 0.754762,34.501628 |  | CEF | Health & Sanitation | 2016/2017 |  | 42675 |  |  |  |  | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | completed | [6 empty] | No | complete | Financial | Yes
338 | Construction of public toilet | Digging of 20ft deep pit,flooring,walling,painting,roofinganfd fitting doors | To enhance access to sanitary facilities at the market | public toilets |  |  | Sirisia | Malakisi/Kulisiru |  |  | CEF | Health & Sanitation | 2016/17 | 22ND/Feb/2017 |  | 22nd /May/2017 |  | 1197052.07 | 1197052.07 | CGB |  | 1197052.07 | 0 |  | 0 |  |  | 1197052.07 | Complete and in use | [6 empty] | No | complete | Financial | Yes
8 | Upgrading of Sirisia Mkt-Bunangeni-Kibingei Junct | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41661 | 41776 |  | 14834082 | 14834082 | 14834082 | County Government of Bungoma |  | 14834082 |  | 14834082 | 100.0% | 14834082 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
17 | Upgrading of Malakisi-Nambuya-Changara | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41661 | 41781 |  | 3924396 | 3924396 | 3924396 | County Government of Bungoma |  | 3924396 |  | 3924396 | 100.0% | 3924396 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
107 | Upgrading of Toloso - Kikwechi And Toloso - Kolani Bridges | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42386 | 42512 |  | 24595549.6 | 24595549.6 | 24595549.6 | County Government of Bungoma |  | 24595549.6 |  | 24595549.6 | 100.0% | 24595549.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
209 | Periodic Maintenance of Chenjeni Junction - Nabuloli Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43232 |  | 4277616 | 4277616 | 4277616 | County Government of Bungoma |  | 4277616 |  | 4277616 |  | 4277616 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
210 | Periodic Maintenance of Roads In Malakisi South Kulisiru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43117 | 43238 |  | 4277616 | 4277616 | 4277616 | County Government of Bungoma |  | 4277616 |  | 4277616 | 93.48% | 4277616 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
390 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
558 | Periodic Maintenance of Londo - Sitabicha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43962 |  | 1878591 | 1878591 | 1878591 | County Government of Bungoma |  | 1878591 |  | 1878591 |  | 1878591 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
559 | Periodic Maintenance of Periodic Maintanance Of Roads In Malakisi-South Kulisiru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43966 |  | 1878591 | 1878591 | 1878591 | County Government of Bungoma |  | 1878591 |  | 1878591 | 97.88% | 1878591 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
560 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 60000000 | 60000000 | 60000000 | County Government of Bungoma |  | 60000000 |  | 60000000 | 100.0% | 60000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
599 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
844 | Construction of Kulisiru - Kasiamo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44336 |  | 11999841 | 11999841 | 11999841 | County Government of Bungoma |  | 11999841 |  | 11999841 |  | 11999841 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
845 | Construction of Sibanga - Chongoyi Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44331 |  | 11999841 | 11999841 | 11999841 | County Government of Bungoma |  | 11999841 |  | 11999841 |  | 11999841 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
846 | Construction of Chenjeni - Nabulooli Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44339 |  | 11999841 | 11999841 | 11999841 | County Government of Bungoma |  | 11999841 |  | 11999841 |  | 11999841 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
847 | Periodic Maintenance of Chebukutumi - Butonge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44334 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
848 | Periodic Maintenance of Sirisia Market - Malinda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44327 |  | 1977423 | 1977423 | 1977423 | County Government of Bungoma |  | 1977423 |  | 1977423 |  | 1977423 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
849 | Upgrading of Roads In Malakisi South Kulisiru Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44338 |  | 11999841 | 11999841 | 11999841 | County Government of Bungoma |  | 11999841 |  | 11999841 | 99.74% | 11999841 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
850 | Periodic Maintenance of Roads In Malakisi/ South Kulisiru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44326 |  | 1977423 | 1977423 | 1977423 | County Government of Bungoma |  | 1977423 |  | 1977423 | 98.17% | 1977423 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1152 | Periodic Maintenance of Kulisiru - Kasiamo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44702 |  | 10408297.2 | 10408297.2 | 10408297.2 | County Government of Bungoma |  | 10408297.2 |  | 10408297.2 |  | 10408297.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1153 | Periodic Maintenance of Sibanga Primary - Karibuni Girls Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44697 |  | 10408297.2 | 10408297.2 | 10408297.2 | County Government of Bungoma |  | 10408297.2 |  | 10408297.2 |  | 10408297.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1154 | Construction of Chenjeni - Nabulooli Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44691 |  | 10408297.2 | 10408297.2 | 10408297.2 | County Government of Bungoma |  | 10408297.2 |  | 10408297.2 |  | 10408297.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1155 | Periodic Maintenance of Kulisiru - Kasiamo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44703 | 44734 | 4473487.8 | 4473487.8 | 4473487.8 | County Government of Bungoma |  | 4473487.8 |  | 4473487.8 |  | 4473487.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1156 | Routine Maintenance Of Kulisiru - Kasiamo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44703 |  | 4473487.8 | 4473487.8 | 4473487.8 | County Government of Bungoma |  | 4473487.8 |  | 4473487.8 | 100.0% | 4473487.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1157 | Periodic Maintenance of Roads In Malakisi - South Kulisiru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44695 |  | 10408297.2 | 10408297.2 | 10408297.2 | County Government of Bungoma |  | 10408297.2 |  | 10408297.2 | 100.0% | 10408297.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1457 | Periodic Maintenance of Ndakaru - Kulisiru -Kukubo -Muanda Primary - Marko Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45068 |  | 5812338 | 5812338 | 5812338 | County Government of Bungoma |  | 5812338 |  | 5812338 |  | 5812338 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1458 | Periodic Maintenance of Ndakaru - Kulisiru - Kukubo - Muanda Primary - Mako Road In Malakisi/Kulisiru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45066 |  | 5812338 | 5812338 | 5812338 | County Government of Bungoma |  | 5812338 |  | 5812338 | 92.8% | 5812338 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1693 | Periodic Maintenance of Sirisia Market - Chinese - Ex Chief - Kasiamo - Ndakaru Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45427 |  | 9247984 | 9247984 | 9247984 | County Government of Bungoma |  | 9247984 |  | 9247984 |  | 9247984 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1694 | Periodic Maintenance of Sirisia Market - Chinese - Ex Chief - Kasiamo - Ndakaru Road In Malakisi/South Kulisiru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45436 |  | 9247984 | 9247984 | 9247984 | County Government of Bungoma |  | 9247984 |  | 9247984 | 100.0% | 9247984 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
11 | Purchase of 1 Acre for Bisunu dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land Purchased for Bisunu dispensary | 3110599 | Ward based projects | Sirisia | Malakisi/Kulisiru |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 44986 | 45444 |  | 1200000 | - | 1200000 | CGB | N/A | 1200000 | 0 | 1200000 | 1 | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2023/24 |  | 0 | No | Compete | [7 empty] | The project is stalled due Lack of documentations(Title deed)
57 | Proposed Renovation and refurbishment of 6 units staff quarters 3 at tamlega, 2 at malakisi Hospital quarters and 1 cooperative Hous | Renovation and refurbishment | To enhance revenue collection | Six units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2021/22 | 44594 | 31/3/2022 | 44566 | 3000000 | 2877492 | 2877492 | CGB |  | 2877492 |  | 2877492 | 1 | 2877492 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
69 | proposed security fencing of county residential estate with barbed wire and chainlinnk | Fencing with barbed wire and chainlinnk | To enhance security at the estate | Perimeter wall of county residential estate with barbed wire and chainlinnk constructed | 3110604 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru | 0.753808,34.503775 | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2020/21 | 13/5/2020 | 14/7/2020 | 22/8/2020 | 1500000 | 1083788 | 1083788 | CGB |  | 1083788 |  | 1083788 | 1 | 1083788 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
135 | Proposed renovation and refurbishment and external works of county houses No:BCC/SIRI/1A&B,BCC/SIRI/2A&B,BCC/SIRI/3A&B, | Renovation and refurbishment and external works | To enhance revenue collection | Six units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Sirisia | Malakisi/Kulisiru | 0.753808,34.503775 | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2017/18 | 19/11/2017 | 19/1/2018 | 16/2/2018 | 350000 | 350000 | 350000 | CGB | N/A | 350000 |  | 350000 | 1 | 350000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
52 | Proposed Erection And Completion Works Of 1no. Ecdeclassroom At Ngalasia, Namang’ofulo, Sirisia Mal, Maeni, Bukokholo, Musieba And Tembelela Primary Schools In Malakisi/Kulisiru Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Malakisi/Kulisiru | sirisia mala(o.753782,34.510285) Bukokholo pri(0.702033,34.49673) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 10500000 | 9850925 | 10500000 | County Government of Bungoma | N/A | 10500000 | 0 | 4922165.07 | 0.49967 | 4922165.07 | 4928759.93 | 4928759.93 | complete | 1
85 | construction of 1No ECDE at Butonge primary, yabeko primary | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Malakisi/Kulisiru |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 4500000 | 4497940 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 2597118.9 | 0.5774 | 2597118.9 | 1900821.1 | 1900821.1 | Complete and in use
86 | Construction of workshop at Nabuloli VTC | Construction of VTC workshop | To construct VTC providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Malakisi/Kulisiru |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  |  |  |  | County Government of Bungoma | N/A |  | 0 |  | #DIV/0! |  | 0 | 0 | Complete and in use | 1
149 | Proposed Erection And Completion Of 1 No. Ecde At Bisunu, Kibeu, Ndakaru, Lukaala And Kasiamo Primary Schools In Malakisi Kulisiru Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Malakisi/Kulisiru | lukala(0.730552,34.502810) bisunu(0.711271,34.500238) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 8424382.54 | 8123750 | 8424382.54 | County Government of Bungoma | N/A | 8424382.54 | 0 | 8123750 | 1 | 7723215.94 | 400534.06 | 0 | complete and in use | 1
176 | Construction Of 1no. Classrooms And Toilets At Matunda, Malinda S.A, Kulisiru, Namunyu, Chebukutuni, Lutaso And Namawanga Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Malakisi/Kulisiru | chebukutumi(0.716583,34.472500) Matunda pri.(0.708537,34.465742) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 8400000 | 8303558 | 8400000 | County Government of Bungoma | N/A | 8400000 | 0 | 8303558 | 1 | 8303558 | 0 |  | complete | 1
202 | The Proposed Erection And Completion Of 1 N0 Classroom At Nabulooli Primary School In Malakisi/Kulisiru Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Malakisi/Kulisiru | nabulooli(0.700850,34.489916) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 1200000 | 1200000 | 1200000 | County Government of Bungoma | N/A | 1200000 |  | 1200000 | 1 | 1200000 | 0 |  | stalled | 100.0%
[5 empty] | 2640599 | Other Capital Grants and Transfers | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | [6 empty] | FLLOCA | N/A |  | 0 |  | 1 |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
35 | Proposed Rehabilitation Of Rivers Kuywa, Malakisi, And Bukokholo Dam | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5916000 | 5879250 | 5879250 | FLLOCA | IDA | 0 | 5879250 | 0 | 1 | 0 | 0 |  | On going and not in use | 0.43 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
66 | Upgrading of borehole at Chongoi Primary | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3400000 | 3314700 | 3314700 | CGB | N/A | 3314700 | 0 | 3314700 | 1 | 3314700 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
82 | Upgrading of borehole at Kulisiru primary | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3400000 | 3685740 | 3685740 | CGB | N/A | 3685740 | 0 | 3685740 | 1 | 0 | 3685740 | 0 | Work in progress | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
218 | REHABILITATION AND EXTENSION OF CHESIKAKI-SIRISIA-BUMULA WATER PROJECT PHASE I | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 34000000 | 33391751.4 | 33391751.4 |  | N/A | 33391751.4 | 0 | 33391751.4 | 1 | 23831829 | 9559922 | 0 | Work in progress | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
222 | DRILLING OF 3NO. BOREHOLES IN MALAKISI-KULISIRU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 6500000 | 6417800 | 6417800 |  | N/A | 6417800 | 0 | 6417800 | 1 | 6417800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
225 | DRILLING AND EQUIPING OF CHENJENI BOREHOLE IN MALAKISI/KULISIRU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2000000 | 1984644 | 1984644 |  | N/A | 1984644 | 0 | 1984644 | 1 | 1984644 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
268 | DRILLING OF NDAKARU PRIMARY BOREHOLE IN MALAKISI KULISIRU | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1800000 | 1756800 | 1756800 |  | N/A | 1756800 | 0 | 1756800 | 1 | 1756800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
287 | DRILLING OF BUKOKHOLO BOREHOLE IN MALAKISI/KULISIRU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2200000 | 2058480 | 2058480 |  | N/A | 2058480 | 0 | 2058480 | 1 | 2058480 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
288 | DRILLING OF SIBANDA AND NGALASIA BOREHOLES IN MALAKISI/KULISIRU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3800000 | 3749120 | 3749120 |  | N/A | 3749120 | 0 | 3749120 | 1 | 3749120 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
352 | Construction of 5Roof catchment and 1 Storage tank at chepsitati primary school | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 tank constructed | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1500000 | 1368750 | 1368750 |  | N/A | 1368750 | 0 | 1368750 | 1 | 1368750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
416 | Protection of 7 water springs and Construction of 3 Roof catchments | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 7 water springs constructed and 3 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru | 0.754257,34.502997 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1505130 | 1505130 |  | N/A | 1505130 | 0 | 1505130 | 1 | 1505130 | 0 | 0 | completed wauswa and wauyo springs | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
424 | Rehabilitation of Bitonge dam | pipeline extension, rehabilitation of spillway | To enhance access to clean and safe drinking water | 1 dam rehabilitated | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru | 0.713114,34.469672 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 5100000 | 5017742.4 | 5017742.4 |  | N/A | 5017742.4 | 0 | 5017742.4 | 1 | 5017742.4 | 0 | 0 | stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
456 | Kabuchai Community Water Project including 50m3 storage tank | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed and No. 1 of storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 8500000 | 8203321.52 | 8203321.52 |  | N/A | 8203321.52 | 0 | 8203321.52 | 1 | 8203321.52 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
489 | Drilling of Namangofulo Boreholes | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1575000 | 1575000 |  | N/A | 1575000 | 0 | 1575000 | 1 | 1575000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
490 | Rehabilitation of Bitonge dam | pipeline extension; rehabilitation of spillway | To enhance access to clean and safe drinking water | 1 dam rehabilitated | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru | 0.713114,34.469672 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 5200000 | 5017742 | 5017742 |  | N/A | 5017742 | 0 | 5017742 | 1 | 5017742 | 0 | 0 | stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
565 | Protection of 7 water springs and Construction of 3 Roof catchments | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; construction of roof catchment and storage tank with water points | To enhance access to clean and safe drinking water | 7 water springs constructed and 3 roof catchments | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1700000 | 1505130 | 1505130 |  | N/A | 1505130 | 0 | 1505130 | 1 | 1505130 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
566 | Bisuno chief camp borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Malakisi/Kulisiru | 0.708118,34.505171 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1692600 | 1692600 |  | N/A | 1692600 | 0 | 1692600 | 1 | 1692600 | 0 | 0 | complete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
2 | Construction of Malakisi/ Kulisiru ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Malakisi/ Kulisiru ward office constructed | 3111504 | Construction of non- residential buildings | Sirisia | Malakisi/Kulisiru | 0.7112361,34.485053 | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 42870 | 9500000 | 11189045 | 9500000 | County Government of Bungoma | - | 11189045 | - | 11189045 | 1 | 11189045 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Purchase and installation of Automatic Weather Stations | Purchase and installation of 4 Automatic Weather Stations in Bumula, Township, Malakisi/Kulisiru and Elgon Wards | To collect precise and continous weather data | 4 Automatic Weather stations installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Sirisia | Malakisi/Kulisiru | 0.7373791,34.42126185 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 40000000 | 35547910 | 40000000 | County Government of Bungoma |  | 35547910 |  | 35547910 | 1 | 35547910 |  | 0 | completed but not working
| Rehabilitation of Butonge dam | Rehabilitation of Butonge dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Sirisia | Malakisi/Kulisiru | 0.713715,34.469672 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 8000000 | 6500000 | 6500000 | County Government of Bungoma |  | 6500000 |  | 6500000 | 1 | 6500000 | 0 | 0 | stalled
| Supply of marking ink used in inspection of Meat | Supply of marking ink used in inspection of Meat for Bungoma, Webuye East & West, Kimilili and Sirisia Slaughtershouses | To promote meat safety and suitability for human consumption | Marking ink supplied for meat inspection | 2211007 | Agricultural materials, supplies and small equipment | Sirisia | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 3000000 | 1750000 | 2000000 | County Government of Bungoma |  | 1750000 |  | 1750000 | 1 | 1750000 | 0 | 0 | Completed
| Rehabilitation Of Butonge Dam | Rehabilitation Of Butonge Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Sirisia | Malakisi/Kulisiru | Adjacent AC Butonge high school | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43009 | 43014 | 42860 | 8000000 | 6500000 | 6500000 | County Government of Bungoma |  | 6500000 | 0 | 6500000 | 1 | 6500000 | 0 | 0 | stalled
| Distilling and fencing of Lukala dam | Distilling and fencing of Lukala dam | To store water for irrigation and flood control | 1 Dam distilled and fenced | 3110504 | Other infrastructure and civil works | Sirisia | Malakisi/Kulisiru | 0.742575,34.503625 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/4/2021 | 20/7/2021 | 44322 | 6000000 | 4398548 | 4398548 | County Government of Bungoma |  | 4398548 | 0 | 4398548 | 1 | 4398548 | 0 | 0 | Completed
| Rehabilitation of Lukala Dam | Rehabilitation of Lukala Dam in Sirisia Sub County | To store water for irrigation and flood control | 1 Dams distilled and fenced | 3110504 | Other infrastructure and civil works | Sirisia | Malakisi/Kulisiru | 0.742575,34.503625 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 15/1/2022 | 15/5/2022 | 25/4/2022 | 10000000 | 4398548 | 4500000 | County Government of Bungoma |  | 4398548 | 0 | 4398548 | 1 | 4398548 | 0 | 0 | Completed
26 | Proposed Installation and commissioning of 3No. Solar powered Floodlight | Installation of Solar of 3No | promotion of MSMEs and security | Solar powered floodligts installed | 1472960-2023-24 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 5620000 |  |  | CGB | [8 empty] | Complete | 100 | 3
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Malakisi/Kulisiru |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
128 | Construction of 2 boda boda sheds | Of sheds streetlights | [5 empty] | Malakisi/Kulisiru | 0.754763,34.502810 |  |  | Bravick Company Ltd | 2018/19 |  | Complete |  | 498104 |  |  | CGG | [8 empty] | done- sirisia stage 1 no.1
252 | Periodic Maintenance of Chenjeni Junction - Nabuloli Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43232 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
433 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | SEVERAL | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
653 | Periodic Maintenance of Londo - Sitabicha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43962 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
953 | Construction of Kulisiru - Kasiamo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
954 | Construction of Sibanga - Chongoyi Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44331 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
955 | Construction of Chenjeni - Nabulooli Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44339 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
956 | Periodic Maintenance of Chebukutumi - Butonge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44334 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
957 | Periodic Maintenance of Sirisia Market - Malinda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44327 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1286 | Periodic Maintenance of Kulisiru - Kasiamo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44702 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1287 | Periodic Maintenance of Sibanga Primary - Karibuni Girls Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44697 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1288 | Construction of Chenjeni - Nabulooli Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44691 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1289 | Periodic Maintenance of Kulisiru - Kasiamo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44703 | 44734 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1545 | Periodic Maintenance of Ndakaru - Kulisiru -Kukubo -Muanda Primary - Marko Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45068 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1792 | Periodic Maintenance of Sirisia Market - Chinese - Ex Chief - Kasiamo - Ndakaru Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45427 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1793 | Periodic Maintenance of Sirisia Market - Chinese - Ex Chief - Kasiamo - Ndakaru Road In Malakisi/South Kulisiru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | SIRISIA | Malakisi/Kulisiru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45436 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Malakisi/Kulisiru | 0.753291,34.510295 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | completed-Yabeko
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | completed (tembelela)
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Malakisi/Kulisiru | 0.753181,34.510301 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Malakisi/Kulisiru | 0.753291,34.510282 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Malakisi/Kulisiru | 0.753291,34.510282 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Malakisi/Kulisiru | 0.712361,34.485033 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Malakisi/Kulisiru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Malakisi/Kulisiru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
8 | Erection and completion of modern maternity at Luuya dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Modern maternity wings constructed |  |  | Kabuchai | Luuya bwake | 0-65221449,34-638820 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 23-2-2024 |  |  | 3000000 | 2825934 | 2825934 | CGB |  | 2825934 | 0 | 0 | 0 | 0 | 849829 | 2825934 | On-going | 55 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
25 | Renovation of Lwanda health center | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Health centres renovated |  |  | Kabuchai | Luuya bwake | 0.6947838,34.6040190 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 23-2-2024 |  |  | 1000000 | 949805 | 949805 | CGB |  | 949805 | 0 | 0 | 0 | 0 |  | 949805 | on-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
33 | Purchase of medical equipment for Nasaka, Luuya, Khachonge and Lwanda . | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Kabuchai | Luuya bwake | 0.6353441,34.6539175 0.6926679,34.6218265 0.6947838,34.638820 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 19/4/24 |  |  | 2000000 | 1898140 | 1898140 | CGB |  | 1898140 | 0 | 1898140 | 1 | 1898140 | 0 | 0 | completed, needs to br fully equiped | [6 empty] | No | complete | Financial | Yes |  |  |  | No
49 | Construction of 4NO. Doors pit latrines at Khachonge dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Kabuchai | Luuya bwake | 0.6926679,34.6218265 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 22/4/24 |  |  | 1000000 | 935400 | 935400 | CGB |  | 935400 | 0 |  | 0 |  |  | z | completed and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
68 | Construction of 4NO. Doors pit latrines at Khachonge dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Kabuchai | Luuya bwake | 0.6926679,34.6218265 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 22/4/24 |  |  | 1000000 | 935400 | 935400 | CGB |  | 935400 | 0 | 769657.3 | 0.82281 | 769657.3 | 165742.7 | 165742.7 | completed and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
109 | Construction Of Khachonge Market Toilet |  |  | Toilets constructed |  |  | Kabuchai | Luuya bwake | 0.6842376,34.6281199 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1000000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | completed and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
110 | Matunda Ecde Toilets |  |  | Toilets constructed |  |  | Kabuchai | Luuya bwake | 0.6365253,34.6647295 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 400000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | stalled, not available | [6 empty] | No | complete | Financial | Yes |  |  |  | No
2 | Construction of Nalondo Stadium | Construction of Nalondo Stadium | To enhance sporting activities in the county | Concrete poles with chainlink and metallic stand constructed | 3111504 | Other infrastructure and civil works | Kabuchai | Luuya bwake |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2020/21 | 44198 | 44202 |  | 10000000 | 9500000 | 7984759 | County Government of Bungoma | n/a | n/a | n/a | 7984759 | 0.8405 | 7984759 | 1515241 | 1515241 | Stalled | 0.73 | 0.73 | Delayed project implementation due to lack of funds by the contractor | 2022 |  |  | No | Cancel | `
381 | Periodic Maintenance of Marobo - Luuya Girls - Chekulo Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.642162,34.615054 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43598 |  | 6608404 | 6608404 | 6608404 | County Government of Bungoma |  | 6608404 |  | 6608404 |  | 6608404 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
382 | Periodic Maintenance of Roads In Luyha Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.709446,34.612763 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43481 | 43596 |  | 6608404 | 6608404 | 6608404 | County Government of Bungoma |  | 6608404 |  | 6608404 | 99.48% | 6608404 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
383 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
384 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
552 | Periodic Maintenance of Khachonge Factory - Sichei Cattle Dip Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.69266,34.621826 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43969 |  | 6974616 | 6974616 | 6974616 | County Government of Bungoma |  | 6974616 |  | 6974616 |  | 6974616 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
553 | Periodic Maintenance of Roads In Luuya-Bwake | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.709446,34.612763 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43971 |  | 6974616 | 6974616 | 6974616 | County Government of Bungoma |  | 6974616 |  | 6974616 | 99.88% | 6974616 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
560 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 60000000 | 60000000 | 60000000 | County Government of Bungoma |  | 60000000 |  | 60000000 | 100.0% | 60000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
599 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
828 | Periodic Maintenance of Matunda - Nasaka - Kiboochi - Ngalasia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.630423,34.614931 0.636525,34.664729 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44329 |  | 8935248 | 8935248 | 8935248 | County Government of Bungoma |  | 8935248 |  | 8935248 |  | 8935248 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
829 | Upgrading of Luuya - Marobo Drift | Road improvement works | To improve the road condition and enhance accessibility | 6.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44334 |  | 8935248 | 8935248 | 8935248 | County Government of Bungoma |  | 8935248 |  | 8935248 |  | 8935248 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
830 | Periodic Maintenance of Roads In Luuya - Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.709446,34.612763 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44329 |  | 8935248 | 8935248 | 8935248 | County Government of Bungoma |  | 8935248 |  | 8935248 | 97.07% | 8935248 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1142 | Periodic Maintenance of Nalondo - Khatiri - Nangili - Sikinga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 9.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.668352,34.64159 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44699 |  | 13801854 | 13801854 | 13801854 | County Government of Bungoma |  | 13801854 |  | 13801854 |  | 13801854 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1143 | Periodic Maintenance of Mahanga Sec - Chekulo - Sikinga Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Luuya bwake | 0.668352,34.64159 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44700 | 44731 | 3483868.6 | 3483868.6 | 3483868.6 | County Government of Bungoma |  | 3483868.6 |  | 3483868.6 |  | 3483868.6 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1144 | Periodic Maintenance of Roads In Luuya-Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 9.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44702 |  | 13801854 | 13801854 | 13801854 | County Government of Bungoma |  | 13801854 |  | 13801854 | 100.0% | 13801854 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1145 | Routine Maintenance Of Mahanga Secondary - Chekulo - Sikinga Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Luuya bwake | 0.668352,34.64159 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44694 |  | 3483868.6 | 3483868.6 | 3483868.6 | County Government of Bungoma |  | 3483868.6 |  | 3483868.6 | 100.0% | 3483868.6 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1445 | Periodic Maintenance of Lwanda - Namilama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.694086,34.602650 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45057 | 45088 | 8496430 | 8496430 | 8496430 | County Government of Bungoma |  | 8496430 |  | 8496430 |  | 8496430 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1446 | Periodic Maintenance of Chekulo - Misanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.647260,34.659050 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45057 | 45088 | 8496430 | 8496430 | 8496430 | County Government of Bungoma |  | 8496430 |  | 8496430 |  | 8496430 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1447 | Periodic Maintenance of Lwanda - Namilama, Chekulo Misanga Road In Luuya Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.6940866,34.6281199999 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45065 |  | 8496430 | 8496430 | 8496430 | County Government of Bungoma |  | 8496430 |  | 8496430 | 98.23% | 8496430 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1679 | Periodic Maintenance of Khatiri - Nangili - Sikinga Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45424 |  | 8523564 | 8523564 | 8523564 | County Government of Bungoma |  | 8523564 |  | 8523564 |  | 8523564 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1680 | Periodic Maintenance of Mabwi - Sichei Polytechnic Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.7094466,34.6124048 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45434 |  | 2736474 | 2736474 | 2736474 | County Government of Bungoma |  | 2736474 |  | 2736474 |  | 2736474 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1681 | Construction of Emergency Works For Kibochi- Nasaka Box Culvert. | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45427 |  | 9827080.19 | 9827080.19 | 9827080.19 | County Government of Bungoma |  | 9827080.19 |  | 9827080.19 | 100.0% | 9827080.19 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1682 | Construction of Emergency Works Kibochi-Nasaka Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Kabuchai | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45422 |  | 9827080.19 | 9827080.19 | 9827080.19 | County Government of Bungoma |  | 9827080.19 |  | 9827080.19 | 100.0% | 9827080.19 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1683 | Periodic Maintenance of Nangili - Sikinga - Khatiri Road In Luuya/Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.6683527,34.641596199 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45433 |  | 8523564 | 8523564 | 8523564 | County Government of Bungoma |  | 8523564 |  | 8523564 | 99.61% | 8523564 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1684 | Periodic Maintenance of Mabwi - Sichei Polytechnic Road In Luuya/Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Luuya bwake | 0.7094466,34.6127634 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45435 |  | 2736474 | 2736474 | 2736474 | County Government of Bungoma |  | 2736474 |  | 2736474 | 107.61% | 2736474 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
53 | Purchase of land for Expansion of Khachonge dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of dispensary | One acres of Land for Expansion of Khachonge dispensary Purchased | 3110599 | Ward based projects | Kabuchai | Luuya bwake | 0.684237,34.628119 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2021/22 | 44594 | 30/3/2022 |  | 7000000 | 5000000 | 5000000 | CGB |  | 5000000 |  | 5000000 | 1 | 5200000 |  |  | completed and need entry road | 1 | [14 empty] | The project is 100% complete and in use
73 | Purchase of land for Expansion of Khachonge dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of dispensary | One acre of Land for Khachonge dispensary Purchased | 3110599 | Ward based projects | Kabuchai | Luuya bwake | 0.684237,34.628119 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 | 29/1/2019 | 17/6/2019 | 30/6/2019 | 7000000 | 5000000 | 5000000 | CGB |  | 5000000 |  | 5000000 | 1 | 5200000 |  |  | completed and need entry road | 1 | [14 empty] | The project is 100% complete and in use
49 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Kiboochi, Mabanga And Lwanda Pefa Primary Schools In Luuya/Bwake Ward | Construction of ECDE classroom | To avail chairs | Chairs supplied | 3110599 | Construction and Civil works | Kabuchai | Luuya bwake | 0.6275912,34.6411398699999996 0.674091,34.6133738 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 4500000 | 4247200 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 0 | 0 | 0 | 4247200 | 4247200 | completed, lwanda pefa stalled | 1
50 | Supply And Delivery Of Ecde Chairs In Luuya/Bwake Ward | Procurement of chairs | To construct ECDE classroom and pit latrine providing a conducive learning environment | ECDE classroom and pit latrine constructed | 3110599 | Construction and Civil works | Kabuchai | Luuya bwake |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 1000000 | 989000 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 0 | 0 | 0 | 989000 | 989000 | completed | 1
83 | PEFA PRI SCHOOL,KIBOOCHI PRI,Mabanga and luuya primary ECDE,AND CONSTRUCTION OF 3 NO PIT LATRINE | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Luuya bwake |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 6000000 | 6077470 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 |  | 0 |  | 6077470 | 6077470 | Complete and in use | 1
115 | Construction Of 1 No. Ecde Classroom And 2 No. Door Pit Latrine At Mikayu, Bwake And Ngalasia Ack Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Luuya bwake | 0.6081021999,34.6288458 0.6304236999,34.6149319 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4500000 | 4497370 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 3717454.5 | 0.82658 | 3717454.5 | 779915.5 | 779915.5 | completed and in use | 0.9
146 | Prposed Erection And Completion Of 1 No. Ecde At Sichei Rc And Khachonge Rc Primary Schools And Mabwi And Bwake Vtc In Luuya Bwake Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Luuya bwake | 0.6926679,34.6218265 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 6533265.41 | 6482450 | 6533265.41 | County Government of Bungoma | N/A | 6533265.41 | 0 | 6482450 | 1 | 6255730.45 | 226719.55 | 0 | complete and in use | 1
173 | Construction Of 1 Ecde Classroom At Nangili Rc, Chekulo Baptist And Marobo Primary Schools. | Construction of ECDE classroom and VTC workshop | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Luuya bwake | 0.6652914,34.6349732 0.6421624 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 3600000 | 3599800 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3599800 | 1 | 3599800 | 0 |  | copmleted | 1
200 | Construction Of 01 No. Ecde Classroom At Matunda, Chekulo, Misiri Rc, Namikelo, Sango And Nangubo Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Luuya bwake | 0.7156222,34.5758934 0.69530569999,34.6063782 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 7500000 | 8048219 | 7500000 | County Government of Bungoma | N/A | 7500000 |  | 8048219 | 1 | 8048219 | 0 |  | completed, need to add more classrooms | 100.0%
39 | Proposed Tree Growing Within Institutions In Luuya/Bwake, Matulo, Mihuu, Kamukuywa, And Naitiri/Kabuyefwe Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45452 | 45455 | 45455 | 5917500 | 5910500 | 5910500 | FLLOCA | IDA | 0 | 5910500 | 0 | 1 | 0 | 0 |  | completed | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
122 | Protection of 9no. water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 9 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1800000 | 1749057.28 | 1749057.28 |  | N/A | 1749057.28 | 0 | 1749057.28 | 1 | 1749057.28 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
123 | protection of 8no. water springs | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 Water springs constructed protected | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1800000 | 1562334.4 | 1562334.4 |  | N/A | 1562334.4 | 0 | 1562334.4 | 1 | 1562334.4 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
151 | Drilling of borehole at Misri primary | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2000000 | 1939600 | 1939600 |  | N/A | 1939600 | 0 | 1939600 | 1 | 1939600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
197 | CONSTRUCTION AND PROTECTION 3NR WATER SPRINGS NAMELY - KHACHONGE, MABONGA AND MANG’ALA WATER SPRINGS | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 500000 | 448980 | 448980 |  | N/A | 448980 | 0 | 448980 | 1 | 448980 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
231 | DRILLING OF CARDINAL OTUNGA BOREHOLE AND REHABILITATION OF 6NO WATER SPRINGS IN LUUYA/BWAKE WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 borehole drilled and 6 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake | 0.70777226,34.6127634 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2800000 | 2711907 | 2711907 |  | N/A | 2711907 | 0 | 2711907 | 1 | 2711907 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
271 | PROTECTION OF WEBALA SPRING IN LUUYA BWAKE WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 200000 | 200000 | 200000 |  | N/A | 200000 | 0 | 200000 | 1 | 200000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
280 | DRILLING OF KHATIRI PRIMARY SCHOOL BOREHOLE IN LUUYA BWAKE WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake | 0.6716761,34.6126336999996 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2045080 | 2045080 |  | N/A | 2045080 | 0 | 2045080 | 1 | 2045080 | 0 | 0 | completed, not working | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
281 | DRILLING OF MIKAYU SECONDARY SCHOOL BOREHOLE IN LUUYA BWAKE WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake | 0.6081021,34.628845 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1903759 | 1903759 |  | N/A | 1903759 | 0 | 1903759 | 1 | 1903759 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
282 | DRILLLING AND SINKING OF KIBOCHI POLYTECHNIC BOREHOLE AND CONTRUCTION AND PROTECTION OF 2NO. WATER SPRINGS IN LUUYA BWAKE WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 2 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake | 0.6364348,34.6404537999996 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3500000 | 3224880 | 3224880 |  | N/A | 3224880 | 0 | 3224880 | 1 | 3224880 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
380 | Construction of 5 Roof Catchment,Construction of 50m3 Masonry tank at Mechimeru Health. | Erection of storage tank; piping and costruction of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and tank constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1533656.6 | 1533656.6 |  | N/A | 1533656.6 | 0 | 1533656.6 | 1 | 1533656.6 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
395 | Chekulo sec school Bore hole and 2 springs | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water pointsExcavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole drilled and 2 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake | 0.6472604,34.6590509 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 5000000 | 4897786 | 4897786 |  | N/A | 4897786 | 0 | 4897786 | 1 | 4897786 | 0 | 0 | complete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
422 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1725638.4 | 1725638.4 |  | N/A | 1725638.4 | 0 | 1725638.4 | 1 | 1725638.4 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
498 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1917376.16 | 1917376.16 |  | N/A | 1917376.16 | 0 | 1917376.16 | 1 | 1917376.16 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
569 | Chekulo sec school Bore hole and 2 springs | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 of borehole drilled and 2 of water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Luuya bwake | 0.6472604,34.6590509 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 5000000 | 4897786 | 4897786 |  | N/A | 4897786 | 0 | 4897786 | 1 | 4897786 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Supply of Mobile Grain Dryers | Supply and delivery of 2 Mobile Grain Dryers in Mabanga ATC | To reduce post-harvest losses by quickly removing moisture from grain, preventing spoilage and improving storage quality. | 2 mobile grain driers supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 45000000 | 31337370 | 8200000 | County Government of Bungoma |  | 31337370 |  | 31337370 |  | 31337370 |  | 0 | Completed
| Supply and delivery of Mobile Moisture Metres | Supply and delivery of Mobile Moisture Metres | To provide accurate and timely measurements of moisture content in soils, grains, enabing farmers to optimize irrigation, improve grain storage and minimize post-harvest losses | 45 Mobile Moisture Metres supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 15000000 | 9945000 | 10000000 | County Government of Bungoma |  | 9945000 |  | 9945000 | 1 | 9945000 | 0 | 0 | Completed
| Supply of a 80-85 4wd Tractor | Supply of a 80-85 4wd Tractor | To improve mechanization during land preparation and harvesting | 1 80-85 4wd tractor supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 7500000 | 7347600 | 7500000 | County Government of Bungoma |  | 7347600 |  | 7347600 | 1 | 7347600 | 0 | 0 | Completed
| Supply of 80-85 Hp 2wd Tractor | Supply of 5 80-85 Hp 2wd Tractors | To improve mechanization during land preparation and harvesting | 5 80-85 Hp 2wd tractors supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 25000000 | 21973800 | 25000000 | County Government of Bungoma |  | 21973800 |  | 21973800 | 1 | 21973800 | 0 | 0 | Completed
| Supply And Delivey Of Mobile Soil Laboratory | Supply and Delivey of 3 Mobile Soil Laboratory | To assess soil fertility, nutrient status and identify any deficiencies or imbalances that may affect plant growth | 3 Mobile soil laboratory supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41695 | 50000000 | 47780010 | 50000000 | County Government of Bungoma |  | 47780010 |  | 47780010 | 1 | 47780010 | 0 | 0 | Completed
| Renovation of works for Mabanga FTC | Renovation of works for Mabanga FTC | To provide for a conducive and an enabling working environment | 2 Buildings renovated | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 23/12/2015 | 23/4/2016 | 20/4/2016 | 10000000 | 6998466 | 7000000 | County Government of Bungoma |  | 6998466 |  | 6998466 | 1 | 6998466 | 0 | 0 | Completed
| Supply Of 3 Soil Labs | Supply Of 3 Soil Labs at Mabanga ATC | To assess soil fertility, nutrient status and identify any deficiencies or imbalances that may affect plant growth | 3 soil labs supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 42856 | 42860 | 18/4/2017 | 50000000 | 45795457 | 48000000 | County Government of Bungoma |  | 45795457 | 0 | 45795457 | 1 | 45795457 | 0 | 0 | Completed
| Rehabilitation of buildings | Rehabilitation of conference hall and dining at Mabanga ATC | To provide a conducive and an enabling working environment | Building rehabilitated | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43647 | 43652 | 20/6/2019 | 15000000 | 12824980 | 15000000 | County Government of Bungoma |  | 12824980 | 0 | 10400000 | 0.81 | 10400000 | 2424980 | 2424980 | Completed
| Procurement and installation of solar water heaters | Procurement and installation of solar water heaters in Mabanga ATC | To harness free solar energy to heat water for various farming operations for increased production and sustainability | 1 Solar Water heaters procured and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43591 | 43556 | 10000000 | 7300000 | 7300000 | County Government of Bungoma |  | 7300000 | 0 | 7300000 | 1 | 7300000 | 0 | 0 | Completed
| Establishment of Modern Dairy unit | Establishment of Modern Dairy unit for 20 cows | To enhance dairy production and income generation | 1 modern dairy unit of 20 cows established | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43770 | 45966 | 28/3/2025 | 3000000 | 1000000 | 1000000 | County Government of Bungoma |  | 1000000 | 0 | 1000000 | 1 | 1000000 | 0 | 0 | Completed
| Construction of a local chicken production unit | Construction of a local chicken production unit in Mabanga | To enhance inprme generation among dairy farmers | Local chicken production unit constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 27/04/2019 | 26/10/2019 | 43744 | 3500000 | 2500000 | 2500000 | County Government of Bungoma |  | 2500000 | 0 | 2500000 | 1 | 2500000 | 0 | 0 | Completed
| Procurement of Disc ploughs | Procurement of Disc ploughs | To enhance crop production, productivity and income generation | 1 Disc plough procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 26/2/2019 | 2000000 | 1000000 | 1000000 | County Government of Bungoma |  | 1000000 | 0 | 1000000 | 1 | 1000000 | 0 | 0 | Completed
| Procurement of Hydraulic harrows | Procurement of Hydraulic harrows | To enhance crop production, productivity and income generation | 1 Hydraulic harrow procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 20/2/2019 | 2000000 | 1500000 | 1500000 | County Government of Bungoma |  | 1500000 | 0 | 1500000 | 1 | 1500000 | 0 | 0 | Completed
| Procurement of Seed planters | Procurement of Seed planters | To enhance crop production, productivity and income generation | Seed planter procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 17/2/2019 | 5000000 | 1600000 | 1600000 | County Government of Bungoma |  | 1600000 | 0 | 1600000 | 1 | 1600000 | 0 | 0 | Completed
| Procurement of a Row cultivator | Procurement of a Row cultivator | To enhance crop production, productivity and income generation | 1 Row cultivator procuremeed | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 28/2/2019 | 2000000 | 725000 | 725000 | County Government of Bungoma |  | 725000 | 0 | 725000 | 1 | 725000 | 0 | 0 | Completed
| Procurement of a Chisel plough | Procurement of a Chisel plough | To enhance crop production, productivity and income generation | 1 Chisel plough procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 18/2/2019 | 2000000 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 | 1 | 500000 | 0 | 0 | Completed
| Procurement of Maize shellers | Procurement of Maize shellers | To enhance efficiency and minimize post harvest losses | Maize shellers procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 20/2/2019 | 2000000 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 | 1 | 500000 | 0 | 0 | Completed
| Procurement of a Forage chopper | Procurement of a Forage chopper | To enhance efficiency and improve feed quality | 1 Forage Chopper procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 43468 | 2000000 | 450000 | 450000 | County Government of Bungoma |  | 450000 | 0 | 450000 | 1 | 450000 | 0 | 0 | Completed
| Procurement of a boom sprayer | Procurement of a boom sprayer | To control pests and diseases | 1 boom sprayer procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43586 | 43588 | 22/2/2019 | 1,500,00 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 | 1 | 500000 | 0 | 0 | Completed
| Construction of water tower | Proposed construction of water tower at Mabanga ATC | To provide reliable water distribution at the institution | 1 Water tower constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44166 | 44170 | 28/4/2020 | 5000000 | 4765860 | 5000000 | County Government of Bungoma |  | 4765860 | 0 | 4765860 | 1 | 4765860 | 0 | 0 | Completed
| Rehabilitation of cattle dips | Rehabilitation of cattle dips in Luuya, Kibisi, Bukembe, Lutaso, Tulumba, and Myanga Cattle Dips | To improve animal health and productivity | 6 Cattle dips rehabiliatated | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44136 | 44139 | 14/3/2020 | 5000000 | 3486950 | 3548016 | County Government of Bungoma |  | 3486950 | 0 | 3486950 | 1 | 3486950 | 0 | 0 | Completed
| Industrial crop development | Industrial Crop Development (Avocado, mango, macadamia, passion fruits) at Mabanga ATC | To enhance crop production, productivity and income generation | Assorted seedlings planted | 3111301 | Purchase of Certified Crop seed | Kabuchai | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 44229 | 44232 | 22/4/2021 | 25000000 | 17775000 | 17882199 | County Government of Bungoma |  | 17775000 | 0 | 17775000 | 1 | 17775000 | 0 | 0 | Completed
| Establishment of coffee nurseries at Mabanga ATC | Establishment of coffee nurseries at Mabanga ATC | To promote coffee production and enhance income generation s | 300kgs of Coffee seedlings purchased and planted | 3111301 | Purchase of Certified Crop seed | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 44229 | 44232 | 44534 | 5000000 | 1792800 | 1813993 | County Government of Bungoma |  | 1792800 | 0 | 1792800 | 1 | 1792800 | 0 | 0 | Completed
| Supply, delivery, installation, testing and commissioning of standby diesel Generator | Supply, delivery, installation, testing and commissioning of 1n0.standby diesel Generator with accessories-100 Kva 3 Phase at Mabanga ATC | To enhance smooth operations at the institution | 1 standby Generator supplied | 2211007 | Agricultural materials, supplies and small equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 23/2/2022 | 10000000 | 6150000 | 6150000 | County Government of Bungoma |  | 6150000 | 0 | 6150000 | 1 | 6150000 | 0 | 0 | Completed
| Renovation of buildings at Mabanga ATC (ablution blocks, hostels) | Renovation works of 2.No Hostels and 1. N0 Classroom Block at Mabanga ATC | To provide an enabling working environment | 2 Hostels and 1 classroom renovated | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44835 | 44839 | 18/3/2022 | 9000000 | 5805400 | 5805400 | County Government of Bungoma |  | 5805400 | 0 | 5805400 | 1 | 5805400 | 0 | 0 | Completed
| Supply and delivery of incubators for Mabanga ATC | Supply and delivery of 4.No Incubators for Mabanga ATC | To enhance poultry production and increase household incomes | 4 incubator supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 20/2/2022 | 2500000 | 1192000 | 1192000 | County Government of Bungoma |  | 1192000 | 0 | 1192000 | 1 | 1192000 | 0 | 0 | Completed
| Completion works of Zero Grazing Unit at Mabanga ATC | Completion works of Zero Grazing Unit at Mabanga ATC | To improve livestock production and enhance income generation | 1 Zero grazing unit completed | 3110504 | Other infrastructure and civil works | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 18/1/2022 | 18/5/2022 | 30/4/2022 | 3000000 | 1520000 | 1520000 | County Government of Bungoma |  | 1520000 | 0 | 1520000 | 1 | 1520000 | 0 | 0 | Completed
| Erection and completion of Machinery Shade at Mabanga ATC | Erection and completion of AMC Machinery Shade At Mabanga ATC | To provide shade for machinery within Mabanga institution | I AMC Machinery shade constructed | 3120199 | Purchase of fertilizer | Kabuchai | Luuya bwake | 0.597878,34.620875 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44743 | 44747 | 22/4/2022 | 5000000 | 3247304 | 3500000 | County Government of Bungoma |  | 3247304 | 0 | 3247304 | 1 | 3247304 | 0 | 0 | Completed
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Luuya bwake |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Luuya bwake |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
299 | Periodic Maintenance of Marobo - Luuya Girls - Chekulo Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43598 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
300 | Periodic Maintenance of Roads In Luyha Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43481 | 43596 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.48% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
301 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | SEVERAL | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
302 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | SEVERAL | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
490 | Periodic Maintenance of Khachonge Factory - Sichei Cattle Dip Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43969 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
491 | Periodic Maintenance of Roads In Luuya-Bwake | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.88% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
622 | Upgrading of Bwake-Khachonge Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43967 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
719 | Periodic Maintenance of Matunda - Nasaka - Kiboochi - Ngalasia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44329 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
720 | Upgrading of Luuya - Marobo Drift | Road improvement works | To improve the road condition and enhance accessibility | 6.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44334 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
721 | Periodic Maintenance of Roads In Luuya - Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44329 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 97.07% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1042 | Periodic Maintenance of Nalondo - Khatiri - Nangili - Sikinga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 9.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44699 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1043 | Periodic Maintenance of Mahanga Sec - Chekulo - Sikinga Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44700 | 44731 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1044 | Periodic Maintenance of Roads In Luuya-Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 9.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44702 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1045 | Routine Maintenance Of Mahanga Secondary - Chekulo - Sikinga Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44694 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1367 | Periodic Maintenance of Lwanda - Namilama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45057 | 45088 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1368 | Periodic Maintenance of Chekulo - Misanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45057 | 45088 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1369 | Periodic Maintenance of Lwanda - Namilama, Chekulo Misanga Road In Luuya Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45065 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 98.23% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1614 | Periodic Maintenance of Khatiri - Nangili - Sikinga Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45424 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1615 | Periodic Maintenance of Mabwi - Sichei Polytechnic Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45434 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1616 | Construction of Emergency Works For Kibochi- Nasaka Box Culvert. | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45427 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1617 | Construction of Emergency Works Kibochi-Nasaka Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45422 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1618 | Periodic Maintenance of Nangili - Sikinga - Khatiri Road In Luuya/Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45433 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.61% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1619 | Periodic Maintenance of Mabwi - Sichei Polytechnic Road In Luuya/Bwake Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Luuya bwake |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45435 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 107.61% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Luuya bwake |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Luuya bwake |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
36 | Purchase of medical equipment for Lungai, Sirakaru, Makhanga dispensaries | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Tongaren | NAITIRI/KABUYEFWE | 0.8084,34.8868 0.77937,34.898232 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21/5/24 |  |  | 3120000 | 1485230 | 1485230 | CGB |  | 1485230 | 0 | 0 | 0 | 0 | 1485230 | 1485230 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
244 | Completion Of A Stalled Room At Sirakaru Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Dispensaries completed |  |  | Tongaren | NAITIRI/KABUYEFWE |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1000000 | 1904047.2 | 1904047.2 | CGB |  | 1904047.2 | 0 | 1771691.2 | 0.93049 | 1771691.2 |  | 132356 | Complete and in use | [6 empty] | No | complete | Financial | Yes
314 | Purchase of one acre of land | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health facilities. | acres of land purchased |  |  | Tongaren | NAITIRI/KABUYEFWE | [9 empty] | 800000 | 800000 | CGB |  | 800000 | 0 | 800000 | 1 | 800000 |  | 0 | N/A | [6 empty] | No | complete | Financial | Yes
227 | Periodic Maintenance of Naitiri Junction - Sango - Kiminini | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43242 |  | 8201037.6 | 8201037.6 | 8201037.6 | County Government of Bungoma |  | 8201037.6 |  | 8201037.6 |  | 8201037.6 | 0 | 0 |  | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
228 | Periodic Maintenance of Sango - Mukuusi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.8381,34.9005 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43244 |  | 8201037.6 | 8201037.6 | 8201037.6 | County Government of Bungoma |  | 8201037.6 |  | 8201037.6 |  | 8201037.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
229 | Upgrading of Wamanga Drift | Road improvement works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43234 |  | 8201037.6 | 8201037.6 | 8201037.6 | County Government of Bungoma |  | 8201037.6 |  | 8201037.6 |  | 8201037.6 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
230 | Periodic Maintenance of Roads In Naitiri/Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43234 |  | 8201037.6 | 8201037.6 | 8201037.6 | County Government of Bungoma |  | 8201037.6 |  | 8201037.6 | 82.54% | 8201037.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
413 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
414 | Periodic Maintenance of Roads Naitiri /Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43480 | 43600 |  | 9224875 | 9224875 | 9224875 | County Government of Bungoma |  | 9224875 |  | 9224875 | 99.95% | 9224875 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
492 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
598 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
612 | Periodic Maintenance of Mulembe - Sirakaru - Freich - Buyuni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43973 | 44004 | 6014910 | 6014910 | 6014910 | County Government of Bungoma |  | 6014910 |  | 6014910 |  | 6014910 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
613 | Grading of Sirende-Lumboka-Makia Road | Grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43962 | 43993 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
614 | Periodic Maitenance Of Rural Roads Through West Kenya Sugar Mou | Grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43967 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | ongoing | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
615 | Periodic Maintenance of Roads In Naitiri-Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43966 |  | 6014910 | 6014910 | 6014910 | County Government of Bungoma |  | 6014910 |  | 6014910 | 99.95% | 6014910 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
916 | Periodic Maintenance of Wetungu Junction - Nakwoba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44338 |  | 11939126.1 | 11939126.1 | 11939126.1 | County Government of Bungoma |  | 11939126.1 |  | 11939126.1 |  | 11939126.1 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
917 | Periodic Maintenance of Pwani Mkt - Yabuna Dam - Sirakaru Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44339 |  | 11939126.1 | 11939126.1 | 11939126.1 | County Government of Bungoma |  | 11939126.1 |  | 11939126.1 |  | 11939126.1 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
918 | Periodic Maintenance of Nyange - Khakoni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.7411,34.8976 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44333 |  | 11939126.1 | 11939126.1 | 11939126.1 | County Government of Bungoma |  | 11939126.1 |  | 11939126.1 |  | 11939126.1 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
919 | Periodic Maintenance of Roads In Naitiri Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44338 |  | 11939126.1 | 11939126.1 | 11939126.1 | County Government of Bungoma |  | 11939126.1 |  | 11939126.1 | 99.64% | 11939126.1 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1232 | Periodic Maintenance of Pag - Mukumu - Pwani - Wandabwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44695 | 44726 | 12855100.86 | 12855100.86 | 12855100.86 | County Government of Bungoma |  | 12855100.86 |  | 12855100.86 |  | 12855100.86 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1233 | Periodic Maintenance of Naitiri Junction - Sango - Kiminini Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44703 | 44734 | 12855100.86 | 12855100.86 | 12855100.86 | County Government of Bungoma |  | 12855100.86 |  | 12855100.86 |  | 12855100.86 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1234 | Periodic Maintenance of Sango - Mukuusi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44705 | 44736 | 12855100.86 | 12855100.86 | 12855100.86 | County Government of Bungoma |  | 12855100.86 |  | 12855100.86 |  | 12855100.86 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1235 | Periodic Maintenance of Lungai Junction - Sir George Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.773705,34.887548 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44698 | 44729 | 12855100.86 | 12855100.86 | 12855100.86 | County Government of Bungoma |  | 12855100.86 |  | 12855100.86 |  | 12855100.86 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1236 | Periodic Maintenance of Naitiri Junction - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44697 | 44728 | 7172295 | 7172295 | 7172295 | County Government of Bungoma |  | 7172295 |  | 7172295 |  | 7172295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1237 | Periodic Maintenance of Roads In Naitiri-Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.760473,34.889116 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44704 |  | 12855100.86 | 12855100.86 | 12855100.86 | County Government of Bungoma |  | 12855100.86 |  | 12855100.86 | 48.84% | 12855100.86 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1238 | Routine Maintenance Of Naitiri Junction - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44704 |  | 7172295 | 7172295 | 7172295 | County Government of Bungoma |  | 7172295 |  | 7172295 | 97.75% | 7172295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1513 | Periodic Maintenance of Nasianda - Lungai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.778837,34.898183 0.778837,34.0905203 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45063 |  | 6089489 | 6089489 | 6089489 | County Government of Bungoma |  | 6089489 |  | 6089489 |  | 6089489 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1514 | Periodic Maintenance of Obwayo - Kahiga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.768906,34.890183 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45059 |  | 6089489 | 6089489 | 6089489 | County Government of Bungoma |  | 6089489 |  | 6089489 |  | 6089489 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1515 | Periodic Maintenance of Nasyanda - Lungai Road, Obwayo Kahiga Road In Naitiri/Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45061 |  | 6089489 | 6089489 | 6089489 | County Government of Bungoma |  | 6089489 |  | 6089489 | 99.97% | 6089489 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1764 | Periodic Maintenance of Pepela - Mark Tonyi - Khadenyi - Sango Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45432 | 45463 | 5728863 | 5728863 | 5728863 | County Government of Bungoma |  | 5728863 |  | 5728863 |  | 5728863 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1765 | Periodic Maintenance of Pepela - Mark Tonyi - Khadenyi - Sango Market Road And Kewa - Wamusoro Road In Naitiri/Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.7660091,34.906696 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45435 |  | 5728863 | 5728863 | 5728863 | County Government of Bungoma |  | 5728863 |  | 5728863 | 100.0% | 5728863 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
13 | Purchase of 1 Acre for Nasianda dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land Purchased for Nasianda dispensary | 3110599 | Ward based projects | Tongaren | NAITIRI/KABUYEFWE |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45352 | 45809 |  | 1056000 | - | 1056000 | CGB | N/A | 1056000 | 0 | 1056000 | 1 | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
14 | Purchase of 1 Acre for Siumbwa dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land Purchased for Siumbwa Dispensary | 3110599 | Ward based projects | Tongaren | NAITIRI/KABUYEFWE |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45352 | 45809 |  | 1056000 | - | 1056000 | CGB | N/A | 1056000 | 0 | 1056000 | 1 | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
89 | Preparation of intergrated plan for Naitiri | Document review,Desktop research, Gaps analysis, Report Writing and formulation of new maps, Stakeholder engagement for new vision and direction of the urban area | To guide sustainable and inclusive growth of urban areas through land use,infrastructure development and improved service delivery | One Physical and land use plan developed | 2211311 | Development/Physical Planning | Tongaren | NAITIRI/KABUYEFWE |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 43681 | 43748 | 30/10/2019 | 4000000 | 3594444 | 3594444 | CGB |  | 3594444 |  | 3594444 |  | 3594444 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
14 | Repair of ECDE classroom at Bishop Wabukala and ST. Joan Sango primary Schools and construction of Toilets at Bishop Wabukala and Dr. Reginalda primary schools in Naitiri/Kanuyefwe Ward | To repair class floors and paint walls | To renovate ECDE classroom and provide conducive learning environment | ECDE classroom repaired | 3110599 | Construction and Civil works | Tongaren | NAITIRI/KABUYEFWE |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3120000 | 3046760 | 3120000 | County Government of Bungoma | N/A | 3120000 | 0 |  | 0 |  | 3046760 | 3046760 | stalled | At finishes (95%)
91 | the proposed erection and completion Works for 1 no. ECDE Classroom and 2 No. Door pit latrine at St. peters Makumu and construction of 1 no. ECDE classroom at Naitiri FYM, Makhonge DEB and Nyange DEB primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NAITIRI/KABUYEFWE |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 4900000 | 4899890 | 4900000 | County Government of Bungoma | N/A | 4900000 | 0 | 2739725.85 | 0.55914 | 2739725.85 | 2160164.15 | 2160164.15 | Complete and in use | 0.5
124 | Construction Of 1 No. Ecde Classroom At Ndengelwa S.A, Nakoba Fym, Sango S.A And Dkt. Reginalda Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NAITIRI/KABUYEFWE | 0.8132,34.9123 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 5200000 | 5984920 | 5200000 | County Government of Bungoma | N/A | 5200000 | 0 | 4975778.35 | 0.83139 | 4975778.35 | 1009141.65 | 1009141.65 | complete and in use | 1
158 | Proposed Erection And Completion Of 1 No. Ecde At Naitiri Fym, Sirakaru S.A, Nyange Deb And Sango Primary Schools In Naitiri Kabuyefwe Ward | Construction of ECDE classroom | To construct ECDE and a toilet classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NAITIRI/KABUYEFWE |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 4866790.68 | 4754000 | 4866790.68 | County Government of Bungoma | N/A | 4866790.68 | 0 | 4754000 | 1 | 2357032.15 | 2396967.85 | 0 | complete | 0.9
208 | Construction Of 1no. Ecde Classroom At Pwani Fym, Kewa Deb And Sirende Primary Schools In Naitiri/Kabuyefwe Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NAITIRI/KABUYEFWE | 0.8173,34.8953 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4000000 | 4190960 | 4000000 | County Government of Bungoma | N/A | 4000000 |  | 4190960 | 1 | 4190960 | 0 |  | complete and in use | 100.0%
39 | Proposed Tree Growing Within Institutions In Luuya/Bwake, Matulo, Mihuu, Kamukuywa, And Naitiri/Kabuyefwe Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Tongaren | NAITIRI/KABUYEFWE | 0.766342,34.895473 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45452 | 45455 | 45455 | 5917500 | 5910500 | 5910500 | FLLOCA | IDA | 0 | 5910500 | 0 | 1 | 0 | 0 |  | 0n-going | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
70 | Kewa Water Project In Naitiri Kabuyefwe Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Water project constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.759497,34.906687 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2112000 | 2051344 | 2051344 | CGB | N/A | 2051344 | 0 | 2051344 | 1 | 2051344 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
134 | Drilling and equipping of Makhonge primary borehole and construction of 7no. Water springs in Naitiri/Kabuyefwe ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole drilled and 7 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.7394,34.9038 0.784722,34.895012 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 3500000 | 3495370 | 3495370 |  | N/A | 3495370 | 0 | 3495370 | 1 | 3495370 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
203 | DRILLING OF 1NO. BOREHOLE AT SIARAKARU VOCATIONAL TRAINING CENTRE IN NAITIRI/KABUYEFWE WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1800000 | 1797072 | 1797072 |  | N/A | 1797072 | 0 | 1797072 | 1 | 1797072 | 0 | 0 | stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
319 | DRILLING AND EQUIPPING OF 2NO. BOREHOLES AND 2NO.SPRING IN NAITIRI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | Boreholes drilled and water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3500000 | 3420000 | 3420000 |  | N/A | 3420000 | 0 | 3420000 | 1 | 3420000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
358 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.7389,34.9119 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 609052 | 609052 |  | N/A | 609052 | 0 | 609052 | 1 | 609052 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
372 | Construction of 5 roof Catchments and 50m3 Masonry tank | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 tanks constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 645608 | 645608 |  | N/A | 645608 | 0 | 645608 | 1 | 645608 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
377 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1617630 | 1617630 |  | N/A | 1617630 | 0 | 1617630 | 1 | 1617630 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
426 | Drill 1No borehole at Wabukhonyi market and equip with hand pump | Site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1000000 | 993825 | 993825 |  | N/A | 993825 | 0 | 993825 | 1 | 993825 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
433 | Construction of 5 roof Catchments and 50m3 Masonry tank | erection of storage tank; pipeline extension and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1200000 | 1198985.45 | 1198985.45 |  | N/A | 1198985.45 | 0 | 1198985.45 | 1 | 1198985.45 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
444 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs. constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.7351,34.9038 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1000000 | 913578 | 913578 |  | N/A | 913578 | 0 | 913578 | 1 | 913578 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
467 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE | 0.7184,34.9119 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1617630 | 1617630 |  | N/A | 1617630 | 0 | 1617630 | 1 | 1617630 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
468 | Construction of 5 roof Catchments and 50m3 Masonry tank | construction of roof catchment;storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1844593 | 1844593 |  | N/A | 1844593 | 0 | 1844593 | 1 | 1844593 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
469 | Drill 1No borehole at Wabukhonyi market and equip with hand pump | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1419750 | 1419750 |  | N/A | 1419750 | 0 | 1419750 | 1 | 1419750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
550 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1522630 | 1522630 |  | N/A | 1522630 | 0 | 1522630 | 1 | 1522630 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
551 | Drill 2No borehole at pwani market and nyange primary school and equip with hand pump | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | NAITIRI/KABUYEFWE |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2800000 | 2664200 | 2664200 |  | N/A | 2664200 | 0 | 2664200 | 1 | 2664200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Supply and delivery of two months old improved vaccinated indigeneous chicks and chick mash (feeds) | Supply and delivery of two months old improved vaccinated indigeneous chicks and chick mash (feeds) | To enhance poultry production and increase household incomes | 9,000 2-months old improved vaccinated chicks supplied and delivered to farmer groups | 3110599 | Ward Based projects | Tongaren | NAITIRI/KABUYEFWE | 0.763174,34.899617 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 7000000 | 6998975 | 7000000 | County Government of Bungoma |  | 6998975 | 0 | 6998975 | 1 | 6998975 | 0 | 0 | Completed
| Supply and delivery of young dairy animals(Heifers) 18 to 24 months $ young dairy goats 12 to 18 months old | Supply and delivery of young dairy animals(Heifers) 18 to 24 months $ young dairy goats 12 to 18 months old | To enhance dairy production, value addition and income generation | 58 Dairy animals (heifers) supplied and delivered to farmer groups | 3110599 | Ward Based projects | Tongaren | NAITIRI/KABUYEFWE | 0.763174,34.899617 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 6800000 | 6800000 | 6800000 | County Government of Bungoma |  | 6800000 | 0 | 6800000 | 1 | 6800000 | 0 | 0 | Completed
| Supply and delivery of two months old improved vaccinated indigenous chicks and chick mash (feeds) | Supply and delivery of two months old improved vaccinated indigenous chicks and chick mash (feeds) | To enhance poultry production and increase household incomes | 1587 Chicks and 1428kgs of feeds supplied and delivered | 3110599 | Ward Based projects | Tongaren | NAITIRI/KABUYEFWE | 0.763174,34.899617 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 1500000 | 1500000 | 1500000 | County Government of Bungoma |  | 1500000 | 0 | 1500000 |  | 1500000 | 0 | 0 | Completed
| Provision of improved breeds (sheep) | Provision of 30 ewes and 3 Rams to 3 elite breeders,2 in Naitiri/Kabuyefwe (NAKASIMA SLCA) and one in Kaptama (KAPCHEKO SLCA) | To enhance production, productivity and income generation | 30 ewes and 3 Rams purchased and issued to 3 elite breeders | 2640503 | Other Capital grants and transfer (KeLCoP) | Tongaren | NAITIRI/KABUYEFWE | 0.760126,34.889367 0.766342,34.895473 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45630 | 45633 | 45357 |  | 956880 | 1029280 | Development partner | IFAD | 0 | 956880 | 956880 |  | 956880 | 0 | 0 | complete
| Provision of improved breeds of chicken | Provision of improved breeds (Indigenous poultry) chicken – day old chicks | To enhance production, productivity and income generation | 14 MOFAG beneffitted by each getting 575 breeds | 2640503 | Other Capital grants and transfer (KeLCoP) | Tongaren | NAITIRI/KABUYEFWE | 0.760125,34.889340 0.766342,34.895473 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/3/2024 | 23/6/2024 | 28/5/2024 |  | 1387730 | 1447460 | Development partner | IFAD | 0 | 1387730 | 1387730 |  | 1387730 | 0 | 0 | Complete
| Upscaling production of grass seeds | Upscaling production of grass seeds by distrbuting 100 bags of 50kgs of organic fertilizer | To enhance productivity and income generation | 100 bags of 50kg organic fertilizer procured and distributed to 8 farmers. | 2640503 | Other Capital grants and transfer (KeLCoP) | Tongaren | NAITIRI/KABUYEFWE | 0.760089,34.889385 0.766342,34.895473 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45242 | 45598 | 45444 |  | 144940 | 145 940 | Development partner | IFAD | 0 | 620398 | 144940 |  | 144940 | 0 | 0 | Complete
| Purchase and distribution of day old Chicks Rainbow Roosters | Purchase and delivery of 8,050 day old Chicks rainbow roosters to 14 MOFAG Indigenous chicken groups | To enhance poultry production and increase household incomes | 8,050 chicks purchased and delivered to 14 MOFAG indingeneous chicken groups | 2640503 | Other Capital grants and transfer (KeLCoP) | Tongaren | NAITIRI/KABUYEFWE | 0.766342,34.895473 0.763174,34.889514 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 31/3/2024 | 31/6/2024 | 45510 | [12 empty] | complete
26 | Proposed Installation and commissioning of 3No. Solar powered Floodlight | Installation of Solar of 3No | promotion of MSMEs and security | Solar powered floodligts installed | 1472960-2023-24 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 5620000 |  |  | CGB | [8 empty] | Complete | 100 | 3
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NAITIRI/KABUYEFWE |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | NAITIRI/KABUYEFWE |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
175 | Periodic Maintenance of Naitiri Junction - Sango - Kiminini | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43242 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
176 | Periodic Maintenance of Sango - Mukuusi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43244 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
177 | Upgrading of Wamanga Drift | Road improvement works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43234 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
335 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | SEVERAL | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
518 | Periodic Maintenance of Mulembe - Sirakaru - Freich - Buyuni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43973 | 44004 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
519 | Grading of Sirende-Lumboka-Makia Road | Grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43962 | 43993 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
520 | Periodic Maitenance Of Rural Roads Through West Kenya Sugar Mou | Grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43967 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
759 | Periodic Maintenance of Wetungu Junction - Nakwoba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44338 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
760 | Periodic Maintenance of Pwani Mkt - Yabuna Dam - Sirakaru Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44339 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
761 | Periodic Maintenance of Nyange - Khakoni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44333 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1083 | Periodic Maintenance of Pag - Mukumu - Pwani - Wandabwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44695 | 44726 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1084 | Periodic Maintenance of Naitiri Junction - Sango - Kiminini Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44703 | 44734 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1085 | Periodic Maintenance of Sango - Mukuusi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44705 | 44736 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1086 | Periodic Maintenance of Lungai Junction - Sir George Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44698 | 44729 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1087 | Periodic Maintenance of Naitiri Junction - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44697 | 44728 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1396 | Periodic Maintenance of Nasianda - Lungai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45063 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1397 | Periodic Maintenance of Obwayo - Kahiga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45059 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1650 | Periodic Maintenance of Pepela - Mark Tonyi - Khadenyi - Sango Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45432 | 45463 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1651 | Periodic Maintenance of Pepela - Mark Tonyi - Khadenyi - Sango Market Road And Kewa - Wamusoro Road In Naitiri/Kabuyefwe Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | NAITIRI/KABUYEFWE |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45435 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | stalled
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | stalled
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.76,34.88 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | stalled
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.760146,34.889044 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.760146,34.889044 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.760146,34.889044 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.780865,34.910056 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.760058,34.889181 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.776123,34.892609 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.760052,34.88922 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.773705,34.887548 0.760054,34.89020 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.773705,34.887548 0.760053,34.89029 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.760055,34.99087 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.767345,34.886199 0.76059,34.88925 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE | 0.774679,34.899460 0.76059,34.889250 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | ongoing
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | NAITIRI/KABUYEFWE |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | NAITIRI/KABUYEFWE | 0.761092,34.897925 | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | complete |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | NAITIRI/KABUYEFWE |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
[7 empty] | tONGAREN | NAITIRI/KABUYEFWE
| Nasinyama-polytechnic road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8153,34.8701 | Roads infrastructure and public works |  |  | 2024/25
| Wabukhonyi VTC Makete cattle dip | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8181,34.8791 | Agriculture and Irrigation | [18 empty] | ongoing
| Matofari bridge | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8204,34.8871 | Roads infrastructure and public works |  |  | 2024/25 | [15 empty] | vtc in use, cattle dip stalled
| Yukah-Kombi road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8236,34.8714 | Roads infrastructure and public works | [18 empty] | ongoing
| Okudoyi mtongoi spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8275,34.8802 | Natural resources, water and climate change | [18 empty] | complete
| kombi flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8317,34.8884 | Trade |  |  | 2023/24 | [15 empty] | complete
| sango cattle dip | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8357,34.9054 | Trade | [18 empty] | complete
| sango primary school ecde | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8351,34.9057 | Education | [18 empty] | stalled
| amani-sasaka sango road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8341,34.9078 | roads infrastructure and public works |  |  | 2023/24 | [15 empty] | complete
| sango naitiri dispensary flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8324,34.9105 | Trade |  |  | 2024/25 | [15 empty] | complete
| mukusi water spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8953,34.9183 | Waer and irrigation | [18 empty] | complete
| lungui spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8251,34.9182 | Waer and irrigation | [18 empty] | complete
| sikumba spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8365,34.9162 | Waer and irrigation | [18 empty] | complete
| sango mukusi road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8381,34.9005 | Roads, infrastructure & public works |  |  | 2024/25 | [15 empty] | complete
| kutta spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8249,34.8866 | Water & irrigation |  |  | 2024/25 | [15 empty] | complete
| kombi nasinyama road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8220,34.8924 | Roads, infrastructure & public works |  |  | 2024/25 | [15 empty] | ongoing
| sirende cattle dip | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8172,34.8947 | Trade | [18 empty] | stalled
| St kizito sirende flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8173,34.8953 | Education & vocational training | [18 empty] | complete
| Nakoba ecde primary | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8180,34.8960 |  |  |  | 2024/25 | [15 empty] | complete
| Nakoba flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8132,34.9123 | Education | [18 empty] | complete
| Wasike sangura spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8123,34.9142 | Trade | [18 empty] | complete
| Rasto spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8215,34.9081 | Water& irrigation | [18 empty] | complete
| Makhanga ecde | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7956,34.8905 | Water& irrigation |  |  | 2023/24 | [15 empty] | complete
| Mulatispring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7951,34.8879 | Early childhood education | [18 empty] | stalled
| Makhanga dispensary | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8046,34.8868 | Water& irrigation |  |  | 2024/25 | [15 empty] | complete
| Makhanga flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.80,34.8879 | Health& sanitation |  |  | 2024/25 | [15 empty] | stalled
| Makhanga boda boda shed | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8089,34.8886 | Trade | [18 empty] | complete
| Naulikha spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8086,34.8891 | Trade | [18 empty] | complete
| Makhanga junction polytechnic road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8081,34.8915 | Water& irrigation | [18 empty] | complete
| Makhanga primary school road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8036,34.8790 | Roads, infrastructure& public works | [18 empty] | complete
| Wabukhonyi boda boda shed | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.842,34.8778 | Trade | [18 empty] | complete
| Wabukhonyi market borehole | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8042,34.8667 | Water& irrigation | [18 empty] | complete, but dried up
| Wabukhonyi flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8032,34.8667 | Trade | [18 empty] | complete, but not in use
| Lungai sirende road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.773511,34.887396 | Roads |  |  | 2023/24 | [15 empty] | completed
| Kipukha/ lumboka road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.775120,34.888110 | Roads |  |  | 2023/24 | [15 empty] | completed
| Lungai/ Wabusia/ Waiti road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.776662,34.895012 | Roads |  |  | 2023/24 | [15 empty] | stalled
| Muyila spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.784722,34.895012 | Water |  |  | 2023/24 | [15 empty] | completed
| Lungai ecde | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.8161,34.900200 | Education |  |  | 2021/22 | [15 empty] | completed
| Mikali springs | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.774696,34.907848 | Water |  |  | 2022/23 | [15 empty] | completed
| Flat lights lungai | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.778654,34.899324 | Trade |  |  | 2015/16 | [15 empty] | completed
| PAG mukweyi road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7254,34.9095 | Roads, and public works |  |  | 2020/21 | [15 empty] | completed
| Siumbwa junction wanakai road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7293,34.9051 | Roads, and public works |  |  | 2023/24 | [15 empty] | completed
| Namuyonga road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7459,34.4970 | Roads, and public works |  |  | 2023/24 | [15 empty] | completed
| Nyange boda boda | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7366,34.8985 |  |  |  | 2020/21 | [15 empty] | completed
| Mukweyi spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7260,34.9190 | Tourism, environment & natural resources |  |  | 2022/23 | [15 empty] | completed
| Fedha bitali spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7454,34.9035 | Tourism, environment & natural resources | [18 empty] | completed
| Mitua flood lights | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7200,34.9165 | Energy |  |  | 2022/23 | [15 empty] | completed
| Mitua boda boda shed | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7200,34.9165 |  |  |  | 2022/23 | [15 empty] | completed
| Siumbwa ecde classroom | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7331,34.9169 |  |  |  | 2021/22 | [15 empty] | completed
| Stock farm spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.69571,34.9020 | Water |  |  | 2023/24 | [15 empty] | completed
| Supply of fertilizer& seeds | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE |  | Agriculture |  |  | 2024/25 | [15 empty] | completed
| Mitua- pwani-nzoia road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.6973,34.8999 | Roads |  |  | 2019/20 | [15 empty] | completed
| Sokomoko- ndengelwa road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.69899,34.9007 | Roads |  |  | 2019/20 | [15 empty] | completed
| Sirakaru flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.72559,34.8979 | Trade |  |  | 2015/16 | [15 empty] | completed
| Pwani dispensary | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.7035,34.903 | Health |  |  | 2007/08 | [15 empty] | completed
| Anthony spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.766135,34.896012 | Water |  |  | 2023/24 | [15 empty] | completed
| Namanjala dam | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.766342,34.895473 | Water |  |  | 2023/24 | [15 empty] | ongoing
| Namasambu springs | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.776060,34.917687 | Water |  |  | 2023/24 | [15 empty] | completed
| Wabwala foot light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.773664,34.915157 | Trade |  |  | 2023/24 | [15 empty] | completed
| Nabuka ecde | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.78661,34.925278 | Education |  |  | 2023/24 | [15 empty] | ongoing
| Nasianda flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.762042,34.918375 | Trade |  |  | 2023/24 | [15 empty] | completed
| Kewa water project | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.759497,34.906687 | Water |  |  | 2023/24 | [15 empty] | completed
| Kewa ecde | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE |  | Education |  |  | 2021/22 | [15 empty] | completed
| Naitiri junction sango rural road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.737613,34.927106 | Roads |  |  | 2023/24 | [15 empty] | completed
| Pepella junction market road | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.744978,34.921876 | Roads |  |  | 2023/24 | [15 empty] | completed
| sango market flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.753603,34925458 | Trade |  |  | 2023/24 | [15 empty] | completed
| Siamba flood light | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.756246,34.921108 | Trade |  |  | 2023/24 | [15 empty] | completed
| Mafumbo/ Tochi spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.753265,34.913402 | Water |  |  | 2023/24 | [15 empty] | ongoing
| Isaboke spring | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.743300,34.923108 | Water |  |  | 2023/24 | [15 empty] | stalled
| St Joan sango ecde | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.742709,34.923435 | Education |  |  | 2016/17 | [15 empty] | stalled
| Supply of fertilizer& seeds | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE |  | Agriculture |  |  | 2024/25 | [15 empty] | completed
| Sango dispensary | [5 empty] | TONGAREN | NAITIRI/KABUYEFWE | 0.753593,34.925475 | Health |  |  | 2014/15 | [15 empty] | completed
3 | Construction of Lunao dispensary phase 2 | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | BUMULA | 0.556498,34.415993 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45508 |  |  | 2000000 | 1899700 | 1899700 | CGB |  | 1899700 | 0 | 0 | 0 | 0 |  | 1899700 | stalled | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
71 | Erection And Completion Of Outpatient Wing At Lunao Dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Outpatient wings erected and completed |  |  | Bumula | BUMULA | 0.556498,34.415993 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2000000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Yet To Start | [6 empty] | No | complete | Financial | Yes |  |  |  | No
98 | Construction Of Maternity Wing At Nasyanda Health Center And Fencing Mabusi Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Bumula | BUMULA | 0.500938,34.448072 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 4000000 | 3975990 | 3975990 | CGB |  | 3975990 | 0 | 2715231 | 0.68291 | 2715231 |  | 1260759 | Complete but not in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
122 | Complition Of Mabusi Dispensary |  |  | dispensaries completed |  |  | Bumula | BUMULA | 0.570781,34.420067 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2000000 | 1871130 | 1871130 | CGB |  | 1871130 | 0 | 1871130 | 1 | 1871130 |  | 0 | completed and in use | [6 empty] | No | complete | Financial | Yes
123 | Erection And Completion Of Pit Latrines Mabusi Dispensary | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | pit latrines erected and completed |  |  | Bumula | BUMULA | 0.5223092,34.424152 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 1100000 | 988760 | 988760 | CGB |  | 988760 | 0 | 609495.9 | 0.61642 | 609495.9 |  | 379264.1 | stalled | [6 empty] | No | complete | Financial | Yes
217 | Constuction Of 1 Outpatient Room At Mabusi Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Outpatient wings erected and constructed |  |  | Bumula | BUMULA | 0.570781,34.420067 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 4800000 | 5756558 | 5756558 | CGB |  | 5756558 | 0 | 5756558 | 1 | 5756558 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
257 | Renovation and completion of Nasyanda dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the . | Dispensaries renovated/completed |  |  | Bumula | BUMULA | 0.500938,34.448072 |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42185 |  |  | 2747796 | 2747796 | CGB |  | 2747796 | 0 | 1005766 | 0.36603 | 1005766 |  | 1742030 | completed | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
263 | Construction of ablution block at Bumula sub county Hospital | Digging of 20ft deep pit, flooring, walling, roofing, fitting of doors and windows, and painting. | To develop and maintain infrastructure for enhanced access to quality health care services. | Ablution blocks constructed |  |  | Bumula | BUMULA | 0.548647,34.460910 | [8 empty] | 5506961 | 5506961 | CGB |  | 5506961 | 0 |  | 0 |  |  | 5506961 | Stalled. | [6 empty] | No | complete | Financial | Yes |  |  |  | No
54 | Upgrading of Mukwa Mkt-Netima Mkt Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41663 | 41774 |  | 4401852 | 4401852 | 4401852 | County Government of Bungoma |  | 4401852 |  | 4401852 | 100.0% | 4401852 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
99 | Periodic Maintenance of Peridic Maintenance Of Bumula - Kimwanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42379 | 42514 |  | 8235942 | 8235942 | 8235942 | County Government of Bungoma |  | 8235942 |  | 8235942 | 99.57% | 8235942 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
100 | Periodic Maintenance of Lunao - Namatotoa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42384 | 42508 |  | 3964514 | 3964514 | 3964514 | County Government of Bungoma |  | 3964514 |  | 3964514 | 100.0% | 3964514 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
117 | Upgrading of Masuno - Harambee Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.481953,34.525663 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42746 | 42866 |  | 25670223.5 | 25670223.5 | 25670223.5 | County Government of Bungoma |  | 25670223.5 |  | 25670223.5 | 100.0% | 25670223.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
118 | Periodic Maintenance of Periodic Maintanance Of Bunambobi-Sikinga Junt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42755 | 42875 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
119 | Periodic Maintenance of Namatotoa Primary - Buyofu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42753 | 42871 |  | 10133760 | 10133760 | 10133760 | County Government of Bungoma |  | 10133760 |  | 10133760 | 22.8% | 10133760 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
120 | Periodic Maintenance of Talitiya Kabula Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42746 | 42865 |  | 8022966.6 | 8022966.6 | 8022966.6 | County Government of Bungoma |  | 8022966.6 |  | 8022966.6 | 99.58% | 8022966.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
121 | Periodic Maintenance of Tulumba Pri - Mateka Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42748 | 42870 |  | 8250488.4 | 8250488.4 | 8250488.4 | County Government of Bungoma |  | 8250488.4 |  | 8250488.4 | 91.21% | 8250488.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
152 | Periodic Maintenance of Sikinga - Mwenge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.524631,34.445606 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43116 | 43236 |  | 6278302.8 | 6278302.8 | 6278302.8 | County Government of Bungoma |  | 6278302.8 |  | 6278302.8 |  | 6278302.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
153 | Periodic Maintenance of Roads In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43235 |  | 6278302.8 | 6278302.8 | 6278302.8 | County Government of Bungoma |  | 6278302.8 |  | 6278302.8 | 99.87% | 6278302.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
154 | Periodic Maintenance of Kimatuni-Khayo-Lukhuni | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA | 0.515041,34.450061 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43123 | 43232 |  | 8854802 | 8854802 | 8854802 | County Government of Bungoma |  | 8854802 |  | 8854802 | 100.0% | 8854802 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
155 | Periodic Maintenance of Malakisi Sirende-Musakasa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43244 |  | 9938764 | 9938764 | 9938764 | County Government of Bungoma |  | 9938764 |  | 9938764 | 98.72% | 9938764 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
285 | Periodic Maintenance of Tabuti - Lurare - Bumula Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.547658,34.448418 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43479 | 43599 | 43630 | 7494713 | 7494713 | 7494713 | County Government of Bungoma |  | 7494713 |  | 7494713 |  | 7494713 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
286 | Periodic Maintenance of Roads In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43604 |  | 7494713 | 7494713 | 7494713 | County Government of Bungoma |  | 7494713 |  | 7494713 | 99.47% | 7494713 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
287 | Construction of Costruction Of Mabusi Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.536129,34.409106 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43479 | 43607 |  | 12954845 | 12954845 | 12954845 | County Government of Bungoma |  | 12954845 |  | 12954845 |  | 12954845 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
288 | Construction of Lubunda Namusasi Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43609 |  | 11153120 | 11153120 | 11153120 | County Government of Bungoma |  | 11153120 |  | 11153120 |  | 11153120 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
289 | Periodic Maintenance of Maintenance Of Napara - Bitobo - A1 Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43481 | 43603 |  | 12806052 | 12806052 | 12806052 | County Government of Bungoma |  | 12806052 |  | 12806052 | 96.96% | 12806052 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
290 | Construction of Lubunda-Namusasi Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43481 | 43603 |  | 11153120 | 11153120 | 11153120 | County Government of Bungoma |  | 11153120 |  | 11153120 | 99.18% | 11153120 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
291 | Construction of Mabusi Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43597 |  | 12954845 | 12954845 | 12954845 | County Government of Bungoma |  | 12954845 |  | 12954845 | 62.89% | 12954845 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
292 | Periodic Maintenance of Watoya-Sio River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43608 |  | 9963849 | 9963849 | 9963849 | County Government of Bungoma |  | 9963849 |  | 9963849 | 86.33% | 9963849 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
293 | Periodic Maintenance of Myanga Mkt- Mt Carmel School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43484 | 43609 |  | 9188476 | 9188476 | 9188476 | County Government of Bungoma |  | 9188476 |  | 9188476 | 88.37% | 9188476 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
385 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
478 | Periodic Maintenance of Masuno - Namusasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.492354,34.465549 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 8938380 | 8938380 | 8938380 | County Government of Bungoma |  | 8938380 |  | 8938380 |  | 8938380 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
479 | Periodic Maintenance of Mikokwe - Wesimikha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43971 |  | 8938380 | 8938380 | 8938380 | County Government of Bungoma |  | 8938380 |  | 8938380 |  | 8938380 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
480 | Periodic Maintenance of Roads In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43975 |  | 8938380 | 8938380 | 8938380 | County Government of Bungoma |  | 8938380 |  | 8938380 | 99.98% | 8938380 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
481 | Periodic Maintenance of Chief Naulikha - Khauni - Nakalila - Masielo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43971 |  | 9006805.5 | 9006805.5 | 9006805.5 | County Government of Bungoma |  | 9006805.5 |  | 9006805.5 |  | 9006805.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
482 | Periodic Maintenance of Kimwanga - Siboti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43964 |  | 7187418 | 7187418 | 7187418 | County Government of Bungoma |  | 7187418 |  | 7187418 |  | 7187418 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
483 | Periodic Maintenance of Kimwanga - Siboti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43970 |  | 7187418 | 7187418 | 7187418 | County Government of Bungoma |  | 7187418 |  | 7187418 |  | 7187418 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
484 | Periodic Maintenance of Kimwanga - Siboti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43973 |  | 7187418 | 7187418 | 7187418 | County Government of Bungoma |  | 7187418 |  | 7187418 |  | 7187418 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
485 | Periodic Maintenance of Siboti - Bosio Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43972 |  | 7420056 | 7420056 | 7420056 | County Government of Bungoma |  | 7420056 |  | 7420056 |  | 7420056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
486 | Upgrading of Wamunyiri - Samichi - Malinda | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43962 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
487 | Periodic Maintenance of Chief Naulikha-Khauni-Nakalila-Masielo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43973 |  | 9006805.5 | 9006805.5 | 9006805.5 | County Government of Bungoma |  | 9006805.5 |  | 9006805.5 | 98.59% | 9006805.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
488 | Periodic Maintenance of Kimwanga-Siboti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43963 |  | 7187418 | 7187418 | 7187418 | County Government of Bungoma |  | 7187418 |  | 7187418 | 96.72% | 7187418 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
489 | Periodic Maintenance of Siboti-Bosio Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43971 |  | 7420056 | 7420056 | 7420056 | County Government of Bungoma |  | 7420056 |  | 7420056 | 92.29% | 7420056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
539 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
663 | Drainage Works In Kanduyi And Bumula Sub-Counties(Lot 2) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 | 96.54% | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
703 | Periodic Maintenance of Syekumulo - Weighbridge - Chiliba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA | 0.547981,34.492637 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44337 |  | 8781374 | 8781374 | 8781374 | County Government of Bungoma |  | 8781374 |  | 8781374 |  | 8781374 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
704 | Periodic Maintenance of Bunambobi Primary (Principal Masinde) - Lunao Polytechnic - Quarry Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.556983,34.442551 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44331 |  | 5258396 | 5258396 | 5258396 | County Government of Bungoma |  | 5258396 |  | 5258396 |  | 5258396 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
705 | Periodic Maintenance of Roads In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44335 |  | 5258396 | 5258396 | 5258396 | County Government of Bungoma |  | 5258396 |  | 5258396 | 99.99% | 5258396 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
706 | Periodic Maintenance of Syekumulo - Waybridge -Chiliba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA | 0.547981,34.492637 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44340 |  | 8781374 | 8781374 | 8781374 | County Government of Bungoma |  | 8781374 |  | 8781374 | 98.38% | 8781374 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
707 | Periodic Maintenance of Siboti - Musakasa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44334 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
708 | Upgrading of Namanje Crossing Point | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44330 |  | 2496992.8 | 2496992.8 | 2496992.8 | County Government of Bungoma |  | 2496992.8 |  | 2496992.8 |  | 2496992.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
709 | Upgrading of Kimaeti Junction - Bitobo Drift | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44328 |  | 1712879.2 | 1712879.2 | 1712879.2 | County Government of Bungoma |  | 1712879.2 |  | 1712879.2 |  | 1712879.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
710 | Upgrading of Watoya - R. Sio | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44340 |  | 1295915.8 | 1295915.8 | 1295915.8 | County Government of Bungoma |  | 1295915.8 |  | 1295915.8 |  | 1295915.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
711 | Rehabilitation Of Namanje Crossing Point | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44333 |  | 2496992.8 | 2496992.8 | 2496992.8 | County Government of Bungoma |  | 2496992.8 |  | 2496992.8 | 98.69% | 2496992.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
712 | Upgrading of Kimaeti Junction - Bitobo Drift | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44332 |  | 1712879.2 | 1712879.2 | 1712879.2 | County Government of Bungoma |  | 1712879.2 |  | 1712879.2 | 99.72% | 1712879.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
713 | Drainage Works On Watoya - River Sio Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44336 |  | 1295915.8 | 1295915.8 | 1295915.8 | County Government of Bungoma |  | 1295915.8 |  | 1295915.8 | 99.9% | 1295915.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1040 | Periodic Maintenance of Sikinga Junction - Mabusi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.524631,34.45006 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44694 | 44725 | 5427006 | 5427006 | 5427006 | County Government of Bungoma |  | 5427006 |  | 5427006 |  | 5427006 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1041 | Periodic Maintenance of Roads In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44700 |  | 5427006 | 5427006 | 5427006 | County Government of Bungoma |  | 5427006 |  | 5427006 | 98.17% | 5427006 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1353 | Periodic Maintenance of Mzee Alex - Railway Crossing - St. Raphael Pri - Wasilwa - Mzee Mbaisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.541052,34.467816 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45069 |  | 7376793 | 7376793 | 7376793 | County Government of Bungoma |  | 7376793 |  | 7376793 |  | 7376793 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1354 | Periodic Maintenance of Bumula Hospital - Bumula Police Post Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.560465,34.492637 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45063 |  | 7376793 | 7376793 | 7376793 | County Government of Bungoma |  | 7376793 |  | 7376793 |  | 7376793 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1355 | Periodic Maintenance of Mzee Alex - Railway Crossing - St. Raphael Primary - Wasilwa - Mzee Mbaisi, Bumula Hospital - Police Post Road In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.541052,34.467816 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45056 |  | 7376793 | 7376793 | 7376793 | County Government of Bungoma |  | 7376793 |  | 7376793 | 99.99% | 7376793 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1356 | Periodic Maintenance of Harambee Bridge - Kimatuni Joy Valley - Khayo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 9.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.515041,34.450061 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45069 |  | 5867324.31 | 5867324.31 | 5867324.31 | County Government of Bungoma |  | 5867324.31 |  | 5867324.31 |  | 5867324.31 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1357 | Periodic Maintenance of Mareba - Tabuti - Nang'Eni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45063 |  | 4363944 | 4363944 | 4363944 | County Government of Bungoma |  | 4363944 |  | 4363944 |  | 4363944 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1358 | Periodic Maintenance of Mareba - Tabuti - Nang'Eni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45070 |  | 4363944 | 4363944 | 4363944 | County Government of Bungoma |  | 4363944 |  | 4363944 |  | 4363944 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1359 | Construction of Chiliba Pri. Sch. Lunao Fym Sch. Box Culverts | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.54743,34.430602 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45064 |  | 5653085.6 | 5653085.6 | 5653085.6 | County Government of Bungoma |  | 5653085.6 |  | 5653085.6 |  | 5653085.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1360 | Routine Maintenance Of Harambee Bridge - Kimatuni Joy Valley Khayo | Gravelling and grading works | To improve the road condition and enhance accessibility | 9.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45057 |  | 5867324.31 | 5867324.31 | 5867324.31 | County Government of Bungoma |  | 5867324.31 |  | 5867324.31 | 95.89% | 5867324.31 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1361 | Routine Maintenance Of Mareba-Tabuti Nangeni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45057 |  | 4363944 | 4363944 | 4363944 | County Government of Bungoma |  | 4363944 |  | 4363944 | 99.5% | 4363944 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1362 | Construction of Chiliba Pr. School Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45070 |  | 5653085.6 | 5653085.6 | 5653085.6 | County Government of Bungoma |  | 5653085.6 |  | 5653085.6 | 86.81% | 5653085.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1609 | Periodic Maintenance of Malambisia - Namusasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.492264,34.46549 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45433 |  | 10477236 | 10477236 | 10477236 | County Government of Bungoma |  | 10477236 |  | 10477236 |  | 10477236 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1610 | Periodic Maintenance of Chiliba Primary School-Kware Mkt-T Junction In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.54743,34.430602 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45435 |  | 4947516 | 4947516 | 4947516 | County Government of Bungoma |  | 4947516 |  | 4947516 | 99.99% | 4947516 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1611 | Periodic Maintenance of Tito Bridge - Khelela - Malambisia - Namusasi Road In Bumula Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | BUMULA | 0.543608,34.438465 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45426 |  | 10477236 | 10477236 | 10477236 | County Government of Bungoma |  | 10477236 |  | 10477236 | 99.98% | 10477236 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
5 | Purchase of 1 Acre land for Sifuniame E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land Purchased for Sifuniame ECDE | 3110599 | Ward based projects | Bumula | BUMULA | 0.774058,34.413224 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45352 | 45809 |  | 1000000 | 700000 | 1000000 | CGB | N/A | 1000000 | 0 | 1000000 | 1 | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
6 | Purchase of 1Acre land for Malambisia E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land Purchased for Malambisia ECDE | 3110599 | Ward based projects | Bumula | BUMULA |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45444 | 45809 |  | 1000000 | 1200000 | 1000000 | CGB | N/A | 1000000 | 0 | 1000000 | 1 | 0 |  |  | proposed | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
29 | Purchase of 1 Acre for Maraba E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land for Maranda ECDE purchased. | 3110599 | Ward based projects | Bumula | BUMULA |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | 45323 | 45474 | 45474 | 2000000 | 1000000 | 1000000 | CGB |  | 1000000 |  | 1000000 | 1 | 0 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
44 | Purchase of 1 Acre for Wamaliacha E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land for Wamaliacha E.C.D.E Purchased | 3110599 | Ward based projects | Bumula | BUMULA |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | - | - |  | 2000000 | 1200000 | 1200000 | CGB |  | 1200000 |  | 1200000 | 1 | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2022/23 |  |  | No | Compete | [7 empty] | The project is staled due Lack of documentations(Title deed)
61 | Purchase Of 1 Acre For Namunji E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land For Namunji E.C.D.E Purchased | 3110599 | Ward based projects | Bumula | BUMULA | 0.516961,34.410324 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  | 44594 | 31/3/2022 | 26/4/2022 | 700000 | 700000 | CGB |  | 700000 |  | 700000 | 1 | 650000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
62 | Purchase Of 1 Acre For Lunao Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land For Lunao Dispensary Purchased | 3110599 | Ward based projects | Bumula | BUMULA | 0.556498,34.415993 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  | 20/2/2022 | 31/6/2022 | 31/12/2022 | 700000 | 700000 | CGB |  | 700000 |  | 700000 | 1 | 1000000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
158 | Purchase of 1 acre land for Lurare ECDE Cetnre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Lurare E.C.D.E Purchased | 3110599 | Ward based projects | Bumula | BUMULA | 0.558829,34.460539 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 16/1/2016 | 20/1/2016 | 24/6/2016 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 650000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
24 | Construction of 1 NO. ECDE Classroom at Syekumulo and Masuno primary school in Bumula Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | BUMULA | 0.540213,34.472374 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3000000 | 2955520 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0 |  | 2955520 | 2955520 | completed | At substructure (15%)
34 | Proposed Erection And Completion Works For 1no. Ecde Classroom At Bumula Fym, Chiliba, Mikokwe And Kimatuni Joy Valley Primary Schools In Bumula Ward | Consturction of ECDE classroom | To construct VTCproviding conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | BUMULA | 0.516630,34.451151 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 6000000 | 5620000 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 2183573.7 | 0.38854 | 2183573.7 | 3436426.3 | 3436426.3 | completed | 1
69 | Construction of 2no, ECDE classroon and toiles at Namamuji | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | BUMULA | 0.516961,34.410324 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3000000 | 2999980 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 1301130.6 | 0.43371 | 1301130.6 | 1698849.4 | 1698849.4 | completed | 0.2
102 | Construction Of 1 No. Ecde Classroom And 2 No. Door Pit Latrine At Skinga, Namaika, Khayo Maranatha, Khelela And Namunji Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | BUMULA | 0.536129,34.409106 0.530055,34.49988 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 7500000 | 7249100 | 7500000 | County Government of Bungoma | N/A | 7500000 | 0 | 6181092.35 | 0.85267 | 6181092.35 | 1068007.65 | 1068007.65 | completed | 0.8
132 | Erection And Completionof 1 No. Ecde At Kware, Kimatuni, Joyvalley And Syekumulo Primary Schools In Bumula Ward. | Construction of ECDE classroom |  | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | BUMULA | 0.560022,34.424693 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3600000 | 3578169 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3318671.92 | 0.92748 | 3318671.92 | 259497.08 | 259497.08 | completed | 1
167 | Construction Of 01 No Workshop Masuno Vtc | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | BUMULA | 0.492354,34.465549 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 1500000 | 1465045.2 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1465045.2 | 1 | 1465045.2 | 0 |  | completed | 1
183 | Proposed Erection And Completion Of 1 No. Classroom At Mitua,Lurare And Completion Of Musiya Primary School In Bumula Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | BUMULA | 0.500938,34.448072 0.558829,34.460539 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3600000 | 3443370 | 3600000 | County Government of Bungoma | N/A | 3600000 |  | 3443370 | 1 | 3443370 | 0 |  | complete and in use | 100.0%
|  |  | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Bumula | BUMULA |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | [6 empty] | FLLOCA | N/A |  | 0 |  | 1 |  | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
20 | Hass Avocado Fruit Tree Production In Bumula Sub County | Supply and distribution of certified and grafted Hass avocado seedlings, Provision of manure, pegging, holing , training of nursery operators and maintanance of the orchard for 3 months | To promote climate change mitigation and adaptation | Hass avocado fruit trees planted | 2640599 | Other Capital Grants and Transfers | Bumula | BUMULA | 0.538441,34.460683 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 6871200 | 5980445 | 5980445 | FLLOCA | KFW | 0 | 5980445 | 0 | 1 | 0 | 0 |  | ongoing | 0.85 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
30 | Proposed Establishment And Maintenance Of Tree Nurseries In Kanduyi And Bumula Sub-County Under The Flloca Programme | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Tree nurseries established and maintained | 2640599 | Other Capital Grants and Transfers | Bumula | BUMULA | 0.552802,34.409944 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 8932000 | 8554500 | 8554500 | FLLOCA | IDA | 0 | 8554500 | 0 | 1 | 0 | 0 |  | incomplete | 0.2 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
56 | Drilling and Upgrading of Mutua Primary Borehole In Bumula Ward | site identification; geological survey;drilling development(entails casing and gravel use);construction of borehole chamber; solarization; installation of steel stand and plastic tank; pipeline extension and provision of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.535361,34.445174 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4500000 | 4483980 | 4483980 | CGB | N/A | 4483980 | 0 | 4483980 | 1 | 4483980 | 0 | 0 | completed | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
96 | Upgrading Kimatuni S.A Borehole in Bumula Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.515432,34.451045 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4762702.1 | 4762702.1 | CGB | N/A | 4762702.1 | 0 | 4762702.1 | 1 | 4762702.1 | 0 | 0 | completed | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
101 | Drilling and equipping of Wesimikha Market borehole in bumula ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.5550037,34.39810 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2000000 | 1783384 | 1783384 |  | N/A | 1783384 | 0 | 1783384 | 1 | 1783384 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
141 | upgrading of Mabusi dispensary borehole and construction of water kiosk at mabusi park | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.570781,34.420067 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 3700000 | 3684159 | 3684159 |  | N/A | 3684159 | 0 | 3684159 | 1 | 3684159 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
170 | Upgrading of Syekumulo borehole | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.547981,34.466683 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4000000 | 3930676 | 3930676 |  | N/A | 3930676 | 0 | 3930676 | 1 | 3930676 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
242 | PROTECTION OF 3N0 WATER SPRINGS IN BUMULA WARD AND PIPELINES EXTENSION | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed and KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.549636,34.407864 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1700000 | 1586649 | 1586649 |  | N/A | 1586649 | 0 | 1586649 | 1 | 1586649 | 0 | 0 | completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
264 | DRILLING OF MABUSI BOREHOLE IN BUMULA | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.570781,34.420067 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1500000 | 1311000 | 1311000 |  | N/A | 1311000 | 0 | 1311000 | 1 | 1311000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
299 | CONSTRUCTION OF BUMULA WATER SPRINGS PROJECT IN BUMULA WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection; site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled and 5 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.556957,34.439665 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1925000 | 1925000 |  | N/A | 1925000 | 0 | 1925000 | 1 | 1925000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
600 | Upgradinng of syekumulo Borehole | Improvement of a standard apron with drainage tunnel and replacement of 1 Afrdev hand pump | To enhance access to clean and safe drinking water | 1 borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | BUMULA | 0.547981,34.466683 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2317000 | 2317000 |  | N/A | 2317000 | 0 | 2317000 | 1 | 2317000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Purchase and installation of Automatic Weather Stations | Purchase and installation of 4 Automatic Weather Stations in Bumula, Township, Malakisi/Kulisiru and Elgon Wards | To collect precise and continous weather data | 4 Automatic Weather stations installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Bumula | BUMULA | 0.555638,34.449228 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 40000000 | 35547910 | 40000000 | County Government of Bungoma |  | 35547910 |  | 35547910 | 1 | 35547910 |  | 0 | Completed
| Construction of District Agric Office Bumula | Construction f District Agric Office Bumula | To provide for a conducive and an enabling working environment | 1 Agricultural office constructed | 3110504 | Other infrastructure and civil works | Bumula | BUMULA | 0.555638,34.449228 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 18/2/2017 | 18/5/2017 | 15/5/2017 | 6000000 | 4729714.4 | 4729714.4 | County Government of Bungoma |  | 4729714.4 | 0 | 4729714.4 | 1 | 4729714.4 | 0 | 0 | Completed
| Construction of Bumula DFCS Milk Cooler House | Construction of Bumula DFCS Milk Cooler House | To enhance inMime generation among dairy farmers | 1Milk Cooler House constructed | 3110504 | Other infrastructure and civil works | Bumula | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 27/1/2019 | 27/6/2019 | 20/10/2024 | 8000000 | 7825070 | 6000000 | County Government of Bungoma |  | 7825070 | 0 | 3434490.36 | 0.44 | 3434490.36 | 4390579.64 | 4390579.64 | Completed
| Supply and delivery of Hybrid Cotton Seeds | Supply and Delivery of Hybrid Cotton Seeds for Sirisia and Bumula | To enhance crop production, productivity and income generation | 9,950kgs of cotton seeds supplied and delivered | 3111301 | Purchase of Certified Crop seed | Bumula | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 18/12/2021 | 44776 | 44836 | 2000000 | 1990380 | 2000000 | County Government of Bungoma |  | 1990380 | 0 | 1990380 | 1 | 1990380 | 0 | 0 | Completed
40 | Proposed installation and commissioning of 1 NO. 15M high solar powered floodlights | installation of M M high | promotion of MSMEs and security | High solar flood light installed | 1358964/2023-24 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy |  | 2023/2024 |  | Terminated procurement proceedings | Does not exist | 1500000 |  |  | CGB | [8 empty] | Project was terminated |  | 1
75 | Installation of 50 grid powered streetlights in Bumula sub-counties . | of streetlights Bumula streetlights in | [5 empty] | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | M/S Emricon Limited | 2021/22 |  | Complete and in use |  | 3565000 |  |  | CGB
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | BUMULA |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | BUMULA |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | BUMULA | 0.535504,34.431816 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | BUMULA | 0.553061,34.443743 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | BUMULA | 0.553061,34.443743 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | BUMULA | 0.553061,34.443743 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | BUMULA | 0.559563,34.459260 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | BUMULA | 0.559563,34.459260 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA | 0.551651,34.449448 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA | 0.551651,34.449448 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA | 0.5493252,34.460620 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA | 0.5493252,34.460620 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA | 0.552802,34.409948 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA | 0.552802,34.409948 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | BUMULA | 0.555638,34.449228 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA | 0.076887,37.906192 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA | 0.076887,37.906192 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | BUMULA |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | BUMULA | 0.545835,34.462970 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | BUMULA | 0.545835,34.462970 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | BUMULA | 0.547658,34.448418 | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | incomplete |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | BUMULA |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Installation of solar security lights at mabusi, khelela and mikokwe markets | [5 empty] | Bumula | BUMULA |  | Energy |  |  | 2022/23 | [15 empty] | Installed
| Installation of 10 solar security lights at bumula centre | [5 empty] | Bumula | BUMULA |  | Energy |  |  | 2015/16 | [15 empty] | Completed
| Construction of 1 ecde classroom at Lunao RC school | [5 empty] | Bumula | BUMULA |  | Early Childhood Development Education | [18 empty] | Completed
| Construction of 10 door pit latrines at lunao sec school | [5 empty] | Bumula | BUMULA |  | Early Childhood Development Education | [18 empty] | Completed
| construction of 1 ecde at mukuyuni pri. School | [5 empty] | Bumula | BUMULA |  | Early Childhood Development Education | [18 empty] | Completed
| Drilling and installation of hand pump at Bunambobi pri school | [5 empty] | Bumula | BUMULA |  | Tourism, Environment, Natural Resources, Water and Cilamte change |  |  | 2023/24 | [15 empty] | Completed
| Upgrading of matokho bore to solar to solar powered | [5 empty] | Bumula | BUMULA |  | Tourism, Environment, Natural Resources, Water and Cilamte change |  |  | 2023/24 | [15 empty] | Completed
| Extension of piping line from Lunao sec to the kiosk | [5 empty] | Bumula | BUMULA |  | Tourism, Environment, Natural Resources, Water and Cilamte change | [18 empty] | Completed
| Upgrading of Sindani borehole | [5 empty] | Bumula | BUMULA |  | Tourism, Environment, Natural Resources, Water and Cilamte change |  |  | 2015/16 | [15 empty] | Completed
| Drilling of a borehole and installation of a hand pump at St. Raphael ecde centre | [5 empty] | Bumula | BUMULA |  | Tourism, Environment, Natural Resources, Water and Cilamte change |  |  | 2023/24 | [15 empty] | Completed
4 | Completion works for maternity ward at Chesikaki dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wards completed |  |  | Mt. Elgon | CHESIKAKI | 0.805111,34.517351 |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 1500000 | 1400000 | 1400000 | CGB |  | 1400000 | 0 | 0 | 0 | 0 |  | 1400000 | completed | 92 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
5 | Construction of maternity at Marigo dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | CHESIKAKI | 0.821048,34.478178 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45628 |  |  | 1000000 | 993700 | 993700 | CGB |  | 993700 | 0 | 0 | 0 | 0 |  | 993700 | completed | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
47 | Drainage works at mulatiwa market |  |  | drainage works completed |  |  | Mt. Elgon | CHESIKAKI | 0.801846,34.506654 |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 1000000 |  |  | CGB |  |  |  |  | #DIV/0! |  |  | 0 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
66 | Drainage works at mulatiwa market |  |  | drainage works completed |  |  | Mt. Elgon | CHESIKAKI | 0.801846,34.506654 |  | Health & Sanitation | Health & Sanitation | 2023-2024 |  |  |  | 1000000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
75 | Completion Of Wards At Tuikut Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Wards constructed |  |  | Mt. Elgon | CHESIKAKI | 0.812695,34.498368 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2000000 | 0 | 0 | CGB |  | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
220 | Construction Of 2no.Maternity Wings At Tuikut, Kapkota | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 2no door toilets and maternity wings constructed |  |  | Mt. Elgon | CHESIKAKI | 0.7713953,34.4688621 0.812712,34.498252 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2500000 | 2476560 | 2476560 | CGB |  | 2476560 | 0 | 749959.72 | 0.30282 | 749959.72 |  | 1726600.28 | ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
221 | Construction Of 2 No Maternity Wings at Kimama and Chesikaki dispensaries | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | 2no door toilets and maternity wings constructed |  |  | Mt. Elgon | CHESIKAKI | 0.80511,34.517351 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2500000 | 2470500 | 2470500 | CGB |  | 2470500 | 0 | 1288900 | 0.52172 | 1288900 |  | 1181600 | completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No
276 | Purchase of 1-acre land for Kimama Dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | CHESIKAKI | 0.49176,34.521099 |  | Ward Based | Health & Sanitation | 2015/2016 | 18.08.2015 | Feb – 2016 | 11.02.2016 |  | 410000 | 410000 | CGB |  | 410000 | 0 | 410000 | 1 | 410000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
287 | Purchase of one acre of Land for construction of Kimama dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | CHESIKAKI | 0.49176,34.521099 |  | CEF | Health & Sanitation | 2016/2017 | 18.08.2015 |  | 11.02.2016 |  | 410000 | 410000 | CGB |  | 410000 | 0 | 410000 | 1 | 410000 |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
159 | Periodic Maintenance of Kimama - Embakasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.79862,34.50489 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43232 |  | 3154620 | 3154620 | 3154620 | County Government of Bungoma |  | 3154620 |  | 3154620 |  | 3154620 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
160 | Periodic Maintenance of Roads In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43117 | 43236 |  | 3154620 | 3154620 | 3154620 | County Government of Bungoma |  | 3154620 |  | 3154620 | 90.36% | 3154620 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
310 | Periodic Maintenance of Mulukhu - Melon - Kapkoto Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.780130,34.500288 0.788883,34.512302 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43608 | 43639 | 7467375 | 7467375 | 7467375 | County Government of Bungoma |  | 7467375 |  | 7467375 |  | 7467375 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
311 | Periodic Maintenance of Roads In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43482 | 43602 |  | 7467375 | 7467375 | 7467375 | County Government of Bungoma |  | 7467375 |  | 7467375 | 99.94% | 7467375 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
312 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
500 | Periodic Maintenance of Mulatiwa - Astu -Chemondi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.804848,34.518406 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43965 |  | 9721844 | 9721844 | 9721844 | County Government of Bungoma |  | 9721844 |  | 9721844 |  | 9721844 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
501 | Periodic Maintenance of Toroso Vtc - Kiptii Primary - Ngatipkong Sda Church Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.810112,34.484723 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43970 |  | 9721844 | 9721844 | 9721844 | County Government of Bungoma |  | 9721844 |  | 9721844 |  | 9721844 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
502 | Periodic Maintenance of Roads In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43970 |  | 9721844 | 9721844 | 9721844 | County Government of Bungoma |  | 9721844 |  | 9721844 | 99.48% | 9721844 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
727 | Periodic Maintenance of Tuikut - Kamarang Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.812960,34.496443 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44331 | 44362 | 11547249 | 11547249 | 11547249 | County Government of Bungoma |  | 11547249 |  | 11547249 |  | 11547249 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
728 | Periodic Maintenance of Toroso - Kiptii - Marigo Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.807725,34.490072 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44339 | 44370 | 11547249 | 11547249 | 11547249 | County Government of Bungoma |  | 11547249 |  | 11547249 |  | 11547249 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
729 | Periodic Maintenance of Kapkoto Secondary - Mulukhu Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.7899314,34.4865298 0.791807,34.486505 0.780517,34.500078 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44328 | 44359 | 2172303 | 2172303 | 2172303 | County Government of Bungoma |  | 2172303 |  | 2172303 |  | 2172303 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
730 | Periodic Maintenance of Roads In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44334 |  | 11547249 | 11547249 | 11547249 | County Government of Bungoma |  | 11547249 |  | 11547249 | 99.93% | 11547249 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
731 | Periodic Maintenance of Roads In Chesikaki Ward - Negotiation 872526 | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44326 |  | 2172303 | 2172303 | 2172303 | County Government of Bungoma |  | 2172303 |  | 2172303 | 99.08% | 2172303 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1060 | Periodic Maintenance of Emanang River - Kabero Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44697 | 44728 | 13570260 | 13570260 | 13570260 | County Government of Bungoma |  | 13570260 |  | 13570260 |  | 13570260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1061 | Periodic Maintenance of Kapkurong - Chebinyinyi Primary | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.80195,34.5323 0.79752,34.49138 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44693 | 44724 | 13570260 | 13570260 | 13570260 | County Government of Bungoma |  | 13570260 |  | 13570260 |  | 13570260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1062 | Periodic Maintenance of Roads In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44703 |  | 13570260 | 13570260 | 13570260 | County Government of Bungoma |  | 13570260 |  | 13570260 | 100.0% | 13570260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1375 | Periodic Maintenance of Embakasi - Chesiywo - Water Supply Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.79862,34.50489 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45057 |  | 4398740 | 4398740 | 4398740 | County Government of Bungoma |  | 4398740 |  | 4398740 |  | 4398740 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1376 | Periodic Maintenance of Mulatiwa - Chemondi - Kapchekui Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.814141,34.511212 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45061 |  | 4398003 | 4398003 | 4398003 | County Government of Bungoma |  | 4398003 |  | 4398003 |  | 4398003 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1377 | Periodic Maintenance of Embakasi - Chepsiywo - Water Supply Road In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.79862,34.50489 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45059 |  | 4398740 | 4398740 | 4398740 | County Government of Bungoma |  | 4398740 |  | 4398740 | 87.55% | 4398740 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1378 | Periodic Maintenance of Mulatiwa - Chemondi - Kapchekui Road In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.814141,34.511212 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45065 |  | 4398003 | 4398003 | 4398003 | County Government of Bungoma |  | 4398003 |  | 4398003 | 81.29% | 4398003 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1631 | Upgrading of Emergency Works For Kimabole Kapkota Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Mt. Elgon | CHESIKAKI | 0.787273,34.498780 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45435 |  | 24334596 | 24334596 | 24334596 | County Government of Bungoma |  | 24334596 |  | 24334596 | 100.0% | 24334596 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1632 | Upgrading of Emergency Works For Kimabole-Kapkota Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Mt. Elgon | CHESIKAKI | 0.787273,34.498780 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45422 |  | 24334596 | 24334596 | 24334596 | County Government of Bungoma |  | 24334596 |  | 24334596 | 100.0% | 24334596 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1633 | Periodic Maintenance of Embakasi - Kapchebus - Mulukhu - Kimabole Road In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.795575,34.510874 0.779357,34.5154220.787273,34.498780 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45436 |  | 7195944 | 7195944 | 7195944 | County Government of Bungoma |  | 7195944 |  | 7195944 | 99.75% | 7195944 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1634 | Periodic Maintenance of Toroso Tuikut Kapchepkui Road In Chesikaki Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHESIKAKI | 0.86633,34.490245 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45429 |  | 5663700 | 5663700 | 5663700 | County Government of Bungoma |  | 5663700 |  | 5663700 | 99.74% | 5663700 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
182 | Purchase of land for Chebunyinyi ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Chebunyinyi ECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | CHESIKAKI | 0.80381,34.53619 0.48"13.72428",34.32"10.2655 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42343 | 42346 | 42345 | 400000 | 400000 | 400000 | CGB | N/A | 400000 |  | 400000 |  | 400000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
183 | Purchase of land for Kapchekui ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Kapchekui ECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | CHESIKAKI | 0.827865,34.305351 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 18/08/2015 | 18/11/2016 | 42676 | 425000 | 425000 | 425000 | CGB | N/A | 425000 |  | 425000 |  | 425000 |  |  | completed | 1 | [14 empty] | The project is 100% complete and in use
186 | Purchase of land for Chemwa ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Chemwa ECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | CHESIKAKI | 0.830,34.494730 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 18/08/2015 | 18/11/2016 | 42676 | 425000 | 425000 | 425000 | CGB | N/A | 425000 |  | 425000 |  | 425000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
200 | Purchase of land for Chemeker ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Chemeker ECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | CHESIKAKI | 0.8063796,34.4657439 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 42343 | 42346 | 42345 | 400000 | 400000 | 400000 | CGB | N/A | 400000 |  | 400000 |  | 400000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
3 | Construction of 1 NO ECDE classroom at Kabero and Toroso Primary Schools in Chesikaki Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHESIKAKI | 0.830155,34.481337 0.807628,34.489200 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 2700000 | 2630170 | 2700000 | County Government of Bungoma | N/A | 2700000 | 0 | 2630170 | 1 | 2630170 | 0 | 0 | Completed
72 | Construction of 1 No ECDE and 2N0. Door pit latrine at Chemondi S.A | Construction of ECDE classroom and pit latrine | To construct ECDE classroom and pit latrine providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHESIKAKI | 0.821298,34.509984 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1500000 | 1499390 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1499390 | 1 | 1499390 | 0 | 0 | Complete and in use | 1
134 | Erection And Completion Of 1 No Ecde At Chemwoikut Primary School In Chesikaki Ward | Construction of ECDE classroom |  | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHESIKAKI | 0.790165,34.510210 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1393155.65 | 1343920 | 1393155.65 | County Government of Bungoma | N/A | 1393155.65 | 0 | 1146039.35 | 0.85276 | 1146039.35 | 197880.65 | 197880.65 | incomplete | 1
169 | Construction Of 01 Ecde Classrooms At Chesikaki Fym, Chesiywo, Chemondi S.A, Kabero P.R, Kimerin And Bukonoi | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHESIKAKI | 0.790165,34.510210 0.80479,34.52645 0.48"17.25",34.31"35.20812" | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 6800000 | 6750900 | 6800000 | County Government of Bungoma | N/A | 6800000 | 0 | 6750900 | 1 | 4053195.55 | 2697704.45 |  | at finishing stage | AT FINISHING
188 | Construction Of 2no. Classrooms And Toilet At Kimabole And Toroso Polytechnic In Chesikaki Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHESIKAKI | 0,779300,34.515439 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 5000000 | 5819220 | 5000000 | County Government of Bungoma | N/A | 5000000 |  | 2750383.2 | 0.47264 | 2750383.2 | 3068836.8 |  | ongoing, at finishes level. | 100.0%
32 | Proposed Rehabilitation Of Kuywa, Lwakhakha Rivers And Matere Stream In Chepyuk, Cheptais And Chesikaki Wards Respectively. | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7888000 | 5909325 | 5909325 | FLLOCA | IDA | 0 | 5909325 | 0 | 1 | 0 | 0 |  | Re-tendered | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
38 | Proposed Tree Growing Within Institutions In Khasoko, Kabula, Musikoma, Bukembe East, West Nalondo And Chesikaki Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | CHESIKAKI | 0.791096,34.508540 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7101000 | 6960000 | 6960000 | FLLOCA | IDA | 0 | 6960000 | 0 | 1 | 0 | 0 |  | ongoing | 0.2 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
57 | Protection of 7 NO water springs in Chesikaki Ward | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 7 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 1800000 | 1718920 | 1718920 | CGB | N/A | 1718920 | 0 | 1718920 | 1 | 1718920 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
120 | Rehabilitation of Cheseker water project in Chesikaki ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI | 0.832115,34.518504 0.848232 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 6000000 | 5888624 | 5888624 |  | N/A | 5888624 | 0 | 5888624 | 1 | 5888624 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
143 | Marigo water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI | 0.836138,34.83003 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4789640 | 4789640 |  | N/A | 4789640 | 0 | 4789640 | 1 | 4789640 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
144 | kapkota water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI | 0.7976456,34.5035014 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4849100 | 4849100 |  | N/A | 4849100 | 0 | 4849100 | 1 | 4849100 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
183 | EXTENSION OF PIPING ON CHESIKAKI WATER PROJECT | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2800000 | 2783880 | 2783880 |  | N/A | 2783880 | 0 | 2783880 | 1 | 2783880 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
218 | REHABILITATION AND EXTENSION OF CHESIKAKI-SIRISIA-BUMULA WATER PROJECT PHASE I | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 34000000 | 33391751.4 | 33391751.4 |  | N/A | 33391751.4 | 0 | 33391751.4 | 1 | 23831829 | 9559922 | 0 | Work in progress | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
311 | CONSTRUCTION OF WATER PIPELINE EXTENSION FOR CHESIKAKI WATER PROJECT IN CHESIKAKI WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI | 0.810733,34.485547 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4800000 | 4508000 | 4508000 |  | N/A | 4508000 | 0 | 4508000 | 1 | 4508000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
340 | SUPPLY OF CHEMICALS |  | To enhance access to clean and safe drinking water |  | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 600000 | 551840 | 551840 |  | N/A | 551840 | 0 | 551840 | 1 | 551840 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
356 | EMIA CHENGOYWO Springs construction | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 618300 | 618300 |  | N/A | 618300 | 0 | 618300 | 1 | 618300 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
428 | Constuction of Chesekar water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI | 0.832115,34.518504 0.832978,34.495138 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2586760 | 2586760 |  | N/A | 2586760 | 0 | 2586760 | 1 | 2586760 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
454 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2597616 | 2597616 |  | N/A | 2597616 | 0 | 2597616 | 1 | 2597616 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
461 | EMIA CHENGOYWO Springs construction | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1545750 | 1545750 |  | N/A | 1545750 | 0 | 1545750 | 1 | 1545750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
545 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points; | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 10000000 | 9277200 | 9277200 |  | N/A | 9277200 | 0 | 9277200 | 1 | 9277200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
546 | EMIA CHENGOYWO Springs construction | excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 8000000 | 7527750 | 7527750 |  | N/A | 7527750 | 0 | 7527750 | 1 | 7527750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
548 | Constuction of Chesekar water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHESIKAKI | 0.832978,34.495138 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 7600000 | 7485200 | 7485200 |  | N/A | 7485200 | 0 | 7485200 | 1 | 7485200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Purchase and installation of weigh bridges | Purchase and Installation of weigh bridges at Musese and Chesikaki Coffee Milling Plants | To weigh incoming and outgoing coffee for inventory control and sales purposes | 2 weigh bridges purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Mt. Elgon | CHESIKAKI | 0.802212,34.500012 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 43313 | 43316 | 30/3/2018 | 20000000 | 18000000 | 18000000 | County Government of Bungoma |  | 18000000 | 0 | 18000000 | 1 | 18000000 | 0 | 0 | Completed
| Construction of a coffee warehouse/bean store | Construction of a coffee warehouse/bean store at Mt. Elgon Coffee Mill and Musese coffee mill | To enhance instme generation among dairy farmers | 2 Coffee warehouse/bean store constructed | 3110504 | Other infrastructure and civil works | Mt. Elgon | CHESIKAKI | 0.802325,34.500092 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 43435 | 43440 | 42648 | 18000000 | 18000000 | 18000000 | County Government of Bungoma |  | 18000000 | 0 | 18000000 | 1 | 18000000 | 0 | 0 | Completed
| Construction of Chesikaki Coffee Warehouse | Construction of Chesikaki Coffee Warehouse | To promote coffee production and income generation | 1 warehouse constructed | 3110504 | Other infrastructure and civil works | Mt. Elgon | CHESIKAKI | 0.802325,34.500092 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 15/1/2020 | 15/6/2020 | 28/5/2020 | 10000000 | 7887623 | 8000000 | County Government of Bungoma |  | 7887623 | 0 | 7887623 | 1 | 7887623 | 0 | 0 | Completed
| Purchase and delivery of Coffee seedlings | Purchase and delivery of 650kgs of Coffee seedlings | To promote coffee production and income generation | 650kgs of coffee seedlings purchased and delivered | 3111301 | Purchase of Certified Crop seed | Mt. Elgon | CHESIKAKI | 0.820352,34.500650 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 30/3/2020 | 10,00,000 | 4999137 | 5000000 | County Government of Bungoma |  | 4999137 | 0 | 4999137 | 1 | 4999137 | 0 | 0 | Completed
| Purchase of coffee seed tubes | Purchase and delivery of 50 dozens of 12 Coffee Seed tubes to cooperative Societies | To promote coffee production and income generation | 50 dozens of 12 Coffee Seed tubes purchased and delivered to coffee societies | 3111301 | Purchase of Certified Crop seed | Mt. Elgon | CHESIKAKI |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 28/3/2020 | 5000000 | 1990000 | 2000000 | County Government of Bungoma |  | 1990000 | 0 | 1990000 | 1 | 1990000 | 0 | 0 | Completed
| Renovation and purchase of Sasuri Coffee Drying Tables | Renovation and purchase of 20 Coffee Drying Tables at Sasuri | To promote coffee production and enhance income generation among Coffee farmers | 20 Coffee drying tables purchased and delivered | 3110504 | Other infrastructure and civil works | Mt. Elgon | CHESIKAKI | 0.8090251,34.4723267 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44835 | 44838 | 44685 | 5000000 | 3099999.98 | 3500000 | County Government of Bungoma |  | 3099999.98 | 0 | 3099999.98 | 1 | 3099999.98 | 0 | 0 | Completed
38 | Proposed supply and installation of 3 NO. solar powered street lights | supply of NO solar | promotion of MSMEs and security | solar powered street lights installed | 1358887/2023-24 |  |  | CHESIKAKI | 0.814812,34.49915 | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE LIMITED | 2023/2024 |  | Completed | Complete and in use | 1000000 |  |  | CGB | [8 empty] | Complete | 100 | 3
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
106 | Proposed installation of 25 no. Grid powered street lights in Mt. Elgon Sub County | installation Grid lights street in Mt | [5 empty] | CHESIKAKI |  |  |  | M/S FECAKO Investments Limited | 2020/21 |  | Complete |  | 2434212.5 |  |  | CGG
117 | Installation of 2 no. Solar Powered High Mast Flood lights at Tuikut and Chemondi markets | of Powered Flood Mast at Tuikut | [5 empty] | CHESIKAKI | 0.814421,34.510849 0.813212,34.497170 |  |  | Go Solar Systems Ltd | 2019/20 |  | Complete |  | 2000600 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHESIKAKI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
| Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
| Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | CHESIKAKI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Chemondi road to mulatiwa | [5 empty] | Mt. Elgon | CHESIKAKI | 0.8144141,34.511212 | Trade
| Kaptoboi water spring | [5 empty] | Mt. Elgon | CHESIKAKI | 0.831587,34.500830 | Water |  |  | 2023/24 | [15 empty] | completed
| Kiptaywa bridge | [5 empty] | Mt. Elgon | CHESIKAKI | 0.825153,34.511910 |  |  |  | 2024/25 | [15 empty] | incomplete
| Tuikuit- county- kiptaywa streetlights at county | [5 empty] | Mt. Elgon | CHESIKAKI | 0.82565,34.509701
| Street lights at mulatiwa | [5 empty] | Mt. Elgon | CHESIKAKI | 0.803736,34.505979 | [19 empty] | incomplete
| Street lights at chemondi | [5 empty] | Mt. Elgon | CHESIKAKI | 0.814421,34.510849 | [19 empty] | incomplete
| Upgrading of Toroso- Kaptoka Barracks- R.Sasuri | [5 empty] | Mt. Elgon | CHESIKAKI | 0.8105069,34.4972673 0.8054011,34.465051 |  |  |  | 2013/14 | [15 empty] | incomplete
| Openning/ murraming of Tekwe- Toroso mixed- Kipchirchir road | [5 empty] | Mt. Elgon | CHESIKAKI | 0.8082326,34.4778696 |  | Roads |  | 2024/25 | [15 empty] | completed
| Construction of 1 NO classroom at chemeker pri. | [5 empty] | Mt. Elgon | CHESIKAKI | 0.8063796,34.4657439 |  | Education |  | 2024/25 | [15 empty] | completed
| Periodic maintainance of chepkechir- toroso mixed- tekwei home | [5 empty] | Mt. Elgon | CHESIKAKI | 0.8068555,34.4674763 0.8082326,34.4778696 |  | Roads |  | 2024/25 | [15 empty] | completed
| Purchase of 1 acre of land for kamarang dispensary | [5 empty] | Mt. Elgon | CHESIKAKI | 0.820043,34.491137 |  | land& physical planning |  | 2024 | [15 empty] | completed
| Kaptoboi ecde classroom | [5 empty] | Mt. Elgon | CHESIKAKI | 0.824448,34.501 |  | ecde |  | 2020 | [15 empty] | completed
| Kipsis/ maringo box culvert at emanang river | [5 empty] | Mt. Elgon | CHESIKAKI | 0.825918,34.475160 |  | Roads |  | 2025 | [15 empty] | stalled
| Kamoso road box culvert at matia bridge at R, emanang | [5 empty] | Mt. Elgon | CHESIKAKI | 0.818729,34.473940 |  | Roads |  | 2025 | [15 empty] | ongoing
| Bukonoi cdf- chemige bridge- SDA road | [5 empty] | Mt. Elgon | CHESIKAKI | 0.809251,34.47127 |  | Roads |  | 2024 | [15 empty] | ongoing
179 | Construction of Makutano Health Center | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | health centres constructed |  |  | Tongaren | Soysambu/Mitua |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 10000000 | 14443311 | 14443311 | CGB |  | 14443311 | 0 | 4861513 | 0.33659 | 4861513 |  | 9581798 | stalled | [6 empty] | No | complete | Financial | Yes
210 | Construction Of Makutano Health Center | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | health centres constructed |  |  | Tongaren | Soysambu/Mitua |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 8200000 | 8,738,048 | 8,738,048 | CGB |  | 8,738,048 | 0 | 8,737,410 | 0.99993 | 8,737,410 |  | 638 | stalled | [6 empty] | No | complete | Financial | Yes
212 | Purchase Of 3 Acres For Makutano Health Centre |  |  | acres of land purchased |  |  | Tongaren | Soysambu/Mitua |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 8200000 | 8738048 | 8738048 | CGB |  | 8738048 | 0 | 8737410 | 0.99993 | 8737410 |  | 638 | N/A | [6 empty] | No | complete | Financial | Yes
252 | Construction Of An Outpatient Wing And A Two Door Pit Latrine At Misanga Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Outpatient wings 2No. Door pit latrines constructed |  |  | Tongaren | Soysambu/Mitua | 0.696165,34.6478 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 6000000 | 5891976.4 | 5891976.4 | CGB |  | 5891976.4 | 0 | 2000000 | 0.33944 | 2000000 |  | 3891976.4 | Ongoing | [6 empty] | No | complete | Financial | Yes
253 | Periodic Maintenance of Miti Mbili Deb - Mulunda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43238 |  | 5455422 | 5455422 | 5455422 | County Government of Bungoma |  | 5455422 |  | 5455422 |  | 5455422 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
254 | Periodic Maintenance of Roads In Mitua Soysambu | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43242 |  | 5455422 | 5455422 | 5455422 | County Government of Bungoma |  | 5455422 |  | 5455422 | 98.04% | 5455422 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
492 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
628 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
958 | Periodic Maintenance of Nyange Sec - Mang'Oli/ Musalaba - Sabwami Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44333 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 |  | 16017918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
959 | Periodic Maintenance of Namunyiri Girls - Kititi - Mukenya - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44334 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 |  | 16017918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
960 | Periodic Maintenance of King'Oro - Namunyiri Dispensary - Nalianya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44326 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 |  | 16017918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
961 | Periodic Maintenance of Soysambu Booster - Sibabi/ Ngaira - Matumbai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua | 0.696185, 34.6478 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44328 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 |  | 16017918 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
962 | Periodic Maintenance of Karani - Misanga - Lunao Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua | 0.5614,34.4175 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44335 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 |  | 16017918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
963 | Periodic Maintenance of Mitua Girls - St. Paul Catholic - Wanjala Lasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44335 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 |  | 16017918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
964 | Periodic Maintenance of Okosi - Mfunje - Marauni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44331 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 |  | 16017918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
965 | Periodic Maintenance of Soysambu - Mwikhupo - Maresi - St. Paul Narati Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44333 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
966 | Periodic Maintenance of Roads In Soysambu Mitua Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44331 |  | 16017918 | 16017918 | 16017918 | County Government of Bungoma |  | 16017918 |  | 16017918 | 97.52% | 16017918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1290 | Periodic Maintenance of Amuko - Obaye - Mifunje | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44694 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 |  | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1291 | Periodic Maintenance of Topster - Timleen - Booster - Makenji Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44699 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 |  | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1292 | Periodic Maintenance of Ambeva - Mkasawembe - Akou | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44695 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 |  | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1293 | Periodic Maintenance of Juma Karani - Misanga - Lunao Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44697 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 |  | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1294 | Periodic Maintenance of Check Point - Mabati Tatu - Werunga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44696 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 |  | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1295 | Upgrading of St. Paul Narati - Bridge Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44696 |  | 4198649 | 4198649 | 4198649 | County Government of Bungoma |  | 4198649 |  | 4198649 |  | 4198649 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1296 | Periodic Maintenance of Kananachi Primary - Richard Sabwami Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44704 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 |  | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1297 | Periodic Maintenance of Mitua Girls - Wanjala Lasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44693 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 |  | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1298 | Periodic Maintenance of Roads In Soysambu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44701 |  | 11968980.77 | 11968980.77 | 11968980.77 | County Government of Bungoma |  | 11968980.77 |  | 11968980.77 | 97.16% | 11968980.77 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1299 | Spot Improvement Of St. Paul Narati - Bridge Rehabilitation | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44693 |  | 4198649 | 4198649 | 4198649 | County Government of Bungoma |  | 4198649 |  | 4198649 | 100.0% | 4198649 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1546 | Periodic Maintenance of Kwa Wateso Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45066 |  | 8535900 | 8535900 | 8535900 | County Government of Bungoma |  | 8535900 |  | 8535900 |  | 8535900 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1547 | Construction of Shirandula Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45067 |  | 8535900 | 8535900 | 8535900 | County Government of Bungoma |  | 8535900 |  | 8535900 |  | 8535900 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1548 | Periodic Maintenance of Koroti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45058 |  | 4943050 | 4943050 | 4943050 | County Government of Bungoma |  | 4943050 |  | 4943050 |  | 4943050 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1549 | Periodic Maintenance of Kwa Wateso Road And Sirandula Box Culvert In Soysambu/ Mitua Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45062 |  | 8535900 | 8535900 | 8535900 | County Government of Bungoma |  | 8535900 |  | 8535900 | 99.53% | 8535900 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1550 | Routine Maintenance Koroti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45062 |  | 4943050 | 4943050 | 4943050 | County Government of Bungoma |  | 4943050 |  | 4943050 | 96.71% | 4943050 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1794 | Periodic Maintenance of Pentagon - Mama Spence Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45436 | 45467 | 5990124 | 5990124 | 5990124 | County Government of Bungoma |  | 5990124 |  | 5990124 |  | 5990124 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1795 | Periodic Maintenance of Wateso Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45428 | 45459 | 5990124 | 5990124 | 5990124 | County Government of Bungoma |  | 5990124 |  | 5990124 |  | 5990124 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1796 | Periodic Maintenance of Koroti - Pius - Mwikhupo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45426 | 45457 | 9159926 | 9159926 | 9159926 | County Government of Bungoma |  | 9159926 |  | 9159926 |  | 9159926 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1797 | Construction of Koroti Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45426 | 45457 | 9159926 | 9159926 | 9159926 | County Government of Bungoma |  | 9159926 |  | 9159926 |  | 9159926 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1798 | Periodic Maintenance of Kakame-Obaye Mufunje Road In Tongaren | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45423 |  | 4745328 | 4745328 | 4745328 | County Government of Bungoma |  | 4745328 |  | 4745328 | 100.0% | 4745328 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1799 | Periodic Maintenance of Koroti - Pius - Mwikhupo Road And A Box Culvert In Mitua/Soysambu Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45425 |  | 9159926 | 9159926 | 9159926 | County Government of Bungoma |  | 9159926 |  | 9159926 | 100.0% | 9159926 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1800 | Periodic Maintenance of Pentagon - Mama Spence Road And Wateso Road In Mitua/Soysambu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45425 |  | 5990124 | 5990124 | 5990124 | County Government of Bungoma |  | 5990124 |  | 5990124 | 99.99% | 5990124 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
97 | Purchase Of 3 Acres For Makutano Health Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new health centre | Three acres of Land For Makutano Health Centre Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 |  |  |  | 2500000 | 2300000 | 2300000 | CGB |  | 2300000 |  | 2300000 |  |  |  |  | Stalled | 0 | [14 empty] | The project is staled due Lack of documentations(Title deed)
128 | Purchase Of 1 Acre For Bishop Wabukala E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for expansion of ECDE | One acres of Land for Bishop Wabukala E.C.D.E Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 23/10/2017 | 23/12/2017 | 43253 | 2300000 | 2300000 | 2300000 | CGB | N/A | 2300000 |  | 2300000 | 1 | 6500000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
147 | Purchase of land for Buyanzi ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Buyanzi ECDE Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 42374 | 42376 | 42742 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 |  | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
148 | Purchase of land for St. Paul’s Narati ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Paul’s Narati ECDE Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 15/07/2015 | 42194 | 42555 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 |  | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
159 | Purchase of 1 acre land for mashinani ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for mashinani E.C.D.E Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua | 0.785665,345.01824 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 17/7/2015 | 18/9/2015 | 42318 | 400000 | 400000 | 400000 | CGB | N/A | 400000 |  | 400000 | 1 | 400000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
160 | Purchase of 1 acre land for Soysambu S.A ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of Expansion of ECDE centre | One acres of Land for Soysambu S.A E.C.D.E Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/01/2016 | 21/03/2016 | 42647 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 1 | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
161 | Purchase of 1 acre land for St. pauls Narati ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of expansion ECDE centre | One acres of Land for St. pauls Narati E.C.D.E Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42194 | 18/11/2015 | 42320 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
162 | Purchase of 1 acre land for Kewa ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Kewa E.C.D.E Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua | 0..8131,35.7154 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 25/2/2016 | 25/5/2016 | 27/6/2016 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 1 | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
163 | purchase of 1 acre land for Bishop Wabukala ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Bishop Wabukala E.C.D.E Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42402 | 42405 | 20/6/2016 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 1 | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
164 | purchase of 1 acre land for Misanga dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Misanga dispensary Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua | 0.696185,34.6478 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 1 | 0 |  |  | completed | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
188 | Purchase of land for Soysambu SA ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Soysambu SA ECDE Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 15/9/2015 | 15/12/2015 | 23/12/2015 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 |  | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
199 | Purchase of land for Mashinani ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Mashinani ECDE Purchased | 3110599 | Ward based projects | Tongaren | Soysambu/Mitua | 0.785665,345.01824 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 14/5/2015 | 14/8/2015 | 14/7/2015 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 |  | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
18 | Construction of 5 No. ECDE classrooms at St Pauls Narati in Soysambu/Mitua Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Soysambu/Mitua |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 7000000 | 6898450 | 7000000 | County Government of Bungoma | N/A | 7000000 | 0 |  | 0 |  | 6898450 | 6898450 | stalled | At substructure (15%)
63 | Proposed Erection And Completion Works Of 6no. Ecde Classrooms At Mashinani Primary School In Soysambu/Mitua Ward | Completion of ECDE classroom | To renovate ECDE classroom providing a conducive learning environment | ECDE classroom renovated | 3110599 | Construction and Civil works | Tongaren | Soysambu/Mitua | 0.785665,35.01824 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 9000000 | 8730000 | 9000000 | County Government of Bungoma | N/A | 9000000 | 0 | 4115182.85 | 0.47138 | 4115182.85 | 4614817.15 | 4614817.15 | stalled | 1
94 | Construction of 2no. ecde classrooms and toilets at st pauls narati primary |  | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Soysambu/Mitua |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3000000 | 2993780 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2402835.05 | 0.80261 | 2402835.05 | 590944.95 | 590944.95 | completed | 1
161 | Proposed Erection And Completion Of 1 No. Ecde At Bishop Wabukala And Kananachi Primary School In Soysambu Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Soysambu/Mitua |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3000000 | 2956880 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2956880 | 1 | 2956880 | 0 | 0 | complete and in use | 1
215 | Construction Of 1no. Ecde Classroom At Bishop Wabukala And Namunyiri Rcea In Soysambu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Soysambu/Mitua |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2000000 | 2464060 | 2000000 | County Government of Bungoma | N/A | 2000000 |  | 2464060 | 1 | 2464060 | 0 |  | complete and in use | 100.0%
129 | Rehabilitation of 4no. Borehole handpumps in Soysambu/Mitua ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 4 Boreholes rehabilitated | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1000000 | 998620.8 | 998620.8 |  | N/A | 998620.8 | 0 | 998620.8 | 1 | 998620.8 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
211 | DRILLING AND EQUIPPING OF 2NO. BOREHOLES IN SOYSAMBU- MITUA WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 4000000 | 3799000 | 3799000 |  | N/A | 3799000 | 0 | 3799000 | 1 | 3799000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
360 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 of water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 200000 | 157942 | 157942 |  | N/A | 157942 | 0 | 157942 | 1 | 157942 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
382 | Construction of 5 Roofcatchments | Construction of roof catchment and erection of water tank plus provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and tank constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 660890 | 660890 |  | N/A | 660890 | 0 | 660890 | 1 | 660890 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
383 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1500000 | 1465144 | 1465144 |  | N/A | 1465144 | 0 | 1465144 | 1 | 1465144 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
403 | Drill 2No boreholes at Mwipukho and makutano dispensary and equip with hand pump | Site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3000000 | 2963150 | 2963150 |  | N/A | 2963150 | 0 | 2963150 | 1 | 2963150 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
478 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1465144 | 1465144 |  | N/A | 1465144 | 0 | 1465144 | 1 | 1465144 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
479 | Construction of 5 roof catchment | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 Roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 660890 | 660890 |  | N/A | 660890 | 0 | 660890 | 1 | 660890 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
480 | Drill 1No borehole (SOYSAMBU OLD MARKET) | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1634902 | 1634902 |  | N/A | 1634902 | 0 | 1634902 | 1 | 1634902 | 0 | 0 | stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
558 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works |  | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1579420 | 1579420 |  | N/A | 1579420 | 0 | 1579420 | 1 | 1579420 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
559 | Drill 2No boreholes at Mwipukho and makutano dispensary and equip with hand pump | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 boreholes drilled and equipped | 3110599 | Other Infrastructure &Civil Works | Tongaren | Soysambu/Mitua |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3000000 | 2963150 | 2963150 |  | N/A | 2963150 | 0 | 2963150 | 1 | 2963150 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Rehabilitation of Brigadier Dam | Rehabilitation of Brigadier Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Tongaren | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 5000000 | 3769700 | 4000000 | County Government of Bungoma |  | 3769700 |  | 3769700 | 1 | 3769700 | 0 | 0 | Completed
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Soysambu/Mitua |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Soysambu/Mitua |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
217 | Periodic Maintenance of Miti Mbili Deb - Mulunda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43238 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
218 | Periodic Maintenance of Roads In Mitua Soysambu | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43242 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 98.04% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
888 | Periodic Maintenance of Nyange Sec - Mang'Oli/ Musalaba - Sabwami Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44333 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
889 | Periodic Maintenance of Namunyiri Girls - Kititi - Mukenya - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44334 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
890 | Periodic Maintenance of King'Oro - Namunyiri Dispensary - Nalianya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44326 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
891 | Periodic Maintenance of Soysambu Booster - Sibabi/ Ngaira - Matumbai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44328 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
892 | Periodic Maintenance of Karani - Misanga - Lunao Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44335 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
893 | Periodic Maintenance of Mitua Girls - St. Paul Catholic - Wanjala Lasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44335 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
894 | Periodic Maintenance of Okosi - Mfunje - Marauni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44331 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
895 | Periodic Maintenance of Soysambu - Mwikhupo - Maresi - St. Paul Narati Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44333 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
896 | Periodic Maintenance of Roads In Soysambu Mitua Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44331 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 97.52% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1206 | Periodic Maintenance of Amuko - Obaye - Mifunje | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44694 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1207 | Periodic Maintenance of Topster - Timleen - Booster - Makenji Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44699 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1208 | Periodic Maintenance of Ambeva - Mkasawembe - Akou | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44695 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1209 | Periodic Maintenance of Juma Karani - Misanga - Lunao Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44697 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1210 | Periodic Maintenance of Check Point - Mabati Tatu - Werunga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44696 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1211 | Upgrading of St. Paul Narati - Bridge Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44696 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1212 | Periodic Maintenance of Kananachi Primary - Richard Sabwami Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44704 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1213 | Periodic Maintenance of Mitua Girls - Wanjala Lasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44693 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1214 | Periodic Maintenance of Roads In Soysambu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44701 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 97.16% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1215 | Spot Improvement Of St. Paul Narati - Bridge Rehabilitation | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44693 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1489 | Periodic Maintenance of Kwa Wateso Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45066 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1490 | Construction of Shirandula Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45067 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1491 | Periodic Maintenance of Koroti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45058 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1492 | Periodic Maintenance of Kwa Wateso Road And Sirandula Box Culvert In Soysambu/ Mitua Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45062 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.53% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1493 | Routine Maintenance Koroti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45062 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 96.71% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1747 | Periodic Maintenance of Pentagon - Mama Spence Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45436 | 45467 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1748 | Periodic Maintenance of Wateso Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45428 | 45459 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1749 | Periodic Maintenance of Koroti - Pius - Mwikhupo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45426 | 45457 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1750 | Construction of Koroti Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45426 | 45457 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1751 | Periodic Maintenance of Kakame-Obaye Mufunje Road In Tongaren | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45423 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1752 | Periodic Maintenance of Koroti - Pius - Mwikhupo Road And A Box Culvert In Mitua/Soysambu Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45425 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1753 | Periodic Maintenance of Pentagon - Mama Spence Road And Wateso Road In Mitua/Soysambu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | TONGAREN | Soysambu/Mitua |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45425 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.99% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | N/A
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Soysambu/Mitua |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Soysambu/Mitua |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
1 | Erection and completion of male and female ward at Misanga dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Male and female wards erected and completed |  |  | Kanduyi | Bukembe east | 0.6209149,34.6725618 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21/3/24 |  |  | 4000000 | 3780100 | 3780100 | CGB |  | 3780100 | 0 | 1207821.75 | 0.31952 | 1207821.75 |  | 2572278.25 | completed | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
57 | construction of 4NO.Door pit latrines at misanga dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Kanduyi | Bukembe east | 0.6209149,34.6725618 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 20/2/24 |  |  | 800000 | 738340 | 738340 | CGB |  | 738340 | 0 | 0 | 0 | 0 |  | 738340 | completed | 92 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
96 | Construction Of Male And Female Ward At Bukembe Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | male and female wards constructed |  |  | Kanduyi | Bukembe east | 0.60967490,34.6559026 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 4500000 | 4454670 | 4454670 | CGB |  | 4454670 | 0 | 2617773 | 0.58765 | 2617773 |  | 1836897 | completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No
149 | Construction Of Misanga Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Kanduyi | Bukembe east | 0.6209149,34.6725618 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 1800000 | 1746000 | 1746000 | CGB |  | 1746000 | 0 | 0 | 0 | 0 |  | 1746000 | Completed | [6 empty] | No | complete | Financial | Yes
184 | Equipping of Maternity ward at Bukembe Dispensary | Equipping with drugs and medical equipment |  | Maternity wards equipped |  |  | Kanduyi | Bukembe east | 0.609674900,34.6559026 |  | WBPSPCU | Health & Sanitation | 2019-2020 | [6 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes
195 | Construction Of Ecosan Pit Latrines At Ekitale And Ndengelwa Markets | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Ecosan pit latrines constructed |  |  | Kanduyi | Bukembe east |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 1500000 | 1613860 | 1613860 | CGB |  | 1613860 | 0 | 1611750.4 | 0.99869 | 1611750.4 |  | 2109.6 | complete and in use | [6 empty] | No | complete | Financial | Yes
213 | Equipping Of A Maternity Ward At Bukembe Dispensary | Equipping with drugs and medical equipment |  | Maternity wards equipped |  |  | Kanduyi | Bukembe east | 0.609674900,34.6559026 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1000000 | 290538 | 290538 | CGB |  | 290538 | 0 | 290538 | 1 | 290538 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
214 | Construction Of 4 Door Pit Latrine At Kongoli,Nandolia and Sudi Markets | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Kanduyi | Bukembe east | 0.6129642,34.6509111 0.5821,34.64294 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2500000 | 2100110 | 2100110 | CGB |  | 2100110 | 0 | 2100110 | 1 | 2100110 |  | 0 | completed | [6 empty] | No | complete | Financial | Yes
308 | Proposed Renovation of Kongoli Dispensary maternity wing | Walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable maternal health services within the community | Maternity wings renovated |  |  | Kanduyi | Bukembe east | 0.5550021,34.6301642 |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42185 |  |  | 1404180 | 1404180 | CGB |  | 1404180 | 0 | 1404180 | 1 | 1404180 |  | 0 | completed and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
312 | Proposed Renovation of Bukembe Dispensary maternity wing | Walling,roofing,painting,fixing of dors and windows | To provide accessible and affordable maternal health services within the community | Maternity wings renovated |  |  | Kanduyi | Bukembe east | 0.609674900,34.6559026 | [10 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | ongoing and in use | [6 empty] | No | complete | Financial | Yes
5 | Upgrading of Mabanga -Ekitale | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41653 | 41782 |  | 7659027.6 | 7659027.6 | 7659027.6 | County Government of Bungoma |  | 7659027.6 |  | 7659027.6 | 100.0% | 7659027.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
71 | Construction of Box Culvert And Gravelling Of Kmtc-S.A Church Primar A1 Road | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41662 | 41773 |  | 14768696.6 | 14768696.6 | 14768696.6 | County Government of Bungoma |  | 14768696.6 |  | 14768696.6 | 100.0% | 14768696.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
150 | Periodic Maintenance of Machinjoni - Proffessor - Kimaleni - Bukembe Polytechnic - Sudi Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.59212899,34.6529482 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43230 |  | 2654022 | 2654022 | 2654022 | County Government of Bungoma |  | 2654022 |  | 2654022 |  | 2654022 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
151 | Periodic Maintenance of Roads In Bukembe East Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.59212899,34.6529482 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43236 |  | 2654022 | 2654022 | 2654022 | County Government of Bungoma |  | 2654022 |  | 2654022 | 97.35% | 2654022 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
279 | Periodic Maintenance of Machinjoni - Professor - Sudi Mkt Road (Completion) | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.59212899,34.6529482 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43486 | 43599 |  | 9401742 | 9401742 | 9401742 | County Government of Bungoma |  | 9401742 |  | 9401742 |  | 9401742 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
280 | Periodic Maintenance of Periodic Maintenance Roads In Bukembe East Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43602 |  | 9401742 | 9401742 | 9401742 | County Government of Bungoma |  | 9401742 |  | 9401742 | 99.92% | 9401742 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
281 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
282 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
467 | Periodic Maintenance of Necko - Mapesa - Kokonya - Stima Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.5818879,34.6535845 0.8731302,34.6536554 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43964 | 43995 | 10687776 | 10687776 | 10687776 | County Government of Bungoma |  | 10687776 |  | 10687776 |  | 10687776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
468 | Periodic Maintenance of Gospel Believers - Yohana Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.5799638,34.6554056 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43967 | 43998 | 10687776 | 10687776 | 10687776 | County Government of Bungoma |  | 10687776 |  | 10687776 |  | 10687776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
469 | Periodic Maintenance of Makuti - Makenzi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.569989,346530504 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43966 | 43997 | 10687776 | 10687776 | 10687776 | County Government of Bungoma |  | 10687776 |  | 10687776 |  | 10687776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
470 | Periodic Maintenance of Bukembe - Njukhilila Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.6158705,34.6670553 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43973 |  | 10687776 | 10687776 | 10687776 | County Government of Bungoma |  | 10687776 |  | 10687776 |  | 10687776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
471 | Periodic Maintenance of Roads In Bukembe East Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43961 |  | 10687776 | 10687776 | 10687776 | County Government of Bungoma |  | 10687776 |  | 10687776 | 94.18% | 10687776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
692 | Periodic Maintenance of Luuya Junction - Misanga Primary | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.6177367,34.6714045 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44327 |  | 10895984.4 | 10895984.4 | 10895984.4 | County Government of Bungoma |  | 10895984.4 |  | 10895984.4 |  | 10895984.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
693 | Periodic Maintenance of Marko -Sirende Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.6158705,34.6670553 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44327 |  | 10895984.4 | 10895984.4 | 10895984.4 | County Government of Bungoma |  | 10895984.4 |  | 10895984.4 |  | 10895984.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
694 | Periodic Maintenance of Kombo Primary - A104 Tarmac Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.6105883,34.6447635 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44332 |  | 10895984.4 | 10895984.4 | 10895984.4 | County Government of Bungoma |  | 10895984.4 |  | 10895984.4 |  | 10895984.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
695 | Periodic Maintenance of Land Bokoli Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.6078302,34.66521859 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44337 |  | 10895984.4 | 10895984.4 | 10895984.4 | County Government of Bungoma |  | 10895984.4 |  | 10895984.4 |  | 10895984.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
696 | Periodic Maintenance of Kongoli - Tembelela - Kisuluni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.4186558,34.6799483 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44337 | 44368 | 1551732 | 1551732 | 1551732 | County Government of Bungoma |  | 1551732 |  | 1551732 |  | 1551732 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
697 | Periodic Maintenance of Roads In Bukembe East Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44331 |  | 10895984.4 | 10895984.4 | 10895984.4 | County Government of Bungoma |  | 10895984.4 |  | 10895984.4 | 98.57% | 10895984.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
698 | Periodic Maintenance of Roads In Bukembe East Ward - Negotiation 872539 | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44336 |  | 1551732 | 1551732 | 1551732 | County Government of Bungoma |  | 1551732 |  | 1551732 | 99.42% | 1551732 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1032 | Periodic Maintenance of Makambo Friends Church - Saratuki - R. Sichei Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44701 | 44732 | 2381364 | 2381364 | 2381364 | County Government of Bungoma |  | 2381364 |  | 2381364 |  | 2381364 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1033 | Periodic Maintenance of Roads In Bukembe East Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44691 |  | 2381364 | 2381364 | 2381364 | County Government of Bungoma |  | 2381364 |  | 2381364 | 92.81% | 2381364 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1349 | Periodic Maintenance of Kongoli - Natundwe - Ekitale Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.5372171,34.6647395 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45059 |  | 5367000 | 5367000 | 5367000 | County Government of Bungoma |  | 5367000 |  | 5367000 |  | 5367000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1350 | Periodic Maintenance of Kongoli - Natundwe - Ekitale Road In Bukembe East | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.5372171,34.6647395 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45063 |  | 5367000 | 5367000 | 5367000 | County Government of Bungoma |  | 5367000 |  | 5367000 | 100.0% | 5367000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1605 | Periodic Maintenance of Mupeli - Halleluyah - Sipinduli - Mukubwa - Sango Road, A104 - Misanga - Lusaka - Makambo Friends Church Road In Bukembe East Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe east | 0.61908809,34.6744586 0.6177367,34.6714045 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45430 |  | 7667675 | 7667675 | 7667675 | County Government of Bungoma |  | 7667675 |  | 7667675 | 94.89% | 7667675 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
4 | Purchase of 1 Acre land for Bunana E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land Purchased for Bunana ECDE | 3110599 | Ward based projects | Kanduyi | Bukembe east |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45078 | 45809 |  | 1500000 | - | 1500000 | CGB | N/A | 1500000 | 0 | 1500000 | 1 | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
72 | Purchase Of 1acre For Misanga Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land For Misanga Dispensary Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.6209149,34.6725618 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 | 43810 | 43893 | 30/6/2020 | 1500000 | 1032051 | 1032051 | CGB |  | 1032051 |  | 1032051 | 1 | 950000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
102 | Purchase of land for Sitawa ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new ECDE centre | One acre of Land for Sitawa ECDE Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.61879089,34.66513829 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 23/11/2018 | 17/5/2019 | 30/6/2019 | 1000000 | 950000 | 950000 | CGB |  | 950000 |  | 950000 |  | 950000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
112 | Purchase Of 2 Acre Land For Natundwe E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new ECDE centre | One acres of Land for Natundwe E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.5820402,34.637772 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43049 | 15/3/2018 | 18/6/2018 | 800000 | 800000 | 800000 | CGB | N/A | 800000 | 0 | 800000 | 1 | 1200000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
113 | Purchase Of 1 Acre Land For Sitawa E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new ECDE centre | One acres of Land for SitawaE.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.61879089,34.66513829 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42959 | 43376 | 13/5/2018 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 950000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
114 | Purchase Of Land For Misanga Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new dispensary | One acres of Land for Misanga Dispensary Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.61879089,34.6725618 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 17/9/2017 | 19/11/2017 | 43435 | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 1 | 1200000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
154 | Purchase of 1 acre land for Sango ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | Acres of Land Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.6139715,34.679821 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 950000 | 950000 | 950000 | CGB | N/A | 950000 |  | 950000 | 1 |  |  |  | completed | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
155 | Purchase of 1 acre for Natundwe dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Natundwe Dispensary Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/01/2016 | 21/03/2016 | 42647 | 1200000 | 1200000 | 1200000 | CGB | N/A | 1200000 |  | 1200000 | 1 | 1200000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
156 | Purchase of 1 acre for Sitawa E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Sitawa E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.6128359,34.66513829 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 15/11/2015 | 16/1/2016 | 20/1/2016 | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 1 | 500000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
157 | Purchase of ¾ of an acre for Namirembe dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | Three and a quater acres of Land for Namirembe Dispensary Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 15/8/2015 | 15/11/2015 | 13/12/2015 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
180 | Purchase of land for Sango ECDE centre. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Sango ECDE Purchased | 3110599 | Ward based projects | Kanduyi | Bukembe east | 0.61397135,34.67982100 | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42498 | 42501 | 42530 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 |  | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
1 | Construction of 1 NO. ECDE at Sitawa primary School in Bukembe East Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe east | 0.61879089,34.66513829 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 1500000 | 1480210 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1480210 | 1 | 1480210 | 0 | 0 | Completed
31 | Proposed Renovation Of 2no. Classrooms And Offices At Bukembe Vtc In Bukembe East Ward | Construction of ECDE classroom and pit latrine | To construct ECDE classroom and pit latrine providing a conducive learning environment | ECDE classroom and pit latrine constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe east | 0.5428999,34.673261 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2910120 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 | 0 | 0 | 2910120 | 2910120 | Stalled | 0 | 0 | Contractor declined
32 | Proposed Erection And Completion Works Of 1no. Ecde Classroom And 2blocks Of 2no. Door Pit Latrine At Natundwe Primary School In Bukembe East Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe east | 0.5389424,34.6242851 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2937792 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2321787.15 | 0.79032 | 2321787.15 | 616004.85 | 616004.85 | Complete and in use | 1
68 | construction of a Twin Workshop Shade in Bukembe VTC. | Construction of VTC workshop | To construct VTC workshop providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe east | 0.5428999,34.673261 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 4000000 | 3999000 | 4000000 | County Government of Bungoma | N/A | 4000000 | 0 | 1401168.75 | 0.35038 | 1401168.75 | 2597831.25 | 2597831.25 | complete | 0.9
100 | Construction Of 1 No. Ecde At Ndengelwa And Ekitale Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe east |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3000000 | 2950200 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2950200 | 1 | 2950200 | 0 | 0 | at roofing level. | 0.9
131 | Erection And Completion Of 1 No. Ecde At Hututu Primary School In Bukembe East Primary School In Bukembe East Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe east | 0.60565899,34.7436242 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1300000 | 1292785 | 1300000 | County Government of Bungoma | N/A | 1300000 | 0 | 1270583.65 | 0.98283 | 1270583.65 | 22201.35 | 22201.35 | complete and in use | 1
184 | Erection And Completion Of 1 N0 Classroom At Industrial Area And Sango Primary School In Bukembe East Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe east | 0.5838639,34.6580743 0.6139715,34.679821000 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3000000 | 2982200 | 3000000 | County Government of Bungoma | N/A | 3000000 |  | 2982200 | 1 | 2982200 | 0 |  | complete and in use | 100.0%
11 | Extension of Nandolia and Khaoya Water Projects in Bukembe East/west wards | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | Water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kanduyi | Bukembe east | 0.5673208,34.0523785 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 7000000 | 6025504 | 6025504 | FLLOCA | N/A | 6025504 | 0 | 0 | 1 | 6025504 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
38 | Proposed Tree Growing Within Institutions In Khasoko, Kabula, Musikoma, Bukembe East, West Nalondo And Chesikaki Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Kanduyi | Bukembe east |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7101000 | 6960000 | 6960000 | FLLOCA | IDA | 0 | 6960000 | 0 | 1 | 0 | 0 |  | On going and not in use | 0.2 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
42 | Drilling and Upgrading of Nandolia Market Borehole in Bukembe East Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east | 0.5673208,34.6523795 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4000000 | 3794592 | 3794592 | CGB | N/A | 3794592 | 0 | 3794592 | 1 | 3794592 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
94 | Upgrading of Kongoli Dispensary Borehole and Protection of Springs In Bukembe East Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; excavation; construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole upgraded and 1 water spring constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east | 0.5550021,34.6351094 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4866849.6 | 4866849.6 | CGB | N/A | 4866849.6 | 0 | 4866849.6 | 1 | 4866849.6 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
100 | Drilling and upgrading of Misanga market borehole in bukembe east ward. | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east | 0.620657,34.67090777 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2500000 | 2365541.6 | 2365541.6 |  | N/A | 2365541.6 | 0 | 2365541.6 | 1 | 0 | 2365541.6 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | BOREHOLE DRILLED .FABRICATION OF STAND AND TANK AND INSTALLATION COMPLETE.SOLAR SYSTEM REMAINING
253 | CONSRUCTION OF BUKEMBE MARKET WATER PROJECT IN BUKEMBE EAST WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east | 0.620657,34.6709077 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 4700000 | 4505672 | 4505672 |  | N/A | 4505672 | 0 | 4505672 | 1 | 4505672 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
338 | CONSTRUCTION OF NAVAKHOLO BOREHOLE WATER PROJECT IN BUKEMBE EAST WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3800000 | 3725521 | 3725521 |  | N/A | 3725521 | 0 | 3725521 | 1 | 3725521 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
342 | Construction of 5 Roof Catchment Construction of 50m3 Masonry tank at Kongoli Sec. School.and extension of nzowasco pipeline to misanga secondary. | Construction of 5 Roof Catchment and concrete tank; pipeline extension and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 tank constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 2200000 | 2196876 | 2196876 |  | N/A | 2196876 | 0 | 2196876 | 1 | 2196876 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
374 | Protection of 9 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 9 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1500000 | 1484960 | 1484960 |  | N/A | 1484960 | 0 | 1484960 | 1 | 1484960 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
506 | Protection of 9 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 9 water springs | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1484960 | 1484960 |  | N/A | 1484960 | 0 | 1484960 | 1 | 1484960 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
507 | Construction of 3 Roof Catchment Construction of 50m3 Masonry tank at Kongoli Sec. School.and extension of nzowasco pipeline to misanga secondary. | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2200000 | 2196876 | 2196876 |  | N/A | 2196876 | 0 | 2196876 | 1 | 2196876 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
575 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1700000 | 1591930 | 1591930 |  | N/A | 1591930 | 0 | 1591930 | 1 | 1591930 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
576 | Bukembe water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe east | 0.6128359,34.65740969 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2402625 | 2402625 |  | N/A | 2402625 | 0 | 2402625 | 1 | 2402625 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
11 | Construction of Bukembe East ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Bukembe East ward office constructed | 3111504 | Construction of non- residential buildings | Kanduyi | Bukembe east | 0.59222899,34.662948 | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43567 | 9500000 | 9698168 | 9500000 | County Government of Bungoma | - | 9698168 | - | 9698168 | 1 | 9698168 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Dairy Commercialization Area Network for Bukembe | Dairy Commercialization Area Network for Bukembe | To increase milk production, productivity and income generation | 1 Commercialization area network developed | 3110504 | Other infrastructure and civil works | Kanduyi | Bukembe east | 0.59212899,34.6529482 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42496 | 30/5/2016 | 15000000 | 11363600 | 10000000 | County Government of Bungoma |  | 11363600 |  | 9377350 | 0.83 | 9377350 | 1986250 | 1986250 | stalled
| Purchase of Young Dairy Animals | Purchase and delivery of 29 Young Dairy Animals | To increase dairy production, value addition and income generation | 29 Dairy animals purchased and delivered | 3110599 | Ward Based projects | Kanduyi | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44835 | 44837 | 25/2/2022 | 3000000 | 2910000 | 3000000 | County Government of Bungoma |  | 2910000 | 0 | 2910000 | 1 | 2910000 | 0 | 0 | Completed
| Purchase Of Dairy Cows | Purchase and delivery of 14 Dairy Cows | To increase dairy production, value addition and income generation | 14 Dairy animals purchase and delivered | 3110599 | Ward Based projects | Kanduyi | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44835 | 44837 | 25/2/2022 | 1500000 | 1455000 | 1500000 | County Government of Bungoma |  | 1455000 | 0 | 1455000 | 1 | 1455000 | 0 | 0 | Completed
| Supply and delivery of young dairy animals(Heifers) 18 to 24 months $ young dairy goats 12 to 18 months old | Supply and delivery of young dairy animals(Heifers) 18 to 24 months $ young dairy goats 12 to 18 months old | To enhance dairy production, value addition and income generation | 58 Dairy animals (heifers) supplied and delivered to farmer groups | 3110599 | Ward Based projects | Kanduyi | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 6800000 | 6800000 | 6800000 | County Government of Bungoma |  | 6800000 | 0 | 6800000 | 1 | 6800000 | 0 | 0 | Completed
| Renovation and fencing of cattle Dip | Renovation and fencing of 1 cattle Dip | To improve animal health and productivity | 1 Cattle dip renovated | 3110599 | Ward Based projects | Kanduyi | Bukembe east | 0.602218199,34.6416944 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 44969 | 45356 | 45354 | 1000000 | 1000000 | 1000000 | County Government of Bungoma |  | 1000000 | 0 | 1000000 | 1 | 1000000 | 0 | 0 | Completed
| Provision of improved breeds (meat goats) | Provision of 30 does and 3 Bucks to 3 elite breeders,2 in Bukembe East (BUKONONA SLCA) and 1 in Musikoma (MUSIKOMA SLCA) | To enhance production, productivity and income generation | 30 does and 3 Bucks purchased and issued to 3 elite breeders | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 18/4/2024 | 18/7/2024 | 45447 |  | 961980 | 1029280 | Development partner | IFAD | 0 | 961980 | 961980 |  | 961980 | 0 | 0 | Complete
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
80 | Proposed construction of cabro laying in Bukembe open air market | construction laying in Bukembe | [5 empty] | Bukembe east | 0.6128359,34.6574096 | Trade, Energy and Industrialization | Dept of Trade | M/S Jei De construction company limited | 2021/22 |  | Complete and in use |  | 4395275 |  |  | CGB | [8 empty] | completed
85 | Installation of 2No high mast flood lights | of lights No high | [5 empty] | Bukembe east | 0.61283599,34.65740969 | Trade, Energy and Industrialization | Dept of Energy | Cavram Holdings Limited | 2021/22 |  | Complete and in use |  | 1937744 |  |  | CGB | [8 empty] | complete and in use
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A | [5 empty] | Bukembe east |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east | 0.69212899,34.6529482 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east | 0.59212899,34.6529422 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east | 0.59212899,34.6529422 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east | 0.59212899,34.6529423 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe east | 0.59212899,34.6529423 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe east |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Bukembe east |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Construction of 4 door pit latrine at nandolia market | [5 empty] | Kanduyi | Bukembe east | 0.569989499,34.6530504 | Health& sanitation |  |  | 2017/18 | [15 empty] | completed
| coca-cola- mayende road | [5 empty] | Kanduyi | Bukembe east | 0.5678206,34.6525813 | Roads, infrastructure and public work |  |  | 2019/20 | [15 empty] | completed
| coca-cola- mayende road | [5 empty] | Kanduyi | Bukembe east | 0.5678206,34.6525813 | Roads, infrastructure and public work |  |  | 2024/25 | [15 empty] | completed
| Kongoli market boda boda shed | [5 empty] | Kanduyi | Bukembe east
| Shadrack juma- sitawa ecde- highway road | [5 empty] | Kanduyi | Bukembe east | [20 empty] | completed
| Bunana ecde purchase of land | [5 empty] | Kanduyi | Bukembe east |  |  |  |  | 2023/24 | [15 empty] | ongoing
| Masibo sring maintainance | [5 empty] | Kanduyi | Bukembe east |  |  |  |  | 2024/25 | [15 empty] | completed
130 | Contruction Of Chebukwabi Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Kimilili | Kibingei | 0.47"36.1",34.38"16.2" |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2811900 | 2811900 | CGB |  | 2811900 | 0 | 2811900 | 1 | 2811900 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
164 | Purchase Of Furniture For Daraja Mungu Dispensary |  |  | Furniture purchased |  |  | Kimilili | Kibingei | 0.48"3.4236",34.38"44" |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 500000 | 499000 | 499000 | CGB |  | 499000 | 0 | 499000 | 1 | 499000 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
191 | Purchase Of Medical Equipments For Daraja Mungu Dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Kimilili | Kibingei | 0.48"3.4236",34.38"44" |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 300000 |  |  | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | completed | [6 empty] | No | complete | Financial | Yes
192 | Purchase Of Furniture For Daraja Mungu Dispensary |  |  | Furniture purchased |  |  | Kimilili | Kibingei |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 500000 | 499000 | 499000 | CGB |  | 499000 | 0 | 499000 | 1 | 499000 |  | 0 | Complete - need to verify usability | [6 empty] | No | complete | Financial | Yes
227 | Construction Of Kibingei Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Kimilili | Kibingei | 0.74",34.67" |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 3700000 | 4257339.2 | 4257339.2 | CGB |  | 4257339.2 | 0 | 4257339.2 | 1 | 4257339.2 |  | 0 | ongoing | [6 empty] | No | complete | Financial | Yes
228 | Completion Of A Nurse House At Daraja Mungu | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Nurse houses completed |  |  | Kimilili | Kibingei |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2800000 |  |  | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
322 | Purchase of 0.5 acre land. | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | acres of land purchased |  |  | Kimilili | Kibingei |  |  | Ward Based | Health & Sanitation | 2015/2016 | 42522 |  | 42552 |  | 435000 | 435000 | CGB |  | 435000 | 0 | 435000 | 1 | 435000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
323 | Purchase Of 1 Acre Land For Kitayi Dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | acres of land purchased |  |  | Kimilili | Kibingei |  |  | Ward Based | Health & Sanitation | 2015/2016 | 42491 |  | 42248 |  | 700000 | 700000 | CGB |  | 700000 | 0 | 700000 | 1 | 700000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
324 | Purchase of 1 acre land for extension of Kibingei Kispensary. | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | acres of land purchased |  |  | Kimilili | Kibingei |  |  | CEF | Health & Sanitation | 2016/2017 | 15.05.2017 |  | 01.07.2017 |  | 800000 | 800000 | CGB |  | 800000 | 0 | 800000 | 1 | 800000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
331 | Purchase of half an acre of land. | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of Health facilities. | acres of land purchased |  |  | Kimilili | Kibingei |  |  | Ward Based | Health & Sanitation | 2015/16 | 22.06.2016 |  | 1.07.2016 |  | 435000 | 435000 | CGB |  | 435000 | 0 | 435000 | 1 | 435000 |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
48 | Upgrading of Chebukwabi-Mwai Mwai | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.48"7.02",34.40"7.4" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41650 | 41778 |  | 4474932 | 4474932 | 4474932 | County Government of Bungoma |  | 4474932 |  | 4474932 | 100.0% | 4474932 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
365 | Periodic Maintenance of Kunda - Kolongolo Friends - River Kibisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43480 | 43608 |  | 9138712 | 9138712 | 9138712 | County Government of Bungoma |  | 9138712 |  | 9138712 |  | 9138712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
366 | Periodic Maintenance of Naporora - Ndalila - Lutaso - Siuma Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.48"3.42",34.38"44.6" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43481 | 43598 |  | 9138712 | 9138712 | 9138712 | County Government of Bungoma |  | 9138712 |  | 9138712 |  | 9138712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
367 | Periodic Maintenance of Roads In Kibingei Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43482 | 43596 |  | 9138712 | 9138712 | 9138712 | County Government of Bungoma |  | 9138712 |  | 9138712 | 99.99% | 9138712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
368 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
543 | Periodic Maintenance of Naporora - Josek - Muricho Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.48"5.03",34.39"0.7" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43969 | 44000 | 6380000 | 6380000 | 6380000 | County Government of Bungoma |  | 6380000 |  | 6380000 |  | 6380000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
544 | Periodic Maintenance of Fred Masafu - Shitubi - Hon. Murunga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43968 | 43999 | 6380000 | 6380000 | 6380000 | County Government of Bungoma |  | 6380000 |  | 6380000 |  | 6380000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
545 | Construction of Siuna Kimalewa Box Culvert(River Kibisi) | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Kimilili | Kibingei | 0.47"25.63116",34.39"12.31334" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43965 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
546 | Construction of Siuna Kimalewa Box Culvert(River Kibisi) | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Kimilili | Kibingei | 0.47"25.63116",34.39"12.31334" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43970 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
547 | Periodic Maintenance of Roads In Kibingei Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43962 |  | 6380000 | 6380000 | 6380000 | County Government of Bungoma |  | 6380000 |  | 6380000 | 98.69% | 6380000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
794 | Periodic Maintenance of Wamulwonyi - Kibisi River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.47"35.41817",34,38"56.7744 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44327 |  | 6906060 | 6906060 | 6906060 | County Government of Bungoma |  | 6906060 |  | 6906060 |  | 6906060 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
795 | Periodic Maintenance of Kamusinga Highway - Major Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.47"59.55",34.44"2.2" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44328 |  | 6906060 | 6906060 | 6906060 | County Government of Bungoma |  | 6906060 |  | 6906060 |  | 6906060 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
796 | Periodic Maintenance of Kamusinga Girls - Ack Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44335 |  | 6906060 | 6906060 | 6906060 | County Government of Bungoma |  | 6906060 |  | 6906060 |  | 6906060 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
797 | Periodic Maintenance of Kuywa River - Kibunde - Saenyi - Kibingei - Stendi Maziwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44334 |  | 3104682 | 3104682 | 3104682 | County Government of Bungoma |  | 3104682 |  | 3104682 |  | 3104682 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
798 | Periodic Maintenance of Roads In Kibingei Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44335 |  | 6906060 | 6906060 | 6906060 | County Government of Bungoma |  | 6906060 |  | 6906060 | 95.39% | 6906060 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
799 | Periodic Maintenance of Roads In Kibingei Ward - Negotiation 872510 | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44332 |  | 3104682 | 3104682 | 3104682 | County Government of Bungoma |  | 3104682 |  | 3104682 | 99.94% | 3104682 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
800 | Drainage Works In Kimilili And Tongaren | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44326 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1123 | Periodic Maintenance of Pawawa Mkt - Daylight School | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.47"54.98088",34.39"44.904241" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44694 |  | 9990891 | 9990891 | 9990891 | County Government of Bungoma |  | 9990891 |  | 9990891 |  | 9990891 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1124 | Periodic Maintenance of Friends School Kamusinga - Allan Bradley | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44692 | 44723 | 9990891 | 9990891 | 9990891 | County Government of Bungoma |  | 9990891 |  | 9990891 |  | 9990891 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1125 | Periodic Maintenance of Moi Girls - Full Gospel Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44691 | 44722 | 9990891 | 9990891 | 9990891 | County Government of Bungoma |  | 9990891 |  | 9990891 |  | 9990891 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1126 | Periodic Maintenance of Mulwoni - Kibisi River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.47"35.41812",34.38"56.77" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44693 | 44724 | 9990891 | 9990891 | 9990891 | County Government of Bungoma |  | 9990891 |  | 9990891 |  | 9990891 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1127 | Periodic Maintenance of Kibingei High School - Stendi Maziwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44692 | 44723 | 3509058 | 3509058 | 3509058 | County Government of Bungoma |  | 3509058 |  | 3509058 |  | 3509058 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1128 | Construction of Moi Girls - Kaptola Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44704 |  | 5132652 | 5132652 | 5132652 | County Government of Bungoma |  | 5132652 |  | 5132652 |  | 5132652 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1129 | Periodic Maintenance of Roads In Kibingei Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44697 |  | 9990891 | 9990891 | 9990891 | County Government of Bungoma |  | 9990891 |  | 9990891 | 99.49% | 9990891 | 0 | 0 | stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1130 | Routine Maintenance Of Kibingei High School - Stendi Maziwa | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44693 |  | 3509058 | 3509058 | 3509058 | County Government of Bungoma |  | 3509058 |  | 3509058 | 97.83% | 3509058 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1131 | Routine Maintenance Of Moi Girls - Kaptola Box Culverts (2.5*2M) | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44702 |  | 5132652 | 5132652 | 5132652 | County Government of Bungoma |  | 5132652 |  | 5132652 | 29.22% | 5132652 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1419 | Construction of Sda Church - Sitabicha Road Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45058 |  | 3510885 | 3510885 | 3510885 | County Government of Bungoma |  | 3510885 |  | 3510885 |  | 3510885 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1420 | Periodic Maintenance of Mulongo - Moi Girls Primary - Ben Luke - Musamali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.47"59.55",34.42"25.5" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45069 |  | 8689565 | 8689565 | 8689565 | County Government of Bungoma |  | 8689565 |  | 8689565 |  | 8689565 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1421 | Periodic Maintenance of Daylight - Mwai Mwai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei | 0.48"7.029",34.40"7.45572" | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45060 |  | 8689565 | 8689565 | 8689565 | County Government of Bungoma |  | 8689565 |  | 8689565 |  | 8689565 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1422 | Periodic Maintenance of Daylight - Mwai, Mwai Road, Mulongo - Moi Girls Primary - Ben Luke Musamali Road In Kibingei Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45065 |  | 8689565 | 8689565 | 8689565 | County Government of Bungoma |  | 8689565 |  | 8689565 | 99.99% | 8689565 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1423 | Upgrading of Roads In Kimilili Ward And Installation Of Culverts At Sda Church - Sitabicha Road | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kibingei |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45064 |  | 3510885 | 3510885 | 3510885 | County Government of Bungoma |  | 3510885 |  | 3510885 | 99.37% | 3510885 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
93 | Purchase of land for Chepkwabi dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land for Chepkwabi dispensary Purchased | 3110599 | Ward based projects | Kimilili | Kibingei |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 43232 | 26/3/2019 | 16/6/2019 | 1000000 | 900000 | 900000 | CGB |  | 900000 |  | 900000 |  | 850000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
144 | Proposed Erection And Completion Of 1 No. Ecde At Siilila Primary School In Kibingei Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kibingei |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1212767.14 | 1194713 | 1212767.14 | County Government of Bungoma | N/A | 1212767.14 | 0 | 1194713 | 1 | 1194713 | 0 | 0 | complete and in use | 1
196 | The Proposed Erection And Completion Of 1 N0 Classroom At Chebukwabi And Daraja Mungu S.A Primary Schools In Kibingei Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kibingei | 0.47"56.1",34.39"36.6" | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2650000 | 2926380 | 2650000 | County Government of Bungoma | N/A | 2650000 |  | 2926380 | 1 | 2926380 | 0 |  | complete and in use | 100.0%
197 | Construction Of 3no. Classrooms At Saenyi, Namakhele And Allan Bradley Primary Schools In Kibingei Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kibingei |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4000000 | 3933490 | 4000000 | County Government of Bungoma | N/A | 4000000 |  | 3933490 | 1 | 3933490 | 0 |  | N/A | 100.0%
1 | Upgrading of Riziki to Slaughter house road | Upgrading of road from Riziki- Slaughterhouse to butimenous standard | To enhance road accessbility | 1.6KM of Road Upgraded to butimenous Standard | 2640503 | Other capital Grants and Transfer | Kimilili | Kibingei |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2018/2019 | 6th May,2019 | 6th October,2020 | 21st October,2020 | 100000000 | 88082969.88 | 88082969.88 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 0 |  |  |  | 88055037.4 |  | 0 | Completed | 1 | 0 | [13 empty] | Complete and in use
7 | Installation of highmast lights at Chebukwabi market | Installation of highmast lights at Chebukwabi market | To light the market and enhance security | 1 Highmast light installed | 2640503 | Other capital Grants and Transfer | Kimilili | Kibingei | 0.47"15.2",34.41"25.1" | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 45238 | 45340 | 45369 | 3000000 | 2990400 | 2990400 | County Government[Equitable share] | Kenya urban support progamme-World Bank |  | 2990400 | 2990400 | 1 | 2990400 |  |  | Completed | 1 | [14 empty] | Complete and in use
10 | Periodic Maintenance of Miruri SA-Babasaba Road | Periodic Maintenance of Miruri SA-Babasaba Road | To enhance road accessibility | 1.6 KM of Road maintained | 3110599 | Other infrastructure and Civil Works | Kimilili | Kibingei | 0.51"13.4",34.38"35.7" | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 2nd Feb,2024 | 2nd May,2024 | 5th,Apil,2024 | 4000000 | 3800000 | 3800000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 3573670 | 0 | 3573670 | 1 | 3573670 |  |  | completed | 1 | [14 empty] | Complete and in use
16 | Periodic Maintenance of Apostalic Church-Kaptola-Nakhobani Road | Periodic Maintenance of Apostalic Church-Kaptola-Nakhobani Road | To enhance road accessibility | 2.1 KM of Road maintained | 2640503 | Other capital Grants and Transfer | Kimilili | Kibingei | 0.48"16",34.70"69" | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 2nd Feb,2024 | 2nd May,2024 | 5th,March,2024 | 4000000 | 3800000 | 3800000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 0 | 3677113 | 3677113 | 1 | 3677113 | 0 | 0 | Completed | 1 | [14 empty] | Complete and in use
25 | Upgrading of Kimilili FYM Primary Borehole and Pipeline Extention to Tembatemba | Upgrading of Kimilili FYM Primary Borehole and Pipeline Extention to Tembatemba | To enhance access to clean water | 1 Borehole and KM of Pipeline Extention completed | 3110599 | Other infrastructure and Civil Works | Kimilili | Kibingei | 0.46"24.6",34.41"25.8" | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 11th April,2024 | 11th July,2024 | 13 th June,2024 | 2850000 | 2850000 | 2850000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 2750000 |  | 2750000 | 0 | 0 | 2750000 |  | ongoing | 0.78
28 | Proposed Erection and Completion for 1 N0. ECDE Classroom at Kimilili FYM Primary | Proposed Erection and Completion for 1 N0. ECDE Classroom at Kimilili FYM Primary | To enhance access education | 1 ECDE class constructed | 3110599 | Other infrastructure and Civil Works | Kimilili | Kibingei |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 11th April,2024 | 11th July,2024 | 19 th June 2024 | 3250000 | 1425000 | 1425000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 1425000 | 0 | 0 | 0 | 0 | 1425000 | 1425000 | Completed | 1
31 | Upgrading of Kimilili FYM Primary Borehole and Pipeline Extention to Tembatemba | Upgrading of Kimilili FYM Primary Borehole and Pipeline Extention to Tembatemba | To enhance access to clean water | 1 Borehole and Pipeline Extention completed | 3110504 | Other infrastructure and Civil Works | Kimilili | Kibingei |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 11th April,2024 | 11th July,2024 | 13th June,2024 | 2850000 | 2850000 | 2850000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 2842500 |  | 0 | 0 | 0 | 2842500 | 2842500 | Completed | 1 | [14 empty] | Complete and in use
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers |  | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | [7 empty] | FLLOCA | N/A |  | 0 |  | 1 |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
130 | Extension of main line-Daraje Mungu-Chebukwabi market water project and drilling of a borehole at Kamusinga Pri in Kibingei ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei | 0.47"27",34.41"13" | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 5000000 | 4851740 | 4851740 |  | N/A | 4851740 | 0 | 4851740 | 1 | 4851740 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
193 | CONSTRUCTION AND PROTECTION OF 4NO. WATER SPRINGS IN KIBINGEI WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1000000 | 964312 | 964312 |  | N/A | 964312 | 0 | 964312 | 1 | 964312 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
194 | MIRURI WATER PROJECT IN KIBINGEI WARD | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei | 0.51"13.4",34.33"35" | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 4000000 | 3825308 | 3825308 |  | N/A | 3825308 | 0 | 3825308 | 1 | 3825308 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
247 | PROTECTION OF 5NO WATER SPRINGS IN KIBINGEI WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1000000 | 947140 | 947140 |  | N/A | 947140 | 0 | 947140 | 1 | 947140 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
316 | CHEBKWABI-KIBINGE WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt Elgon,Kimilili | Kibingei | 0.46"59.8",34.41"43.7" | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 36034960 | 36034960 | 36034960 |  | N/A | 36034960 | 0 | 36034960 |  | 29188318 | 6846642 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
325 | DRILLING OF KIMILILI FYM BOREHOLE AND CONSTRUCTION OF 1 NO. WATER SPRING IN KIBINGEI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole drilled and 1 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2800000 | 2503678 | 2503678 |  | N/A | 2503678 | 0 | 2503678 | 1 | 2503678 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
326 | DRILLING OF KITAYI BOREHOLE IN KIBINGEI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1972000 | 1972000 |  | N/A | 1972000 | 0 | 1972000 | 1 | 1972000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
376 | Kibingei Chepkwabi water –construction of intake works and laying of main pipe line | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei | 0.45"50.9",34.36"51.3 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 6000000 | 5848212.5 | 5848212.5 |  | N/A | 5848212.5 | 0 | 5848212.5 | 1 | 5848212.5 | 0 | 0 | icomplete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
418 | Protect 10No Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works |  | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1463250 | 1463250 |  | N/A | 1463250 | 0 | 1463250 | 1 | 1463250 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
538 | Protect 10No Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1463250 | 1463250 |  | N/A | 1463250 | 0 | 1463250 | 1 | 1463250 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
539 | Construct 5No Roof catchment and 1No Storage tank at Chebkwabi market | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchments constructed and 1 water tank constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei | 0.47"36.4",34.39"26.9" | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1324946 | 1324946 |  | N/A | 1324946 | 0 | 1324946 | 1 | 1324946 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
540 | Kibingei Chepkwabi water –construction of intake works and laying of main pipe line | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works |  | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 12000000 | 11696695 | 11696695 |  | N/A | 11696695 | 0 | 11696695 | 1 | 11696695 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
615 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1611600 | 1611600 |  | N/A | 1611600 | 0 | 1611600 | 1 | 1611600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
616 | Upgrading of Kundan water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kibingei |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2248280 | 2248280 |  | N/A | 2248280 | 0 | 2248280 | 1 | 2248280 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Rehabilitation of cattle dips | Rehabilitation of cattle dips in Luuya, Kibisi, Bukembe, Lutaso, Tulumba, and Myanga Cattle Dips | To improve animal health and productivity | 6 Cattle dips rehabiliatated | 3110504 | Other infrastructure and civil works | Kabuchai/Kimilili/Kanduyi/Bumula | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44136 | 44139 | 14/3/2020 | 5000000 | 3486950 | 3548016 | County Government of Bungoma |  | 3486950 | 0 | 3486950 | 1 | 3486950 | 0 | 0 | Completed
| Purchase Of Dairy Animals | Purchase and delivery of 29 Dairy Animals | To increase dairy production, value addition and income generation | 29 Dairy animals purchased and delivered | 3110599 | Ward Based projects | Kimilili | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 15/12/2021 | 15/3/2022 | 26/2/2022 | 3000000 | 2910000 | 3000000 | County Government of Bungoma |  | 2910000 | 0 | 2910000 | 1 | 2910000 | 0 | 0 | Completed
| Construction of Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | Construction of 20 Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | To support growth of coffee farmers and enhance income generation | 20 Coffee drying tables constructed | 3110504 | Other infrastructure and civil works | Kimilili/Webuye West, Mt. Elgon | Kibingei |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44900 | 44838 | 10000000 | 3087863.88 | 3100000 | County Government of Bungoma |  | 3087863.88 | 0 | 3087863.88 | 1 | 3087863.88 | 0 | 0 | Completed
| Construction of Coffee Drying Table at Sichei, Chenjeni, and Kibisi | Construction of 10 Coffee Drying Table at Sichei, Chenjeni, and Kibisi | To support growth of coffee farmers and enhance income generation | 10 Coffee Drying tables constructed at Nanjikobe FCS | 3110504 | Other infrastructure and civil works | Kabuchai/Kimilili | Kibingei |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44479 | 44837 | 23/5/2022 | 6000000 | 1450000 | 1500000 | County Government of Bungoma |  | 1450000 | 0 | 1450000 | 1 | 1450000 | 0 | 0 | Completed
| Purchase of pulping machine at Daraja Mungu Coffee Factory | Purchase of pulping machine at Daraja Mungu Coffee Factory | To promote coffee production and enhance income generation among Coffee farmers | 1 Coffee of pulping machines purchased | 3110599 | Ward Based projects | Kimilili | Kibingei | 0.48"18",34.37"8" | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 18/1/2023 | 18/3/2023 | 45140 | 4000000 | 3995000 | 4000000 | County Government of Bungoma |  | 3995000 | 0 | 3995000 | 1 | 3995000 | 0 | 0 | Completed
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye | [5 empty] | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Kibingei |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kibingei |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Kibingei |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Construction of ecde classroom at kibunde primary | [5 empty] | Kimilili | Kibingei | 0.44",34.39" | Education& vocational training |  |  | 2019/20 | [15 empty] | completed
| Construction classroom at kibingei fym | [5 empty] | Kimilili | Kibingei | 0.74",34.60" | Education& vocational training | [18 empty] | completed
| Construction of ecde classroom at Kolongolo | [5 empty] | Kimilili | Kibingei |  | Education& vocational training |  |  | 2018/19 | [15 empty] | completed
| Construction of kibinsei vtc | [5 empty] | Kimilili | Kibingei | 0.74",34.6" | Education& vocational training |  |  | 2016/17 | [15 empty] | completed
| Gabriel water spring | [5 empty] | Kimilili | Kibingei |  | Education& vocational training | [18 empty] | completed
| Construction of Musima bridge | [5 empty] | Kimilili | Kibingei |  | Roads, infrastructure and public works | [18 empty] | stalled
| Kitayi ecde | [5 empty] | Kimilili | Kibingei |  | Education$ Vocational training | [18 empty] | completed
| Animal feed | [5 empty] | Kimilili | Kibingei | 0.47"50.5670",34.39243.3494" | Cooperative | [18 empty] | ongoing
| Napororo sspring | [5 empty] | Kimilili | Kibingei | 0.472,34.88"54" | Water |  |  | 2019/20 | [15 empty] | completed
| Daylight- pawawa road | [5 empty] | Kimilili | Kibingei | 0.4821.224",34.408" | Roads
| Tool and equipments chebukaka vtc | [5 empty] | Kimilili | Kibingei | 0.47"27",34.41"13" | Education |  |  | 2024/25 | [15 empty] | completed
| One workshop at VTC | [5 empty] | Kimilili | Kibingei | 0.47"27",34.41"13" | Education | [18 empty] | incomplete
| Nambale- muruno road | [5 empty] | Kimilili | Kibingei | 0.48"3.4236",34.38"44" | Roads | [18 empty] | ongoing
| Abolution block at Daraja Mungu Dispensary | [5 empty] | Kimilili | Kibingei |  | Health | [18 empty] | completed
| Construction of Namakhele ecde | [5 empty] | Kimilili | Kibingei |  | Education |  |  | 2017/18 | [15 empty] | completed
| Construction of Allan Bradley | [5 empty] | Kimilili | Kibingei |  |  |  |  | 2019/20 | [15 empty] | completed
| Construction of khwiroroAC | [5 empty] | Kimilili | Kibingei |  |  |  |  | 2022/23 | [15 empty] | completed
| Dilling of borehole Khwiroro ACK | [5 empty] | Kimilili | Kibingei |  |  |  |  | 2022/23 | [15 empty] | completed
| Drilling of borehole at Kamusinga A.C | [5 empty] | Kimilili | Kibingei |  |  |  |  | 2024/25 | [15 empty] | completed
| Construction of 1 ecde at miruri R.C | [5 empty] | Kimilili | Kibingei | 0.51"13.4",34.33"35.7" |  |  |  | 2024/25 | [15 empty] | completed
| Construction of 1 ecde at Siuna S.A | [5 empty] | Kimilili | Kibingei |  |  |  |  | 2014/15 | [15 empty] | incomplete
104 | Purchase Of Medical Equipment For Sulwe And Maghonge Dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Kimilili | Kamukuywa |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 3000000 |  |  | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No
129 | Purchase For Medical Equipments | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Kimilili | Kamukuywa |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2800000 | 2800000 | CGB |  | 2800000 | 0 | 2800000 | 1 | 2800000 |  | 0 | Information not available | [6 empty] | No | complete | Financial | Yes
187 | Purchase Of Medical Equipments For Kamukuywa Sulwe And Makhonge Dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Kimilili | Kamukuywa |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3027352 | 3019770 | 3019770 | CGB |  | 3019770 | 0 | 3019770 | 1 | 3019770 |  | 0 | Compllete and use | [6 empty] | No | complete | Financial | Yes
321 | Construction of Public toilets. | Digging of 20ft deep pit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the market | Public toilets constructed |  |  | Kimilili | Kamukuywa |  |  | Ward Fund | Health & Sanitation | 2014/15 | 9/4/20115 |  | 43350 |  | 1475102.4 | 1475102.4 | CGB |  | 1475102.4 | 0 | 815416.2 | 0.55279 | 815416.2 |  | 659686.2 | Complete | [6 empty] | No | complete | Financial | Yes
329 | Erection And Completion Of The Proposed Public Toilet | Digging of 20ft deep pit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the market | public toilets erected and completed |  |  | Kimilili | Kamukuywa |  |  | Ward Fund | Health & Sanitation | 2014/15 | 9/4/20115 |  | 43350 |  | 1475102.4 | 1475102.4 | CGB |  | 1475102.4 | 0 | 815416.2 | 0.55279 | 815416.2 |  | 659686.2 | Complete | [6 empty] | No | complete | Financial | Yes
178 | Periodic Maintenance of Chesamisi-Namasanda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43116 | 43231 |  | 6110706 | 6110706 | 6110706 | County Government of Bungoma |  | 6110706 |  | 6110706 |  | 6110706 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
179 | Periodic Maintenance of Roads In Kamukuywa Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43232 |  | 6110706 | 6110706 | 6110706 | County Government of Bungoma |  | 6110706 |  | 6110706 | 96.5% | 6110706 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
180 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43239 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
336 | Periodic Maintenance of Musembe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa | 0.77869,34.78848 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43600 |  | 9792720 | 9792720 | 9792720 | County Government of Bungoma |  | 9792720 |  | 9792720 |  | 9792720 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
337 | Periodic Maintenance of Makhonge - Marofu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 9792720 | 9792720 | 9792720 | County Government of Bungoma |  | 9792720 |  | 9792720 |  | 9792720 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
338 | Periodic Maintenance of Roads In Kamukuywa Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43609 |  | 9792720 | 9792720 | 9792720 | County Government of Bungoma |  | 9792720 |  | 9792720 | 99.47% | 9792720 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
339 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
340 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
521 | Periodic Maintenance of Chesamisi - Sango Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43966 | 43997 | 4832977.6 | 4832977.6 | 4832977.6 | County Government of Bungoma |  | 4832977.6 |  | 4832977.6 |  | 4832977.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
522 | Periodic Maintenance of Roads In Kamukuywa Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43968 |  | 4832977.6 | 4832977.6 | 4832977.6 | County Government of Bungoma |  | 4832977.6 |  | 4832977.6 | 99.99% | 4832977.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
598 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
762 | Periodic Maintenance of Nakalira - Ondoti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44334 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1088 | Construction of Makhonge Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44702 |  | 2654652.4 | 2654652.4 | 2654652.4 | County Government of Bungoma |  | 2654652.4 |  | 2654652.4 |  | 2654652.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1089 | Upgrading of Roads In Kamukuywa Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44705 |  | 2654652.4 | 2654652.4 | 2654652.4 | County Government of Bungoma |  | 2654652.4 |  | 2654652.4 | 85.38% | 2654652.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1398 | Periodic Maintenance of Nakalira Catholic - Weyong'O - Mukuyuni Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45061 |  | 8936663 | 8936663 | 8936663 | County Government of Bungoma |  | 8936663 |  | 8936663 |  | 8936663 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1399 | Periodic Maintenance of Deliverance - Sulwe Dispensary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45057 |  | 8936663 | 8936663 | 8936663 | County Government of Bungoma |  | 8936663 |  | 8936663 |  | 8936663 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1400 | Periodic Maintenance of Barikiwa - Nyongesa - Kiveti Water Spring Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45057 |  | 8936663 | 8936663 | 8936663 | County Government of Bungoma |  | 8936663 |  | 8936663 |  | 8936663 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1401 | Periodic Maintenance of Nakalira Catholic - Weyongo Mukuni Bridge, Mbarikiwa Nyongesa Kiveti Water Springs, Deliverence Sulwe Dispensary Road In Kamukuywa Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45069 |  | 8936663 | 8936663 | 8936663 | County Government of Bungoma |  | 8936663 |  | 8936663 | 91.85% | 8936663 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1652 | Construction of Sango - Number One Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45432 |  | 8000201 | 8000201 | 8000201 | County Government of Bungoma |  | 8000201 |  | 8000201 |  | 8000201 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1653 | Periodic Maintenance of Ditina - Kere Road In Kamukuywa Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa | 13.257601,32.3035 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45424 |  | 2158992 | 2158992 | 2158992 | County Government of Bungoma |  | 2158992 |  | 2158992 | 100.0% | 2158992 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1654 | Periodic Maintenance of Simbakware - Wenyila Road In Kamukuywa Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa | 13.118625,32.337311 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45430 |  | 5648040 | 5648040 | 5648040 | County Government of Bungoma |  | 5648040 |  | 5648040 | 99.94% | 5648040 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1655 | Periodic Maintenance of Makhonge - Chalicha Box Culvert Road In Kamukuywa Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45427 |  | 5077900 | 5077900 | 5077900 | County Government of Bungoma |  | 5077900 |  | 5077900 | 99.98% | 5077900 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1656 | Proposed Sango - Number One Box Culvert In Kamukuywa Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kimilili | Kamukuywa |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45436 |  | 8000201 | 8000201 | 8000201 | County Government of Bungoma |  | 8000201 |  | 8000201 | 100.0% | 8000201 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
9 | Purchase of 1 acre land for Mbongi dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land Purchased for Mbongi dispensary | 3110599 | Ward based projects | Kimilili | Kamukuywa |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45352 | 45444 |  | 1500000 | - | 1500000 | CGB | N/A | 1500000 | 0 | 1500000 | 1 | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
48 | Purchase of 0.22 Acre land for Lutaso water project | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new water project | Zero point Two two acre of Land for Lutaso water projec Purchased | 3110599 | Ward based projects | Kimilili | Kamukuywa |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2021/22 | - | - |  | 500000 | 200000 | 200000 | CGB |  | 200000 |  | 200000 | 1 | 0 |  |  | Stalled | 0 |  | Lack of documentations(Title deed) | [12 empty] | The project is staled due Lack of documentations(Title deed)
5 | Construction of 1 NO. ECDE classroom at Mapera, Kamkuywa and Sulwe Primary Schools in Kamukuywa Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kamukuywa | 0.79304,34.79842 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 4500000 | 4454220 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 |  | 0 |  | 4454220 | 4454220 | stalled | Not yet started (0%). | 0 | Contract failed to undertake the works
42 | Construction Of Classroom At Sibakala Vtc In Kamukuywa Ward | Construction of VTC | To construct ECDE classroom and pit latrine providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kamukuywa | 0.74847,34.77391 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 1500000 | 1497850 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 0 | 0 | 0 | 1497850 | 1497850 |  | 0.5
43 | Construction Of 1no. Ecde Classroom & 2 Door Pit Latrine At Lukhome Primary In Kamukuywa Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kamukuywa |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 1500000 | 1495570 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 0 | 0 | 0 | 1495570 | 1495570 | Complete and not in use | 1
110 | Construction Of 1no. Classroom And 3 No. Door Toilet At Sulwe And Sibakala Vtc. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kamukuywa | 0.74847,34.77391 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3600000 | 3489270 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 0 | 0 | 0 | 3489270 | 3489270 | incomplete | 0.8
192 | Construction Of 01 No. Ecde And Toilet At Namasanda Primary School | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Kamukuywa |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 5500000 | 1594470 | 5500000 | County Government of Bungoma | N/A | 5500000 |  | 1594470 | 1 | 1594470 | 0 |  | complete and in use | 100.0%
3 | Upgrading of Kamukuywa Primary and Kitayi Primary Boreholes in Kamukuywa/ Kibingei Ward | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Kimilili | Kamukuywa | 0.79304,34.79842 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 6000000 | 5939220.88 | 5939220.88 | FLLOCA | N/A | 5939220.88 | 0 | 0 | 1 | 5939220.88 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
39 | Proposed Tree Growing Within Institutions In Luuya/Bwake, Matulo, Mihuu, Kamukuywa, And Naitiri/Kabuyefwe Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45452 | 45455 | 45455 | 5917500 | 5910500 | 5910500 | FLLOCA | IDA | 0 | 5910500 | 0 | 1 | 0 | 0 |  | Re-tendered | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
50 | Construction of Water project from Sulwe to Sango and Protection of 1no. Water spring in Kamukuywa ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; excavation; construction of wing walls, fixing of draw pipes and trenching of cut off drai | To enhance access to clean and safe drinking water | KM of Water pipeline extended and construction & protection of 1 water spring | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2500000 | 2427141.6 | 2427141.6 | CGB | N/A | 2427141.6 | 0 | 2427141.6 | 1 | 2427141.6 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
127 | Nabikoto water project PHASE 3 in Kamukuywa ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2500000 | 2375400 | 2375400 |  | N/A | 2375400 | 0 | 2375400 | 1 | 2375400 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
128 | Borehole Drilling And Upgrading At Makhonge Health Centre In Kamukuywa Ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4500000 | 4466232 | 4466232 |  | N/A | 4466232 | 0 | 4466232 | 1 | 4466232 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
146 | Lutaso water project (extension of pipeline and water kiosk) | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 3500000 | 3392188 | 3392188 |  | N/A | 3392188 | 0 | 3392188 | 1 | 0 | 3392188 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
147 | Nabikoto Project(rehabilitation,pipeline water kiosk and masonary tank) | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4500000 | 4362760 | 4362760 |  | N/A | 4362760 | 0 | 4362760 | 1 | 0 | 4362760 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
188 | LUTASO WATER PROJECT | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 6000000 | 5953381 | 5953381 |  | N/A | 5953381 | 0 | 5953381 |  | 3054222 | 2899159 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
324 | CONSTRUCTION OF CHESAMISI –MUKHUYU PIPELINE IN KAMUKUYWA WARD | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2496315 | 2496315 |  | N/A | 2496315 | 0 | 2496315 | 1 | 2496315 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
349 | Chesamisi Kamukuywa Water Project including a 50m3 Masonry tank. | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | KM of pipeline constructed and 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 8500000 | 8412112 | 8412112 |  | N/A | 8412112 | 0 | 8412112 | 1 | 8412112 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
441 | Construction of Chesamisi - Kamukuywa Water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works |  | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 10000000 | 9875090 | 9875090 |  | N/A | 9875090 | 0 | 9875090 | 1 | 9875090 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
537 | Chesamisi Kamukuywa Water Project including a 50m3 Masonry tank. | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed and construction of 1 water tank | 3110599 | Other Infrastructure &Civil Works | Kimilili | Kamukuywa |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 20000000 | 18287202 | 18287202 |  | N/A | 18287202 | 0 | 18287202 | 1 | 18287202 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Supply and Delivery of Fingerlings for farmers | Supply and Delivery of Fingerlings for farmers | To increase fish production and improve on food and nutrition security | Kgs of fish feeds purchased | 3110599 | Ward Based projects | Bumula/Kimilili | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44682 | 44684 | 18/2/2022 | 5000000 | 4797000 | 5000000 | County Government of Bungoma |  | 4797000 | 0 | 4797000 | 1 | 4797000 | 0 | 0 | Completed
| Purchase of seedlings for Samita- Kaborom SLM Project | Purchase of seedlings for Samita- Kaborom SLM Project | To enhance fruit production, productity and income generation | Seedlings purchased and distributed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon/Kimilili | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44784 | 45139 | 45079 |  | 1566800 | 1566800 | Development partner | IDA | 0 | 1566800 | 1566800 |  | 1566800 | 0 | 0 | Completed
| Purchase and installation of pond liners, water tanks and solar pump kits | Purchase and installation of pond liners, water tanks and solar pump kits for Samita -Kaborom SLM project | To control loss of water through infiltration | 1,165,117 pcs of pond liners purchased, delivered and installed | 2640503 | Other Capital grants and transfer (NARGIP) |  | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44959 | 44963 | 45266 |  | 4440000 | 4500000 | Development partner | IDA | 0 | 4440000 | 4440000 | 1 | 4440000 | 0 | 0 | Completed
19 | Construction of Modern Stalls and Shades at Kamukuywa Market. | of and at and Shades | Promotion of MSMEs | Mordern stalls and shades constructed | 1289356/2022-23 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Trade | Wells Trading Co. Ltd. | 2023/2024 |  | Ongoing | Ongoing and not in use |  |  |  | CGB | [8 empty] | The works are on schedule |  | 72
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye | [5 empty] | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
91 | Installation of 3 No solar powered flood lights and 3 No street lighta | of powered lights lights and |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Ms Pisonaz International limited | 2021/22 |  | Complete and in use |  | 4790400 |  |  | CGB
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A | [5 empty] | Kamukuywa |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kamukuywa |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights |  |  |  |  | Kimilili | Kamukuywa |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
73 | Installation of 1NO. Solar lights KAMUKUYWA POLICE POST | [5 empty] | Kimilili | Kamukuywa | 0.764860,34.786413 |  | Dept. of Trade |  | 2024/25 | [15 empty] | Completed
74 | Construction & protection of 4 NO water springs Namanda,Booster musina water spring,Mzee ndala water spring, Ndolelele water spring | [5 empty] | Kimilili | Kamukuywa | 0.7782,34.44730687 0.72363,34.453012876 0.88251,34.462109216 0.87955,34.77391 |  | Tourism, Environment,Natural Resources, Water and Climate Change |  | 2024/25 | [15 empty] | Completed
| Construction of one classroom at musembe ecde | [5 empty] | Kimilili | Kamukuywa | 0.80113,34.77978 |  | Early Childhood Development Education |  | 2014/15 | [15 empty] | Completed
| Installation of 5 NO of street lights at Namutokho | [5 empty] | Kimilili | Kamukuywa | 0.764860,34.786413 |  | Dept. of Trade |  | 2014/15 | [15 empty] | Completed
| Matisi primary ecde | [5 empty] | Kimilili | Kamukuywa | 0.88303,34.83016 |  | Early Childhood Development Education |  | 2017/18 | [15 empty] | Completed
| Kamukuywa ACK( MAPERA) ecde | [5 empty] | Kimilili | Kamukuywa | 0.79304,34.79842 |  | Early Childhood Development Education |  | 2024/25 | [15 empty] | stalled
| Street light sokomoko | [5 empty] | Kimilili | Kamukuywa | 0.79304,34.494858788 |  | Dept of trade |  | 2017/18 | [15 empty] | completed
| Laying of pipes from main tarmac road- matisi (sokomoko) | [5 empty] | Kimilili | Kamukuywa | 0.79304,34.49" |  | Tourism, Environment,Natural Resources, Water and Climate Change |  | 2018/19 | [15 empty] | stalled
| Periodic maintainance of sokomoko- matisi road(2.8km) | [5 empty] | Kimilili | Kamukuywa | 0.89304,34.47" |  | Roads, Infrastructute and Public Works |  | 2018/19 | [15 empty] | stalled
| Periodic maintainance of lurare-chalicha road | [5 empty] | Kimilili | Kamukuywa | 0.79304,34.49" |  | Roads, Infrastructute and Public Works |  | 2016/17 | [15 empty] | completed
| Purchased of medical equipment for makhonge health centre | [5 empty] | Kimilili | Kamukuywa | 0.82122,34.79678 |  | Public health & sanitation |  | 2021/22 | [15 empty] | completed
| Supply & delivery of fingerlings to farmers | [5 empty] | Kimilili | Kamukuywa | 0.82122,34.78697 |  | Livestock, Fisheries and Veterinary Services |  | 2021/22 | [15 empty] | completed
| Borehole Drilling And Upgrading At Makhonge Health Centre | [5 empty] | Kimilili | Kamukuywa | 0.82122,34.78698 |  | Tourism, Environment,Natural Resources, Water and Climate Change |  | 2022/23 | [15 empty] | completed
| Lutaso water project | [5 empty] | Kimilili | Kamukuywa | 0.8177,34.787029 |  | Tourism, Environment,Natural Resources, Water and Climate Change |  | 2021/22 | [15 empty] | incomplete
| Lutaso water project | [5 empty] | Kimilili | Kamukuywa | 0.83594,34.7912 |  | Tourism, Environment,Natural Resources, Water and Climate Change |  | 2021/22 | [15 empty] | incomplete
| Chesamisi Kamukuywa Water Project including a 50m3 Masonry tank. | [5 empty] | Kimilili | Kamukuywa | 0.82259,34.80728 |  | Tourism, Environment,Natural Resources, Water and Climate Change |  | 2014/15 | [15 empty] | stalled
| Periodic maintainance of makhonge- marofu road | [5 empty] | Kimilili | Kamukuywa | 0.823192,34.8112 |  | Roads, Infrastructute and Public Works |  | 2018/19 | [15 empty] | incomplete
| Periodic maintainance of makhonge- chalicha box culvert | [5 empty] | Kimilili | Kamukuywa | 0.81955,34.7975 |  | Roads, Infrastructute and Public Works |  | 2023/24 | [15 empty] | completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | [5 empty] | Kimilili | Kamukuywa | 0.81955,34.7976 |  | Agriculture and irrigation |  | 2022/23 | [15 empty] | completed
| Proposed construction of 4 boda boda shed at makhonge stage | [5 empty] | Kimilili | Kamukuywa | 0.81955,34.7977 |  | Trade |  | 2024/25 | [15 empty] | completed
9 | Erection and completion of Maternity wing at Tulienge dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completion |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 28-2-2024 |  |  | 2000000 | 1967390 | 1967390 | CGB |  | 1967390 | 0 | 0 | 0 | 0 | 1880920 | 1967390 | On-going | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
63 | proposed erection and completion of maternity wing at Lwakhakha dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Sirisia | Lwandanyi | 0.789087,34.379415 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 45628 |  |  | 4000000 | 3939050 | 3939050 | CGB |  | 3939050 | 0 | 0 | 0 | 0 |  | 3939050 | complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
167 | Construction Of Septic Tank At Lwandanyi Dispensary | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | Septic tanks constructed |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1050000 | 1161650 | 1161650 | CGB |  | 1161650 | 0 | 1161650 | 1 | 1161650 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
168 | Construction Of Maternity Wing At Karosisndet Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Sirisia | Lwandanyi | 0.74446,34.4391 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1963330 | 1963330 | CGB |  | 1963330 | 0 | 878500 | 0.44745 | 878500 |  | 1084830 | Complete and in use | [6 empty] | No | complete | Financial | Yes
169 | Renovation Of Health Facility And Staff Quarters At Lwakhakha Dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Staff quarters erected and renovated |  |  | Sirisia | Lwandanyi | 0.789087,34.379415 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1034983 | 1292924 | 1292924 | CGB |  | 1292924 | 0 | 1163037 | 0.89954 | 1163037 |  | 129887 | Complete and in use | [6 empty] | No | complete | Financial | Yes
232 | Construction Of Public Toilets At Wamono And Tulienge Market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Public toilets constructed |  |  | Sirisia | Lwandanyi | 0.764613,34.453373 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 800000 | 876200 | 876200 | CGB |  | 876200 | 0 | 876200 | 1 | 876200 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
385 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
554 | Periodic Maintenance of Lurare - Bishop Wabukala Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43972 |  | 5111401 | 5111401 | 5111401 | County Government of Bungoma |  | 5111401 |  | 5111401 |  | 5111401 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
555 | Upgrading of Tamulega-Malakisi Bridge (River Malakisi) | Road improvement works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43970 | 44001 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
556 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43964 |  | 5111401 | 5111401 | 5111401 | County Government of Bungoma |  | 5111401 |  | 5111401 | 100.0% | 5111401 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
831 | Periodic Maintenance of Wamono - Khabukoya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44332 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 |  | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
832 | Periodic Maintenance of Tulienge - Nasala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44335 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 |  | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
833 | Periodic Maintenance of Namosi - Bishop Wabukala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
834 | Construction of Arch. Bishop Wabukala - Namwesi Twin Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
835 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44329 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 | 99.84% | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1146 | Periodic Maintenance of Bukayabi - Kaburweti - Namutokholo - Lwakhakha Border Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi | 0.798738,34.402095 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44705 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1147 | Periodic Maintenance of Katomei Junction - Changara Drift Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44699 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1148 | Periodic Maintenance of Kibindoi - Makwere - Kapkara - Lwandanyi Miracle Church Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44692 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1149 | Periodic Maintenance of Nambuya - Tamulega Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44697 | 44728 | 2317424.8 | 2317424.8 | 2317424.8 | County Government of Bungoma |  | 2317424.8 |  | 2317424.8 |  | 2317424.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1150 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44702 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 | 99.62% | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1151 | Routine Maintenance Of Nambuya - Tamulega Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44700 |  | 2317424.8 | 2317424.8 | 2317424.8 | County Government of Bungoma |  | 2317424.8 |  | 2317424.8 | 100.0% | 2317424.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1448 | Periodic Maintenance of St. Paul Lwandanyi - Namundi Tarmac Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi | 0.76114,34.40162 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45056 |  | 3643608 | 3643608 | 3643608 | County Government of Bungoma |  | 3643608 |  | 3643608 |  | 3643608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1449 | Periodic Maintenance of Lwakhakha - Township Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi | 0.77924017,34.39197600 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45066 |  | 4487867 | 4487867 | 4487867 | County Government of Bungoma |  | 4487867 |  | 4487867 |  | 4487867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1450 | Periodic Maintenance of Mufungu - Namang'Ofulo - Tulienge - Namubila Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45058 |  | 6895712 | 6895712 | 6895712 | County Government of Bungoma |  | 6895712 |  | 6895712 |  | 6895712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1451 | Upgrading of Machakha- Tinga Moja | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45068 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1452 | Periodic Maintenance of Lwakhakha - Township Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi | 0.77924017,34.39197600 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45058 |  | 4487867 | 4487867 | 4487867 | County Government of Bungoma |  | 4487867 |  | 4487867 | 99.87% | 4487867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1453 | Periodic Maintenance of Mfungu - Namang'Ofulo - Tulienge - Namubila Primary Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45068 |  | 6895712 | 6895712 | 6895712 | County Government of Bungoma |  | 6895712 |  | 6895712 | 100.0% | 6895712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1454 | Periodic Maintenance of St. Pauls Lwandanyi - Namundi Tarmac Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi | 0.79147908,34.39424843 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45064 |  | 3643608 | 3643608 | 3643608 | County Government of Bungoma |  | 3643608 |  | 3643608 | 82.75% | 3643608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1685 | Periodic Maintenance of Katomei - Allakar - Korosiondet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi | 0.77064,34.40356 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45427 |  | 4168808 | 4168808 | 4168808 | County Government of Bungoma |  | 4168808 |  | 4168808 |  | 4168808 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1686 | Periodic Maintenance of Kisiero - Wakenda - Kakala Primary - Munialo - Wabomba - Tarmac Road - Oriama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45422 |  | 4092480 | 4092480 | 4092480 | County Government of Bungoma |  | 4092480 |  | 4092480 |  | 4092480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1687 | Periodic Maintenance of Sitabicha - Bukokholo Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45436 |  | 4566282 | 4566282 | 4566282 | County Government of Bungoma |  | 4566282 |  | 4566282 |  | 4566282 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1688 | Periodic Maintenance of Malakisi Health Centre - Rwatama - Malakisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45427 | 45458 | 3112744 | 3112744 | 3112744 | County Government of Bungoma |  | 3112744 |  | 3112744 |  | 3112744 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1689 | Periodic Maintenance of Malakisi Health Center-Rwatama-Malakisi Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45436 |  | 3112744 | 3112744 | 3112744 | County Government of Bungoma |  | 3112744 |  | 3112744 | 99.96% | 3112744 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1690 | Periodic Maintenance of Katomei - Allakar - Korosiondet Sda Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi | 0.77064,34.40356 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45434 |  | 4168808 | 4168808 | 4168808 | County Government of Bungoma |  | 4168808 |  | 4168808 | 99.97% | 4168808 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1691 | Periodic Maintenance of Kisiero - Wekunda - Kakala - Tarmac - Oriama Road In Lwadanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45430 |  | 4092480 | 4092480 | 4092480 | County Government of Bungoma |  | 4092480 |  | 4092480 | 100.0% | 4092480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1692 | Periodic Maintenance of Sitabicha - Bukokholo Junction Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45433 |  | 4566282 | 4566282 | 4566282 | County Government of Bungoma |  | 4566282 |  | 4566282 | 100.0% | 4566282 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
29 | Proposed completion of 1no.ECDE classroom at Marakaru, Londo and Namundi primary schools | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi | 0.740533,34.451932 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3500000 | 3346250 | 3500000 | County Government of Bungoma | N/A | 3500000 | 0 | 3346250 | 1 | 3346250 | 0 | 0 | Completed
51 | Proposed Erection And Completion Works Of 1no. Ecde Classroom And 2no. Door Pit Latrine At Lwakhakha And Wamono Primary Schools In Lwandanyi Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi | 0.78898,34.3794 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 4000000 | 3913160 | 4000000 | County Government of Bungoma | N/A | 4000000 | 0 | 2469174.55 | 0.63099 | 2469174.55 | 1443985.45 | 1443985.45 | complete and in use | 1
116 | Completion Of 1 No. Ecde Classroom At Mukhuyu Primary School | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 1000000 | 1292600 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 0 | 0 | 0 | 1292600 | 1292600 | ongoing. At ring beam. | 0.7
117 | Construction Of 1 No. Ecde Classroom At Marakaru, Londo And Namundi Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi | 0.78729658,34.38966138 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4300000 | 4244630 | 4300000 | County Government of Bungoma | N/A | 4300000 | 0 | 876038.95 | 0.20639 | 876038.95 | 3368591.05 | 3368591.05 | complete and in use | 1
147 | Proposed Erection And Completion Of 1 No. Ecde At Kibindoi Primary School In Lwandanyi Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1500000 | 1497000 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1497000 | 1 | 1497000 | 0 | 0 | complete and in use | 1
174 | Construction Of 08 Ecde Classrooms At Kaburuet, Chebukunyi, Kaprot, Namubila, Namawanga, Tulienge, Kibindoi, And Kapendo Primary Schools | Construction of ECDE classroom and VTC workshop | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi | 0.793619,34.395271 0.781981,34.383626 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 8200000 | 8473660.8 | 8200000 | County Government of Bungoma | N/A | 8200000 | 0 | 8473660.8 | 1 | 8473660.8 | 0 |  | complete and in use | 1
175 | Purchase Of 525 Desks For Eight Ecde Classes | Construction of toilets | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 1000000 | 1000000 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 1000000 | 1 | 1000000 | 0 |  | complete and in use | 1
64 | Drilling of Borehole at Kakala Primary School | site identification; geological survey;drilling development(entails casing and gravel use);construction of borehole chamber; construction of water points. | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2000000 | 1999376 | 1999376 | CGB | N/A | 1999376 | 0 | 1999376 | 1 | 1999376 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
174 | Upgrading of Lurare/Namwesi borehole | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi | 0.70151,34.4477 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4000000 | 3989124 | 3989124 |  | N/A | 3989124 | 0 | 3989124 | 1 | 3989124 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
198 | DRILLING AND EQUIPPING OF BOREHOLE IN TORORO PRIMARY SCHOOL | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1800000 | 1679680 | 1679680 |  | N/A | 1679680 | 0 | 1679680 | 1 | 1679680 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
218 | REHABILITATION AND EXTENSION OF CHESIKAKI-SIRISIA-BUMULA WATER PROJECT PHASE I | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 34000000 | 33391751.4 | 33391751.4 |  | N/A | 33391751.4 | 0 | 33391751.4 | 1 | 23831829 | 9559922 | 0 | Work in progress | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
221 | DRILLING OF 4NO. BOREHOLES IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 4 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi | 0.6824,34.4288 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 6000000 | 5877482 | 5877482 |  | N/A | 5877482 | 0 | 5877482 | 1 | 2938741 | 2938741 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
284 | DRILLING OF NASALA AND LURARE BOREHOLES IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3700000 | 3540800 | 3540800 |  | N/A | 3540800 | 0 | 3540800 | 1 | 3540800 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
285 | DRILLING OF MACHAKHA BOREHOLE IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi | 0.755727,34.438842 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1782000 | 1782000 |  | N/A | 1782000 | 0 | 1782000 | 1 | 1782000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
286 | REHABILITATION OF 3 NO. BOREHOLES AND CONSTRUCTION OF 10 NO. WATER SPRINGS IN LWANDANYI WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 Boreholes rehabilitated and 10 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi | 0.82346313,34.43212967 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2499921 | 2499921 |  | N/A | 2499921 | 0 | 2499921 | 1 | 2499921 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
385 | Lwandanyi borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 600000 | 556225 | 556225 |  | N/A | 556225 | 0 | 556225 | 1 | 556225 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
454 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2597616 | 2597616 |  | N/A | 2597616 | 0 | 2597616 | 1 | 2597616 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
545 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points; | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 10000000 | 9277200 | 9277200 |  | N/A | 9277200 | 0 | 9277200 | 1 | 9277200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
561 | Protection of 7 water springs and Construction of 3 Roof catchments | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; construction of roof catchment and storage tank with water points | To enhance access to clean and safe drinking water | 7 water springs constructed and 3 roof catchments | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi | 0.82346313,34.43212967 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2498640 | 2498640 |  | N/A | 2498640 | 0 | 2498640 | 1 | 2498640 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
562 | Drill a borehole at Kapkara | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works |  | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2224900 | 2224900 |  | N/A | 2224900 | 0 | 2224900 | 1 | 2224900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
3 | Construction of Lwandanyi ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Lwandanyi ward office constructed | 3111504 | Construction of non- residential buildings | Sirisia | Lwandanyi | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 42879 | 9500000 | 9039375 | 9500000 | County Government of Bungoma | - | 9039375 | - | 9039375 | 1 | 9039375 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Rehabilitation of Kapkara Dam | Rehabilitation of Kapkara Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 10000000 | 7675000 | 8000000 | County Government of Bungoma |  | 7675000 |  | 7675000 | 1 | 7675000 | 0 | 0 | Completed
| Construction of farm ponds at Kabkara watershed | Construction of 20no. farm ponds at Kabkara watershed | To store water for irrigation and flood control | 20 farm ponds constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | [5 empty] | 4999144 | 5000000 | Development partner | IDA | 0 | 4999144 | 4999144 |  | 4999144 | 0 | 0 | Completed
| Construction of Kabkara Earth Dam | Construction of Kabkara Earth Dam | To store water for irrigation and flood control | 1 dam constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Sirisia | Lwandanyi | 0.766667,34.4167 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 24/5/2022 | 24/11/2022 | 21/3/2024 |  | 50866669 | 50866669 | Development partner | IDA | 0 | 50866669 | 50866669 |  | 50866669 | 0 | 0 | Complete
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
96 | Installation of 2 No high mast flood lights | of lights No high | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Ms Emricon Limited | 2021/22 |  | Complete and in use |  | 1900000 |  |  | CGB
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Lwandanyi |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
123 | Construction of 3 no. Mama Mboga sheds | sheds of 3 no | [5 empty] | Lwandanyi |  |  |  | Dry Port | 2018/19 |  | Complete |  | 1595174 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Lwandanyi |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
133 | Construction of 8 No. Boda Boda Sheds | heds of 8 No | [5 empty] | Lwandanyi | 0.74446,34.4391 |  |  | M/S Mamofa Construction Company Limited P.O Box 41658 Bungoma | 2017/18 |  |  |  | 2756979 |  |  | CGB
134 | Renovation of Lwakhakha market | [6 empty] | Lwandanyi |  |  | Dept of Trade | Adept General Contractors | 2016/17 |  | Complete |  | 24409776 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi | 0.77525,34.39416 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi | 0.7196,34.4143 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi | 0.7196,34.4143 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi | 0.7196,34.4143 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi | 0.7196,34.4143 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
51 | Erection and completion works for maternity wing at Mukhweya Dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings erected and completed |  |  | Kabuchai | Chwele/Kabuchai | 0.677194 ,34.579162 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 13/2/2024 |  |  | 5000000 | 4814556 | 4814556 | CGB |  | 4814556 | 0 | 2482770.4 | 0.51568 | 2482770.4 |  | 2331785.6 | On-going | 55 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
76 | Renovation/Completion And Construction Of Maternity Phase mukhweya Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Dispensaries renovated/completed |  |  | Kabuchai | Chwele/Kabuchai | 0.677194 ,34.579162 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 3000000 | 2911750 | 2911750 | CGB |  | 2911750 | 0 | 0 | 0 | 0 |  | 2911750 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
123 | Upgrading of Chwele Market Roads | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42746 | 42871 |  | 36106026.17 | 36106026.17 | 36106026.17 | County Government of Bungoma |  | 36106026.17 |  | 36106026.17 | 100.0% | 36106026.17 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
161 | Periodic Maintenance of Namilama - Walukaya - Musese Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.73354,34.57564 0.73264,34.57477 0.73264,34.57477 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43243 |  | 6720010.5 | 6720010.5 | 6720010.5 | County Government of Bungoma |  | 6720010.5 |  | 6720010.5 |  | 6720010.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
162 | Periodic Maintenance of Roads In Chwele Kabuchai Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.7351,34.57852 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43242 |  | 6720010.5 | 6720010.5 | 6720010.5 | County Government of Bungoma |  | 6720010.5 |  | 6720010.5 | 95.78% | 6720010.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
313 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai | 0.722057,34.582211 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
314 | Periodic Maintenance of Yoram - Namilama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43606 | 43637 | 6529698 | 6529698 | 6529698 | County Government of Bungoma |  | 6529698 |  | 6529698 |  | 6529698 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
315 | Construction of Muyayi-Nangwe Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43482 | 43602 |  | 11024129.6 | 11024129.6 | 11024129.6 | County Government of Bungoma |  | 11024129.6 |  | 11024129.6 |  | 11024129.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
316 | Upgrading of Drainage Works At Chwele Marketd | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.736336,34.580426 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43608 |  | 4988000 | 4988000 | 4988000 | County Government of Bungoma |  | 4988000 |  | 4988000 |  | 4988000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
317 | Periodic Maintenance of Roads In Chwele Kabuchali Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.736336,34.580426 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43489 | 43606 |  | 6529698 | 6529698 | 6529698 | County Government of Bungoma |  | 6529698 |  | 6529698 | 97.06% | 6529698 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
503 | Periodic Maintenance of Namilama - Musese C33 Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43975 |  | 5860294 | 5860294 | 5860294 | County Government of Bungoma |  | 5860294 |  | 5860294 |  | 5860294 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
504 | Periodic Maintenance of Lukhuna - Misri Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.716948,34.589564 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43969 | 44000 | 8027316 | 8027316 | 8027316 | County Government of Bungoma |  | 8027316 |  | 8027316 |  | 8027316 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
505 | Periodic Maintenance of Khachonge - Chwele Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43962 |  | 6919458 | 6919458 | 6919458 | County Government of Bungoma |  | 6919458 |  | 6919458 |  | 6919458 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
506 | Periodic Maintenance of Khachonge - Chwele Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43965 |  | 6919458 | 6919458 | 6919458 | County Government of Bungoma |  | 6919458 |  | 6919458 |  | 6919458 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
507 | Periodic Maintenance of Roads In Chwele-Kabuchai Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43974 |  | 8027316 | 8027316 | 8027316 | County Government of Bungoma |  | 8027316 |  | 8027316 | 99.86% | 8027316 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
508 | Periodic Maintenance of Namila - Musese C33 Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43965 |  | 5860294 | 5860294 | 5860294 | County Government of Bungoma |  | 5860294 |  | 5860294 | 97.97% | 5860294 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
732 | Periodic Maintenance of Lufutu - Nakitumba - Sengeteti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.73268,34.57476 0.73285,34.575092 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44335 |  | 5466384 | 5466384 | 5466384 | County Government of Bungoma |  | 5466384 |  | 5466384 |  | 5466384 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
733 | Periodic Maintenance of Marakaru - Namosi - Kisiwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44337 |  | 13376569 | 13376569 | 13376569 | County Government of Bungoma |  | 13376569 |  | 13376569 |  | 13376569 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
734 | Periodic Maintenance of Chwele - Makhonge - Namwela - Menu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai | 0.763224,34.575803 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44331 |  | 11875804.5 | 11875804.5 | 11875804.5 | County Government of Bungoma |  | 11875804.5 |  | 11875804.5 |  | 11875804.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
735 | Periodic Maintenance of Chwele - Makhonge - Namwela - Menu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44339 |  | 11875804.5 | 11875804.5 | 11875804.5 | County Government of Bungoma |  | 11875804.5 |  | 11875804.5 |  | 11875804.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
736 | Periodic Maintenance of Lurende - Khachonge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44338 |  | 4389440 | 4389440 | 4389440 | County Government of Bungoma |  | 4389440 |  | 4389440 |  | 4389440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
737 | Periodic Maintenance of Lurende - Khachonge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44334 |  | 4389440 | 4389440 | 4389440 | County Government of Bungoma |  | 4389440 |  | 4389440 |  | 4389440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
738 | Upgrading of Sikusi - Mukhweya - Lurende | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai | 0.679250,34.576274 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44334 |  | 2787373.5 | 2787373.5 | 2787373.5 | County Government of Bungoma |  | 2787373.5 |  | 2787373.5 |  | 2787373.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
739 | Periodic Maintenance of Chebukaka - Mpakani - Terem Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44329 |  | 6471680 | 6471680 | 6471680 | County Government of Bungoma |  | 6471680 |  | 6471680 |  | 6471680 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
740 | Periodic Maintenance of Chebukaka - Mpakani - Terem Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44327 |  | 6471680 | 6471680 | 6471680 | County Government of Bungoma |  | 6471680 |  | 6471680 |  | 6471680 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
741 | Periodic Maintenance of Roads In Chwele Kabuchai Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44339 |  | 5466384 | 5466384 | 5466384 | County Government of Bungoma |  | 5466384 |  | 5466384 | 99.67% | 5466384 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1063 | Periodic Maintenance of Sikusi - Khalaba - Coffee Factory - Namilama - Lwanda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.67943,34.56893 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44692 | 44723 | 16240000 | 16240000 | 16240000 | County Government of Bungoma |  | 16240000 |  | 16240000 |  | 16240000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1064 | Periodic Maintenance of Lwanda - Wamunyokoli - Kibichori Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44695 | 44726 | 16240000 | 16240000 | 16240000 | County Government of Bungoma |  | 16240000 |  | 16240000 |  | 16240000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1065 | Periodic Maintenance of Chenjeni - St. Walumoli - Madisi Market Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44703 | 44734 | 3733170 | 3733170 | 3733170 | County Government of Bungoma |  | 3733170 |  | 3733170 |  | 3733170 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1066 | Periodic Maintenance of Roads In Chwele Kabuchai Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44697 |  | 16240000 | 16240000 | 16240000 | County Government of Bungoma |  | 16240000 |  | 16240000 | 12.32% | 16240000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1379 | Periodic Maintenance of William Mapanga - West Special School - Chwele Vtc - Namake - Nabulobe River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.7351,34.57852 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45068 | 45099 | 8681407 | 8681407 | 8681407 | County Government of Bungoma |  | 8681407 |  | 8681407 |  | 8681407 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1380 | Periodic Maintenance of William Mapanga - West Special School - Chwele Vtc - Namake Vtc - Nanabulobe River Road In Chwele/ Kabuchai Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.7351,34.57852 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45070 |  | 8681407 | 8681407 | 8681407 | County Government of Bungoma |  | 8681407 |  | 8681407 | 99.91% | 8681407 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1635 | Construction of Chwele Coffee Factory Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.73477,34.57862 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45431 |  | 6783471 | 6783471 | 6783471 | County Government of Bungoma |  | 6783471 |  | 6783471 |  | 6783471 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1636 | Periodic Maintenance of Mukhweya - Namakhele - Chenane Road In Chwele/Kabuchai Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.679213,34.577462 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45424 |  | 9344496 | 9344496 | 9344496 | County Government of Bungoma |  | 9344496 |  | 9344496 | 100.0% | 9344496 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1637 | Construction of Chwele Coffee Factory Box Culvert In Chwele/Kabuchai Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kabuchai | Chwele/Kabuchai | 0.745956,34.577976 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45430 |  | 6783471 | 6783471 | 6783471 | County Government of Bungoma |  | 6783471 |  | 6783471 | 99.98% | 6783471 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
4 | Construction of 1 NO. ECDE classroom at Makhonge Primary School and Completion of an ECDE classroom at Makhonge primary School in Chwele/Kabuchai Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Chwele/Kabuchai |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 2920703 | 2791500 | 2920703 | County Government of Bungoma | N/A | 2920703 | 0 |  | 0 |  | 2791500 | 2791500 | Completed
73 | construction of 1n0. ECDE Classroom at Nakitumba and Lubembe primary schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Chwele/Kabuchai |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3000000 | 3000860 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 3000860 | 1 | 3000860 | 0 | 0 | ongoing and not in use | 0.9
106 | Construction Of 1 No. Ecde Classroom At Namilama Deb, Kibichori,Sanandiki S.A And Sandiki Fym Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Chwele/Kabuchai | Nakitomba pri. (0.73268,34.57467) Lubembe pri. (0.773285,34.57502) Namilama DEB pri. (0.73354,34.57564) Kibichoriy pri. (0.73264,34.576477) Sanandiki SA pri.(0.73262,34.5749) Nalondo DEBpri(0.73261,34.5749)Wabukhonyi pri. (o.73262,34.57493) Makhongesa pri. (0.77326234.57492) Mukhweya pri. (0.73262,34.57492) | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4800000 | 4607840 | 4800000 | County Government of Bungoma | N/A | 4800000 | 0 | 1814825.9 | 0.39386 | 1814825.9 | 2793014.1 | 2793014.1 | complete and in use | 1
135 | Erection And Completion Of 1 No. Ecde At Sikusi, Nalondo And Wabukhonyi Primary Schools In Chwele Kabuchai Ward | Construction of ECDE classroom |  | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Chwele/Kabuchai |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 4506013.66 | 4000020 | 4506013.66 | County Government of Bungoma | N/A | 4506013.66 | 0 | 3815292.6 | 0.95382 | 3815292.6 | 184727.4 | 184727.4 | complete and in use | 1
170 | Construction Of 1 No Ecde And Toilets At Makhonge S.A Primary | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Chwele/Kabuchai |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 1200000 | 1175793.4 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 1175793.4 | 1 | 1175793.4 | 0 |  | stalled. | 0.4
189 | Erection And Complition Of 1 Classroom At mukhweya, Lufutu Sa, Matibo Fym, Sirwa Deb, nairumbi deb and walukaya deb primary schools in chwele ward, | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | Chwele/Kabuchai | 0.7328,34.57379 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 7000000 | 6961000 | 7000000 | County Government of Bungoma | N/A | 7000000 |  | 6961000 | 1 | 6961000 | 0 |  | complete and in use | 100.0%
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | [7 empty] | FLLOCA | N/A |  | 0 |  | 1 |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
33 | Proposed Rehabilitation Of River Khalaba, Khalaba Dam And River Chwele In Tuuti/Marakaru And Bukembe West Wards | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai | 0.67943,34.56893 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5916000 | 5715000 | 5715000 | FLLOCA | IDA | 0 | 5715000 | 0 | 1 | 0 | 0 |  | On going and not in use | 0.45 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
34 | Proposed Rehabilitation Of Rivers Khalaba B, Chwele, Wabukhonyi And Chwele Dams In Chwele/Kabuchai Ward In Kabuchai Sub County | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai | 0.67943,34.56893 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5916000 | 5552000 | 5552000 | FLLOCA | IDA | 0 | 5552000 | 0 | 1 | 0 | 0 |  | On going and not in use | 0.3 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
41 | Proposed Supply And Installation Of Combustion Chamber For Improved Stoves And Energy Centre For Research On Training Of Energy Technologies In Maraka And Kabuchai | 1.construction of combustion chamber (Kiln) for production of clean energy saving jikos. 2.Provision and Assemblying of production materials for the two burner / saving jikos. 3.Training of youths and women on installation of single /two burner jikos to the community. | To promote climate change mitigation and adaptation | Construction of combustion chambers in 2 wards | 2640599 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai | 0.73482,34.57688 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 6000000 | 5955480 | 5955480 | FLLOCA | IDA | 0 | 5955480 | 0 | 1 | 0 | 0 |  | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
48 | Chwele Kabuchai Extension on Koica 2 | Trenching and laying of water pipeline | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai | 0.7351,34.57852 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3500000 | 3444272 | 3444272 | CGB | N/A | 3444272 | 0 | 3444272 | 1 | 3444272 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
58 | Chwele Kabuchai Extension on Koica 1 | Trenching, pipelaying; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 2640503 | Other Capital Grants and Transfers | Kabuchai | Chwele/Kabuchai | 0.73553,34.57866 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3500000 | 2728320 | 2728320 | CGB | N/A | 2728320 | 0 | 2728320 | 1 | 2728320 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
121 | Drilling of 2no. boreholes with handpump installation and upgrading of Farisi water project | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled and 1 water project upgraded | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai | 0.73489,34.57852 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 7000000 | 6831820 | 6831820 |  | N/A | 6831820 | 0 | 6831820 | 1 | 6831820 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
184 | REHABILITATION OF 2 NO. BOREHOLES IN SIKUSI AND SANANDIKI AND INSTALLATION OF HAND PUMPS | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai | 0.73479,34.57689 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1000000 | 919980 | 919980 |  | N/A | 919980 | 0 | 919980 | 1 | 919980 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
230 | DRILLING OF LUTUFU BOREHOLE IN CHWELE/KABUCHAI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai | 0.7327,34.57486 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2000000 | 1895250 | 1895250 |  | N/A | 1895250 | 0 | 1895250 | 1 | 1895250 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
278 | DRILLING OF MATIBO PRIMARY BOREHOLE WATER PROJECT IN CHWELE KABUCHAI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai | 0.7327,34.57486 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2179640 | 2179640 |  | N/A | 2179640 | 0 | 2179640 | 1 | 2179640 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
340 | SUPPLY OF CHEMICALS |  | To enhance access to clean and safe drinking water |  | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai | 0.73726,34.57512 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 600000 | 551840 | 551840 |  | N/A | 551840 | 0 | 551840 | 1 | 551840 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
491 | Construction of 5Roof catchment and 50m3 Masonry tank. | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1468610 | 1468610 |  | N/A | 1468610 | 0 | 1468610 | 1 | 1468610 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
492 | Kabuchai Community Water Project including 50m3 storage tank | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed and tank constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | Chwele/Kabuchai |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 8500000 | 8203321.52 | 8203321.52 |  | N/A | 8203321.52 | 0 | 8203321.52 | 1 | 8203321.52 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Construction of poultry House Chwele | Construction of 1 poultry House at Chwele | To enhance poultry production and increase household incomes | 1 Poultry House constructed at Chwele | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73477,34.57862 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 41914 | 41919 | 23/5/2014 | 15000000 | 10651630.4 | 11000000 | County Government of Bungoma |  | 10651630.4 |  | 10651630.4 | 1 | 10651630.4 | 0 | 0 | Completed
| Supply and delivery of Slaughtrer House Equipment | Supply and delivery of assorted slaughtrer House equipment | To enhance efficiency and hygiene at the slaughter house | Assorted slaughter House equipment supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Kabuchai | Chwele/Kabuchai | 0.73477,34.57862 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 20/1/2014 | 20/4/2014 | 41739 | 5500000 | 5280570 | 5500000 | County Government of Bungoma |  | 5280570 |  | 5280570 | 1 | 5280570 | 0 | 0 | Completed
| Supply of Refrigerators Coolers and Fridge | Supply of Refrigerators Coolers and Fridge for Chwele Slaughterhouse | To enhance milk production, productivity, value addition and income among the farmers | 1 Refrigerator coolers and fridge supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 20/1/2014 | 20/4/2014 | 41752 | 3000000 | 2583900 | 2,600,00 | County Government of Bungoma |  | 2583900 |  | 2583900 | 1 | 2583900 | 0 | 0 | Completed
| Construction of Lagoons | Construction of Lagoons at Chwele Chicken Slaughter House | To treat waste water by using natural processes | 3 Lagoons constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42314 | 42040 | 15000000 | 10993983.52 | 10993983.52 | County Government of Bungoma |  | 10993983.52 |  | 10993983.52 | 1 | 10993983.52 | 0 | 0 | Completed
| Supply Of Monosex Fingerlings | Supply of1500 Monosex Fingerlings | To increase fish production and improve on food and nutrition security | 1500 Monosex fingerlings supplied | 2211023 | Supplies for production | Kabuchai | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 27/3/2015 | 5500000 | 1375000 | 1500000 | County Government of Bungoma |  | 1375000 |  | 1375000 | 1 | 1375000 | 0 | 0 | Completed
| Supply of hormones for Chwele Fish Farm | Supply of hormones for Chwele Fish Farm | To increase fish production and improve on food and nutrition security | 100 bottles of 10ml Hormones supplied for Chwele Fish Farm | 2211023 | Supplies for production | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 28/3/2015 | 6000000 | 1000000 | 1000000 | County Government of Bungoma |  | 1000000 |  | 1000000 | 1 | 1000000 | 0 | 0 | Completed
| Construction of Lagoon at Chwele Slaughter House | Construction of Lagoon and external works at Chwele Slaughter House | To treat waste water by using natural processes, | 1 lagoon constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73579,34.57862 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 18/2/2017 | 18/5/2017 | 43013 | 5000000 | 3700000 | 3700000 | County Government of Bungoma |  | 3700000 | 0 | 3700000 | 1 | 3700000 | 0 | 0 | Completed
| Construction of Slaughter House | Construction of chicken Slaughter House | To ensure quality and safety of meat | 1 slaughterhouse constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/2/2017 | 15/6/2017 | 28/4/2017 | 15000000 | 13362909 | 13362909 | County Government of Bungoma |  | 13362909 | 0 | 13362909 | 1 | 13362909 | 0 | 0 | Completed
| Supply of Pond Liners | Supply of 7,900 square metres of Pond Liners | To control loss of water through infiltration | 7,900 square metres of Pond liners supplied | 2211023 | Supplies for production | Kabuchai | Chwele/Kabuchai | 0.73477,34.57862 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 42952 | 8000000 | 5550000 | 5550000 | County Government of Bungoma |  | 5550000 | 0 | 5550000 | 1 | 5550000 | 0 | 0 | Completed
| Supply of Fingerlings | Supply of 370,000 Fingerlings | To increase fish production and improve on food and nutrition security | 370,000 Fingerlings purchased and delivered | 2211023 | Supplies for production | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 42952 | 8000000 | 999900 | 999900 | County Government of Bungoma |  | 999900 | 0 | 999900 | 1 | 999900 | 0 | 0 | Completed
| Supply of Slaughter House Equipment | Supply of assorted equipment for Slaughter House | To ensure quality and safety of meat | Assorted equipment supplied | 2211007 | Agricultural materials, supplies and small equipment | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 27/5/2017 | 20000000 | 17230000 | 17230000 | County Government of Bungoma |  | 17230000 | 0 | 17230000 | 1 | 17230000 | 0 | 0 | Completed
| Drilling of Borehole and supply of water pipes at Chwele Slaughter House | Drilling of Borehole at Chwele Slaughter House | To supply water for the operations of the slaughter house | 1 borehole drilled and pipes laid | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73477,34.57862 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 28/5/2017 | 5000000 | 2251100 | 2500000 | County Government of Bungoma |  | 2251100 | 0 | 2251100 | 1 | 2251100 | 0 | 0 | Completed
| Completion of Chwele Chicken Slaughterhouse | Completion of Chwele Chicken Slaughterhouse | To enhance inslme generation among dairy farmers | 1 chicken slaughter house completed in Chwele | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73477,34.57862 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 |  | 20000000 | 17000000 | 17000000 | County Government of Bungoma |  | 17000000 | 0 | 17000000 | 1 | 17000000 | 0 | 0 | Completed
| Purchase and installation of weigh bridges | Purchase and Installation of weigh bridges at Musese and Chesikaki Coffee Milling Plants | To weigh incoming and outgoing coffee for inventory control and sales purposes | 2 weigh bridges purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Kabuchai | Chwele/Kabuchai | 0.73478,34.57864 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 43313 | 43316 | 30/3/2018 | 20000000 | 18000000 | 18000000 | County Government of Bungoma |  | 18000000 | 0 | 18000000 | 1 | 18000000 | 0 | 0 | Completed
| Construction of a coffee warehouse/bean store | Construction of a coffee warehouse/bean store at Mt. Elgon Coffee Mill and Musese coffee mill | To enhance instme generation among dairy farmers | 2 Coffee warehouse/bean store constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.734781,34.57864 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 43435 | 43440 | 42648 | 18000000 | 18000000 | 18000000 | County Government of Bungoma |  | 18000000 | 0 | 18000000 | 1 | 18000000 | 0 | 0 | Completed
| Construction of a Coffee Mill Warehouse at Musese Coffee Mill | Construction of a Coffee Mill Warehouse at Musese Coffee Mill | To enhance inMime generation among dairy farmers | 1 Coffee Mill Warehouse constructed at Musese Coffee Factory | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.734781,34.57864 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 27/4/2019 | 27/10/2019 | 43530 | 10000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 | 0 | 6000000 | 1 | 6000000 | 0 | 0 | Completed
| Construction of Recirculating Aquaculture () System at Chwele Fish Farm | Construction of Recirculating Aquaculture (RAS) System at Chwele Fish Farm | To increase fish production and improve on food and nutrition security | 1 Recirculating Aquaculture system constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44105 | 44110 | 22/4/2020 | 5000000 | 2671040 | 2500000 | County Government of Bungoma |  | 2671040 | 0 | 2671040 | 1 | 2671040 | 0 | 0 | Completed
| Purchase and delivery of Coffee seedlings | Purchase and delivery of 650kgs of Coffee seedlings | To promote coffee production and income generation | 650kgs of coffee seedlings purchased and delivered | 3111301 | Purchase of Certified Crop seed | Kabuchai | Chwele/Kabuchai | 0.73477,34.57931 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 30/3/2020 | 10,00,000 | 4999137 | 5000000 | County Government of Bungoma |  | 4999137 | 0 | 4999137 | 1 | 4999137 | 0 | 0 | Completed
| Purchase of coffee seed tubes | Purchase and delivery of 50 dozens of 12 Coffee Seed tubes to cooperative Societies | To promote coffee production and income generation | 50 dozens of 12 Coffee Seed tubes purchased and delivered to coffee societies | 3111301 | Purchase of Certified Crop seed | Kabuchai | Chwele/Kabuchai | 0.73477,34.57931 | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 28/3/2020 | 5000000 | 1990000 | 2000000 | County Government of Bungoma |  | 1990000 | 0 | 1990000 | 1 | 1990000 | 0 | 0 | Completed
| Desiltation of ponds at Chwele Fish Farm | Desiltation of ponds at Chwele Fish Farm | To increase pond surface for increased fish production and income generation | 8 ponds desilted (5093m²) | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 15/1/2020 | 15/4/2020 | 44046 | 6000000 | 2881440 | 3000000 | County Government of Bungoma |  | 2881440 | 0 | 2881440 | 1 | 2881440 | 0 | 0 | Completed
| Desiltation of Ponds and flood control at Chwele Fish Farm | Desiltation of Ponds and flood control at Chwele Fish Farm | To increase pond surface area for fish production | 12 ponds desilted (3375m²) | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 44348 | 44351 | 26/2/2021 |  | 1455439 | 1455439 | County Government of Bungoma |  | 1455439 | 0 | 1455439 | 1 | 1455439 | 0 | 0 | Completed
| Construction of Catering Facility at Chwele fish farm | Construction of Catering Facility at Chwele fish farm | To cater for trainees during training sessions | Catering constructed we Maeni Cooperative Society | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44900 | 44777 | 2800000 | 2798500 | 2800000 | County Government of Bungoma |  | 2798500 | 0 | 2798500 | 1 | 2798500 | 0 | 0 | Completed
| Desiltation of Fish Ponds | Desiltation of Fish Ponds | To increase pond surface area for increased fish production | 8 Fish ponds desilted | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44653 | 44657 | 28/3/2022 | 1600000 | 1598210 | 1600000 | County Government of Bungoma |  | 1598210 | 0 | 1598210 | 1 | 1598210 | 0 | 0 | Completed
| Construction of Rass/Hatchery at Chwele fish farm | Construction of Rass/Hatchery at Chwele fish farm | To improve on fingerling production | 1 Rass/hatchery constructed | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 18/12/2021 | 18/4/2022 | 25/4/2022 | 3000000 | 2671040 | 3000000 | County Government of Bungoma |  | 2671040 | 0 | 2671040 | 1 | 2671040 | 0 | 0 | Completed
| Supply and Delivery of Fish Feeds | Supply and Delivery of 375 bags of 20kgs ofFish Feeds | To increase fish production and improve on food and nutrition security | 375 bags of 20kgs of Fish feeds purchased and delivered | 2211023 | Supplies for production | Kabuchai | Chwele/Kabuchai | 0.73526,34.57931 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44835 | 44837 | 22/2/2022 | 5000000 | 1588750 | 1600000 | County Government of Bungoma |  | 1588750 | 0 | 1588750 | 1 | 1588750 | 0 | 0 | Completed
| Rehabilitation of Chwele Dam next to Chwele Fish Farm | Rehabilitation of Chwele Dam next to Chwele Fish Farm | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai | 0.73481,34.57801 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44713 | 44718 | 44686 | 6500000 | 3900000 | 3900000 | County Government of Bungoma |  | 3900000 | 0 | 3900000 | 1 | 3900000 | 0 | 0 | Completed
| Supply and delivery of Fish Feeds for Chwele Fish Farm | Supply and delivery of Fish Feeds for Chwele Fish Farm | To increase fish production and improve on food and nutrition security | 707 bags of 20kg of fish feed supplied and delivered | 3110599 | Ward Based projects | Kabuchai | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 27/1/2024 | 27/4/2024 | 27/3/2024 | 3000000 | 2998400 | 3000000 | County Government of Bungoma |  | 2998400 | 0 | 2998400 | 1 | 2998400 | 0 | 0 | Completed
| Disilitation of of Fish Ponds at Chwele Fish Farm | Disilitation of 8 No. of Fish Ponds at Chwele Fish Farm | To increase pond surface area for increased fish production | 8 Fish ponds desiltated (3472m²) | 3110504 | Other infrastructure and civil works | Kabuchai | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 17/12/2023 | 17/5/2024 | 17/3/2024 | 2000000 | 1910230 | 2000000 | County Government of Bungoma |  | 1910230 | 0 | 1910230 | 1 | 1910230 | 0 | 0 | Completed
| Supply and delivery of two months old improved vaccinated indigeneous chicks and chick mash (feeds) | Supply and delivery of two months old improved vaccinated indigeneous chicks and chick mash (feeds) | To enhance poultry production and increase household incomes | 9,000 2-months old improved vaccinated chicks supplied and delivered to farmer groups | 3110599 | Ward Based projects | Kabuchai | Chwele/Kabuchai | 0.73775,34.57449 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 7000000 | 6998975 | 7000000 | County Government of Bungoma |  | 6998975 | 0 | 6998975 | 1 | 6998975 | 0 | 0 | Completed
| Supply and delivery of chicks and chick mash (feeds) | Supply And delivery of two months old improved vaccinated indigenous chicks and chick mash (feeds) | To enhance poultry production and increase household incomes | 6,840 chicks and feeds supplied and delivered | 3110599 | Ward Based projects | Kabuchai | Chwele/Kabuchai | 0.73775,34.57449 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 5000000 | 5000000 | 5000000 | County Government of Bungoma |  | 5000000 | 0 | 5000000 | 1 | 5000000 | 0 | 0 | Completed
16 | Proposed installation and Commissioning of 20M high 1No.grid powered floodlight at Sikusi Market | installation of No high powered floodlight | promotion of MSMEs and security | Grid powered floodlights installed | BGM/CNTY/TEI/03/OT/2024-2025 1667815-2024/2025 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | PHILAFE ENGINEERING | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 4000000 |  |  | CGB | [8 empty] | Works to commence |  | 1
21 | Proposed laying of Cabros and Drainage at Chwele Market | laying and at and Drainage | Imroved market infrastructure | Drainage and Cabros installed | 1477172/2023/2024 |  |  | Chwele/Kabuchai | 0.7351,34.57852 | Trade, Energy and Industrialization | Dept of Trade | DELLE INTERNATIONAL LIMITED | 2023/2024 |  | At 99% complete | Ongoing but in use | 15000000 |  |  | CGB | [8 empty] | The national government has taken over upgarading of the market |  | 1
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Chwele/Kabuchai |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
122 | Renovation of Perimeter Wall and fixing of gates at Chwele market | of and of of gates | [5 empty] | Chwele/Kabuchai | 0.7351,34.57852 |  |  | Dry Port Contractors | 2018/19 |  | Complete |  | 3954300.8 |  |  | CGG
125 | Construction of 3 boda boda sheds | Of sheds streetlights | [5 empty] | Chwele/Kabuchai |  |  |  | M/S Gaspas Engineering Works | 2018/19 |  | Complete |  | 855339 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Chwele/Kabuchai |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
11 | Upgrading of Vihiga Miti Mbili-Misanga | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41659 | 41780 |  | 6045574 | 6045574 | 6045574 | County Government of Bungoma |  | 6045574 |  | 6045574 | 100.0% | 6045574 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
26 | Upgrading of Mikayu-Nanjofu | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41651 | 41773 |  | 4348260 | 4348260 | 4348260 | County Government of Bungoma |  | 4348260 |  | 4348260 | 100.0% | 4348260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
33 | Construction of Periodic Maintanance Of Wabukhoyi-R.Kibisi-Makuselwa With Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41651 | 41778 |  | 15299419.8 | 15299419.8 | 15299419.8 | County Government of Bungoma |  | 15299419.8 |  | 15299419.8 | 100.0% | 15299419.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
47 | Upgrading of Muyekhe-Mutoto Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41651 | 41774 |  | 4474932 | 4474932 | 4474932 | County Government of Bungoma |  | 4474932 |  | 4474932 | 100.0% | 4474932 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
51 | Upgrading of Lufutu-Nakituba-Sengeteti Junt | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41663 | 41773 |  | 4474932 | 4474932 | 4474932 | County Government of Bungoma |  | 4474932 |  | 4474932 | 100.0% | 4474932 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
89 | Periodic Maintenance of Matisi - Bokoli - Teremi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2014/2015 | 42020 | 42141 |  | 63019616.52 | 63019616.52 | 63019616.52 | County Government of Bungoma |  | 63019616.52 |  | 63019616.52 | 100.0% | 63019616.52 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
102 | Periodic Maintenance of Sikusi Dispensary - Kolani Market | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42391 | 42509 |  | 5742000 | 5742000 | 5742000 | County Government of Bungoma |  | 5742000 |  | 5742000 | 96.62% | 5742000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
124 | Periodic Maintenance of Chebukwa - Marakaru Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42750 | 42866 |  | 9984433 | 9984433 | 9984433 | County Government of Bungoma |  | 9984433 |  | 9984433 | 90.81% | 9984433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
169 | Periodic Maintenance of Periodic Mainenance Of Sasuri Nabukhisa-Kakichuma-Toloso River-Najikobe | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43117 | 43241 |  | 7010344 | 7010344 | 7010344 | County Government of Bungoma |  | 7010344 |  | 7010344 | 99.5% | 7010344 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
170 | Periodic Maintenance of Mikayu-Kasosi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43233 |  | 6871260 | 6871260 | 6871260 | County Government of Bungoma |  | 6871260 |  | 6871260 | 98.91% | 6871260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
171 | Periodic Maintenance of Sirare Pri-Marobo Ack Church | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43242 |  | 6372982 | 6372982 | 6372982 | County Government of Bungoma |  | 6372982 |  | 6372982 | 99.77% | 6372982 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
326 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | SEVERAL | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
327 | Construction of Muyayi-Nangwe Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43603 |  | 11024129.6 | 11024129.6 | 11024129.6 | County Government of Bungoma |  | 11024129.6 |  | 11024129.6 | 99.97% | 11024129.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
328 | Construction of Kipchori Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43479 | 43597 |  | 10235918.88 | 10235918.88 | 10235918.88 | County Government of Bungoma |  | 10235918.88 |  | 10235918.88 | 99.87% | 10235918.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
329 | Periodic Maintenance of Chebukaka - Kimalewa Juction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43597 |  | 9485784 | 9485784 | 9485784 | County Government of Bungoma |  | 9485784 |  | 9485784 | 94.66% | 9485784 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
330 | Drainage Works At Chwele Market | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43480 | 43607 |  | 4988000 | 4988000 | 4988000 | County Government of Bungoma |  | 4988000 |  | 4988000 | 99.65% | 4988000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
515 | Periodic Maintenance of Khachonge - Chwele Kmtc Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43965 |  | 6919458 | 6919458 | 6919458 | County Government of Bungoma |  | 6919458 |  | 6919458 | 98.45% | 6919458 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
750 | Periodic Maintenance Of Marakaru - Namosi - Kisiwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44335 |  | 13376569 | 13376569 | 13376569 | County Government of Bungoma |  | 13376569 |  | 13376569 | 99.21% | 13376569 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
751 | Periodic Maintenance of Chwele - Mahonge - Namwela - Menu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44337 |  | 11875804.5 | 11875804.5 | 11875804.5 | County Government of Bungoma |  | 11875804.5 |  | 11875804.5 | 97.78% | 11875804.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
752 | Spot Improvement Of Lurende - Khachonge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44327 |  | 4389440 | 4389440 | 4389440 | County Government of Bungoma |  | 4389440 |  | 4389440 | 93.96% | 4389440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
753 | Spot Improvement Of Sikusi - Mukhweya - Lurende Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44336 |  | 2787373.5 | 2787373.5 | 2787373.5 | County Government of Bungoma |  | 2787373.5 |  | 2787373.5 | 98.91% | 2787373.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
754 | Periodic Maintenance of Chebukaka - Mpakani - Teremi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44335 |  | 6471680 | 6471680 | 6471680 | County Government of Bungoma |  | 6471680 |  | 6471680 | 99.86% | 6471680 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1076 | Periodic Maintenance of Chenjen - St Walumoli - Madisi Mkt (Junct) Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44705 |  | 3733170 | 3733170 | 3733170 | County Government of Bungoma |  | 3733170 |  | 3733170 | 100.0% | 3733170 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1386 | Routine Maintenance Of Bukembe - Sawa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45063 |  | 5715577.52 | 5715577.52 | 5715577.52 | County Government of Bungoma |  | 5715577.52 |  | 5715577.52 | 99.85% | 5715577.52 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1387 | Routine Maintenance Of Sikata Primary Chemwa-Luucho Khalaba Musukho Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45063 |  | 3857090.17 | 3857090.17 | 3857090.17 | County Government of Bungoma |  | 3857090.17 |  | 3857090.17 | 98.28% | 3857090.17 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1388 | Periodic Maintenance of Cbsm School-Mulongo Namakhele Primary | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45068 |  | 3023154.18 | 3023154.18 | 3023154.18 | County Government of Bungoma |  | 3023154.18 |  | 3023154.18 | 99.0% | 3023154.18 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1389 | Routine Maintenance Of Chebukwa Kisiwa TTI | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45060 |  | 3076129 | 3076129 | 3076129 | County Government of Bungoma |  | 3076129 |  | 3076129 | 99.84% | 3076129 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1390 | Construction of Kibochi- Ngalasia Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45070 |  | 6272491.2 | 6272491.2 | 6272491.2 | County Government of Bungoma |  | 6272491.2 |  | 6272491.2 | 99.93% | 6272491.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1644 | Construction of Chwele Coffee Factory Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45431 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1645 | Periodic Maintenance of Mukhweya - Namakhele - Chenane Road In Chwele/Kabuchai Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45424 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1646 | Construction of Chwele Coffee Factory Box Culvert In Chwele/Kabuchai Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | KABUCHAI | Chwele/Kabuchai |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45430 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.98% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
20 | Construction of Governors residence | Erection and completion of governors residence | To provide secure official residence and enhance adminstrative efficiency | One Governor's Residential house constructed | 3111504 | Other Infrastructure and Civil Works | Luuya/Bwake | Chwele/Kabuchai |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2023/24 | 14/8/2023 | 13/8/25 |  | 45000000 | 10000000 | 10000000 | CGB |  | 10000000 |  | 10000000 | 1 | 0 |  | 35000000 | Ongoing | 0.3 | [14 empty] | The project is 30% complete
24 | Construction works for 5NO. public security lighting in Mjini, Bungoma town and Landi Matope, Chwele town, settlements in Bungoma County. | Installation of street lights | To enhance security at the slums | Five Street lights in Mjini, Bungoma town and Landi Matope, Chwele town, settlements in Bungoma County installed | 2640503 | Other Infrastructure and Civil Works | Musikoma/Chwele Kabuchai | Chwele/Kabuchai |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2023/24 | 29/1/2024 | 18/4/2024 | 25/4/2025 | 50000000 | 50000000 | 50000000 | CGB/KISIP(WB) | KISIP(WB) | 0 | 50000000 | 50000000 | 1 | 27900000 |  | 0 | Completed | 1 | [14 empty] | The project is 100% complete and in use
31 | Fencing of Matunda E.C.D.E land. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One Matunda ECDE Land fenced | 3110599 | Ward based projects | Luuya/Bwake | Chwele/Kabuchai |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 |  |  |  | 1000000 | 200000 | 200000 | CGB |  | 200000 |  | 200000 | 1 | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2022/23 |  |  | No | Compete | [7 empty] | The project is staled due Lack of documentations(Title deed)
32 | Purchase of land for Chekulo market. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new market centre | One acre of Land Purchased for Chekulo market | 3110599 | Ward based projects | Luuya/Bwake | Chwele/Kabuchai |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | - | - |  | 2000000 | 1500000 | 1500000 | CGB |  | 1500000 |  | 1500000 | 1 | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2022/23 |  |  | No | Compete | [7 empty] | The project is staled due Lack of documentations(Title deed)
45 | Construction of Governors residence | Erection and completion of governors residence | To provide secure official residence and enhance adminstrative efficiency | One Governors Residential house constructed | 3111504 | Other Infrastructure and Civil Works | Luuya/Bwake | Chwele/Kabuchai |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2022/23 | 14/8/2023 | 13/8/25 |  | 45000000 | 5000000 | 5000000 | CGB |  | 5000000 |  | 5000000 | 0 | 0 |  | 35000000 | Ongoing | 0.3 | 0 |  |  |  |  | No | Compete | [7 empty] | The project is 30% complete
47 | Construction works for 5NO. public security lighting in Mjini, Bungoma town and Landi Matope, Chwele town, settlements in Bungoma County. | Installation of street lights | To enhance security at the slums | Five Street lights in Mjini, Bungoma town and Landi Matope, Chwele town, settlements in Bungoma County installed | 2640503 | Other Infrastructure and Civil Works | Musikoma/Chwele Kabuchai | Chwele/Kabuchai |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2022/23 | 29/1/2024 | 18/4/2024 | 18/4/2024 |  | 50000000 | 50000000 | CGB/KISIP(WB) | KISIP(WB) | 0 | 50000000 | 50000000 | 1 | 27900000 |  | 0 | Completed | 1 | [14 empty] | The project is 100% complete and in use
21 | Hass Avocado Fruit Tree Production In Kanduyi And Kabuchai Sub Counties | Supply and distribution of certified and grafted Hass avocado seedlings, Provision of manure, pegging, holing , training of nursery operators and maintanance of the orchard for 3 months | To promote climate change mitigation and adaptation | Hass avocado fruit tree planted | 2640599 | Other Capital Grants and Transfers | Kanduyi,Kabuchai | Chwele/Kabuchai |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 6000000 | 5980445 | 5980445 | FLLOCA | KFW | 0 | 5980445 | 0 | 1 | 0 | 0 |  | On going and not in use | 0.85 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Chwele/Kabuchai | 0.722058,34.582311 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Chwele/Kabuchai | 0.750054,34.571558 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Chwele/Kabuchai | 0.734.57155850054 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.572170 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.729125,34.572170 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Chwele/Kabuchai | 0.7351,34.57852 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Chwele/Kabuchai |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Chwele/Kabuchai |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
41 | Construction of modern pit latrines | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Pit latrines constructed |  |  | Mt. Elgon | Elgon | 0.842187/34.718806 |  | Health & Sanitation | Health & Sanitation | 2023-2024 |  |  |  | 1500000 | 1497620 | 1497620 | CGB |  | 1497620 | 0 | 0 | 0% | 0 |  | 1497620 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Fencing required
77 | Construction Of Modern Pit Latrines At Kiptoitik Ecde Cheptakat Ecde Kipchiria Ecde | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Pit latrines constructed |  |  | Mt. Elgon | Elgon | 0.8475077/34.64922 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 1500000 | 1497620 | 1497620 | CGB |  | 1497620 | 0 | 1205050.25 | 80.46% | 1205050.25 |  | 292569.75 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | No stracture in existance
125 | Construction Of Koshok Maternity Wing | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | Elgon |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2000000 | 1857005 | 1857005 | CGB |  | 1857005 | 0 | 836893 | 45.07% | 836893 |  | 1020112 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
126 | Renovation Of Mwaimwai Dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Dispensaries renovated |  |  | Mt. Elgon | Elgon | 0.8475076/34.65989 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 800000 | 776654 | 776654 | CGB |  | 776654 | 0 | 776654 | 100% | 776654 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | Renovation required
159 | Construction Of Maternity Wing At Chemworemwo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | Elgon | 0.868927/34.730298 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1976240 | 1976240 | CGB |  | 1976240 | 0 | 943090 | 47.72% | 943090 |  | 1033150 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Funds be allocated for completion
185 | Construction Of Maternity Wing At Chemworemwo primary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | Elgon |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1976240 | 1976240 | CGB |  | 1976240 | 0 | 943090 | 47.72% | 943090 |  | 1033150 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
278 | Construction Of 4-door pit Latrines at Kamuneru Dispensary | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | 4No.door pit latrine constructed |  |  | Mt. Elgon | Elgon |  |  | CEF | Health & Sanitation | 2016/2017 | 42856 | 42948 | Ongoing |  | 746042 | 746042 | CGB |  | 746042 | 0 | - | #VALUE! | - |  | #VALUE! | Ongoing | [6 empty] | No | complete | Financial | Yes
279 | Erection And Completion Of Chepkitale Dispensary | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Elgon |  |  | CEF | Health & Sanitation | 2016/2017 | 42856 | 42948 |  |  | 3588460 | 3588460 | CGB |  | 3588460 | 0 | 3587044 | 99.96% | 3587044 |  | 1416 | Complete and in use. | [6 empty] | No | complete | Financial | Yes
76 | Construction of Box Culvert At Masindet Over River Nguresai | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41656 | 41777 |  | 6167226.64 | 6167226.64 | 6167226.64 | County Government of Bungoma |  | 6167226.64 |  | 6167226.64 | 100.0% | 6167226.64 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Good condition
94 | Periodic Maintenance of Kibuk - Kaberwa - Chepkitale Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2014/2015 | 42025 | 42148 |  | 118175092.68 | 118175092.68 | 118175092.68 | County Government of Bungoma |  | 118175092.68 |  | 118175092.68 | 100.0% | 118175092.68 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
95 | Periodic Maintenance of Sirisia - Cheptais - Tisi - Chepkube - Nalondo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2014/2015 | 42021 | 42143 |  | 47529584.8 | 47529584.8 | 47529584.8 | County Government of Bungoma |  | 47529584.8 |  | 47529584.8 | 100.0% | 47529584.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
101 | Periodic Maintenance of Kapsokwony Town(Market Access) Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42380 | 42502 |  | 6498000 | 6498000 | 6498000 | County Government of Bungoma |  | 6498000 |  | 6498000 | 99.63% | 6498000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
106 | Periodic Maintenance of Kaborom - Tulwo - Kaptama - Kositoi - Chelinde | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42388 | 42508 |  | 9682288 | 9682288 | 9682288 | County Government of Bungoma |  | 9682288 |  | 9682288 | 99.52% | 9682288 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
130 | Construction of Kewaanikoy - Kabukwo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42757 | 42871 |  | 7976795.32 | 7976795.32 | 7976795.32 | County Government of Bungoma |  | 7976795.32 |  | 7976795.32 | 100.0% | 7976795.32 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
131 | Periodic Maintenance of Kapkateny - Cheptonoin - Kaimukul Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42758 | 42875 |  | 27855080 | 27855080 | 27855080 | County Government of Bungoma |  | 27855080 |  | 27855080 | 100.0% | 27855080 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
132 | Periodic Maintenance of Masaek - Kipsigon - Benandega Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42754 | 42878 |  | 11516799 | 11516799 | 11516799 | County Government of Bungoma |  | 11516799 |  | 11516799 | 32.22% | 11516799 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
133 | Periodic Maintenance of Land B - Chepyuk Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42758 | 42878 |  | 16566018 | 16566018 | 16566018 | County Government of Bungoma |  | 16566018 |  | 16566018 | 48.85% | 16566018 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
134 | Periodic Maintenance of Tuikut - Kamarang Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42751 | 42872 |  | 10247034 | 10247034 | 10247034 | County Government of Bungoma |  | 10247034 |  | 10247034 | 27.16% | 10247034 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
135 | Periodic Maintenance of Completion Of Kaborom Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42756 | 42873 |  | 9212343 | 9212343 | 9212343 | County Government of Bungoma |  | 9212343 |  | 9212343 | 22.44% | 9212343 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
167 | Periodic Maintenance of Makunga - Sambocho - Kapsong Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.3KM GRAVELLED | 3110399 |  | Mt. Elgon | Elgon | 0.838847/34.64828-0.0.83847/34648285 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43114 | 43238 |  | 7980336 | 7980336 | 7980336 | County Government of Bungoma |  | 7980336 |  | 7980336 |  | 7980336 | 0 | 0 | In complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Stalled needs maintanace periodically
168 | Periodic Maintenance of Roads In Elgon Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.3KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43239 |  | 7980336 | 7980336 | 7980336 | County Government of Bungoma |  | 7980336 |  | 7980336 | 93.28% | 7980336 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
219 | Periodic Maintenance of Maintenance Of Kipsigon - Kabura-Kipkisei | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43232 |  | 22897054 | 22897054 | 22897054 | County Government of Bungoma |  | 22897054 |  | 22897054 | 99.82% | 22897054 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
220 | Periodic Maintenance of -Mpakani-Pefa Church-Kapkateny | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43232 |  | 8572768 | 8572768 | 8572768 | County Government of Bungoma |  | 8572768 |  | 8572768 | 99.96% | 8572768 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
323 | Upgrading of Mwetuny Vented Drift | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.84882473/34.697088 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43478 | 43608 | 43639 | 7192012 | 7192012 | 7192012 | County Government of Bungoma |  | 7192012 |  | 7192012 |  | 7192012 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Passable
324 | Upgrading of Mwetunty Vented Drift In Elgon Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43489 | 43601 |  | 7192012 | 7192012 | 7192012 | County Government of Bungoma |  | 7192012 |  | 7192012 | 98.66% | 7192012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
325 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
405 | Upgrading of Kimama Water Supply Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43601 |  | 28036501.68 | 28036501.68 | 28036501.68 | County Government of Bungoma |  | 28036501.68 |  | 28036501.68 | 16.77% | 28036501.68 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
406 | Periodic Maintenance of Namwela Mkt - Kaptanai - Kipkirong Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43483 | 43597 |  | 15486261 | 15486261 | 15486261 | County Government of Bungoma |  | 15486261 |  | 15486261 | 96.93% | 15486261 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
407 | Periodic Maintenance of Chepkube Fcs-Chebwek-Chesukum Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43599 |  | 9396870 | 9396870 | 9396870 | County Government of Bungoma |  | 9396870 |  | 9396870 | 97.2% | 9396870 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
513 | Periodic Maintenance of Kwa Joseph - Bugaa Forest Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43973 |  | 6570124 | 6570124 | 6570124 | County Government of Bungoma |  | 6570124 |  | 6570124 |  | 6570124 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
514 | Periodic Maintenance of Roads In Elgon Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43961 |  | 6570124 | 6570124 | 6570124 | County Government of Bungoma |  | 6570124 |  | 6570124 | 99.49% | 6570124 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
600 | Periodic Maintenance of Chebus - Kimaswa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43973 |  | 9975000 | 9975000 | 9975000 | County Government of Bungoma |  | 9975000 |  | 9975000 |  | 9975000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
601 | Periodic Maintenance of Chebus - Kimaswa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43974 |  | 9975000 | 9975000 | 9975000 | County Government of Bungoma |  | 9975000 |  | 9975000 |  | 9975000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
602 | Periodic Maintenance of Chebus-Kimama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43970 |  | 9975000 | 9975000 | 9975000 | County Government of Bungoma |  | 9975000 |  | 9975000 | 98.84% | 9975000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
746 | Periodic Maintenance of Chemweisus - Kibundo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.853685/34.721301-0.861468/34.728763 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44333 | 44364 | 7293384 | 7293384 | 7293384 | County Government of Bungoma |  | 7293384 |  | 7293384 |  | 7293384 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintanance required
747 | Periodic Maintenance of Nomorio - Kipyeto Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.840850/34.670445 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44339 |  | 7293384 | 7293384 | 7293384 | County Government of Bungoma |  | 7293384 |  | 7293384 |  | 7293384 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintanance required
748 | Upgrading of Roads In Elgon Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44326 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
749 | Periodic Maintenance of Roads In Elgon Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44329 |  | 7293384 | 7293384 | 7293384 | County Government of Bungoma |  | 7293384 |  | 7293384 | 99.09% | 7293384 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
897 | Periodic Maintenance of Cheptais Town - Cheptais Secondary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44329 |  | 5483682 | 5483682 | 5483682 | County Government of Bungoma |  | 5483682 |  | 5483682 |  | 5483682 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
898 | Periodic Maintenance of Kipsigon - Kapsikei Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 11.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44330 |  | 12496935 | 12496935 | 12496935 | County Government of Bungoma |  | 12496935 |  | 12496935 |  | 12496935 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
899 | Periodic Maintenance of Kimobo - Kamtiong Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon | 0.839671/34.718 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44336 |  | 7884269.73 | 7884269.73 | 7884269.73 | County Government of Bungoma |  | 7884269.73 |  | 7884269.73 |  | 7884269.73 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | In bad condition
900 | Periodic Maintenance of Toloso Kapteywa River - County - Chemodi | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44330 |  | 11412045.2 | 11412045.2 | 11412045.2 | County Government of Bungoma |  | 11412045.2 |  | 11412045.2 |  | 11412045.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
901 | Periodic Maintenance of Kaptekanteet - Sultani - Chepsoikeey Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44332 |  | 5632693 | 5632693 | 5632693 | County Government of Bungoma |  | 5632693 |  | 5632693 |  | 5632693 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
902 | Upgrading of Shiundu - Chelebei - Motherland Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44333 |  | 6198837 | 6198837 | 6198837 | County Government of Bungoma |  | 6198837 |  | 6198837 |  | 6198837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
903 | Upgrading of Shiundu - Chelebei - Motherland Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44326 |  | 6198837 | 6198837 | 6198837 | County Government of Bungoma |  | 6198837 |  | 6198837 |  | 6198837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
904 | Upgrading of Shiundu - Chelebei - Motherland Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44326 |  | 6198837 | 6198837 | 6198837 | County Government of Bungoma |  | 6198837 |  | 6198837 |  | 6198837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
905 | Periodic Maintenance of Cheptais Town - Cheptais Secondary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44331 |  | 5483682 | 5483682 | 5483682 | County Government of Bungoma |  | 5483682 |  | 5483682 | 94.91% | 5483682 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
906 | Spot Improvement Of Kipsigon - Kapsikei Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 11.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44328 |  | 12496935 | 12496935 | 12496935 | County Government of Bungoma |  | 12496935 |  | 12496935 | 99.19% | 12496935 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
907 | Periodic Maintenance of Kimobo - Kamtiong Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44340 |  | 7884269.73 | 7884269.73 | 7884269.73 | County Government of Bungoma |  | 7884269.73 |  | 7884269.73 | 98.42% | 7884269.73 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
908 | Periodic Maintenance of Toloso - Kiptaywa River - County - Chemodi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44339 |  | 11412045.2 | 11412045.2 | 11412045.2 | County Government of Bungoma |  | 11412045.2 |  | 11412045.2 | 99.04% | 11412045.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
909 | Periodic Maintenance of Kaptekanteet - Sultan - Chepsoikeey Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44328 |  | 5632693 | 5632693 | 5632693 | County Government of Bungoma |  | 5632693 |  | 5632693 | 99.93% | 5632693 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
910 | Spot Improvement Of Shiundu - Chelebei - Motherland Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44327 |  | 6198837 | 6198837 | 6198837 | County Government of Bungoma |  | 6198837 |  | 6198837 | 99.98% | 6198837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1071 | Periodic Maintenance of Kimgung Junction - Masindet Sda Church Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44571 | 44705 |  | 13597694 | 13597694 | 13597694 | County Government of Bungoma |  | 13597694 |  | 13597694 |  | 13597694 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintanance required
1072 | Periodic Maintenance of Sambocho - Kaprong Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44695 |  | 13597694 | 13597694 | 13597694 | County Government of Bungoma |  | 13597694 |  | 13597694 |  | 13597694 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1073 | Periodic Maintenance of Kaptola - Cheromis Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.83847/34.648285 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44701 |  | 13597694 | 13597694 | 13597694 | County Government of Bungoma |  | 13597694 |  | 13597694 |  | 13597694 | 0 | 0 | In complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Sub standard work
1074 | Periodic Maintenance of Kibuk - Chebkui Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.8441827/34.699989 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44693 |  | 13597694 | 13597694 | 13597694 | County Government of Bungoma |  | 13597694 |  | 13597694 |  | 13597694 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Poorely done and narrow
1075 | Periodic Maintenance of Roads In Elgon Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44702 |  | 13597694 | 13597694 | 13597694 | County Government of Bungoma |  | 13597694 |  | 13597694 | 100.0% | 13597694 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1247 | Upgrading of Roads In Elgon Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44701 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1254 | Spot Improvement Of Kona Tatu - Kongit -Mashambani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Elgon | 0.859348/34.731790 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44692 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Grading required
1384 | Periodic Maintenance of Sendera - Kipyeto Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.832707/34.66089 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45060 |  | 6240081 | 6240081 | 6240081 | County Government of Bungoma |  | 6240081 |  | 6240081 |  | 6240081 | 0 | 0 | In complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Stalled needs maintanace periodically
1385 | Periodic Maintenance of Sendera - Kipyeto In Elgon Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45059 |  | 6240081 | 6240081 | 6240081 | County Government of Bungoma |  | 6240081 |  | 6240081 | 99.63% | 6240081 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1494 | Periodic Maintenance of Kibuk - Kaberua - Chepkitale | Gravelling and grading works | To improve the road condition and enhance accessibility | 32.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.845815/34.699898 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45056 |  | 32731972.4 | 32731972.4 | 32731972.4 | County Government of Bungoma |  | 32731972.4 |  | 32731972.4 |  | 32731972.4 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Poorely done. Murraming required
1495 | Periodic Maintenance of Kibuk - Kaberua - Chepkitale | Gravelling and grading works | To improve the road condition and enhance accessibility | 32.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45064 |  | 32731972.4 | 32731972.4 | 32731972.4 | County Government of Bungoma |  | 32731972.4 |  | 32731972.4 |  | 32731972.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1496 | Periodic Maintenance of Chepkube Coffee Factory - Chief Kiboi - Burkenwo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45060 |  | 2894292.8 | 2894292.8 | 2894292.8 | County Government of Bungoma |  | 2894292.8 |  | 2894292.8 |  | 2894292.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1497 | Construction of Kubuura - Chepkowo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45068 | 45099 | 7780444.8 | 7780444.8 | 7780444.8 | County Government of Bungoma |  | 7780444.8 |  | 7780444.8 |  | 7780444.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1498 | Construction of Chemwesus - Chemosis Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45064 |  | 7936232.8 | 7936232.8 | 7936232.8 | County Government of Bungoma |  | 7936232.8 |  | 7936232.8 |  | 7936232.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1499 | Periodic Maintenance of Kibuk Kaberua Chepkitale Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 32.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45070 |  | 32731972.4 | 32731972.4 | 32731972.4 | County Government of Bungoma |  | 32731972.4 |  | 32731972.4 | 99.78% | 32731972.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1500 | Periodic Maintenance of Chepkube Coffee Factory-Chief Kiboi Burkenwo | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45063 |  | 2894292.8 | 2894292.8 | 2894292.8 | County Government of Bungoma |  | 2894292.8 |  | 2894292.8 | 95.99% | 2894292.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1501 | Construction of Kubura- Kuruma Saria Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45066 |  | 7780444.8 | 7780444.8 | 7780444.8 | County Government of Bungoma |  | 7780444.8 |  | 7780444.8 | 87.15% | 7780444.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1502 | Construction of Chemwesus-Chemusisi Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45057 |  | 7936232.8 | 7936232.8 | 7936232.8 | County Government of Bungoma |  | 7936232.8 |  | 7936232.8 | 99.96% | 7936232.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1642 | Periodic Maintenance of Kamutiong' Mart Water Supply - Wambete - Cheromis Road In Elgon Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.81461978/34.7019327 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45431 |  | 7059760 | 7059760 | 7059760 | County Government of Bungoma |  | 7059760 |  | 7059760 | 99.87% | 7059760 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Poor drainage system
1643 | Periodic Maintenance of Chemwesus - Kibundo - Kamung'Ou Road Elgon Ward (1450750-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon | 0.8446/34.72 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45428 |  | 7937121.36 | 7937121.36 | 7937121.36 | County Government of Bungoma |  | 7937121.36 |  | 7937121.36 | 100.0% | 7937121.36 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Gravelling required
28 | Purchase of 1 Acre land for Kamuneru dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land for Kamuneru dispensary Purchased. | 3110599 | Ward based projects | Mt. Elgon | Elgon |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | - | - |  | 2000000 | 1000000 | 1000000 | CGB |  | 1000000 |  | 1000000 | 100% | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2022/23 |  |  | No | Compete | [7 empty] | The project is staled due Lack of documentations(Title deed)
40 | Purchase of 1 Acre for Kamarang dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land for Kamarang dispensary. Purchased | 3110599 | Ward based projects | Mt. Elgon | Elgon |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | 45352 | 45809 |  | 3000000 | 1600000 | 1600000 | CGB |  | 1600000 |  | 1600000 | 100% | 0 |  |  | Ongoing | 0.4 | [14 empty] | The project is 40% complete
41 | Purchase of 1 Acre for Chebinyinyi dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land for Chebinyinyi dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | Elgon |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2022/23 | - | - |  | 2000000 | 1600000 | 1600000 | CGB |  | 1600000 |  | 1600000 | 100% | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2022/23 |  |  | No | Compete | [7 empty] | The project is staled due Lack of documentations(Title deed)
87 | Renovation and refurbishment of staff quarters at Kopsiro Health centre | renovation and refurbishment | To enhance revenue collection | 3 units of County residential houses at kopsiro renovated | 3110301 | Other Infrastructure and Civil Works | Mt. Elgon | Elgon |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2019/20 | 21/2/2020 | 22/4/2020 | 21/5/2020 | 900000 | 700000 | 700000 | CGB |  | 700000 |  | 700000 | 100% | 677360 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
88 | Preparation of intergrated plan for Kapsokwony Town | Document review,Desktop research, Gaps analysis, Report Writing and formulation of new maps, Stakeholder engagement for new vision and direction of the urban area | To guide sustainable and inclusive growth of urban areas through land use,infrastructure development and improved service delivery | One Physical and land use plan or Kapsokwony Town developed | 2211311 | Development/Physical Planning | Mt. Elgon | Elgon | 0.842187/34.71 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 43681 | 43748 | 30/10/2019 | 6000000 | 5507464 | 5507464 | CGB |  | 5507464 |  | 5507464 |  | 5507464 |  |  | In complete | 1 | [14 empty] | Public participation
117 | Purchase of 1acre Land For Masindet Coffee Factory | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new Coffee facrory | One acres of Land forMasindet Coffee Factory Purchased | 3110599 | Ward based projects | Mt. Elgon | Elgon |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43077 | 43079 | 23/11/2017 | 2000000 | 2000000 | 2000000 | CGB | N/A | 2000000 |  | 2000000 | 100% | 2400000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
25 | Construction of 1 NO. ECDE Classroom at Tendet primary school in Elgon Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Elgon | 0.817114983/37.70577098 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2023/2024 | 45293 | 30/06/2024 |  | 4000000 | 3904500 | 4000000 | County Government of Bungoma | N/A | 4000000 | 0 |  | 0% |  | 3904500 | 3904500 | Completed
40 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Kamkata And Sendera Primary Schools In Elgon Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Elgon | 0.8475076/34.6977-0.807307/34.697708 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2983955 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 | 0% | 0 | 2983955 | 2983955 | Stalled | 0.5 | [14 empty] | At the lintel
75 | Construtction of 1 No. ECDE classroom at Sandera and Koshok primary schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Elgon | 0.8005/34.66006-0.8437196/34.65948 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3000000 | 2873400 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 | 0% | 0 | 2873400 | 2873400 | Stalled | 0.2 | [14 empty] | Contractor not on sites
108 | Construction Of 1 No. Ecde Classroom At Kiptoitik And Chepkuy Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Elgon | 0.8183215/34.6544 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2018/2019 | 44230 | 44414 |  | 3000000 | 2736640 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 910234.55 | 33.26% | 910234.55 | 1826405.45 | 1826405.45 | Complete. | 1 | [14 empty] | Maintanance and repair
137 | Construction Of 1no.Ecde Classroom At Koshok And Kananachipri.Sch. And 2no. Door Pit Latrine Elgon Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Elgon | 0.8437196/34.65948 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2018/2019 | 43864 | 44049 |  | 3600000 | 3300000 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 2643329.4 | 80.1% | 2643329.4 | 656670.6 | 656670.6 | Complete and in use | 1 | [14 empty] | Operational
8 | Upgrading of Kotiem Spring in Elgon Ward and Extension of Kamneru water project in Kapkatenyi Ward | Rehabilitation of spring, rehabilitation of sump, installation of solar pumping system, pipelaying; erction of a 30cubic metres, elevated pressed tank; construction of water points. | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | Elgon | 0.863215/34.733392 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 8000000 | 7436900 | 7436900 | FLLOCA | N/A | 7436900 | 0 | 0 | 100% | 7436900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Requires upgrade
22 | Hass Avocado Fruit Tree Production In Mt Elgon And Sirisia Sub Counties. | Supply and distribution of certified and grafted Hass avocado seedlings, Provision of manure, pegging, holing , training of nursery operators and maintanance of the orchard for 3 months | To promote climate change mitigation and adaptation | Hass avocado fruit tree planted | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5435600 | 5126000 | 5126000 | FLLOCA | KFW | 0 | 5126000 | 0 | 100% | 0 | 0 |  | On going and not in use | 0.7 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
28 | Proposed Establishment And Maintenance Of Tree Nurseries In Mt. Elgon Sub-County Under The Flloca Programme | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Tree nurseries established and maintained | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5684000 | 5460000 | 5460000 | FLLOCA | IDA | 0 | 5460000 | 0 | 100% | 0 | 0 |  | On going and not in use | 0.1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
80 | Bugaa water project in Elgon Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Water project constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon | 0.84229/34.71 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 6000000 | 5869774 | 5869774 | CGB | N/A | 5869774 | 0 | 5869774 | 100% | 5869774 | 0 | 0 | Complete and in use | 100% completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Maintanance and repair
126 | Rehabilitation and extension of Labaa water project in Elgon ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon | 0.8609849/34.7324365 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 5000000 | 4937555 | 4937555 |  | N/A | 4937555 | 0 | 4937555 | 100% | 4937555 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Water treatment and fencing
186 | PROTECTION OF 3 NO. WATER SPRINGS-Kisungen,Kimobo and Kapsokwony. | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon | 0.8437196/34.65948 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 600000 | 587000 | 587000 |  | N/A | 587000 | 0 | 587000 | 100% | 587000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Fencing
217 | KABERWA-KAPSOWONY-CHESAMISI-MAENI-KAMKUYWA WATER PROJECT PHASE I | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 35200000 | 35057364 | 35057364 |  | N/A | 35057364 | 0 | 35057364 | 100% | 11639962 | 23417402 | 0 | Complete and in use | 0.5 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
261 | SAMBOCHO WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon | 0.8475077/34.64922 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 5000000 | 4963999.6 | 4963999.6 |  | N/A | 4963999.6 | 0 | 4963999.6 | 100% | 4963999.6 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
313 | CONSTRUCTION OF WATER PIPELINE EXTENSION OF NAMORIO | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon | 0.8183215/34.6544 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 6000000 | 5933608.8 | 5933608.8 |  | N/A | 5933608.8 | 0 | 5933608.8 | 100% | 5933608.8 | 0 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Reconstruction
314 | CONSTRUCTION OF CHESAMISI-KAMUKUYWA PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2464800 | 2464800 |  | N/A | 2464800 | 0 | 2464800 | 100% | 2464800 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
316 | CHEBKWABI-KIBINGE WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 36034960 | 36034960 | 36034960 |  | N/A | 36034960 | 0 | 36034960 |  | 29188318 | 6846642 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
396 | Construction of 3 R/Catchment | Erection of storage tank; pipe laying and costruction of water points | To enhance access to clean and safe drinking water | 3 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1300000 | 1223180 | 1223180 |  | N/A | 1223180 | 0 | 1223180 | 100% | 1223180 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
404 | Rehabilitation and Extention of Chepyuk - Kapkateny Water PROJECT | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2200000 | 2028247 | 2028247 |  | N/A | 2028247 | 0 | 2028247 | 100% | 2028247 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
409 | Kapsokwony water project and kipchiria A&B shallow well | Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 2 Shallow well rehabilitated | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon | 0.8414721/34.76 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 4500000 | 4365290 | 4365290 |  | N/A | 4365290 | 0 | 4365290 | 100% | 4365290 | 0 | 0 | In complete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Completion required
435 | Kapsokwony water project and kipchiria A&B shallow well | Trenching; laying of water pipeline and water points; Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | KM of water pipeline constructed; and 1 well constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 4500000 | 4365290 | 4365290 |  | N/A | 4365290 | 0 | 4365290 | 100% | 4365290 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
544 | Kapsokwony water project and kipchiria A shallow well | Trenching; laying of water pipeline and water points; construction of roof catchment; digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of hand pump | To enhance access to clean and safe drinking water | KM of pipeline constructed and 1 shallow well | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 9000000 | 8730580 | 8730580 |  | N/A | 8730580 | 0 | 8730580 | 100% | 8730580 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
618 | Rehabilitation of Chebchekwech pipeline and construction of 3 Springs | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works |  | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3465270 | 3465270 |  | N/A | 3465270 | 0 | 3465270 | 100% | 3465270 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
619 | Construction of 3 R/Catchment | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 3 E4roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Mt Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1400000 | 1223180 | 1223180 |  | N/A | 1223180 | 0 | 1223180 | 100% | 1223180 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
620 | Elgon East Water Project intake rehabilitation | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt Elgon | Elgon |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 95000 | 95000 | 95000 |  | N/A | 95000 | 0 | 95000 | 100% | 95000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Purchase and installation of Automatic Weather Stations | Purchase and installation of 4 Automatic Weather Stations in Bumula, Township, Malakisi/Kulisiru and Elgon Wards | To collect precise and continous weather data | 4 Automatic Weather stations installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Bumula/Kanduyi/Sirisia/Mt. Elgon | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 40000000 | 35547910 | 40000000 | County Government of Bungoma |  | 35547910 |  | 35547910 | 100% | 35547910 |  | 0 | Completed
| Supply Of Tea Seedlings /Cuttings | Supply of 10,000 Tea Seedlings /Cuttings to farmer groups in Mt. Elgon | To enhance on tea production and income generation in the County | 10,000 tea seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | Mt. Elgon | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 42097 | 5000000 | 3700000 | 3700000 | County Government of Bungoma |  | 3700000 |  | 3700000 | 100% | 3700000 | 0 | 0 | Completed
| Support of completion of Coffee Mill at Mt Elgon Cooperative | Support of completion of Coffee Mill at Mt Elgon Cooperative | To enhance coffee production, value addition and income generation | 1 Coffed Mill completed at Mt. Elgon Cooperative | 3110504 | Other infrastructure and civil works | Mt. Elgon | Elgon |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42279 | 42283 | 30/5/2015 | 10000000 | 5000000 | 5000000 | County Government of Bungoma |  | 5000000 |  | 5000000 | 100% | 5000000 | 0 | 0 | Completed
| Completion of Sub County Agricultural Office in Mt Elgon | Completion of Sub County Agricultural Office in Mt Elgon | To provide for a conducive and an enabling working environment | 1 Agricultural office constructed in Mt. Elgon | 3110504 | Other infrastructure and civil works | Mt. Elgon | Elgon | 0.842305/34.7168 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 23/12/2015 | 23/4/2016 | 42374 | 5000000 | 3996976.04 | 4000000 | County Government of Bungoma |  | 3996976.04 |  | 3996976.04 | 100% | 3996976.04 | 0 | 0 | Complete and in use | [15 empty] | Equiping required
| Transportation Of Tea Seedlings | Transportation of Tea Seedlings | To enhance tea production and increase income among tea farmers | 8,000 tea seedlings transported | 2210301 |  | Mt. Elgon | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 20/2/2017 | 6000000 | 2400000 | 2500000 | County Government of Bungoma |  | 2400000 | 0 | 2400000 | 100% | 2400000 | 0 | 0 | Completed
| Purchase of coffee seeds | Purchase of 500kgs ofcoffee seeds | To promote coffee production and enhance income generation among Coffee farmers | 500kgs of Coffee seeds purchased | 3111301 | Purchase of Certified Crop seed | Mt. Elgon | Elgon |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 27/1/2019 | 27/4/2019 | 24/3/2019 | 2000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of Coffee seedlings | Purchase and delivery of 650kgs of Coffee seedlings | To promote coffee production and income generation | 650kgs of coffee seedlings purchased and delivered | 3111301 | Purchase of Certified Crop seed | Mt. Elgon/Kabuchai | Elgon |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 30/3/2020 | 10,00,000 | 4999137 | 5000000 | County Government of Bungoma |  | 4999137 | 0 | 4999137 | 100% | 4999137 | 0 | 0 | Completed
| Purchase of coffee seed tubes | Purchase and delivery of 50 dozens of 12 Coffee Seed tubes to cooperative Societies | To promote coffee production and income generation | 50 dozens of 12 Coffee Seed tubes purchased and delivered to coffee societies | 3111301 | Purchase of Certified Crop seed | Mt. Elgon/Kabuchai | Elgon |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 28/3/2020 | 5000000 | 1990000 | 2000000 | County Government of Bungoma |  | 1990000 | 0 | 1990000 | 100% | 1990000 | 0 | 0 | Completed
| Purchase of Coffee Seedlings | Purchase and delivery of 271kgs of Coffee Seedlings | To promote coffee production and enhance income generation among Coffee farmers | 271kgs of Cofee seedlings purchased and delivered | 3110599 | Ward Based projects | Mt. Elgon | Elgon |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 15/1/2023 | 15/3/2023 | 22/7/2023 | 2500000 | 1996000 | 2500000 | County Government of Bungoma |  | 1996000 | 0 | 1061000 | 53% | 1061000 | 935000 | 935000 | Completed
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
89 | Construction of 3No Bodaboda sheds | Of sheds streetlights | [5 empty] | Elgon |  | Trade, Energy and Industrialization | Dept of Trade | Calsilanic Building and Civil contractors Ltd | 2021/22 |  | Complete and in use |  | 968350 |  |  | CGB
106 | Proposed installation of 25 no. Grid powered street lights in Mt. Elgon Sub County | installation Grid lights street in Mt | [5 empty] | Elgon |  |  |  | M/S FECAKO Investments Limited | 2020/21 |  | Complete |  | 2434212.5 |  |  | CGG
112 | Construction of 1 no. bodaboda shed at Kapsokwony | of Kapsokwony no. bodaboda | [5 empty] | Elgon |  |  |  | Anoksmatic Investments ltd | 2023/2024 | 0.8446/34.74 | Complete |  | 293200 |  |  | CGG | [8 empty] | Complete and in use | [15 empty] | Murraming
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Elgon |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Elgon | 0.8434760/34.7153223 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Complete and in use | [15 empty] | Increased beneficiaries
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Elgon | 0.83961/34.718 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Complete | [15 empty] | Delivered
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Elgon |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Elgon |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
73 | Construction of ECDE classroom at Kananachi Primary school | [7 empty] | 0.81461978/34.7019327 |  |  |  | 2019/2020 | [6 empty] | CGB | [8 empty] | Complete and in use | [15 empty] | Fairely done
74 | Supply and delivery of fertielizer | [5 empty] | Mt. Elgon | Elgon | 0.839671/34.718 | Agriculture, Rural and Urban Development |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete and in use | [15 empty] | Timely delivery
6 | Completion works of outpatient at Kimama dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | outpatient wings completed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45628 |  |  | 1000000 | 986720 | 986720 | CGB |  | 986720 | 0 | 885520 | 89.74% | 885520 | 101200 | 101200 | Complete | 100 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
6 | Erecction and completion works for outpatient at Sacho dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Outpatient wings erected and completed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45628 |  |  | 5000000 | 5687580 | 5687580 | CGB |  | 5687580 | 0 | 1437870 | 25.28% | 1437870 | 985610 | 4249710 | On-going | 38 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
6 | Completion of Kipsabula dispensary and construction of 2NO door pit latrines | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries completed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 2000000 | 1898351 | 1898351 | CGB |  | 1898351 | 0 | 0 | 0% | 0 | 61360 | 1898351 | On-going | 93 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
6 | Erection And Completion Of Maternity Wing And 2no. Door Pit Latrines At Rwanda Dispensary. | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings erected and completed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 4000000 | 3508940 | 3508940 | CGB |  | 3508940 | 0 | 1313350 | 37.43% | 1313350 |  | 2195590 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
6 | Construction Of Placenta Pits At Kapkateny,Sacho, Kpsamba And Kamuneru Dispensaries | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | placenta pits constructed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 1000000 | 925000 | 925000 | CGB |  | 925000 | 0 | 909874 | 98.36% | 909874 |  | 15126 | Complete and in use | [6 empty] | No | complete | Financial | Yes
163 | Costruction Of Kapkeke Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 4000000 | 3748750 | 3748750 | CGB |  | 3748750 | 0 | 1166249 | 31.11% | 1166249 |  | 2582501 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
190 | Costruction Of Kapkeke Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 4000000 | 3748750 | 3748750 | CGB |  | 3748750 | 0 | 1166249 | 31.11% | 1166249 |  | 2582501 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
202 | Construction Of Kapsambu Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 4000000 | 3933745.6 | 3933745.6 | CGB |  | 3933745.6 | 0 | 3933745 | 100% | 3933745 |  | 0.6 | complete and in use | [6 empty] | No | complete | Financial | Yes
203 | Construction Of Kipsabula Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | kapkateny |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 4000000 | 4222168 | 4222168 | CGB |  | 4222168 | 0 | 3617292 | 85.67% | 3617292 |  | 604876 | Stalled at roofing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
223 | Proposed Erection And Completion Of A Maternity Wing At Kamuneru Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Mt. Elgon | kapkateny |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1188640.46 | 1411640 | 1411640 | CGB |  | 1411640 | 0 | 1410896.4 | 99.95% | 1410896.4 |  | 743.6 | Complete and in use | [6 empty] | No | complete | Financial | Yes
224 | Proposed Erection And Completion Of A Maternity Wing At Kamuneru Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Mt. Elgon | kapkateny |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1188640.46 | 1411640 | 1411640 | CGB |  | 1411640 | 0 | 1410896.4 | 99.95% | 1410896.4 |  | 743.6 | Complete and in use | [6 empty] | No | complete | Financial | Yes
280 | Erection and completion of outpatient unit at Kapkateny dispensary | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | Outpatient wings erected and completed |  |  | Mt. Elgon | kapkateny |  |  | CEF | Health & Sanitation | 2016/2017 | 29th Dec 2016 | 29th March 2017 | 17th May 2017 |  | 3230802 | 3230802 | CGB |  | 3230802 | 0 | 2643687 | 81.83% | 2643687 |  | 587115 | 99% complete. | [6 empty] | No | complete | Financial | Yes
31 | Upgrading of Periodic Maintanance Of Kapkateny Mkt-Sacho-Wambete | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41656 | 41778 |  | 4239858 | 4239858 | 4239858 | County Government of Bungoma |  | 4239858 |  | 4239858 | 100.0% | 4239858 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
183 | Periodic Maintenance of Chebich - Cheptakat - Toywandet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43237 |  | 7055143 | 7055143 | 7055143 | County Government of Bungoma |  | 7055143 |  | 7055143 |  | 7055143 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
184 | Periodic Maintenance of Roads In Kapkatenyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43233 |  | 7055143 | 7055143 | 7055143 | County Government of Bungoma |  | 7055143 |  | 7055143 | 140.72% | 7055143 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
349 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
774 | Periodic Maintenance of Masaek Market - Kiptungururwo Primary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44328 |  | 3742914 | 3742914 | 3742914 | County Government of Bungoma |  | 3742914 |  | 3742914 |  | 3742914 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
775 | Periodic Maintenance of Roads In Kapkateny Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44328 |  | 3742914 | 3742914 | 3742914 | County Government of Bungoma |  | 3742914 |  | 3742914 | 99.84% | 3742914 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1096 | Periodic Maintenance of Cheptonon Centre - Chepyuk Border Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44694 | 44725 | 9511362 | 9511362 | 9511362 | County Government of Bungoma |  | 9511362 |  | 9511362 |  | 9511362 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1097 | Periodic Maintenance of Kamuneru Main - Kimakina Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44701 | 44732 | 9511362 | 9511362 | 9511362 | County Government of Bungoma |  | 9511362 |  | 9511362 |  | 9511362 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1098 | Periodic Maintenance of Kapkateny - Sacho - Kamuneru Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44693 |  | 6909627 | 6909627 | 6909627 | County Government of Bungoma |  | 6909627 |  | 6909627 |  | 6909627 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1099 | Periodic Maintenance of Kapkateny - Mpakani - Terem Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44696 |  | 6254827.3 | 6254827.3 | 6254827.3 | County Government of Bungoma |  | 6254827.3 |  | 6254827.3 |  | 6254827.3 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1100 | Periodic Maintenance of Roads In Kapkateny Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44696 |  | 9511362 | 9511362 | 9511362 | County Government of Bungoma |  | 9511362 |  | 9511362 | 82.57% | 9511362 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1101 | Routine Maintenance Of Kapkateny - Sacho - Kamuneru Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44696 |  | 6909627 | 6909627 | 6909627 | County Government of Bungoma |  | 6909627 |  | 6909627 | 90.49% | 6909627 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1102 | Routine Maintenance Of Kapkateny - Mpakani Intake | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44695 |  | 6254827.3 | 6254827.3 | 6254827.3 | County Government of Bungoma |  | 6254827.3 |  | 6254827.3 | 94.44% | 6254827.3 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1248 | Upgrading of Roads In Kapkateny Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44695 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1405 | Periodic Maintenance of Chelebei - Kapkurongo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45067 |  | 9337991 | 9337991 | 9337991 | County Government of Bungoma |  | 9337991 |  | 9337991 |  | 9337991 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1406 | Periodic Maintenance of Kamuneru Bridge - _X000D_ Kapchoywo Primary | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45061 |  | 2952200 | 2952200 | 2952200 | County Government of Bungoma |  | 2952200 |  | 2952200 |  | 2952200 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1407 | Periodic Maintenance of Chelebei - Kapkurongo Road In Kapkateny Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45063 |  | 9337991 | 9337991 | 9337991 | County Government of Bungoma |  | 9337991 |  | 9337991 | 99.27% | 9337991 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1408 | Routine Maintenance Of Kamuneru Bridge - Kapchoywo Primary road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45066 |  | 2952200 | 2952200 | 2952200 | County Government of Bungoma |  | 2952200 |  | 2952200 | 100.0% | 2952200 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1660 | Periodic Maintenance of Toywondet - Kapkeke Dispensary - Kapkeke Primary Road In Kapkateny | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | kapkateny |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45426 |  | 8835372 | 8835372 | 8835372 | County Government of Bungoma |  | 8835372 |  | 8835372 | 79.1% | 8835372 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
49 | Purchase of 1 Acre land for Masaek dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land for Masaek dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | kapkateny |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2021/22 | 44713 | 45078 | 45566 | 1000000 | 500000 | 500000 | CGB |  | 500000 |  | 500000 | 100% | 880000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
75 | Purchase Of Land For Kipsabula Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land For Kipsabula Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | kapkateny |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 |  |  |  | 1000000 | 500000 | 500000 | CGB |  | 500000 |  | 500000 | 100% | 0 | [18 empty] | The project is staled due Lack of documentations(Title deed)
76 | Purchase Of 1/2 An Acre Land For Kamuneru Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | Half an acre of Land For Kamuneru Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | kapkateny |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 |  |  |  | 800000 | 500000 | 500000 | CGB |  | 500000 |  | 500000 | 100% | 0 | [18 empty] | The project is staled due Lack of documentations(Title deed)
77 | Purchase Of 1/2 An Acre Land For Sacho Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | Half an acre of Land For Sacho Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | kapkateny |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 |  |  |  | 1000000 | 500000 | 500000 | CGB |  | 500000 |  | 500000 | 100% | 0 | [18 empty] | The project is staled due Lack of documentations(Title deed)
78 | Purchase Of 1 Acre Land For Kapkeke Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land For Kapkeke Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | kapkateny |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 | 21/2/2020 | 22/4/2020 | 30/6/2020 | 2000000 | 1000000 | 1000000 | CGB |  | 1000000 |  | 1000000 | 100% | 750000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
7 | Construction of 1 No. ECDE Classroom at Kipsabula, Toywondet and Kapchoywa primary schools in Kapkateny Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | kapkateny |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 4500000 | 4490000 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 4490000 | 100% | 4490000 | 0 | 0 | Completed
30 | Proposed completion works for 1.no ECDE classroom at Kipsoen, Kapkeke and Chemosit primary school | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | kapkateny |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 2800000 | 2726696 | 2800000 | County Government of Bungoma | N/A | 2800000 | 0 | 2726696 | 100% | 2726696 | 0 | 0 | Completed
77 | construction of 1 no. ECDE at liambokho, kipteka and chebin primary schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | kapkateny |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 4500000 | 4423600 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 732568.15 | 16.56% | 732568.15 | 3691031.85 | 3691031.85 | Complete and not in use | 1
111 | Construction Of 1 No. Ecde Classroom At Muruani, Chebchabai, Chebich And Masaek Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | kapkateny |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 6000000 | 4224060 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 0 | 0% | 0 | 4224060 | 4224060 | Ongoing | 0.8
139 | Proposed Erection And Completion Of 1 No. Ecde At Kipsoen, Kapkeke And Chemositet Primary Schools In Kapkateny Ward. | Construction of ECDE classroom |  | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | kapkateny |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 4500000 | 4474260 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 1749401 | 39.1% | 1749401 | 2724859 | 2724859 | ongoing. At ring beam | 0.5
171 | Construction Of 1 No Ecde Classroom At Kimorong Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | kapkateny |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 1100000 | 834300 | 1100000 | County Government of Bungoma | N/A | 1100000 | 0 | 834300 | 100% | 834300 | 0 |  | complete and in use | 1
193 | Proposed Erection And Completion Of 1 N0 Classroom At Kamuneru Primary School In Kapkateny Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | kapkateny |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 1584854 | 1673340 | 1584854 | County Government of Bungoma | N/A | 1584854 |  | 1673340 | 100% | 1673340 | 0 |  | complete and in use | 100.0%
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | [6 empty] | FLLOCA | N/A |  | 0 |  | 100% |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
43 | Extension of Kamuneru pipeline | Trenching and laying of water pipeline | To enhance access to clean and safe drinking water | Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2973776 | 2973776 | CGB | N/A | 2973776 | 0 | 2973776 | 100% | 2973776 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
148 | Piping of chabware water to community kapchoywa | Trenching and laying of water pipeline | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2000000 | 1939995 | 1939995 |  | N/A | 1939995 | 0 | 1939995 | 100% | 1939995 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
168 | Extension of Kapsogom-Chepchabai-Cheptonon Water project | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 3000000 | 2994609 | 2994609 |  | N/A | 2994609 | 0 | 2994609 | 100% | 2994609 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
190 | CHEPTONONI,CHEBCHABAI- KIPJIPCHO WATER PROJECT | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2000000 | 1902432 | 1902432 |  | N/A | 1902432 | 0 | 1902432 | 100% | 1902432 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
245 | EXTENSION OF KOICA-KAPSAMBU WATER PROJECT IN KAPKATENY WARD | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1800000 | 1684001 | 1684001 |  | N/A | 1684001 | 0 | 1684001 | 100% | 1684001 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
312 | CONSTRUCTION OF WATER PIPES FROM KAMNERU-SACHO COMMUNITY WATER PROJECTS AND INSTALLTION OF WATER TANK | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 7500000 | 7243748 | 7243748 |  | N/A | 7243748 | 0 | 7243748 | 100% | 7243748 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
316 | CHEBKWABI-KIBINGE WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 36034960 | 36034960 | 36034960 |  | N/A | 36034960 | 0 | 36034960 |  | 29188318 | 6846642 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
356 | EMIA CHENGOYWO Springs construction | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 618300 | 618300 |  | N/A | 618300 | 0 | 618300 | 100% | 618300 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
461 | EMIA CHENGOYWO Springs construction | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1545750 | 1545750 |  | N/A | 1545750 | 0 | 1545750 | 100% | 1545750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
546 | EMIA CHENGOYWO Springs construction | excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 8000000 | 7527750 | 7527750 |  | N/A | 7527750 | 0 | 7527750 | 100% | 7527750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
547 | Construction of Chepyuk Kapkateny water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 5500000 | 5481750 | 5481750 |  | N/A | 5481750 | 0 | 5481750 | 100% | 5481750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
549 | Chepyuk kapkateny/ Water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | kapkateny |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2800000 | 2612550 | 2612550 |  | N/A | 2612550 | 0 | 2612550 | 100% | 2612550 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
15 | Construction of Kapkateny ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Kapkateny ward office constructed | 3111504 | Construction of non- residential buildings | Mt. Elgon | kapkateny | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2023/24 | 45300 | 45415 | - | 9500000 | 9485500 | 9500000 | County Government of Bungoma | - | 9485500 | - | 9485500 | 100% | 0 | 0 | 0 | Ongoing | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | Dite dispute delayed project implementation. No resolved.
| Purchase and delivery of Coffee seedlings | Purchase and delivery of 650kgs of Coffee seedlings | To promote coffee production and income generation | 650kgs of coffee seedlings purchased and delivered | 3111301 | Purchase of Certified Crop seed | Mt. Elgon | kapkateny |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 30/3/2020 | 10,00,000 | 4999137 | 5000000 | County Government of Bungoma |  | 4999137 | 0 | 4999137 | 100% | 4999137 | 0 | 0 | Completed
| Purchase of coffee seed tubes | Purchase and delivery of 50 dozens of 12 Coffee Seed tubes to cooperative Societies | To promote coffee production and income generation | 50 dozens of 12 Coffee Seed tubes purchased and delivered to coffee societies | 3111301 | Purchase of Certified Crop seed | Mt. Elgon | kapkateny |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44167 | 44170 | 28/3/2020 | 5000000 | 1990000 | 2000000 | County Government of Bungoma |  | 1990000 | 0 | 1990000 | 100% | 1990000 | 0 | 0 | Completed
| Purchase of coffee machine for Kapsacho factory | Purchase of Coffee machine for Kapsacho factory | To promote coffee production and enhance income generation among Coffee farmers | 1 Coffee machine purchased | 2211007 | Purchase of Agricultural Machinery and Equipment | Mt. Elgon | kapkateny |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 44470 | 44475 | 13/3/2021 | 5000000 | 2999999 | 3000000 | County Government of Bungoma |  | 2999999 | 0 | 2999999 | 100% | 2999999 | 0 | 0 | Completed
| Construction of Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | Construction of 20 Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | To support growth of coffee farmers and enhance income generation | 20 Coffee drying tables constructed | 3110504 | Other infrastructure and civil works | Mt. Elgon | kapkateny |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44900 | 44838 | 10000000 | 3087863.88 | 3100000 | County Government of Bungoma |  | 3087863.88 | 0 | 3087863.88 | 100% | 3087863.88 | 0 | 0 | Completed
| Purchase of pulping machine at Kutere Coffee Factory | Purchase of pulping machine at Kutere Coffee Factory | To promote coffee production and enhance income generation among Coffee farmers | 1 Coffee of pulping machines purchased | 3110599 | Ward Based projects | Mt. Elgon | kapkateny |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 14/1/2023 | 14/3/2023 | 15/2/2023 | 3500000 | 3495000 | 3500000 | County Government of Bungoma |  | 3495000 | 0 | 3495000 | 100% | 3495000 | 0 | 0 | Completed
79 | Installation of 30 grid powered streetlights in kanduyi, Tongaren and Mt. Elgon sub counties | of streetlights Tongaren kanduyi and Mt | [5 empty] | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | M/S Eagle Power services Limited | 2021/22 |  | Complete and in use |  | 2278500 |  |  | CGB
90 | Construction of 3No Bodaboda sheds | Of sheds streetlights | [5 empty] | kapkateny |  | Trade, Energy and Industrialization | Dept of Trade | Lweya (Kenya) Company Limited | 2021/22 |  | Complete and in use |  | 990340 |  |  | CGB
106 | Proposed installation of 25 no. Grid powered street lights in Mt. Elgon Sub County | installation Grid lights street in Mt | [5 empty] | kapkateny |  |  |  | M/S FECAKO Investments Limited | 2020/21 |  | Complete |  | 2434212.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | kapkateny |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | kapkateny |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | kapkateny |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
28 | Purchase of medical equipment for Milani dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45356 |  |  | 2000000 | 1880920 | 1880920 | CGB |  | 1880920 | 0 | 0 | 0% | 0 | 1880920 | 1880920 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
55 | erection and completion works for male, female and children wards at milani dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Female, male and children wards erected and completed |  |  | Webuye West | Bokoli |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 20/2/24 |  |  | 5000000 | 4901892 | 4901892 | CGB |  | 4901892 | 0 | 2667780 | 54.42% | 2667780 |  | 2234112 | On-going | 91 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
69 | Construction Of Wards At Milani Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2500000 | 2254670 | 2254670 | CGB |  | 2254670 | 0 | 2425000 | 107.6% | 2425000 |  | -170330 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
70 | Construction Of Wards At Machakha Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2500000 | 2303000 | 2303000 | CGB |  | 2303000 | 0 | 545607.69 | 23.69% | 545607.69 |  | 1757392.31 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
94 | Completion Of Milimani Dispensary And Extention Works | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries completed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2100000 | 2060000 | 2060000 | CGB |  | 2060000 | 0 | 0 | 0% | 0 |  | 2060000 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
95 | Construction Of Maternity Wards At Mahanga Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2000000 | 1939880 | 1939880 | CGB |  | 1939880 | 0 | 1531705.24 | 78.96% | 1531705.24 |  | 408174.76 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
121 | Construction Of Milani Dispenary And 2 Pit Latrines | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries and 2no pit latrines constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2700000 | 2599107.6 | 2599107.6 | CGB |  | 2599107.6 | 0 | 1242058.4 | 47.79% | 1242058.4 |  | 1357049.2 | Complete and in use | [6 empty] | No | complete | Financial | Yes
153 | Proposed Erection And Competion Works At Machakha Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2066537 | 1984990 | 1984990 | CGB |  | 1984990 | 0 | 1757803 | 88.55% | 1757803 |  | 227187 | Complete and not in use | [6 empty] | No | complete | Financial | Yes
35 | Construction of Kituni Mkt-R.Kuywa-Miendo Junt With Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41661 | 41783 |  | 16111704 | 16111704 | 16111704 | County Government of Bungoma |  | 16111704 |  | 16111704 | 100.0% | 16111704 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
147 | Periodic Maintenance of Wanyonyi - Mahale-Kaita Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43241 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 |  | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
148 | Periodic Maintenance of Namawanga - Miendo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43233 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 |  | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
149 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43232 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 | 99.24% | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
277 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
278 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
463 | Periodic Maintenance of Sawa- Wanambisi - Kakai Road | Road improvement works | To improve the road condition and enhance accessibility | Road gravelled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43963 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 |  | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
464 | Periodic Maintenance of Mukhale Kaita Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43975 | 44006 | 3137684 | 3137684 | 3137684 | County Government of Bungoma |  | 3137684 |  | 3137684 |  | 3137684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
465 | Periodic Maintenance of Temba-Muchocho Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
466 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43968 |  | 3137684 | 3137684 | 3137684 | County Government of Bungoma |  | 3137684 |  | 3137684 | 99.9% | 3137684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
637 | Routine Maintenance Of Roads In Webuye East And Webuye West Sub- Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
638 | Drainage Works In Webuye East And Webuye West Sub-Counties(Lot 4) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43966 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 | 88.12% | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
688 | Construction of Tuliyonga - Mahanga Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44326 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
689 | Periodic Maintenance of Tuliyonga - Abel - Mahanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44328 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
690 | Periodic Maintenance of Miendo - Chebini Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44326 | 44357 | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
691 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44334 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 | 99.89% | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1024 | Periodic Maintenance of Moyokwe - Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44699 | 44730 | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1025 | Periodic Maintenance of Chebosi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44694 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1026 | Periodic Maintenance of Namilimo - Sitabicha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1027 | Periodic Maintenance of Bruno - Namawanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44701 | 44732 | 5707519.8 | 5707519.8 | 5707519.8 | County Government of Bungoma |  | 5707519.8 |  | 5707519.8 |  | 5707519.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1028 | Periodic Maintenance of Asiba - Kaliwanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44699 | 44730 | 3736012 | 3736012 | 3736012 | County Government of Bungoma |  | 3736012 |  | 3736012 |  | 3736012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1029 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44701 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 | 99.73% | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1030 | Routine Maintenance Of Bruno - Namawanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44697 |  | 5707519.8 | 5707519.8 | 5707519.8 | County Government of Bungoma |  | 5707519.8 |  | 5707519.8 | 100.0% | 5707519.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1031 | Routine Maintenance Of Asiba - Kaliwanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44695 |  | 3736012 | 3736012 | 3736012 | County Government of Bungoma |  | 3736012 |  | 3736012 | 97.38% | 3736012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1253 | Routine Maintenance Of Mahanga Secondary - Chekulo - Sikinga Market Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44693 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1344 | Construction of Chebini Box Culvert On River Bokoli | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45070 |  | 6088985 | 6088985 | 6088985 | County Government of Bungoma |  | 6088985 |  | 6088985 |  | 6088985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1345 | Periodic Maintenance of Nandasaba - Sirwa - Sichai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45064 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 |  | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1346 | Periodic Maintenance of Mlani - Muresia - Mary Kangia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45067 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 |  | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1347 | Construction of Chebini Box Culvert Bokoli River Road In Bokoli Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45063 |  | 6088985 | 6088985 | 6088985 | County Government of Bungoma |  | 6088985 |  | 6088985 | 99.54% | 6088985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1348 | Periodic Maintenance of Nandasaba - Sirwa - Sichai, Mlani - Muresia - Mary Kangia Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45059 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 | 100.0% | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1600 | Periodic Maintenance of Wangwelo - Bokoli River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45431 |  | 3650346 | 3650346 | 3650346 | County Government of Bungoma |  | 3650346 |  | 3650346 |  | 3650346 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1601 | Periodic Maintenance of Wangamati - Malaria - Manga Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45433 |  | 5503411 | 5503411 | 5503411 | County Government of Bungoma |  | 5503411 |  | 5503411 |  | 5503411 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1602 | Periodic Maintenance of Wangwelo - Bokoli River Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45427 |  | 3650346 | 3650346 | 3650346 | County Government of Bungoma |  | 3650346 |  | 3650346 | 99.83% | 3650346 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1603 | Periodic Maintenance of Wangamati - Malaria - Manga Primary Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45435 |  | 5503411 | 5503411 | 5503411 | County Government of Bungoma |  | 5503411 |  | 5503411 | 98.4% | 5503411 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1604 | Periodic Maintenance of Roads In Webuye East And West Sub Counties Chesoli(Mulembe)-John Waswa-R.Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45426 |  | 3883096.4 | 3883096.4 | 3883096.4 | County Government of Bungoma |  | 3883096.4 |  | 3883096.4 | 99.32% | 3883096.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
3 | Purchase of 1 Acre land for Auction ring | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new auction ring | One acre of Land Purchased for auction ring | 3130101 | Purchase of land | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 |  |  |  | 1000000 | - | 1000000 | CGB | N/A | 1000000 | 0 | 1000000 | 100% | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2023/24 |  | 0 | No | Compete | [7 empty] | The project is stalled due Lack of documentations(Title deed)
110 | Purchase Of Land For Proposed Machakha Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new dispensary | One acre of Land for Machakha dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42866 | 18/4/2018 | 30/6/2018 | 700000 | 700000 | 700000 | CGB | N/A | 700000 | 0 | 700000 | 100% | 800000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
111 | Purchase Of Land For Proposed Milani Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new dispensary | One acres of Land for Milani Dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43049 | 15/3/2018 | 18/6/2018 | 700000 | 700000 | 700000 | CGB | N/A | 700000 | 0 | 700000 | 100% | 800000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
165 | Purchase of land-NAMATONDOI ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for NAMATONDOI E.C.D.E Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 750000 | 750000 | 750000 | CGB | N/A | 750000 |  | 750000 | 100% | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
166 | Purchase of 1 acre for milani dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for milani dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 15/8/2015 | 15/11/2015 | 13/12/2015 | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 100% | 1000000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
167 | Purchase of 1 acre for machakha dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for milani dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/01/2016 | 21/03/2016 | 42647 | 475500 | 475500 | 475500 | CGB | N/A | 475500 |  | 475500 | 100% | 475500 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
176 | Purchase of land for Namatondoi ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Namatondoi ECDE Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42461 | 42707 | 42466 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 |  | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
67 | Construction of ECDE classroom at matisi pry school | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1200000 | 1197500 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 0 | 0% | 0 | 1197500 | 1197500 | Complete and not in use | 1
99 | Construction Of 1 No. Ecde Classroom At Chebosi And Miendo Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3000000 | 2895000 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2895000 | 100% | 2895000 | 0 | 0 | complete and in use | 1
130 | Proposed Erection And Completion Of 1 No. Ecde At Sikimbilo Rc, Maloho And Ben Kapten Primary Schools In Bokoli Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 4800000 | 4787390 | 4800000 | County Government of Bungoma | N/A | 4800000 | 0 | 4787190 | 100% | 4787190 | 200 | 200 | complete and in use | 1
165 | Construction Of Ecde Classrooms At Mahanga Primary, Milani, Namilimo Primary And Namatondoi Primary | Construction of ECDE classroom and pit latrine | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli | [5 empty] | 43801 | 43775 |  | 4900000 | 5649840 | 4900000 | County Government of Bungoma | N/A | 4900000 | 0 | 5649840 | 100% | 5649840 | 0 |  | complete and in use | 1
182 | The Proposed Erection And Completion Of 1 N0 Classroom At Lukuku, Bokoli R.C And Sawa Primary School In Bokoli Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4150000 | 3515809 | 4150000 | County Government of Bungoma | N/A | 4150000 |  | 3515809 | 100% | 3515809 | 0 |  | complete and in use | 100.0%
2 | Construction and protection of Sirandafu Spring | Rehabilitation of spring, rehabilitation of sump, installation of solar pumping system, pipelaying; erction of a 30cubic metres, elevated pressed tank; construction of water points. | To enhance access to clean and safe drinking water | 1 Spring constructed and protected | 2640599 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 6000000 | 5812644 | 5812644 | FLLOCA | N/A | 5812644 | 0 | 0 | 100% | 5812644 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
45 | Upgrading of Matunda Borehole in Bokoli Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2960900 | 2960900 | CGB | N/A | 2960900 | 0 | 2960900 | 100% | 2960900 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
53 | Upgrading of Sawa Borehole in Bokoli Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2950000 | 2950000 | CGB | N/A | 2950000 | 0 | 2950000 | 100% | 2950000 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
138 | Drilling of borehole at matunda market ,machakha and bumang'ale | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4945500 | 4945500 |  | N/A | 4945500 | 0 | 4945500 | 100% | 4945500 | 0 | 0 | complete and operational | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
179 | DRILLING AND EQUIPPING OF NAMILIMO BOREHOLE | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2000000 | 1795680 | 1795680 |  | N/A | 1795680 | 0 | 1795680 | 100% | 1795680 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
234 | DRILLING OF SAWA AND SIKILIMBO MARKET BOREHOLES IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 3800000 | 3678824 | 3678824 |  | N/A | 3678824 | 0 | 3678824 | 100% | 3678824 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
235 | DRILLING OF NAMATONDOI PRIMARY BOREHOLE IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1800000 | 1789880 | 1789880 |  | N/A | 1789880 | 0 | 1789880 | 100% | 1789880 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
274 | DRILLING OF KAG CHURCH BOREHOLE IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1800000 | 1699900 | 1699900 |  | N/A | 1699900 | 0 | 1699900 | 100% | 1699900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
275 | DRILLING OF CHEBINI AND MAKUNDA BOREHOLES IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 3500000 | 3398000 | 3398000 |  | N/A | 3398000 | 0 | 3398000 | 100% | 3398000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
297 | CONSTRUCTION OF 4NO. SPRINGS AND DRILLING OF 1 BOREHOLE IN BOKOLI WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection;site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes rehabilitated and 4 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2458624 | 2458624 |  | N/A | 2458624 | 0 | 2458624 | 100% | 2458624 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
351 | Construction of 5Roof catchments and supply 10m3 Plastic tank at stikho youth polytechnic. | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 696710 | 696710 |  | N/A | 696710 | 0 | 696710 | 100% | 696710 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
368 | Nzowasco pipeline extension to Matulo | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1200000 | 1116520 | 1116520 |  | N/A | 1116520 | 0 | 1116520 | 100% | 1116520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
411 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1421260 | 1421260 |  | N/A | 1421260 | 0 | 1421260 | 100% | 1421260 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
516 | Protection of 8 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1300000 | 1116520 | 1116520 |  | N/A | 1116520 | 0 | 1116520 | 100% | 1116520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
517 | Drilling of Borehole and equipping with handpump at Sirwa | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1881065 | 1881065 |  | N/A | 1881065 | 0 | 1881065 | 100% | 1881065 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
595 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1421260 | 1421260 |  | N/A | 1421260 | 0 | 1421260 | 100% | 1421260 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
596 | Miendo piped scheme | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2363240 | 2363240 |  | N/A | 2363240 | 0 | 2363240 | 100% | 2363240 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
4 | Construction of Bokoli ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Bokoli ward office constructed | 3111504 | Construction of non- residential buildings | Webuye West | Bokoli | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43060 | 9500000 | 8960963 | 9500000 | County Government of Bungoma | - | 8960963 | - | 8960963 | 100% | 8960963 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Construction of Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | Construction of 20 Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | To support growth of coffee farmers and enhance income generation | 20 Coffee drying tables constructed | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44900 | 44838 | 10000000 | 3087863.88 | 3100000 | County Government of Bungoma |  | 3087863.88 | 0 | 3087863.88 | 100% | 3087863.88 | 0 | 0 | Completed
| Construction of Coffee Drying Tables at Sirandafu FCS in Bokoli Ward | Construction of 20 Coffee Drying Tables at Sirandafu FCS in Bokoli Ward | To support growth of coffee farmers and enhance income generation | 20 Coffee Drying tables constructed at Sirandafu FCS | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 21/1/2024 | 21/5/2024 | 15/6/2024 |  | 1997000 | 2000000 | County Government of Bungoma |  | 1997000 | 0 | 1997000 | 100% | 1997000 | 0 | 0 | Completed
46 | Proposed installation and commissioning of 3NO. 15M high solar powered floodlights | installation of M M high | promotion of MSMEs and security | Solar flood lights installed | 1358968/2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Project is complete | Complete and in use | 3000000 | 2909990 |  | CGB | [8 empty] | Complete | 100 | 3
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye |  |  |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A |  |  |  |  | Webuye West | Bokoli |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of |  |  |  |  | Webuye West | Bokoli |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
137 | Renovation of Matisi market | [5 empty] | Webuye West | Bokoli |  |  |  | Dynamic General Construction | 2016/17 |  | Complete |  | 12422753.2 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights |  |  |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
52 | construction of 4NO. Door Pit Latrines at Kisawayi Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Bumula | Siboti | 0.67/34.46 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 15/2/24 |  |  | 800000 | 774010 | 774010 | CGB |  | 774010 | 0 | 0 | 0% | 0 |  | 774010 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Contractor not on site
86 | Construction Of 4no. Door Pit Latrines At Miluki Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Bumula | Siboti | 0.64/34.46 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 1000000 | 890500 | 890500 | CGB |  | 890500 | 0 | 0 | 0% | 0 |  | 890500 | Complete but not in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Good work done
142 | Purchase Of Medical Equipments For Kisawanyi Dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Bumula | Siboti | 0.67/34.462 |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 1000000 | 830400 | 830400 | CGB |  | 830400 | 0 | 830400 | 100% | 830400 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
177 | Completion Of Mukwa Dispensary And Construction Of Sango Modern Toilets | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries with toilets constructed |  |  | Bumula | Siboti | 0.67/34.46 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2750290.68 | 2727080 | 2727080 | CGB |  | 2727080 | 0 | 1936040 | 70.99% | 1936040 |  | 791040 | Complete and partially in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | Equiping required
249 | Construction Of Kisawayi Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Siboti | 0.64/34.496 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2000000 | 1946793.2 | 1946793.2 | CGB |  | 1946793.2 | 0 | 1946793.2 | 100% | 1946793.2 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | No electricty
258 | Renovation and completion of Miluki dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the county. | Dispensaries renovated/completed |  |  | Bumula | Siboti | 0.67/34.46 |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42185 |  |  | 1831930 | 1831930 | CGB |  | 1831930 | 0 | 1586013 | 86.58% | 1586013 |  | 245917 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | Painting required
268 | Purchase of a two acre land for Kisawai Dispensary. | Land identification,search,survey,signing of agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Bumula | Siboti |  |  | Ward Based | Health & Sanitation | 2015/16 | 1st April 2015 |  | 20th May 2016 |  | 1400000 | 1400000 | CGB |  | 1400000 | 0 | 1400000 | 100% | 1400000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
269 | Construction of 2 door toilets at Nasyanda market | Digging of 20ft deep pit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the market | 2No. Door pit latrines constructed |  |  | Bumula | Siboti |  |  | Ward Fund | Health & Sanitation | 2014/15 | [6 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
137 | Construction of Masielo - Siboti Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.67/34.456 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42748 | 42868 |  | 7815244 | 7815244 | 7815244 | County Government of Bungoma |  | 7815244 |  | 7815244 | 100.0% | 7815244 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
240 | Periodic Maintenance of Musakasa Market - Siboti Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43112 | 43233 |  | 10600863 | 10600863 | 10600863 | County Government of Bungoma |  | 10600863 |  | 10600863 |  | 10600863 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
241 | Upgrading of Musakasa Market - Siboti Junction Bridge | Road improvement works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.64/34.49 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43233 |  | 10600863 | 10600863 | 10600863 | County Government of Bungoma |  | 10600863 |  | 10600863 |  | 10600863 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
242 | Periodic Maintenance of Wekesa Lazaro - Namuningie River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.67/34.49 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43113 | 43231 |  | 10600863 | 10600863 | 10600863 | County Government of Bungoma |  | 10600863 |  | 10600863 |  | 10600863 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
243 | Periodic Maintenance of Roads In Siboti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.675/34.44 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43235 |  | 10600863 | 10600863 | 10600863 | County Government of Bungoma |  | 10600863 |  | 10600863 | 91.38% | 10600863 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
421 | Periodic Maintenance of Roads In Siboti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.67/34.49 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43598 |  | 8098134 | 8098134 | 8098134 | County Government of Bungoma |  | 8098134 |  | 8098134 | 48.8% | 8098134 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
422 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.66/34.48 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No value for money. Ownership not with the county
639 | Periodic Maintenance of Khasolo - Musakasa - Netima Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.657/34.468 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43966 |  | 13673782 | 13673782 | 13673782 | County Government of Bungoma |  | 13673782 |  | 13673782 |  | 13673782 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
640 | Periodic Maintenance of Netima - Mukwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.657/34.468 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43962 |  | 13673782 | 13673782 | 13673782 | County Government of Bungoma |  | 13673782 |  | 13673782 |  | 13673782 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Maintanance required
641 | Construction of Mukwa Box Culvert(River Namanje) | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 3.5KM GRAVELLED | 3110399 |  | Bumula | Siboti | 0.67/34.48 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43963 |  | 13673782 | 13673782 | 13673782 | County Government of Bungoma |  | 13673782 |  | 13673782 |  | 13673782 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Sand harvesting be controlled
642 | Periodic Maintenance of Roads In Siboti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43963 |  | 13673782 | 13673782 | 13673782 | County Government of Bungoma |  | 13673782 |  | 13673782 | 94.99% | 13673782 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
933 | Periodic Maintenance of Miluki - Namanje - Lukhuna Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Siboti | 0.38/22.3- 0.34/28.30 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44331 |  | 6807373 | 6807373 | 6807373 | County Government of Bungoma |  | 6807373 |  | 6807373 |  | 6807373 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Gravelling and control sand harvesting
934 | Periodic Maintenance of Khasolo - Musakasa - Netima - Mukwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.657/34.468 - 0.6607/34.4701 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44337 |  | 6951126 | 6951126 | 6951126 | County Government of Bungoma |  | 6951126 |  | 6951126 |  | 6951126 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Lack proper drainage
935 | Periodic Maintenance of Roads In Siboti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44336 |  | 6951126 | 6951126 | 6951126 | County Government of Bungoma |  | 6951126 |  | 6951126 | 99.99% | 6951126 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
936 | Periodic Maintenance of Miluki - Namanje - Lukhuna Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44331 |  | 6807373 | 6807373 | 6807373 | County Government of Bungoma |  | 6807373 |  | 6807373 | 95.87% | 6807373 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1267 | Periodic Maintenance of Khasolo - Matisi - Sirende Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.64606/34.43918 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44693 | 44724 | 6451746 | 6451746 | 6451746 | County Government of Bungoma |  | 6451746 |  | 6451746 |  | 6451746 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1268 | Periodic Maintenance of Wakhateli Junction - Musakasa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.6498/34.45 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44697 | 44728 | 6451746 | 6451746 | 6451746 | County Government of Bungoma |  | 6451746 |  | 6451746 |  | 6451746 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Sand harvesting is rampand
1269 | Periodic Maintenance of Nang'Eni - Nangata - Siboti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44695 | 44726 | 10047203.7 | 10047203.7 | 10047203.7 | County Government of Bungoma |  | 10047203.7 |  | 10047203.7 |  | 10047203.7 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1270 | Periodic Maintenance of Roads In Siboti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44692 |  | 6451746 | 6451746 | 6451746 | County Government of Bungoma |  | 6451746 |  | 6451746 | 97.5% | 6451746 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1271 | Periodic Maintenance of Nang'Eni - Nangata - Siboti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44696 |  | 10047203.7 | 10047203.7 | 10047203.7 | County Government of Bungoma |  | 10047203.7 |  | 10047203.7 | 99.01% | 10047203.7 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1527 | Periodic Maintenance of Siboti - Wakheteli Junction - Longino Junction - Lurare - St. Kizito Masielo Sec School - Lurare Ecde - Khaemba Maji Moto Loop Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.64908/34.4517 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45061 |  | 8077432 | 8077432 | 8077432 | County Government of Bungoma |  | 8077432 |  | 8077432 |  | 8077432 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Lacks drainage
1528 | Periodic Maintenance of Siboti - Wawakheteli Junction - Longino Junction - Lurare - St. Kizito Masielo Sec School - Lurare Ecde - Khaemba Maji Moto Loop Road In Siboti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45065 |  | 8077432 | 8077432 | 8077432 | County Government of Bungoma |  | 8077432 |  | 8077432 | 99.42% | 8077432 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1770 | Construction of Proposed 3*2 Box Culvert On Silanga River And 4*2 On Kabubero River In Siboti Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45433 |  | 7316352 | 7316352 | 7316352 | County Government of Bungoma |  | 7316352 |  | 7316352 | 100.0% | 7316352 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1776 | Construction of Box Culverts Along Kabubero - Mukwa Road | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.67/34.4998 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45424 |  | 9487640 | 9487640 | 9487640 | County Government of Bungoma |  | 9487640 |  | 9487640 |  | 9487640 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1777 | Construction of 3X2 Box Culvert On Silanga River And 42 On Kabubero River | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Bumula | Siboti | 0.6596/34.4973-0.6554/34.4978 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45432 |  | 9487640 | 9487640 | 9487640 | County Government of Bungoma |  | 9487640 |  | 9487640 | 100.0% | 9487640 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | In good condition
54 | Purchase of 1 acre for Nangata,Sirende dispensaries,Murumba,Lukhuna,Matisi and Musole E.C.D.E. Centres | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centres | One acre of Land for each Nangata,Sirende dispensaries,Murumba,Lukhuna,Matisi and Musole E.C.D.E. Centres Purchased | 3110301 | Ward based projects | Bumula | Siboti |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2021/22 | 44594 | 29/3/2022 |  | 4500000 | 3000000 | 3000000 | CGB |  | 3000000 |  | 3000000 | 100% | 0 |  |  | Stalled | 0 | [14 empty] | Lack of documentations(Title deed)
191 | Purchase of 2 acres of land for kisawayi dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | Two acres of Land for kisaway dispensary Purchased | 3110599 | Ward based projects | Bumula | Siboti | 0.67/34.46 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 41885 | 41888 | 9/04//2014 | 1400000 | 1400000 | 1400000 | CGB | N/A | 1400000 |  | 1400000 | 100% | 1400000 |  |  | Completed | 1
212 | Construction Of 01 No. Ecde Classroom At Napara Ack And Lurare Primary School | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Siboti | 0.675/34.44 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3000000 | 2801140 | 3000000 | County Government of Bungoma | N/A | 3000000 |  | 2801140 | 100% | 2801140 | 0 |  | complete and in use | 100.0% | [14 empty] | Delapited floor
16 | Rehabilitation of Sitabicha Mult-Purpose Dam | Silt-trap; desilting;embarkment stabilization; spillway rehabilitation, water supply( composite filtration unit construction; underground masonry tank, pipeline, elevated steel tank 64m3 distribution line, solarization, irrigation pipeline, fish pond, apiary unit; fruit tree planting; indigenious tree planting; fencing; abolution block and pump house | To promote climate change mitigation and adaptation | Rehabilitation of 1 dam | 2640599 | Other Capital Grants and Transfers | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45907 | 45907 | 60000000 | 56108513.28 | 56108513.28 | FLLOCA | KFW | 0 | 56108513.28 | 0 | 100% | 0 | 0 |  | On going and not in use | 0.7 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes
72 | Extension of Pipelines in Siboti Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.6752/34.4290 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 8000000 | 7894148 | 7894148 | CGB | N/A | 7894148 | 0 | 7894148 | 100% | 7894148 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | No water at the taps
91 | Upgrading and Extension of Mukwa Community Borehole and Solarisation of Nasimbo Primary Borehole in Siboti Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.6728/34.4933 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 6000000 | 5661612 | 5661612 | CGB | N/A | 5661612 | 0 | 5661612 | 100% | 0 | 5661612 | 0 | complete and in use | 100% complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Brocken down
109 | Drilling and upgrading of Nangata primary and Kabubero primary boreholes in Siboti ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points. Improvement of a standard apron with a drainage tunnel and replacement of 1 Afridev hand pump | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.656/34.4964 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 7000000 | 6863904 | 6863904 |  | N/A | 6863904 | 0 | 6863904 | 100% | 0 | 6863904 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Not functional
110 | Rehabilitation of boreholes and shallow wells in siboti ward Lurende | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; digging of a 15ft shallow well; walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 1 Borehole upgraded and 1 shallow well rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.6791/34.4748 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1800000 | 1612864 | 1612864 |  | N/A | 1612864 | 0 | 1612864 | 100% | 1612864 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Not functional
163 | Masielo water project | Trenching and laying of water pipeline | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4000000 | 3923744 | 3923744 |  | N/A | 3923744 | 0 | 3923744 | 100% | 3923744 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes
176 | Siboti water project | Trenching ; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4968100.2 | 4968100.2 |  | N/A | 4968100.2 | 0 | 4968100.2 | 100% | 4968100.2 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes
209 | CONSTRUCTION OF NANDIKA WATER PROJECT IN SIBOTI WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 4100000 | 4042280 | 4042280 |  | N/A | 4042280 | 0 | 4042280 | 100% | 0 | 4042280 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes
210 | UPGRADING OF KISAWAYI AND MUSAKASA WATER PROJECTS | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.67/34.456 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 | 43253 |  | 43227 | 4200000 | 4077480 | 4077480 |  | N/A | 4077480 | 0 | 4077480 | 100% | 0 | 4077480 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes
218 | REHABILITATION AND EXTENSION OF CHESIKAKI-SIRISIA-BUMULA WATER PROJECT PHASE I | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 34000000 | 33391751.4 | 33391751.4 |  | N/A | 33391751.4 | 0 | 33391751.4 | 100% | 23831829 | 9559922 | 0 | Work in progress | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes
241 | DRILLING OF BOSIO(SURENDE) BOREHOLE AND INSTALLATION OF SOLAR PUMPING SYSTEM IN SIBOTI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and solarised. | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.6565/34.4433 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 3800000 | 3726782 | 3726782 |  | N/A | 3726782 | 0 | 3726782 | 100% | 3726782 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Maintanance required
265 | CONSTRUCTION OF SHALLOW WELLS IN KABUBERO | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points;Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 1 Borehole drilled and 2 shallow well constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.6562/34.4959 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 2200000 | 2099600 | 2099600 |  | N/A | 2099600 | 0 | 2099600 | 100% | 2099600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Not functional
300 | DRILLING OF BISUCHE BOREHOLE IN SIBOTI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.665/34.4666 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1923800 | 1923800 |  | N/A | 1923800 | 0 | 1923800 | 100% | 1923800 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Maintanance required
347 | Rehabilitation of Masielo Water project | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 2800000 | 2756620 | 2756620 |  | N/A | 2756620 | 0 | 2756620 | 100% | 2756620 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
415 | Drilling of borehole at St Patrick Netima Sec School in Mukwa Water Project | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.6728/34.4933 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 4200000 | 4001300 | 4001300 |  | N/A | 4001300 | 0 | 4001300 | 100% | 4001300 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | In adequate water
457 | Rehabilitation of Masielo Water Project | Improvement of a standard apron with drainage tunnel and replacement of 1 Afrdev hand pump | To enhance access to clean and safe drinking water | 1 Borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2700000 | 2565322 | 2565322 |  | N/A | 2565322 | 0 | 2565322 | 100% | 2565322 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
465 | Construct 5No Roof catchment and 1No. 50m3 Storage tank | construction of roof catchment;storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.6498/34.45 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1346695 | 1346695 |  | N/A | 1346695 | 0 | 1346695 | 100% | 1346695 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
531 | Rehabilitation of Masielo Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 5400000 | 5321942 | 5321942 |  | N/A | 5321942 | 0 | 5321942 | 100% | 5321942 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
604 | Upgrading of miluki borehole | Improvement of a standard apron with drainage tunnel and replacement of 1 Afrdev hand pump | To enhance access to clean and safe drinking water | 1 borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti | 0.64/34.49 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1424660 | 1424660 |  | N/A | 1424660 | 0 | 1424660 | 100% | 1424660 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Poor solar system installed
605 | Construction of Musakasa roof catchment | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 1 roof catchment constructed; 1 storage tank erected | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 400000 | 351720 | 351720 |  | N/A | 351720 | 0 | 351720 | 100% | 351720 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
606 | Drilling of a borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Siboti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 4100000 | 4001300 | 4001300 |  | N/A | 4001300 | 0 | 4001300 | 100% | 4001300 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Supply, delivery and installation of pond liners for farm ponds | Supply delivery and installation of pond liners for farm ponds | To control loss of water through infiltration | 10,430 pondliners supplied , delivered and installed | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 |  |  |  |  | 30375 | 50000 | Development partner | IDA | 0 | 30375 | 30375 |  | 30375 | 0 | 0 | Completed
| Purchase of tree seedlings for Wabukhonyi sustainable land management activities | Purchase of tree seedlings for Wabukhonyi sustainable land management activities | To enance fruit production, and income generation | Seedlings purchased and distributed | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 44109 | 44111 | 17/5/2020 |  | 13592 | 15000 | Development partner | IDA | 0 | 13592 | 13592 |  | 13592 | 0 | 0 | Completed
| Purchase and installation of solar pumps for fish ponds | Purchase and installation of 25 solar pumps for fish ponds | To circulate water, oxygenate it and maintain a healthy ecosystem | 25 solar pumps purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/9/2020 | 20/12/2019 | 44147 |  | 1799889 | 2000000 | Development partner | IDA | 0 | 1799889 | 1799889 |  | 1799889 | 0 | 0 | Completed
| Supply and Delivery of Fingerlings for farmers | Supply and Delivery of Fingerlings for farmers | To increase fish production and improve on food and nutrition security | Kgs of fish feeds purchased | 3110599 | Ward Based projects | Bumula | Siboti | 0.6439/34.4509 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44682 | 44684 | 18/2/2022 | 5000000 | 4797000 | 5000000 | County Government of Bungoma |  | 4797000 | 0 | 4797000 | 100% | 4797000 | 0 | 0 | Completed
| Supply and delivery of seedlings | Supply and delivery of seedlings | To enhance fruit production, productity and income generation | Seedlings purchased and distributed | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44784 | 45139 | 45079 |  | 4000 | 4000 | Development partner | IDA | 0 | 4000 | 4000 |  | 4000 | 0 | 0 | Completed
| Purchase of pond liners | Purchase of pond liners G 0.8mm HDPE liners 15,220 pcs PURCHASE OF POND LINERS G 1mm HDPE liners 704 pcs For Wabukhonyi SLM Project. | To control loss of water through infiltration | 15,924 pcs of pond liners purchased and delivered to Wabukhonyi SKM project | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44959 | 44963 | 18/5/2023 |  | 58000 | 58000 | Development partner | IDA | 0 | 58000 | 58000 |  | 58000 | 0 | 0 | Completed
| purchase of fertilizer for Wabukhonyi SLM project. | purchase of fertilizer for Wabukhonyi SLM project. | To increase production and productivity | Kgs of fertilizer purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 |  |  |  |  | 97500 | 97500 | Development partner | IDA | 0 | 97500 | 97500 |  | 97500 | 0 | 0 | Completed
| Purchase of signages for SLM sites. | Purchase of signages for 5no. SLM sites. | To enhance access to SLM sites | 5 signages purchased and installed | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 |  |  |  |  | 150000 | 150000 | Development partner | IDA | 0 | 150000 | 150000 |  | 150000 | 0 | 0 | Completed
| Construction works for Wabukhonyi dam | Construction works for Wabukhonyi dam | To store water for irrigation and flood control | 1 dam constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Bumula | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 29/12/2022 | 29/1/2024 | 31/10/2023 |  | 25902460 | 25902460 | Development partner | IDA | 0 | 25902460 | 25902460 |  | 25902460 | 0 | 0 | Complete
75 | Installation of 50 grid powered streetlights in Bumula sub-counties . | of streetlights Bumula streetlights in | [5 empty] | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | M/S Emricon Limited | 2021/22 |  | Complete and in use |  | 3565000 |  |  | CGB
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Siboti |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Siboti | 0.66661/34.4186 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Complete | [15 empty] | No value for county money
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Siboti | 0.6569/34.4772 - 0.6607/34.47 | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Complete | [15 empty] | Operational
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Siboti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Siboti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
42 | construction of ablution block at namatotoa primary school | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Ablution blocks constructed |  |  | Bumula | Khasoko |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 |  |  |  | 1700000 | 1614770 | 1614770 | CGB |  | 1614770 | 0 | 1614770 | 100% | 1614770 |  | 0 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
48 | Construction of 4NO.Doors Pit Latrines at Mungore Market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Bumula | Khasoko | 0.2915/39.708 - 0.3425/46.36 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 19/2/24 |  |  | 1000000 | 878178 | 878178 | CGB |  | 878178 | 0 |  | 0% |  |  | 878178 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
67 | Construction of 4NO.Doors Pit Latrines at Mungore Market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Bumula | Khasoko |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 |  |  |  | 1000000 | 878178 | 878178 | CGB |  | 878178 | 0 | 0 | 0% | 0 |  | 878178 | On-going | 95 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
79 | Construction Of Ablution Block At Namatotoa Primary School | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Ablution blocks constructed |  |  | Bumula | Khasoko |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 1700000 | 1614770 | 1614770 | CGB |  | 1614770 | 0 | 1614770 | 100% | 1614770 |  | 0 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
80 | Construction Of Pit Latrines At Namanze Primary School. | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Pit latrines constructed |  |  | Bumula | Khasoko | 0.48988/34.399706 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 1000000 | 0 | 0 | CGB |  | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | In complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Poor finishing
90 | Construction Of Pit Latrines At Mundaa Primary School. | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Pit latrines constructed |  |  | Bumula | Khasoko | 0.478395/34.430958 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 1000000 | 1999520 | 1999520 | CGB |  | 1999520 | 0 | 1949920 | 97.52% | 1949920 |  | 49600 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | In use
107 | Construction Of Abolution Block /Pit Latrine At Lubundaa And Mundaa |  |  | Ablution blocks constructed |  |  | Bumula | Khasoko | 0 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2000000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
131 | Renovation Of Mungore Dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Dispensaries renovated |  |  | Bumula | Khasoko | 0.488962/34.415897 |  | WBPSPCU | Health & Sanitation | 2020-2021 | 31/4/2024 |  |  | 1000000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Yet to start | [6 empty] | No | Not done | Financial | Yes |  |  |  | No
132 | Construction Of Pit Latrines At Namanze Dispensary And Fencing | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Pit latrines constructed |  |  | Bumula | Khasoko |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 1000000 | 992475 | 992475 | CGB |  | 992475 | 0 | 992475 | 100% | 992475 |  | 0 | Not implemented | [6 empty] | No | complete | Financial | Yes |  |  |  | No
204 | Construction Of Namanze Health Cente | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | health centres constructed |  |  | Bumula | Khasoko |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 9400000 | 9,138,712 | 9,138,712 | CGB |  | 9,138,712 | 0 | 9,137,378 | 99.99% | 9,137,378 |  | 1334 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
259 | Construction of Namatotoa dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the county. | dispensaries constructed |  |  | Bumula | Khasoko |  |  | CEF | Health & Sanitation | 2016/17 |  |  |  |  | 4067299 | 4067299 | CGB |  | 4067299 | 0 | 3227638 | 79.36% | 3227638 |  | 839661 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | In use
260 | Construction of Namusasi dispensary | Flooring, walling,roofing, fixing of doors and windows and painting works . | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | dispensaries constructed |  |  | Bumula | Khasoko |  |  | Ward Based | Health & Sanitation | 2015/16 |  |  |  |  | 3174073.2 | 3174073.2 | CGB |  | 3174073.2 | 0 | 2449807 | 77.18% | 2449807 |  | 724266.2 | [7 empty] | No | complete | Financial | Yes
261 | Proposed erection and completion of a 10-Door pit latrine at Khasoko. | Digging of 20ft deep pit,flooring,walling,roofing,feeting of doors and windows, and painting. | To enhance access to Sanitary facilities at Khasoko ACK primary school. | 10no.door pit latrine constructed |  |  | Bumula | Khasoko | 0.4352617/34.7061 |  | CEF | Health & Sanitation | 2016/17 | 1st April 2017 | 1stJul-17 | 1st Aug 2017 |  | 2263485 | 2263485 | CGB |  | 2263485 | 0 | 1893726.8 | 83.66% | 1893726.8 |  | 369758.2 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | Renovations required
262 | Completion of one block. | Walling, roofing, painting, fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | blocks completion |  |  | Bumula | Khasoko |  |  | CEF | Health & Sanitation | 2016/17 |  |  |  |  | 3869134 | 3869134 | CGB |  | 3869134 | 0 | 3129402 | 80.88% | 3129402 |  | 739732 | Completed and not in use | [6 empty] | No | complete | Financial | Yes
28 | Upgrading of Periodic Maintanance Of Javan Kwoba-Namusasi-Lubanda Roard | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.474551/34.43605 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 |  |  |  | 4131456 | 4131456 | 4131456 | County Government of Bungoma |  | 4131456 |  | 4131456 | 100.0% | 4131456 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
196 | Periodic Maintenance of Lubunda Junction - Sango Market - Ex-Chief - Mungore Rimary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.478041/34.433362 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 |  |  |  | 9004978.5 | 9004978.5 | 9004978.5 | County Government of Bungoma |  | 9004978.5 |  | 9004978.5 |  | 9004978.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Complete and in use
197 | Periodic Maintenance of Mundaa Primary - Buyofu Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.569772/37.409607 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 |  |  |  | 9004978.5 | 9004978.5 | 9004978.5 | County Government of Bungoma |  | 9004978.5 |  | 9004978.5 |  | 9004978.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Periodic maintanance required
198 | Periodic Maintenance of Roads In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 |  |  |  | 9004978.5 | 9004978.5 | 9004978.5 | County Government of Bungoma |  | 9004978.5 |  | 9004978.5 | 91.0% | 9004978.5 | 0 | 0 | In complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Not all roads were done
362 | Periodic Maintenance of Lubunda - Myanga Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.483220/34.424714 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 |  |  |  | 6641580 | 6641580 | 6641580 | County Government of Bungoma |  | 6641580 |  | 6641580 |  | 6641580 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Maintanance required
363 | Periodic Maintenance of Roads In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110399 |  | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 |  |  |  | 6641580 | 6641580 | 6641580 | County Government of Bungoma |  | 6641580 |  | 6641580 | 99.88% | 6641580 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
364 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 |  |  |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | In complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | In complete
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 |  |  |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Health hazard
540 | Upgrading of Namanze Junction - Srira Water Project - Buyofu Market Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 |  |  |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Poorely done
541 | Periodic Maintenance of Mungore - Lukhuna Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.29125/34.25006 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 20/5/2020 |  |  | 3875212 | 3875212 | 3875212 | County Government of Bungoma |  | 3875212 |  | 3875212 |  | 3875212 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Not complete
542 | Periodic Maintenance of Roads In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 |  |  |  | 3875212 | 3875212 | 3875212 | County Government of Bungoma |  | 3875212 |  | 3875212 | 53.51% | 3875212 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
663 | Drainage Works In Kanduyi And Bumula Sub-Counties(Lot 2) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 |  |  |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | In complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | None was done
789 | Periodic Maintenance of Mungore - River Sio Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Khasoko | 28'45.79356/34.244491036 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 |  |  |  | 4514140 | 4514140 | 4514140 | County Government of Bungoma |  | 4514140 |  | 4514140 |  | 4514140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Laks drainage
790 | Periodic Maintenance of Namusasi - Sio River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 |  |  |  | 9355823.4 | 9355823.4 | 9355823.4 | County Government of Bungoma |  | 9355823.4 |  | 9355823.4 |  | 9355823.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
791 | Construction of Lubunda - Miyanga Junction Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.483163/34.424923 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 |  |  |  | 9355823.4 | 9355823.4 | 9355823.4 | County Government of Bungoma |  | 9355823.4 |  | 9355823.4 |  | 9355823.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Poorely done
792 | Periodic Maintenance of Roads In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 |  |  |  | 9355823.4 | 9355823.4 | 9355823.4 | County Government of Bungoma |  | 9355823.4 |  | 9355823.4 | 99.99% | 9355823.4 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Fairely done
793 | Periodic Maintenance of Mungore - R. Sio Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Khasoko | 0.284579356/34.244491036 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 |  |  |  | 4514140 | 4514140 | 4514140 | County Government of Bungoma |  | 4514140 |  | 4514140 | 95.35% | 4514140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs rehabilitation
1116 | Periodic Maintenance of Mungore - Lukhuna Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.29125/3425006 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 6935292 | 6935292 | 6935292 | County Government of Bungoma |  | 6935292 |  | 6935292 |  | 6935292 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Sub standard work done
1117 | Periodic Maintenance of Mungore - Lubunda - Masibayi Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.479139/34.434158 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 6935292 | 6935292 | 6935292 | County Government of Bungoma |  | 6935292 |  | 6935292 |  | 6935292 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs attention
1118 | Periodic Maintenance of Khasoko Secondary - Khayo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 5728718 | 5728718 | 5728718 | County Government of Bungoma |  | 5728718 |  | 5728718 |  | 5728718 | 0 | 0 | In complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Works done on Bridge alone
1119 | Periodic Maintenance of Namanze Dispensary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 6935292 | 6935292 | 6935292 | County Government of Bungoma |  | 6935292 |  | 6935292 |  | 6935292 | 0 | 0 | Complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Lacks good drainage
1120 | Periodic Maintenance of Reformed Catholic - Lubunda - Nabukhambi Ack Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.491256/34.43555 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 6935292 | 6935292 | 6935292 | County Government of Bungoma |  | 6935292 |  | 6935292 |  | 6935292 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Poorly done but in use
1121 | Periodic Maintenance of Roads In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 6935292 | 6935292 | 6935292 | County Government of Bungoma |  | 6935292 |  | 6935292 | 99.49% | 6935292 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1122 | Routine Maintenance Of Khasoko Secondary - Khayo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 5728718 | 5728718 | 5728718 | County Government of Bungoma |  | 5728718 |  | 5728718 | 100.0% | 5728718 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1249 | Upgrading of Roads In Khasoko Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 |  |  |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1416 | Periodic Maintenance of Mungore Mkt - Mungore Dispensary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 |  |  |  | 4872000 | 4872000 | 4872000 | County Government of Bungoma |  | 4872000 |  | 4872000 |  | 4872000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1417 | Periodic Maintenance of Javan Kwoba Kakumeka - Namusasi Pri/ Sec Schools Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 |  |  |  | 4872000 | 4872000 | 4872000 | County Government of Bungoma |  | 4872000 |  | 4872000 |  | 4872000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1418 | Periodic Maintenance of Mungore Mkt - Mungore Disp. Road, Javan Kwoba, Kakumega - Namusasi Primary/ Secondary Road In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 |  |  |  | 4872000 | 4872000 | 4872000 | County Government of Bungoma |  | 4872000 |  | 4872000 | 99.99% | 4872000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1669 | Periodic Maintenance of Oluti - Nasianda Road In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko | 0.495137/34.434318 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 |  |  |  | 6139146 | 6139146 | 6139146 | County Government of Bungoma |  | 6139146 |  | 6139146 | 100.0% | 6139146 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1670 | Periodic Maintenance of Karakacha - Nambuyi - Namanze Road In Khasoko Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Bumula | Khasoko |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 |  |  |  | 4312938 | 4312938 | 4312938 | County Government of Bungoma |  | 4312938 |  | 4312938 | 99.96% | 4312938 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Culverts not fixed
178 | Purchase of land for Maraba ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Maraba ECDE Purchased | 3110599 | Ward based projects | Bumula | Khasoko | 0.29477798/34.251230204 | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/2016 | 41676 |  | 41676 | 200000 | 200000 | 200000 | CGB | N/A | 200000 |  | 200000 |  | 200000 |  |  | Completed | 1 | [14 empty] | Title not prepared
9 | Construction of 1 No. ECDE classroom at Mungore primary School in Khasoko Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.291152492/34.2447 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2020/2021 |  | 30/06/2024 |  | 1500000 | 1398892 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 |  | 0% |  | 1398892 | 1398892 | Complete
46 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Khasoko Primary Schools In Khasoko Ward | Construction of ECDE classroom | To construct ECDE classroom and pit latrine providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.5392861/32.617807 | Education and Vocational Training | Early Childhood Development Education |  | 2022/2023 |  | 30/06/2023 |  | 1500000 | 1450100 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1193367.45 | 82.3% | 1193367.45 | 256732.55 | 256732.55 | Complete and in use | 1 | [14 empty] | General repairs required
47 | Proposed Erection And Completion Works Of 1no. Ecde Classroom and 4no.Door Pit Latrine With Urinal At Namusasi Primary School In Khasoko Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko |  | Education and Vocational Training | Early Childhood Development Education |  |  |  | 30/06/2023 |  | 2500000 | 2390810 | 2500000 | County Government of Bungoma | N/A | 2500000 | 0 | 1280920.2 | 53.58% | 1280920.2 | 1109889.8 | 1109889.8 | Complete and in use | 1
80 | Construction of entre of excellence at khasoko VTC | construction of centres of excellence | To construct centre of excellenceproviding a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.5380732/21.243609 | Education and Vocational Training | Early Childhood Development Education |  | 2022/2023 |  | 30/6/2022 |  | 5000000 | 5000000 | 5000000 | County Government of Bungoma | N/A | 5000000 | 0 | 0 | 0% | 0 | 5000000 | 5000000 | In complete | 1 | [14 empty] | Not in good condition
81 | construction of ECDE Clasroom at namatotoa primary | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.492910/34.430446 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  |  | 30/6/2022 |  | 1200000 | 1183510 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 517087.25 | 43.69% | 517087.25 | 666422.75 | 666422.75 | Complete and not in use | 1 | [14 empty] | In use. Repair of the floor
113 | Construction Of 1 No. Ecde Classroom At Mungore And Namusasi Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.291264/34.244552956 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2023/2024 |  |  |  | 2400000 | 2327580 | 2400000 | County Government of Bungoma | N/A | 2400000 | 0 | 2327580 | 100% | 2327580 | 0 | 0 | In complete | 0.9 | [14 empty] | Contractor not on site
142 | Proposed Erection And Completion Of 1 No. Ecde And 2 No Door Pit Latrine At Mundaa And Lubunda Primary Schools In Khasoko Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.478572/34.431339 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2018/2019 | 43471 |  | 30/8/2019 | 6673147.62 | 2772655.2 | 6673147.62 | County Government of Bungoma | N/A | 6673147.62 | 0 | 0 | 0% | 0 | 2772655.2 | 2772655.2 | Complete | 0.5 | [14 empty] | Project in use
143 | Proposed Erection And Completion Of 1 No Ecde And 10 No . Door Pit Latrine At Nasianda Primary Schools In Khasoko Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.491363/34.450377 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  |  |  |  | 0 | 2997590 | 0 | County Government of Bungoma | N/A | 0 | 0 | 2997590 | 100% | 2997590 | 0 | 0 | complete and in use | 1 | [14 empty] | In use. Repair of the floor
195 | Construction Of 1 Ecde Classroom And Pit Latrine At Namanze, Bwaliro And Lubunda Primary | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Khasoko | 0.478572/34.432339 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2017/2018 | 43471 |  | 30/08/2019 | 4754562 | 4056130 | 4754562 | County Government of Bungoma | N/A | 4754562 |  | 4056130 | 100% | 4056130 | 0 |  | In complete | [15 empty] | In use, shody work done
38 | Proposed Tree Growing Within Institutions In Khasoko, Kabula, Musikoma, Bukembe East, West Nalondo And Chesikaki Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Bumula | Khasoko | 0.478572/34.431339 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 |  |  |  | 7101000 | 6960000 | 6960000 | FLLOCA | IDA | 0 | 6960000 | 0 | 100% | 0 | 0 |  | Complete | 0.2 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
40 | Proposed Supply And Installation Of Combustion Chamber For Improved Stoves And Energy Centre For Research On Training Of Energy Technologies In Khasoko And Bukembe West Wards | 1.construction of combustion chamber (Kiln) for production of clean energy saving jikos. 2.Provision and Assemblying of production materials for the two burner / saving jikos. 3.Training of youths and women on installation of single /two burner jikos to the community. | To promote climate change mitigation and adaptation | Construction of combustion chambers in 2 wards | 2640599 | Other Capital Grants and Transfers | Bumula | Khasoko | 0.479139/34.434158 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 |  |  |  | 6000000 | 5950005 | 5950005 | FLLOCA | IDA | 0 | 5950005 | 0 | 100% | 0 | 0 |  | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Complete and in use
59 | Upgrading of Nasyanda Primary Borehole in Khasoko Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.491403/34.450619 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2300000 | 2289289.68 | 2289289.68 | CGB | N/A | 2289289.68 | 0 | 2289289.68 | 100% | 2289289.68 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Completed and in use | WORKS COMPLETED AND PROJECT IS OPERATIONAL
60 | Upgrading of Mungore Market Borehole and Protection of Maraba Spring in Khasoko Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and 1 water spring constructed and proctected | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.487588/34.417068 - 0.295451/34.252349496 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 | Complete and in use |  |  | 1800000 | 1717183 | 1717183 | CGB | N/A | 1717183 | 0 | 1717183 | 100% | 1717183 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
61 | Drilling and Equipping of Namusasi Dispensary Borehole and Upgrading of Namanze Dispensary Borehole in Khasoko Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 1 borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4900000 | 4704612 | 4704612 | CGB | N/A | 4704612 | 0 | 4704612 | 100% | 4704612 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Water drawing points notbworking
104 | Drilling of 2no. Boreholes and Equipping with Solar Pump and Protection of Khulutende Spring in Khasoko Ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled and solarised. 1 Water spring constructed and protected | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.477512/34.427604 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 | Complete and in use |  |  | 5200000 | 5120182 | 5120182 |  | N/A | 5120182 | 0 | 5120182 | 100% | 5120182 | 0 | 0 | complete and in use | 1 | [8 empty] | yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
149 | Drilling of Namusasi and namanze health centre borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.479137/34.434158 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 | 14/6/2019 |  |  | 3500000 | 3486960 | 3486960 |  | N/A | 3486960 | 0 | 3486960 | 100% | 3486960 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | Requires repair
177 | Khasoko water project | Trenching ; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.313375/37.2253 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5600000 | 5549136 | 5549136 |  | N/A | 5549136 | 0 | 5549136 | 100% | 5549136 | 0 | 0 | In complete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Poor workmanship
192 | UPGRADING OF MUNGORE DISPENSARY BOREHOLE | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.488962/34.415897 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 | 31/04/2020 |  |  | 1500000 | 1354996 | 1354996 |  | N/A | 1354996 | 0 | 1354996 | 100% | 1354996 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
238 | DRILLING OF 2NO BOREHOLES AND CONSTRUCTION OF 4NO. WATER SPRINGS IN MUNGORE TOWANI INKHASOKO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.29/16.41084-0.3425/36.2424 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 4100000 | 4016674 | 4016674 |  | N/A | 4016674 | 0 | 4016674 | 100% | 4016674 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
307 | DRILLING OF BOREHOLES AT LUBUNDA AND NAMANZE MARKET AND PROTECTION OF 2 SPRINGS IN KHASOKO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 2 Boreholes rehabilitated and 2 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.474949/34.413239 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3986000 | 3986000 |  | N/A | 3986000 | 0 | 3986000 | 100% | 3986000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
357 | Rehabilitation of Khasoko community Water Project | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.346230/32.716004 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 2800000 | 2570535 | 2570535 |  | N/A | 2570535 | 0 | 2570535 | 100% | 2570535 | 0 | 0 | Incomplete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Works not fully done
439 | Rehabilitation of Khasoko community Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2570535 | 2570535 |  | N/A | 2570535 | 0 | 2570535 | 100% | 2570535 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
447 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs. constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko | 0.627937/40.411607 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1567000.3 | 1567000.3 |  | N/A | 1567000.3 | 0 | 1567000.3 | 100% | 1567000.3 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Fencing not done
529 | Rehabilitation of Khasoko community Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 5200000 | 5141070 | 5141070 |  | N/A | 5141070 | 0 | 5141070 | 100% | 5141070 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
601 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Khasoko |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1700000 | 1572100 | 1572100 |  | N/A | 1572100 | 0 | 1572100 | 100% | 1572100 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
34 | Proposed supply and installation of 5 NO. solar powered streetlights | supply of solar of 5 NO | promotion of MSMEs and security | solar powered street lights installed | 1358819/2023-24 |  |  | Khasoko | 02912.5/34.25006 | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE LIMITED | 2023/2024 |  |  |  | 1500000 |  |  | CGB | [8 empty] | Complete | 100 | 5 | [13 empty] | In good condition
75 | Installation of 50 grid powered streetlights in Bumula sub-counties . | of streetlights Bumula streetlights in | [5 empty] | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | M/S Emricon Limited | 2021/22 |  |  |  | 3565000 |  |  | CGB
83 | Proposed construction of cabro laying in Nasianda open air market | construction laying in Nasianda | [5 empty] | Khasoko | 0.492855/34.451337 | Trade, Energy and Industrialization | Dept of Trade | M/S Aeronar Solutions Company | 2021/22 |  |  |  | 4860800 |  |  | CGB | [8 empty] | Stalled | [15 empty] | Stalled
95 | Installation of 1 No high mast flood light solar Mwiyala in Khasoko ward | of mast light mast flood | [5 empty] | Khasoko | 0.498914/34.427532 | Trade, Energy and Industrialization | Dept of Energy | Ms Ryagle Enterprises | 2021/22 |  |  |  | 970000 |  |  | CGB | [8 empty] | Complete | [15 empty] | In good condition
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Khasoko |  |  |  | M/S Sinawa Enterprises | 2020/21 |  |  |  | 4431050 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Khasoko | 0.481113/34.431034 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Complete | [15 empty] | Brocken down
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Khasoko | 0.496054/34.429630 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Complete | [15 empty] | Delivered and distributed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko | 0.498987/34.435810 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 |  | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Complete | [15 empty] | Complete and distributed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Complete | [15 empty] | Minimal repairs
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 |  | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 |  | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 |  | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 |  | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 |  | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 |  | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 |  | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 |  | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 |  | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 |  | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 |  | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 |  | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 |  | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 |  | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khasoko |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 |  | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 |  | installation mantainance solar M poered streetlights | [5 empty] | Khasoko |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
73 | Istallation of 1 NO. High mast flood light | [5 empty] | Bumula | Khasoko | 0.492855/34.451339 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete | [15 empty] | In good condition
74 | Costruction of Sango - Bwalimo box culvert | [5 empty] | Bumula | Khasoko | 0.469587/34.427632 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete
75 | Purchase of Sango VTC Land and construction | [5 empty] | Bumula | Khasoko | 0.479568/34.430071 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete
76 | Costruction of Lubunda - Namusasi Culvert | [5 empty] | Bumula | Khasoko | 0.474551/34.436225 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete
77 | Construction of 4NO.Doors Pit Latrines at Namatotoa dispensary | [5 empty] | Bumula | Khasoko | 0.479139/34.434158 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete and in use
78 | Construction of Namatotoa dispensary water | [5 empty] | Bumula | Khasoko | 0.490068/34.431361 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete and in use | [15 empty] | In good condition
79 | Costruction of Kwoba road | [5 empty] | Bumula | Khasoko |  |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete | [15 empty] | In good condition
80 | Rehabilitation of Namusasi spring | [5 empty] | Bumula | Khasoko | 0.498987/34.435810 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete | [15 empty] | Fencing Required
81 | Rehabilitation of Klukhale spring | [5 empty] | Bumula | Khasoko | 0.495475/34.445868 |  |  |  | 2024/2025 | [6 empty] | CGB | [8 empty] | Complete | [15 empty] | Fencing Required
82 | Construction of Namatotoa dispensary | [5 empty] | Bumula | Khasoko | 0.498987/34.431361 |  |  |  | 2016/2017
83 | Construction of Namusasi dispensary | [5 empty] | Bumula | Khasoko |  |  |  |  | 2015/2016
81 | Erection And Completion Of Maternity Wing At Myanga Dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Bumula | Kimaeti |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 4000000 | 3435280 | 3435280 | CGB |  | 3435280 | 0 | 1435300 | 41.78% | 1435300 |  | 1999980 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
150 | Construction Of Nakhwana Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2896320 | 2896320 | CGB |  | 2896320 | 0 | 2896320 | 100% | 2896320 |  | 0 | Complete and not use | [6 empty] | No | complete | Financial | Yes
165 | Construction Of Bitobo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3034408 | 2898643 | 2898643 | CGB |  | 2898643 | 0 | 1020359 | 35.2% | 1020359 |  | 1878284 | stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
193 | Construction Of Bitobo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3034408 | 2898643 | 2898643 | CGB |  | 2898643 | 0 | 1020359 | 35.2% | 1020359 |  | 1878284 | stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
229 | Completion Of Maternity Wing At Kimaeti Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Bumula | Kimaeti |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1900000 | 4593250 | 4593250 | CGB |  | 4593250 | 0 | 4523414.2 | 98.48% | 4523414.2 |  | 69835.8 | Complete and in use | [6 empty] | No | complete | Financial | Yes
230 | Construction Of Myanga Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Bumula | Kimaeti |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 3000000 | 0 | 0 | CGB |  | 0 | 0 |  | #DIV/0! |  |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
264 | Purchase of one acre of land and Construction of Bitobo Dispensary | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services in the area | acres of land purchased |  |  | Bumula | Kimaeti | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Ongoing | [6 empty] | No | complete | Financial | Yes
265 | Purchase of 1 acre land and Construction of Myanga dispensary | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Bumula | Kimaeti | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Ongoing | [6 empty] | No | complete | Financial | Yes
78 | Upgrading of Lunakwe Mkt-Lumboka Mkt-Mulukoba Pri | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41663 | 41780 |  | 4298322 | 4298322 | 4298322 | County Government of Bungoma |  | 4298322 |  | 4298322 | 100.0% | 4298322 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
199 | Periodic Maintenance of Kimwanga - Tabala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43233 |  | 4086877 | 4086877 | 4086877 | County Government of Bungoma |  | 4086877 |  | 4086877 |  | 4086877 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
200 | Periodic Maintenance of Myanga - Apokori Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43231 |  | 4086877 | 4086877 | 4086877 | County Government of Bungoma |  | 4086877 |  | 4086877 |  | 4086877 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
201 | Periodic Maintenance of Moses Mayubani Wamalwa | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43123 | 43239 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
202 | Periodic Maintenance of Roads In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43235 |  | 4086877 | 4086877 | 4086877 | County Government of Bungoma |  | 4086877 |  | 4086877 | 95.45% | 4086877 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
369 | Grading of Lelekwe - Syombe - Kimaeti Secondary Road | Grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43602 |  | 7497776 | 7497776 | 7497776 | County Government of Bungoma |  | 7497776 |  | 7497776 |  | 7497776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
370 | Periodic Maintenance of Syombe - Tulukuyi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43480 | 43609 |  | 7497776 | 7497776 | 7497776 | County Government of Bungoma |  | 7497776 |  | 7497776 |  | 7497776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
371 | Periodic Maintenance of Raods In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43598 |  | 7497776 | 7497776 | 7497776 | County Government of Bungoma |  | 7497776 |  | 7497776 | 99.9% | 7497776 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
372 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
548 | Upgrading of Tabala-Nakhwana Bridge | Road improvement works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
549 | Construction of Kitingia - Sihilila Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
574 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
801 | Periodic Maintenance of Carmel View - Tabala - Mayanja Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44338 | 44369 | 9991743.38 | 9991743.38 | 9991743.38 | County Government of Bungoma |  | 9991743.38 |  | 9991743.38 |  | 9991743.38 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
802 | Periodic Maintenance of Myanga - Syombe - Sichekeni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44333 |  | 6886572 | 6886572 | 6886572 | County Government of Bungoma |  | 6886572 |  | 6886572 |  | 6886572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
803 | Periodic Maintenance of Masielo Sec - Napara Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44329 |  | 6886572 | 6886572 | 6886572 | County Government of Bungoma |  | 6886572 |  | 6886572 |  | 6886572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
804 | Construction of Tabala - Nakhwana Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44217 | 44330 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
805 | Periodic Maintenance of Roads In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44339 |  | 6886572 | 6886572 | 6886572 | County Government of Bungoma |  | 6886572 |  | 6886572 | 99.98% | 6886572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
806 | Periodic Maintenance of Carmel View - Tabala - Mayanja Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44335 |  | 9991743.38 | 9991743.38 | 9991743.38 | County Government of Bungoma |  | 9991743.38 |  | 9991743.38 | 89.43% | 9991743.38 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1132 | Periodic Maintenance of Wambu - Maseno Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44698 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1133 | Periodic Maintenance of Kimaeti - Syombe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44694 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1134 | Periodic Maintenance of Kitingia - Sihilila Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44705 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1135 | Periodic Maintenance of Kitabisi - Wekelekha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44702 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 |  | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1136 | Periodic Maintenance of Japhesa - Masafwa - Nakhwana - Santos Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44699 | 44730 | 8979023.5 | 8979023.5 | 8979023.5 | County Government of Bungoma |  | 8979023.5 |  | 8979023.5 |  | 8979023.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1137 | Construction of Kimwanga - Wakafura (Road) Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44696 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1138 | Periodic Maintenance of Roads In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44700 |  | 14060592 | 14060592 | 14060592 | County Government of Bungoma |  | 14060592 |  | 14060592 | 88.31% | 14060592 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1139 | Routine Maintenance Of Japhesa - Masafwa - Nakhwana - Santos Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44697 |  | 8979023.5 | 8979023.5 | 8979023.5 | County Government of Bungoma |  | 8979023.5 |  | 8979023.5 | 98.97% | 8979023.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1424 | Periodic Maintenance of Myanga - Tulienge Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45067 |  | 5801375 | 5801375 | 5801375 | County Government of Bungoma |  | 5801375 |  | 5801375 |  | 5801375 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1425 | Periodic Maintenance of Mt. Carmel - Myanga Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45056 |  | 4697826 | 4697826 | 4697826 | County Government of Bungoma |  | 4697826 |  | 4697826 |  | 4697826 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1426 | Upgrading of Nakhwana - Syombe Drift | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45067 |  | 9974337.72 | 9974337.72 | 9974337.72 | County Government of Bungoma |  | 9974337.72 |  | 9974337.72 |  | 9974337.72 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1427 | Construction of Khasolo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45059 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1428 | Periodic Maintenance of Myanga - Tulienge Bridge Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45066 |  | 5801375 | 5801375 | 5801375 | County Government of Bungoma |  | 5801375 |  | 5801375 | 99.31% | 5801375 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1429 | Periodic Maintenance of Mt. Carmel - Myanga Mkt Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45061 |  | 4697826 | 4697826 | 4697826 | County Government of Bungoma |  | 4697826 |  | 4697826 | 98.87% | 4697826 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1430 | Framework Contracts For Maintenance Of Roads In Kanduyi And Bumula Sub Counties | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45070 |  | 9974337.72 | 9974337.72 | 9974337.72 | County Government of Bungoma |  | 9974337.72 |  | 9974337.72 | 99.48% | 9974337.72 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1671 | Periodic Maintenance of Nambuchi - Miyanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45435 |  | 6131760 | 6131760 | 6131760 | County Government of Bungoma |  | 6131760 |  | 6131760 |  | 6131760 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1672 | Periodic Maintenance of Chief Naulikha - Nakalila - Wakafura - Masielo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45426 |  | 3740478 | 3740478 | 3740478 | County Government of Bungoma |  | 3740478 |  | 3740478 |  | 3740478 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1673 | Periodic Maintenance of Nambuchi - Miyanga Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45428 |  | 6131760 | 6131760 | 6131760 | County Government of Bungoma |  | 6131760 |  | 6131760 | 100.0% | 6131760 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1674 | Periodic Maintenance of Impreza - Bitobo Dispensary - Tunduli Junction Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45430 |  | 6002304 | 6002304 | 6002304 | County Government of Bungoma |  | 6002304 |  | 6002304 | 98.35% | 6002304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1675 | Periodic Maintenance of Chief Naulikha - Nakalila - Wakafura - Masielo Road In Kimaeti Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45434 |  | 3740478 | 3740478 | 3740478 | County Government of Bungoma |  | 3740478 |  | 3740478 | 99.97% | 3740478 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
55 | Proposed Renovation and refurbishment of 5 units county staff quarters. | Renovation and refurbishment | To enhance revenue collection | Five units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Bumula | Kimaeti |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2021/22 | 44594 | 31/3/2022 | 20/4/2022 | 3000000 | 2494800 | 2494800 | CGB |  | 2494800 |  | 2494800 | 100% | 2494800 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
120 | Purchase Of One Acre For Kambini Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Kambini Dispensary Purchased | 3110599 | Ward based projects | Bumula | Kimaeti |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42959 | 43376 | 13/5/2018 | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 100% | 1000000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
21 | Construction of 1 NO. ECDE classroom at Syombe primary school and renovation Works at Masielo, Tulukuyi, Bukirimo, Miyanga, Kimaeti, Nakhwana and Kimwanga primary schools. | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 6000000 | 5998960 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 5998960 | 100% | 5998960 | 0 | 0 | Completed
82 | CONSTRUCTION OF ECDE CLASSROOM AT Nakwana,Bitobo.Kitabisi | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3600000 | 3596750 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 2864480 | 79.64% | 2864480 | 732270 | 732270 | Complete and in use | 1
114 | Construction Of 1 No. Ecde Classroom At Khasolo, Radi And Mwiyenga Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3600000 | 1075304 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 0 | 0% | 0 | 1075304 | 1075304 | complete and in use | 1
145 | Proposed Erection And Completion Of 1 No. Ecde At Kimaeti, Myanga And Kimwanga Primary Schools In Kimaeti Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3600000 | 3562000 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3562000 | 100% | 3562000 | 0 | 0 | complete and in use | 1
172 | Construction Of 1 Ecde Classroom At Napara, Silila And Bukirimo Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 3600000 | 3582010 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3582010 | 100% | 3582010 | 0 |  | complete and in use | 1
198 | The Proposed And Completion Of 1 N0 Classroom At Masielo And Tulukuyi Primary School In Kimaeti Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | Kimaeti |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2000000 | 2373810 | 2000000 | County Government of Bungoma | N/A | 2000000 |  | 2373810 | 100% | 2373810 | 0 |  | complete and in use | 100.0%
17 | Upgrading of Mwiyenga Primary and Matokho Boreholes in Kimaeti/Bumula wards | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 2640599 | Other Capital Grants and Transfers | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45544 | 45546 | 45546 | 6000000 | 5777960 | 5777960 | FLLOCA | N/A | 5777960 | 0 | 0 | 100% | 5777960 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
62 | Upgrading of Kimaeti Market Borehole in Kimaeti In Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4988406 | 4988406 | CGB | N/A | 4988406 | 0 | 4988406 | 100% | 4988406 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
95 | Drilling and Equipping of Kitingia Primary Borehole and Rehabilitation of Tabara Primary Water Project | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and equipped | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4954502 | 4954502 | CGB | N/A | 4954502 | 0 | 4954502 | 100% | 4954502 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
105 | Upgrading of Nakhwana primary borehole and drilling of Nambuchi borehole in kimaeti ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points;site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 1 borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4000000 | 3976132 | 3976132 |  | N/A | 3976132 | 0 | 3976132 | 100% | 3976132 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
166 | Rehabilitation and upgrading of Khulwanda and Syombe boreholes | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 3000000 | 2939788 | 2939788 |  | N/A | 2939788 | 0 | 2939788 | 100% | 2939788 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
167 | DRILLING AND EQUIPPING OF SIHILILA PRIMARY BOREHOLE IN KIMAETI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2000000 | 1991720 | 1991720 |  | N/A | 1991720 | 0 | 1991720 | 100% | 1991720 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
195 | DRILLING AND EQUIPING OF BITOBO BOREHOLE AND PROTECTION 2 NO. WATER SPRINGS IN KIMAETI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 2 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2500000 | 2233009 | 2233009 |  | N/A | 2233009 | 0 | 2233009 | 100% | 2233009 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
196 | EXTENSION OF MYANGA WATER PROJECT | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2700000 | 2573692 | 2573692 |  | N/A | 2573692 | 0 | 2573692 | 100% | 2573692 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
219 | REHABILITATION OF BUNJAKU SHALLOW WELL IN KIMAETI WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 well upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 500000 | 489520 | 489520 |  | N/A | 489520 | 0 | 489520 | 100% | 489520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
237 | DRILLING OF SYOMBE AND KIMAETI BOREHOLES IN KIMAETI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 3800000 | 3780206 | 3780206 |  | N/A | 3780206 | 0 | 3780206 | 100% | 3780206 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
308 | ST. JUDE NAPARA GIRLS WATER PROJECT | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 2000000 | 2000000 |  | N/A | 2000000 | 0 | 2000000 | 100% | 2000000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
430 | Extension of nzowasco pipeline to kimaeti market | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3300000 | 3051900 | 3051900 |  | N/A | 3051900 | 0 | 3051900 | 100% | 3051900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
528 | with 6 Springs, 2 Shallow wells and 1 borehole | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump; Site identification; geological survey, drilling development, construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled, 2 wells constructed and 6 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3800000 | 3529200 | 3529200 |  | N/A | 3529200 | 0 | 3529200 | 100% | 3529200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
609 | Drilling and equip Kibabii TTC borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | Kimaeti |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3480000 | 3480000 |  | N/A | 3480000 | 0 | 3480000 | 100% | 3480000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
17 | Construction of Kimaeti ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Kimaeti ward office constructed | 3111504 | Construction of non- residential buildings | Bumula | Kimaeti | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2023/24 | 45300 | 45415 | 45467 | 9500000 | 9453590 | 9500000 | County Government of Bungoma | - | 9453590 | - | 9453590 | 100% | 5875156 | 3578156 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Rehabilitation of cattle dips | Rehabilitation of cattle dips in Luuya, Kibisi, Bukembe, Lutaso, Tulumba, and Myanga Cattle Dips | To improve animal health and productivity | 6 Cattle dips rehabiliatated | 3110504 | Other infrastructure and civil works | Bumula | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44136 | 44139 | 14/3/2020 | 5000000 | 3486950 | 3548016 | County Government of Bungoma |  | 3486950 | 0 | 3486950 | 100% | 3486950 | 0 | 0 | Completed
| Construction of ablution block, fence and gate at Bumula Dairy FCS in Kimaeti Ward | Construction of ablution block, fence and gate at Bumula Dairy FCS in Kimaeti Ward | To enhance income generation among dairy farmers | 1 Ablution block constructed | 3110504 | Other infrastructure and civil works | Bumula | Kimaeti |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 20/1/2024 | 24/5/2024 | 15/7/2024 | 8000000 | 5600000 | 5000000 | County Government of Bungoma |  | 5600000 | 0 | 4900000 | 88% | 4900000 | 700000 | 700000 | Completed
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Kimaeti |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
135 | Renovation of Myanga market | [6 empty] | Kimaeti |  |  |  | Kanduyi Enterprises | 2016/17 |  | Complete |  | 16692817.6 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kimaeti |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Kimaeti |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
180 | Extention Of Sewer Line Prison Estate |  |  | sewerline extended |  |  | Kanduyi | Township | 0.567086/34.556159 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3474408.27 | 3448400 | 3448400 | CGB |  | 3448400 | 0 | 0 | 0% | 0 |  | 3448400 | Never implemented | [6 empty] | No | complete | Financial | Yes | [5 empty] | No work at site
194 | Extention Of Sewer Line Prison Estate |  |  | sewerline extended |  |  | Kanduyi | Township | 0.567086/34.556159 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3474408.27 | 3448400 | 3448400 | CGB |  | 3448400 | 0 | 0 | 0% | 0 |  | 3448400 | Never implemented | [6 empty] | No | complete | Financial | Yes
292 | Supply, Delivery, Installation, Training and Commissioning of ICU Equipment | Supply, Delivery, Installation, Training and Commissioning of ICU Equipment | to enhance capacity of staff and equip the facility for affordable health services within the community | ICU equipments supplied, delivered, installed and commissioned |  |  | Kanduyi | Township | 0.573071/34.559112 |  | Ward Fund | Health & Sanitation | 2013/14 |  |  |  |  | 174500000 | 174500000 | CGB |  | 174500000 | 0 |  | 0% |  |  | 174500000 | Completed | [6 empty] | No | complete | Financial | Yes
293 | Supply And Delivery Of 5 Life Support Ambulances | Supply and delivery of Ambulances. | To provide accessible and quick referral services for patients within and outside the county. |  |  |  | Kanduyi | Township | 0.573071/34.559112 |  | Ward Fund | Health & Sanitation | 2013/14 |  |  |  |  | 36500000 | 36500000 | CGB |  | 36500000 | 0 | 36500000 | 100% | 36500000 |  | 0 | Completed | [6 empty] | No | complete | Financial | Yes
294 | Delivery/Installation Commissioning And Testing Ambulances Tracking Two Way Communication With A Controlled Base | purchase and installation |  | ambulances delivered |  |  | Kanduyi | Township | 0.573071/34.559112 |  | Ward Fund | Health & Sanitation | 2013/14 |  |  |  |  | 1620000 | 1620000 | CGB |  | 1620000 | 0 |  | 0% |  |  | 1620000 | Completed | [6 empty] | No | complete | Financial | Yes
295 | Delivery Installation Training,Maintainance Of Mortuary Equipments | Delivery Installation Training,Maintainance Of Mortuary Equipments | To preserve bodies | Mortuary equipments delivered |  |  | Kanduyi | Township | 0.573071/34.559112 |  | Ward Fund | Health & Sanitation | 2013/14 |  |  |  |  | 16776869 | 16776869 | CGB |  | 16776869 | 0 |  | 0% |  |  | 16776869 | Completed | [6 empty] | No | complete | Financial | Yes
296 | Supply And Delivery Of ICU Unit | Supply and delivery | To provide accessible and quick referral services for patients within and outside the county. | ICU Unit delivered |  |  | Kanduyi | Township | 0.573071/34.559112 |  | Ward Fund | Health & Sanitation | 2013/14 |  |  |  |  | 174500000 | 174500000 | CGB |  | 174500000 | 0 |  | 0% |  |  | 174500000 | Completed | [6 empty] | No | complete | Financial | Yes
297 | Construction of pediatric wing kitchen and fencing. | Excavation of trenches for foundation,construction of thick slab,walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | pediatric wings with kitchen constructed and fenced |  |  | Kanduyi | Township | 0.573071/34.559112 |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42236 |  |  | 14759608 | 14759608 | CGB |  | 14759608 | 0 | 14759608 | 100% | 14759608 |  | 0 | Completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No
298 | Renovation of Bungoma County Referral Hospital | Waling,roofing,painting,fixing doors and windows | To provide access to affordable health services within the community | Referrel hospitals renovated |  |  | Kanduyi | Township |  |  | Ward Based | Health & Sanitation | 2015/16 |  | 42551 |  |  | 66202731 | 66202731 | CGB |  | 66202731 | 0 | 66202731 | 100% | 66202731 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
299 | Construction of casualty department, packing bay and walk ways | Excavation of trenches for foundation,construction of thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide a designate area for handling emergency and trauma cases within the hospital | casuality departments constructed |  |  | Kanduyi | Township |  |  | CEF | Health & Sanitation | 2016/17 |  | 42979 |  |  | 70659329 | 70659329 | CGB |  | 70659329 | 0 | 67785842 | 95.93% | 67785842 |  | 2873487 | Completed | [6 empty] | No | complete | Financial | Yes | [5 empty] | in use and helpful
300 | Construction Of A Perimeter Fence At Bungoma County Referral Hospital | Walling,painting | To secure the hospitals property,staff and patients | perimeter walls constructed |  |  | Kanduyi | Township |  |  | CEF | Health & Sanitation | 2016/17 |  | 43070 |  |  | 53294758 | 53294758 | CGB |  | 53294758 | 0 | 53214464 | 99.85% | 53214464 |  | 80294 | 99% Complete | [6 empty] | No | complete | Financial | Yes
1 | Erection and completion of Masinde Muliro Stadium | Construction of pavilion and football pitch | International stadium constructed to enhance access to sporting activities | Pavillion and football pitch constructed | 3111504 | Other infrastructure and civil works | Kanduyi | Township |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2018/19 | 26/04/2019 | 15/12/2024 |  | 760633733 | 807464800.6 | 734497360.76 | County Government of Bungoma/GoK | GoK | 807464800.6 |  | 734497360.76 | 90.96% | 734497360.76 | 72967440 | 72967439.84 | Ongoing | 0.95 | [7 empty] | fisibility study report | [6 empty] | contractor to speed up finishing so as to boost sporting activities in kanduyi
7 | Upgrading of Marell-Namuyemba-Luucho | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41660 | 41777 |  | 7659224 | 7659224 | 7659224 | County Government of Bungoma |  | 7659224 |  | 7659224 | 100.0% | 7659224 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
29 | Upgrading of Periodic Maintanance Of Teachers Sacco-Blue Waves | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township | 0.568864/34.559141 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41658 | 41769 |  | 4152800 | 4152800 | 4152800 | County Government of Bungoma |  | 4152800 |  | 4152800 | 100.0% | 4152800 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good status
59 | Upgrading of Rehab And Tourist Road And Khetias Cross Road -Site & Scheme | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41653 | 41781 |  | 5436518 | 5436518 | 5436518 | County Government of Bungoma |  | 5436518 |  | 5436518 | 100.0% | 5436518 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
60 | Upgrading of Rehabilitation Of Simba Street | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41657 | 41775 |  | 19923812 | 19923812 | 19923812 | County Government of Bungoma |  | 19923812 |  | 19923812 | 100.0% | 19923812 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
61 | Upgrading of Up Bungoma Posta-Kenya Seed-Chemist Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township | 0.571557/34.562277 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41651 | 41781 |  | 21973102.8 | 21973102.8 | 21973102.8 | County Government of Bungoma |  | 21973102.8 |  | 21973102.8 | 100.0% | 21973102.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need further maintenance
62 | Upgrading of C33 Co Operative-Old Rex Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41654 | 41783 |  | 18766247.15 | 18766247.15 | 18766247.15 | County Government of Bungoma |  | 18766247.15 |  | 18766247.15 | 100.0% | 18766247.15 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | in bad shape cloaking drainage
63 | Upgrading of Police-Milimani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41650 | 41778 |  | 4290689 | 4290689 | 4290689 | County Government of Bungoma |  | 4290689 |  | 4290689 | 100.0% | 4290689 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
64 | Upgrading of Cooperative Bank-Municipal Market Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41649 | 41776 |  | 5124532 | 5124532 | 5124532 | County Government of Bungoma |  | 5124532 |  | 5124532 | 100.0% | 5124532 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
65 | Upgrading of Moi Avenue(Part) | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41650 | 41770 |  | 5882835.6 | 5882835.6 | 5882835.6 | County Government of Bungoma |  | 5882835.6 |  | 5882835.6 | 100.0% | 5882835.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need renovation
66 | Upgrading of Maruti-Mt Crest-Posta Roads | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41650 | 41772 |  | 52112182.2 | 52112182.2 | 52112182.2 | County Government of Bungoma |  | 52112182.2 |  | 52112182.2 | 100.0% | 52112182.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
67 | Upgrading of Gravelling Of Slaughter House Dos Office Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41656 | 41774 |  | 8789204.28 | 8789204.28 | 8789204.28 | County Government of Bungoma |  | 8789204.28 |  | 8789204.28 | 100.0% | 8789204.28 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
68 | Periodic Maintenance of Routine Maintenance Of Highway-Police Training Centre Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41649 | 41781 |  | 4451351.52 | 4451351.52 | 4451351.52 | County Government of Bungoma |  | 4451351.52 |  | 4451351.52 | 100.0% | 4451351.52 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
70 | Upgrading of Kenyatta Street | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41652 | 41781 |  | 15302685 | 15302685 | 15302685 | County Government of Bungoma |  | 15302685 |  | 15302685 | 100.0% | 15302685 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
111 | Periodic Maintenance of Munyali - R. Sio Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Township | 0.567343/34.558747 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 42390 | 42504 |  | 5583638.8 | 5583638.8 | 5583638.8 | County Government of Bungoma |  | 5583638.8 |  | 5583638.8 | 99.37% | 5583638.8 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need further maintenance
264 | Periodic Maintenance of Mufutu - Lady Irene - Kiko Mosque Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.54KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43117 | 43238 |  | 7036629.6 | 7036629.6 | 7036629.6 | County Government of Bungoma |  | 7036629.6 |  | 7036629.6 |  | 7036629.6 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need some maintenance
265 | Periodic Maintenance of Denniz - Pombo Tano Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.54KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43116 | 43237 |  | 7036629.6 | 7036629.6 | 7036629.6 | County Government of Bungoma |  | 7036629.6 |  | 7036629.6 |  | 7036629.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs further gravelling and drainage system
266 | Periodic Maintenance of Railway - Sinoko Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.54KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Township | 0.574768/34.549707 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43237 |  | 7036629.6 | 7036629.6 | 7036629.6 | County Government of Bungoma |  | 7036629.6 |  | 7036629.6 |  | 7036629.6 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need further maintenance
267 | Periodic Maintenance of Roads In Township Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.54KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43231 |  | 7036629.6 | 7036629.6 | 7036629.6 | County Government of Bungoma |  | 7036629.6 |  | 7036629.6 | 99.69% | 7036629.6 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
439 | Periodic Maintenance of Roads In Township Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43609 |  | 2839482 | 2839482 | 2839482 | County Government of Bungoma |  | 2839482 |  | 2839482 | 99.85% | 2839482 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
440 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use through MTF
441 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
662 | Upgrading of Blue Waves - Pombo Tano - Sinoko Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43973 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | to be planned for tarmacking
663 | Drainage Works In Kanduyi And Bumula Sub-Counties(Lot 2) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 | 96.54% | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | roads in the market to acc stage to be unblocked
981 | Periodic Maintenance of Ap - Sinoko - River Sio Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township | 0.573625/34.553940 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44332 |  | 7899887.1 | 7899887.1 | 7899887.1 | County Government of Bungoma |  | 7899887.1 |  | 7899887.1 |  | 7899887.1 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | was tarmacked by KERRA
982 | Periodic Maintenance of Roads In Township Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44327 |  | 7899887.1 | 7899887.1 | 7899887.1 | County Government of Bungoma |  | 7899887.1 |  | 7899887.1 | 99.98% | 7899887.1 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | some need maintenance
1315 | Periodic Maintenance of Shell - Ambayo - Miracle - Pombo Mbili Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township | 0.579313/34.554966 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44695 |  | 3994431 | 3994431 | 3994431 | County Government of Bungoma |  | 3994431 |  | 3994431 |  | 3994431 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good status
1316 | Periodic Maintenance of Ack - Nyota Loop - Deb - Macheusi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Township | 0.57347 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44691 |  | 2237741.5 | 2237741.5 | 2237741.5 | County Government of Bungoma |  | 2237741.5 |  | 2237741.5 |  | 2237741.5 | 0 | 0 | complete and in use | [6 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need further maintenance
1317 | Periodic Maintenance of Roads In Township Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44697 |  | 3994431 | 3994431 | 3994431 | County Government of Bungoma |  | 3994431 |  | 3994431 | 100.0% | 3994431 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1318 | Routine Maintenance Of Ack - Nyota Loop - Deb - Macheusi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Township | 0.573473/34.556901 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44699 |  | 2237741.5 | 2237741.5 | 2237741.5 | County Government of Bungoma |  | 2237741.5 |  | 2237741.5 | 95.17% | 2237741.5 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need further maintenance
1559 | Periodic Maintenance of Lady Irene Mufutu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45069 |  | 11669600 | 11669600 | 11669600 | County Government of Bungoma |  | 11669600 |  | 11669600 |  | 11669600 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | wel done
1560 | Periodic Maintenance of Denniz - Wesamba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45070 |  | 11669600 | 11669600 | 11669600 | County Government of Bungoma |  | 11669600 |  | 11669600 |  | 11669600 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | to be considered for tarmacking as it is an access to musikoma
1561 | Periodic Maintenance of Kivuli Resort - Stadium - Zero Zero Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45060 | 45091 | 11669600 | 11669600 | 11669600 | County Government of Bungoma |  | 11669600 |  | 11669600 |  | 11669600 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | tarmacked kivuli resort to gate 5 of stadium
1562 | Periodic Maintenance of Blue Waves - Pombo Tano - Sinoko Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45062 |  | 11669600 | 11669600 | 11669600 | County Government of Bungoma |  | 11669600 |  | 11669600 |  | 11669600 | 0 | 0 | complete and in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | upper township
1563 | Upgrading of Mama Fanta Street | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45061 |  | 23100549.95 | 23100549.95 | 23100549.95 | County Government of Bungoma |  | 23100549.95 |  | 23100549.95 |  | 23100549.95 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | well carpeted and marked
1564 | Upgrading of Mwireli Lane | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45062 |  | 21213993.7 | 21213993.7 | 21213993.7 | County Government of Bungoma |  | 21213993.7 |  | 21213993.7 |  | 21213993.7 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | well carpeted and marked
1565 | Periodic Maintenance of Lady Irene - Mufutu - Denniz - Wesamba - Kivuli Resort - Stadium -Zero Zero - Rockstar Hotel Road In Township Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45065 |  | 11669600 | 11669600 | 11669600 | County Government of Bungoma |  | 11669600 |  | 11669600 | 99.96% | 11669600 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need continous maintenance especialy from zero-zero to kivuli
1566 | Upgrading of Re Mama Fanta, Township Ward, In Kanduyi Sub County | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45065 |  | 23100549.95 | 23100549.95 | 23100549.95 | County Government of Bungoma |  | 23100549.95 |  | 23100549.95 | 90.56% | 23100549.95 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | in use
1567 | Upgrading of Re Mwireri Street, Township Ward In Kanduyi Sub County | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45064 |  | 21213993.7 | 21213993.7 | 21213993.7 | County Government of Bungoma |  | 21213993.7 |  | 21213993.7 | 99.69% | 21213993.7 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | in use
56 | Proposed Renovation and refurbishment of 6 units staff quarters at public works and a gate residential houses | Renovation and refurbishment | To enhance revenue collection | Six units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2021/22 | 44594 | 31/3/2022 | 20/4/2022 | 3000000 | 2142172 | 2142172 | CGB |  | 2142172 |  | 2142172 | 100% | 2142172 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
58 | Proposed construction and erection of Perimeter wall fence in public works quarters in Kanduyi sub-county | erection of Perimeter wall fence | To enhance security at the estate | One Perimeter wall fence in public works quarters in Kanduyi sub-county constructed | 3110604 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2021/22 | 44594 | 31/3/2022 | 26/4/2022 | 2500000 | 2175650 | 2175650 | CGB |  | 2175650 |  | 2175650 | 100% | 2175650 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
68 | Proposed renovation and refurbishment of 4 county residential houses | renovation and refurbishment | To enhance revenue collection | Four County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2020/21 | 13/5/2020 | 14/7/2020 | 22/8/2020 | 2000000 | 1811646.24 | 1811646.24 | CGB |  | 1811646.24 |  | 1811646.24 | 100% | 1811646.24 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
70 | proposed minor repair to residential at Posta ground | renovation and refurbishment | To enhance revenue collection | 3 units of residential posta ground repaired | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township | 0.568194/34.559281 | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2020/21 | 13/5/2020 | 14/7/2020 | 22/8/2020 | 600000 | 493000.633 | 493000.633 | CGB |  | 493000.633 |  | 493000.633 | 100% | 493000.633 |  |  | Completed | 1 | [14 empty] | need further maintenance
83 | Purchase Of 0.05ha For Pombo Tano Water Project | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of a water project | Zero point zero Five Acres of Land For Pombo Tano Water Project Purchased | 3110599 | Ward based projects | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 |  |  |  | 3000000 | 2687315.38 | 2687315.38 | CGB |  | 2687315.38 |  | 2687315.38 | 100% | 2500000 |  |  | Ongoing | 1 | [14 empty] | we did darmacation
84 | Renovation and refurbishment of 16 county residential houses | renovation and refurbishment | To enhance revenue collection | Sixteen County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2019/20 | 21/2/2020 | 22/4/2020 | 43866 | 5000000 | 4623000 | 4623000 | CGB |  | 4623000 |  | 4623000 | 100% | 4523504 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
85 | Security fencing of county residential estate with natural stones in Kanduyi, | Fencing of county residential estate with natural stones | To enhance security at the estate | One Perimeter wall in kanduyi constructed | 3110604 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2019/20 | 21/2/2020 | 22/4/2020 | 44109 | 2500000 | 2000000 | 2000000 | CGB |  | 2000000 |  | 2000000 | 100% | 1920415 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
86 | Minor repairs to county residential houses | renovation and refurbishment | To enhance revenue collection | 2 units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2019/20 | 21/2/2020 | 22/4/2020 | 44109 | 600000 | 500000 | 500000 | CGB |  | 500000 |  | 500000 | 100% | 500000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
91 | Construction of storm water drainage | Construction of drainage | T o prevent flooding,protect infrastructure and safeguard public health and environment | One storm water drainage constructed | 2211311 | Development/Physical Planning | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 43743 | 43688 | 43749 | 40000000 | 38257250 | 38257250 | CGB |  | 38257250 |  | 38257250 |  | 37257250 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
92 | Purchase of GIS equiment and accessories | Purchase of equipment and accessories | To collect, analyse and visualize spatial data to support decision making | One GIS equiment and assorted accessories purchased. | 2211311 | Development/Physical Planning | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 43743 | 43688 | 25/11/2019 | 18000000 | 18000000 | 18000000 | CGB |  | 18000000 |  | 18000000 |  | 13730000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
103 | Proposed erection and completion of residential units and external works | erection and completion of residential units and external works | To enhance revenue collection | 8 County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2018/19 | 43740 | 43803 | 21/5/2019 | 40000000 | 39713724 | [26 empty] | The project is 100% complete and in use
104 | Proposed major repairs and replacement of Absestos roofing sheets with GCI roofing sheets of county residential houses. | major repairs and replacement of Absestos roofing sheets with GCI roofing sheets | To enhance revenue collection | 5 County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2018/19 | 43740 | 43803 | 43743 |  | 1500000 | [26 empty] | The project is 100% complete and in use
105 | Proposed major repairs and replacement of Asbestos roofing sheets with GCI roofing sheets of county residential houses. | major repairs and replacement of Asbestos roofing sheets with GCI roofing sheets | To enhance revenue collection | 5 County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2018/19 | 43740 | 43803 | 15/5/2019 |  | 1141011.2 | [26 empty] | The project is 100% complete and in use
106 | Proposed major repairs and replacement of Asbestos roofing sheets with GCI roofing sheets of county residential houses ans SQ | major repairs and replacement of Asbestos roofing sheets with GCI roofing sheets | To enhance revenue collection | 3 County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2018/19 | 43740 | 43803 | 20/4/2019 |  | 572428 | [26 empty] | The project is 100% complete and in use
107 | Proposed major repairs and replacement with GCI roofing sheets of the county residential houses. | major repairs and replacement of Asbestos roofing sheets with GCI roofing sheets | To enhance revenue collection | 6 County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2018/19 | 43740 | 43803 | 22/4/2019 | 1300000 | 1249518 | 1249518 | CGB | N/A | 1249518 | 0 | 1249518 | 100% | 1249518 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
109 | Construction of storm water drainage | Requistion,advertisement,survey,valuation,agreement signing and payment | T o prevent flooding,protect infrastructure and safeguard public health and environment | One storm water drainage constructed | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42957 | 43191 | 20/1/2018 | 38000000 | 37257250 | 37257250 | CGB | N/A | 37257250 | 0 | 37257250 | 100% | 37257250 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
132 | Proposed security fencing of lower Milimani estate county residential houses NO BMC5A&B,BMC6A&B,BMC7A&B,BMC8A&B,BMC9A&B,BMC10A&B,BMC11A&B and BMC12A&B | Fencing with barbed wire and chainlinnk | To enhance security at the estate | Sixteen units of County residential estates fenced | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2017/18 | 19/11/2017 | 19/1/2018 | 43254 | 594077.2 | 594077.2 | 594077.2 | CGB | N/A | 594077.2 |  | 594077.2 | 100% | 594077.2 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
133 | Proposed renovations of county residential houses NO.BUNG/CO-OP/1/3,BUNG/CO-OP/1/4 AND BUNG/MED/1/35 | major repairs and replacement of Asbestos roofing sheets with GCI roofing sheets | To enhance revenue collection | Four units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2017/18 | 19/11/2017 | 19/1/2018 | 15/3/2018 | 2801979.76 | 2801979.76 | 2801979.76 | CGB | N/A | 2801979.76 |  | 2801979.76 | 100% | 2801979.76 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
136 | Proposed erection and completion of residential units and external works | Erection and completion of residential units | To enhance revenue collection | 8 units County residential houses constructed | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2017/18 | 19/11/2017 | 19/1/2018 | 26/1/2018 | 38713724 | 38713724 | 38713724 | CGB | N/A | 38713724 |  | 38713724 | 100% | 22176695 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
137 | Proposed minor repairs of county residential houses NO.BUNG/MOW/1/8A&8B,BUNG/MOW/1/17A&17B | Minor repairs | To enhance revenue collection | Four units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2017/18 | 19/11/2017 | 19/1/2018 | 30/1/2018 | 441200 | 441200 | 441200 | CGB | N/A | 441200 |  | 441200 | 100% | - | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
138 | Proposed minor repair and replacement of asbestos roofing sheets with GCI roofing sheets of county residential houses NO.BUNG/MED/1/47A&B.BUNG/MED/1/47 C&B &C,BUNG/MED/ 1/47D AND BMC19 | renovation and replacement of asbestos roofing sheets with GCI roofing sheets | To enhance revenue collection | County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2017/18 | 19/11/2017 | 19/1/2018 | 43436 | 885385.6 | 885385.6 | 885385.6 | CGB | N/A | 885385.6 |  | 885385.6 | 100% | 885385.6 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
139 | Proposed minor repairs of county residential houses NO.BMC 1A&B,BMC2A&B, BMC3A&B,BMC5A&B,BMC6A,&B BMC7A&B | Minor repairs | To enhance revenue collection | twelve units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2017/18 | 19/11/2017 | 19/1/2018 | 20/2/2018 | 995547.5 | 995547.5 | 995547.5 | CGB | N/A | 995547.5 |  | 995547.5 | 100% | 995547.5 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
145 | Internal renovation and refurbishment of county residential house no. BCC8 and BCC19 | Renovation and refurbishment | To enhance revenue collection | Two units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2016/17 | 16/8/2016 | 16/10/2016 | 30/10/2016 | 400000 | 400000 | 400000 | CGB | N/A | 400000 |  | 400000 | 100% | 400000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
150 | Perimeter fencing with reated posts, barbed wire and chainlink) | Perimeter fencing with reated posts, barbed wire and chainlink) | To enhance revenue collection | One County residential estate fenced | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2016/17 | 15/11/2016 | 16/1/2017 | 20/1/2017 | 545000 | 545000 | 545000 | CGB | N/A | 545000 |  | 545000 | 100% | 545000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
173 | Renovation of county residential houses | Renovation and refurbishment | To enhance revenue collection | Eighty units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42461 | 42707 | 42466 | 1200000 | 1110000 | 1110000 | CGB | N/A | 1110000 |  | 1110000 | 100% | 1109116 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
174 | Renovation of county residential houses | Renovation and refurbishment | To enhance revenue collection | Fifteen units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42461 | 42707 | 42465 | 4500000 | 4200000 | 4200000 | CGB | N/A | 4200000 |  | 4200000 | 100% | 4187220.96 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
175 | Minor repairs of county residential houses | Renovation and refurbishment | To enhance revenue collection | Three units of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42461 | 42707 | 42465 | 500000 | 480000 | 480000 | CGB | N/A | 480000 |  | 480000 | 100% | 477420.04 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
201 | Renovation and refurbishment of county house BCC 3B | Renovation and refurbishment | To enhance revenue collection | One unit of County residential houses renovated | 3110301 | Other Infrastructure and Civil Works | Kanduyi | Township |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2014/15 | 41831 | 42340 | 42340 | 700000 | 650000 | 650000 | CGB | N/A | 650000 |  | 650000 |  | 616074 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
96 | Proposed Erection and Completion works for 1 no. ECDE classroom and Office at Mupeli and Central Baptist primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Township |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 4500000 | 4389700 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 1943687 | 44.28% | 1943687 | 2446013 | 2446013 | ongoing | 1 | [14 empty] | classrom at mupeli primary was moved to moi primary
3 | INSTALLATION AND REPAIR OF GRID POWERED STREETLIGHTS IN TOWNSHIP WARD. | REPAIR EXISTING STREET LIGHTS, INSTALL NEW STREET LIGHTS WHERE APPLICABLE, CONNECT LIGHTS TO SOLAR POWER, SETTING UP OF AUTOMATED LIGHTING SWITCHES | TO PROVIDE LIGHTING IN URBAN NEIGHBORHOODS | STREET LIGHTING COMPLETE WITH SOLAR INSTALLATION | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 15/4/2024 | 15/4/2024 | 4000000 | 4000000 | 4000000 | CGB |  | 4000000 | 0 | 4000000 | 100% | 0 | 3988080 | 3988080 | stalled | [6 empty] | NO |  | NON-PAYMENT BY COUNTY TREASURY FOR COMPLETED PROJECTS | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | vandalized as most are not working
4 | REHABILITATION OF DRAINAGE AND PAVEMENT WORKS AT THE MUNICIPAL MARKET IN BUNGOMA TOWN | DRAINAGE WORKS,CIVIL WORKS | TO IMPROVE URBAN BUSINESS ENVIRONMENT | DRAINAGE CHANNELS,PAVED GROUND SURFACES | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 15/4/2024 | 15/4/2024 |  | 9500000 | 9500000 | CGB |  | 9500000 | 0 | 9500000 | 100% | 0 | 9399514 | 9399514 | Ongoing | [6 empty] | NO |  | NON-PAYMENT BY COUNTY TREASURY FOR COMPLETED PROJECTS | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | central township
11 | DRILLING AND UPGRADING OF CENTRAL BAPTIST PRIMARY BOREHOLE | DRILLING, SOLAR POWER INSTALLATION | TO IMPROVE ACCESS TO SAFE DRINKING WATER | DRILLED BOREHOLE WITH CLEAN WATER | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township | 0.566674/34.556277 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 3000000 | 3000000 | 3000000 | CGB |  | 3000000 | 0 | 3000000 | 100% | 0 | 3940130 | 3940130 | ongoing | 0.9 | [5 empty] | NO |  | RISK OF VANDALISM | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
14 | DRILLING AND UPGRADING OF BUNGOMA DEB PRIMARY BOREHOLE AND WATERLINE | DRILLING,PIPE LAYING AND SOLAR POWER INSTALLATION | TO IMPROVE ACCESS TO SAFE DRINKING WATER | DRILLED BOREHOLE WITH CLEAN WATER, LAID PIPES | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township | 0.571172/34.556398 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 3000000 | 5926022 | 5926022 | CGB |  | 5926022 | 0 | 5926022 | 100% | 0 | 5926022 | 5926022 | COMPLETED | [6 empty] | NO |  | RISK OF VANDALISM | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | used by the school alone ,not serving the community
18 | CONSTRUCTION AND REHABILITATION OF POMBO MBILI WATER PROJECT | REHABILITATED WATER PROJECT | TO IMPROVE ACCESS TO SAFE DRINKING WATER | USABLE CLEAN WATER | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township | 0.574627/34.549910 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 1000000 | 1000000 | 1000000 | CGB |  | 1000000 | 0 | 1000000 | 100% | 0 | 989546 | 989546 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
19 | PURCHASE OF LAND FOR EXPANSION OF CHEPKUBE MARKET | PURCHASED LAND | TO PROVIDE CONDUSIVE MARKET FOR TRADING ACTIVITIES | LAND SPACE FOR MARKET EXPANSION | 3130101 | ACQUISITION OF LAND | Kanduyi | Township |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 38000000 | 38000000 | 38000000 | CGB |  | 38000000 | 0 | 38000000 | 100% | 0 | 32729000 | 32729000 | Ongoing | [6 empty] | NO |  | CONTRACTUAL RISK | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | at proposal level
21 | UPGRADING OF WINGS-WAMBIYA JUNCTION AND OTHER ROADS WITHIN THE CBD TO CABROS STANDARDS. | TARMACKING , DRAINAGE WORK | TO IMPROVE ACCESSIBILITY TO URBAN CENTRE | CABRO ROAD | 2640503 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 15/06/2020 | 15/12/2020 | 15/12/2020 | 57621459.61 | 57621459.61 | 57621459.61 | WORLD BANK- KUSP I | WORLD BANK | 0 | 57621459.61 | 57621459.61 | 100% | 52870749 | 0 | 0 | COMPLETED | [6 empty] | NO | [8 empty] | in use
22 | UPGRADING OF SUNRISE, BUNGOMA HIGH AND MOI PRIMARY TO CABROS STANDARDS. | TARMACKING , DRAINAGE WORK | TO IMPROVE ACCESSIBILITY TO URBAN CENTRE | CABRO ROAD | 2640503 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township | 0.571210/34.556379 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 20/08/2020 | 20/02/2021 | 20/02/2021 | 52723255.47 | 52723255.47 | 52723255.47 | WORLD BANK- KUSP I | WORLD BANK | 0 | 52723255.47 | 52723255.47 | 100% | 48255065 | 0 | 0 | COMPLETED | [6 empty] | NO | [8 empty] | in use
24 | UPGRADING OF SHARIFF CENTRE TO POLICE TO PRISONS, KHETIAS STORES TO MAMA FANTA ROAD | TARMACKING , DRAINAGE WORK | TO IMPROVE ACCESSIBILITY TO URBAN CENTRE | TARMACK ROAD | 2640503 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Township | 0.569400/34.557891 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 43621 | 43627 | 43627 | 51046624.19 | 51046624.19 | 51046624.19 | WORLD BANK- KUSP I | WORLD BANK | 0 | 51046624.19 | 51046624.19 | 100% | 48389766.76 | 0 | 0 | COMPLETED | [6 empty] | NO | [8 empty] | in use
113 | Drilling and upgrading of Moi DEB primary borehole in township ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 3000000 | 2829000 | 2829000 |  | N/A | 2829000 | 0 | 2829000 | 100% | 2829000 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use and helpful
160 | Construction of Wings-Mufutu-Mupeli-sewerline | Trenching, haunching, pipe laying of sewerline; back-filling; masonry works; metal works | To enhance access to clean and safe drinking water | KM of Sewerline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 10000000 | 9194044 | 9194044 |  | N/A | 9194044 | 0 | 9194044 | 100% | 9194044 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
213 | CONSTRUCTION OF MANDIZINI – OLDREX – MUFUTU – JAMIA MOSQUE SEWERLINE AND ERECTION OF WATER TANK AT BUNGOMA D.E.B PRI. SCHOOL | Trenching, haunching, pipe laying of sewerline; back-filling; masonry works; metal works | To enhance access to clean and safe drinking water | KM of sewerline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 9000000 | 8619670 | 8619670 |  | N/A | 8619670 | 0 | 8619670 | 100% | 8619670 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | serving the community well
250 | CONSTRUCTION OF TOWNSHIP WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 8500000 | 8414652 | 8414652 |  | N/A | 8414652 | 0 | 8414652 | 100% | 8414652 | 0 | 0 | completed but not in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | the borehole has no sufficient water
255 | CONSTRUCTION OF SEWERLINE IN TOWNSHIP WARD | Trenching, haunching, pipe laying of sewerline; back-filling; masonry works; metal works | To enhance access to clean and safe drinking water | KM of sewerline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 5100000 | 5041940 | 5041940 |  | N/A | 5041940 | 0 | 5041940 | 100% | 5041940 | 0 | 0 | stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | to bre budgeted fo in new fyr
339 | CONSTRUCTION OF TOWNSHIP SEWER LINE | Trenching, haunching, pipe laying of sewerline; back-filling; masonry works; metal works | To enhance access to clean and safe drinking water | KM of sewerline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 5000000 | 5000000 | 5000000 |  | N/A | 5000000 | 0 | 5000000 | 100% | 5000000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
455 | Protection of 1 and Construction of 50m3 Masonry tank at Namachanja Secondary School water Springs Construction of 4 Roof Catchment | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; construction of roof catchment and storage tank with water points | To enhance access to clean and safe drinking water | 1 water springs constructed and 4 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1554190 | 1554190 |  | N/A | 1554190 | 0 | 1554190 | 100% | 1554190 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | central township
504 | Protection of 1 spring and Construction of 50m3 Masonry tank at Namachanja Secondary School Construction of 4 Roof Catchment | construction of roof catchment; erection of storage tank and provision of water points; Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed; 1 spring protected | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1554190 | 1554190 |  | N/A | 1554190 | 0 | 1554190 | 100% | 1554190 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | central township
505 | Extension of Nzowasco pipeline to six Estate. Construction of 2 kiosks at six Estate and Mulikamwizi mandizini | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed and construction of 2 water kiosks | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1890742.7 | 1890742.7 |  | N/A | 1890742.7 | 0 | 1890742.7 | 100% | 1890742.7 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
574 | Extension of Nzowasco water pipeline and construction of kiosks | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Township |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 4000000 | 3910850 | 3910850 |  | N/A | 3910850 | 0 | 3910850 | 100% | 3910850 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Supply of Liquid Nitrogen | Supply of Liquid Nitrogen | To preserve semen by ensuring it remains usable and ready for future insemination | Litres of liquid nitrogen supplied | 2211007 | Agricultural materials, supplies and small equipment | Kanduyi | Township | 0.572468/34.559454 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 10000000 | 6800000 | 7000000 | County Government of Bungoma |  | 6800000 |  | 6800000 |  | 6800000 | 0 | 0 | Completed
| Purchase and installation of Automatic Weather Stations | Purchase and installation of 4 Automatic Weather Stations in Bumula, Township, Malakisi/Kulisiru and Elgon Wards | To collect precise and continous weather data | 4 Automatic Weather stations installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Kanduyi | Township | 0.572468/34.559454 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 40000000 | 35547910 | 40000000 | County Government of Bungoma |  | 35547910 |  | 35547910 | 100% | 35547910 |  | 0 | Completed
| Supply of Milk Coolers | Supply of Milk Coolers | To enhance milk production, productivity, value addition and income among the farmers | 5 Milk coolers supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | Kanduyi | Township | 0.572468/34.559454 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 20/1/2014 | 20/4/2014 | 41743 | 5500000 | 5200000 | 5500000 | County Government of Bungoma |  | 5200000 |  | 5200000 | 100% | 5200000 | 0 | 0 | Completed
| Purchase and delivery of incubators | Purchase and delivery of incubators at the County HQs | To enhance poultry production and increase household incomes | 47 Incubators purchased and delivered | 2211023 | Supplies for production | Kanduyi | Township | 0.572468/34.559454 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 20/1/2014 | 20/4/2014 | 41733 | 6000000 | 5920431.2 | 6000000 | County Government of Bungoma |  | 5920431.2 |  | 5920431.2 | 100% | 5920431.2 | 0 | 0 | Completed | [15 empty] | Can not be found in the ground
| Supply of formulated Fish Feeds and Protein Feeds | Supply of 380 bags of 20kgs of formulated Fish Feeds and Protein Feeds at the Headquarter to be distributed to farmers across the County | To increase fish production and improve on food and nutrition security | 380 bags of 20kgs of formulated fish feeds and protein feeds supplied | 2211023 | Supplies for production | Kanduyi | Township | 0.572468/34.559454 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 30/3/2015 | 8000000 | 1600000 | 1600000 | County Government of Bungoma |  | 1600000 |  | 1600000 | 100% | 1600000 | 0 | 0 | Completed
| Supply of Fish Inputs | Supply of 220 bags of 20kgs of Fish Inputs at the Headquarter to be distributed to farmers across the County | To increase fish production and improve on food and nutrition security | 220 bags of 20kgs of fish inputs supplied | 2211023 | Supplies for production | Kanduyi | Township | 0.572468/34.559452 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 15000000 | 949550 | 1000000 | County Government of Bungoma |  | 949550 |  | 949550 | 100% | 949550 | 0 | 0 | Completed
| Supply of 4*4 Double Cabins and 1 Ford Focus Motor vehicles | Supply Of 6, 4*4 Double Cabins And 1 Ford Focus Motor vehicles | To enhance efficient service delivery | 6 4*4 Double cabin and 1 Ford Focus motor vehicles procured and delivered |  | Purchase of motor vehicles | Kanduyi | Township | 0.572468/34.559452 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 42949 | 42952 | 13/5/2017 | 40000000 | 31250000 | 32000000 | County Government of Bungoma |  | 31250000 | 0 | 31250000 | 100% | 31250000 | 0 | 0 | Completed
| Construction of Lagoons and fencing of Tannery | Construction Of Lagoons, External Works and Fencing for Tannery in Bungoma | To treat waste water by using natural processes | 2 lagoons constructed and tannery fenced | 3110504 | Other infrastructure and civil works | Kanduyi | Township | 0.572468/34.559452 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 18/2/2017 | 18/5/2017 | 42860 | 10000000 | 7855193.8 | 7855193.8 | County Government of Bungoma |  | 7855193.8 | 0 | 7855193.8 | 100% | 7855193.8 | 0 | 0 | Completed
| Rehabilitation of County Cooperative Office | Rehabilitation of County Office Cooperative Office | To provide an enabling working environment | 1 Office rehabilitated | 3110504 | Other infrastructure and civil works | Kanduyi | Township |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 42771 | 6000000 | 5920431.2 | 6000000 | County Government of Bungoma |  | 5920431.2 | 0 | 5920431.2 | 100% | 5920431.2 | 0 | 0 | Completed
| Development of livestock sale yard bill | Development of livestock sale yard bill | To support to regulatory mechanism for markets- | 1 bill developed | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 |  |  | 14/5/2024 |  | 3639838 | 4352740 | Development partner | IFAD | 0 | 3639838 | 3639838 |  | 3639838 | 0 | 0 | Complete
5 | Proposed repair and maintenance of 2 No high mast lights at soko kubwa and Chebkube. | Instalation of high mast flood lights | promotion of MSMEs and security | High mast lights repaired and mantained | BGM/CNTY/TEI/14/OT/2024-2025 1668557-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | ENERGIA ENGINEERING | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 4000000 |  |  | CGB | [8 empty] | only chebukube mast was repaired. |  | 2 | [13 empty] | half of the budget did repairs and installation of street lightsi.eshell,elegant,old-rex,moi avenue etc
52 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Streetlights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 33809926 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | need periodic maintenance
56 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 22134813 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | some are using direct greed power
57 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 19706238 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | some are using direct greed power
58 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 17277663 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | some are using direct greed power
60 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 12420513 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | some are using direct greed power
61 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 9991938 | 0 |  | CGB | [8 empty] | stalled | [15 empty] | vandalized is in upper town
63 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 5134788 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | vandalized is in upper town
65 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | 277638 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | vandalized is in upper town
68 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | -7008087 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | vandalized is in upper town
71 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | -14293812 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | vandalized is in upper town
73 | Proposed supply, installation and commisioning of solar street lights in bungoma town | supply commisioning street solar street lights |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Integrated Services Delinery Lsd Logistics limited | 2022/23 |  | Complete and in use |  | -19150962 | 0 |  | CGB | [8 empty] | Completed | [15 empty] | vandalized is in upper town
76 | Installation of 41 grid powered streetlights in Kanduyi Sub-county . | of streetlights Kanduyi streetlights in |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S Mbale Town Electro Works Umeme | 2021/22 |  | Complete and in use |  | 3116001 |  |  | CGB
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | Township |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
108 | Construction of market stalls | [6 empty] | Township |  |  |  | Kisiwa Technical Institiute | 2019/20 |  | Complete |  | 9994738 |  |  | CGG | [8 empty] | ongoing | [15 empty] | currently status in kanduyi is at 70% completition
121 | Purchase of Cherry Pick up | Of up streetlights | [5 empty] | Township |  |  |  | IZUZU Kenya | 2019/20 |  | Delivered and in use |  | 13793500 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township | 0.572453/34.559438 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed | [15 empty] | well distributed to farmers
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed | [15 empty] | installed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed | [15 empty] | well served to famers
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed | [15 empty] | well served to famers
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed | [15 empty] | need more seeds due to growth of famers
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed | [15 empty] | need more fertilizers
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed | [15 empty] | done
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed | [15 empty] | done
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed | [15 empty] | done
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed | [15 empty] | order to be increased
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed | [15 empty] | done
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed | [15 empty] | well distributed to farmers
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed | [15 empty] | well served to famers
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed | [15 empty] | well distributed to farmers
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed | [15 empty] | well distributed to farmers
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed | [15 empty] | well distributed to farmers
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed | [15 empty] | well distributed to farmers
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed | [15 empty] | well distributed to farmers
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | stalled | [15 empty] | to be re-introduced
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Township |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed | [15 empty] | well served to famers
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Township |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
13 | Upgrading of R. Sio-Samoya Mkt-Bungoma | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41657 | 41777 |  | 9834132 | 9834132 | 9834132 | County Government of Bungoma |  | 9834132 |  | 9834132 | 100.0% | 9834132 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
19 | Upgrading of Chebukwa Junct Luucho-R.Khalaba Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41663 | 41770 |  | 4146070 | 4146070 | 4146070 | County Government of Bungoma |  | 4146070 |  | 4146070 | 100.0% | 4146070 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
27 | Upgrading of Muyayi-R.Khalaba-Pamus Ttc | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41649 | 41779 |  | 4109532 | 4109532 | 4109532 | County Government of Bungoma |  | 4109532 |  | 4109532 | 100.0% | 4109532 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
30 | Upgrading of Periodic Maintanance Of R.Khalaba-Kabula(C33)-Sioya-Mateka-R.Sio | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41653 | 41775 |  | 18952140.9 | 18952140.9 | 18952140.9 | County Government of Bungoma |  | 18952140.9 |  | 18952140.9 | 100.0% | 18952140.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
103 | Periodic Maintenance of Marell - Namuyemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Khalaba | 0.578583/34.561833 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2015/2016 | 31/11/2016 | 42501 | 19/01/2017 | 5198424 | 5198424 | 5198424 | County Government of Bungoma |  | 5198424 |  | 5198424 | 97.68% | 5198424 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
189 | Periodic Maintenance of C33 Igc Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.570861/34.557972 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43123 | 43234 |  | 13649882 | 13649882 | 13649882 | County Government of Bungoma |  | 13649882 |  | 13649882 |  | 13649882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use,no culverts,poor drainage at mama Hersi apartments
190 | Periodic Maintenance of C33 King Jesus Faith Church - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.558972/34.560972 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 28/1/2019 | 43232 | 2019 | 13649882 | 13649882 | 13649882 | County Government of Bungoma |  | 13649882 |  | 13649882 |  | 13649882 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
191 | Periodic Maintenance of C33 Chetambe Posho Mill - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.548277/34.557277 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 15/1/2019 | 43244 | 2019 | 13649882 | 13649882 | 13649882 | County Government of Bungoma |  | 13649882 |  | 13649882 |  | 13649882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | insufficient culverts installation
192 | Periodic Maintenance of Mother Kelvin Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.555805/34.559722 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 14/1/2019 | 43239 | 2019 | 13649882 | 13649882 | 13649882 | County Government of Bungoma |  | 13649882 |  | 13649882 |  | 13649882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor workmanship
193 | Periodic Maintenance of Sunrise Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.589972/34.562111 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43233 |  | 13649882 | 13649882 | 13649882 | County Government of Bungoma |  | 13649882 |  | 13649882 |  | 13649882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
194 | Periodic Maintenance of Maina Friends - Tenstar - Marell Namuyemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.587527/34.567944 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43739 | 43230 | 43497 | 13649882 | 13649882 | 13649882 | County Government of Bungoma |  | 13649882 |  | 13649882 |  | 13649882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts and poor drainage
195 | Periodic Maintenance of Roads In Khalaba Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43236 |  | 13649882 | 13649882 | 13649882 | County Government of Bungoma |  | 13649882 |  | 13649882 | 100.0% | 13649882 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
354 | Periodic Maintenance of C33 Pork Butchery - R. Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.569527/34.563222 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43530 | 43602 | 30/9/2019 | 10121395 | 10121395 | 10121395 | County Government of Bungoma |  | 10121395 |  | 10121395 |  | 10121395 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the road did not reach the river
355 | Periodic Maintenance of C33 Chebukube Mkt - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.557833/34.560583 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43530 | 43600 | 30/9/2019 | 10121395 | 10121395 | 10121395 | County Government of Bungoma |  | 10121395 |  | 10121395 |  | 10121395 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | grading and gravelling was done
356 | Periodic Maintenance of Mija Guest House Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.568694/34.563138 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43530 | 43600 | 30/9/2019 | 10121395 | 10121395 | 10121395 | County Government of Bungoma |  | 10121395 |  | 10121395 |  | 10121395 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the road didn't reach the river and it has never been done
357 | Periodic Maintenance of Wandiaka - Juma Bakari Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.530694/34.559083 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43530 | 43599 | 30/9/2019 | 10121395 | 10121395 | 10121395 | County Government of Bungoma |  | 10121395 |  | 10121395 |  | 10121395 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | done grading,gravelling $ culverts installation
358 | Periodic Maintenance of C33 Royal Hotel Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.530694/34.553388 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43530 | 43597 | 30/9/2019 | 10121395 | 10121395 | 10121395 | County Government of Bungoma |  | 10121395 |  | 10121395 |  | 10121395 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts installation
359 | Periodic Maintenance of C33 Mwatikho (Khalaba Hospital) Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.545861/34.557722 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43530 | 43606 | 30/9/2019 | 10121395 | 10121395 | 10121395 | County Government of Bungoma |  | 10121395 |  | 10121395 |  | 10121395 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | done grading and gravelling
360 | Periodic Maintenance of Roads In Khalaba Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43486 | 43608 |  | 10121395 | 10121395 | 10121395 | County Government of Bungoma |  | 10121395 |  | 10121395 | 87.42% | 10121395 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
361 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
532 | Upgrading of Okumu - Pamus R - Khalaba Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43969 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
533 | Periodic Maintenance of C33 - Khetias Highway - R. Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.567888/34.563166 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 44050 | 43970 | 30/8/2020 | 8186665 | 8186665 | 8186665 | County Government of Bungoma |  | 8186665 |  | 8186665 |  | 8186665 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the road did not reach the river,tarmacking was not done by county government
534 | Periodic Maintenance of C33 Cereals Board - R. Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.574694/34.564083 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 29/6/2020 | 43969 | 30/8/2020 | 8186665 | 8186665 | 8186665 | County Government of Bungoma |  | 8186665 |  | 8186665 |  | 8186665 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the road did not reach the river
535 | Periodic Maintenance of C33 - Bebamin - R. Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.571722/34.563611 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 44019 | 43973 | 30/8/2020 | 8186665 | 8186665 | 8186665 | County Government of Bungoma |  | 8186665 |  | 8186665 |  | 8186665 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the road did not reach the river
536 | Upgrading of C33 - Cereals - River Khalaba Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43962 | 43993 | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
537 | Upgrading of C33 - Cereals - River Khalaba Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43971 | 44002 | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
538 | Periodic Maintenance of Roads In Khalaba Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 8186665 | 8186665 | 8186665 | County Government of Bungoma |  | 8186665 |  | 8186665 | 89.72% | 8186665 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
539 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
663 | Drainage Works In Kanduyi And Bumula Sub-Counties(Lot 2) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 | 96.54% | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
778 | Periodic Maintenance of Pamus - Ndengelwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Khalaba | 0.577722/34.564194 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44336 |  | 7098547.5 | 7098547.5 | 7098547.5 | County Government of Bungoma |  | 7098547.5 |  | 7098547.5 |  | 7098547.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
779 | Periodic Maintenance of Elmas - R. Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.522888/34.552111 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44326 |  | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 |  | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
780 | Periodic Maintenance of Musikoma Police Post - Juma Bakari Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.533416/34.554194 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44229 | 44336 | 44232 | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 |  | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the road does not reach the river,encroachment and insufficient culverts
781 | Periodic Maintenance of Village Inn - R. Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.534666/34.555194 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44229 | 44337 | 44232 | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 |  | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the road didn't reach the river as at 2020/2021,encroachment
782 | Periodic Maintenance of Countryside - Marrell Namuyemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.583222/34.557222 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44229 | 44329 | 44232 | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 |  | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | only two culverts installed on of them private as at the time
783 | Periodic Maintenance of Hon Tim Wanyonyi - Grace Community - Wamalwa Kijana Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 3.086111/37.136111 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44330 |  | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 |  | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | only one culvert at Grace Community-Total junction and poor drainage at the time
784 | Periodic Maintenance of Tenstar - Lusaka Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.586083/34.56325 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44229 | 44333 | 44232 | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 |  | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Tenstar no culverts at the time
785 | Periodic Maintenance of A104 Total - Redcross Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.59841666/34.558666 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44229 | 44333 | 44232 | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 |  | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts at the time
786 | Upgrading of Royal Hotel - R. Khalaba Road | Road improvement works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.530694/34.553388 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44330 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
787 | Periodic Maintenance of Wandiaka - Juma Bakari Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.538722/34.559083 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44229 | 44339 | 44232 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | insufficient culverts
788 | Periodic Maintenance of Roads In Khalaba Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44331 |  | 13353786.6 | 13353786.6 | 13353786.6 | County Government of Bungoma |  | 13353786.6 |  | 13353786.6 | 99.9% | 13353786.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1109 | Periodic Maintenance of Pork Butchery - Harvest Miracle Church | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.569527/34.563222 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44698 |  | 10921806 | 10921806 | 10921806 | County Government of Bungoma |  | 10921806 |  | 10921806 |  | 10921806 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts installation,encroachment and private stone pitching towards the river
1110 | Periodic Maintenance of C33 - Mukhaweli Primary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.567888/34.563166 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44700 |  | 10921806 | 10921806 | 10921806 | County Government of Bungoma |  | 10921806 |  | 10921806 |  | 10921806 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor murraming,no culverts installation $ poor drainage
1111 | Periodic Maintenance of C33 Musikoma Mosque River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.528666/34.553444 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44693 |  | 10921806 | 10921806 | 10921806 | County Government of Bungoma |  | 10921806 |  | 10921806 |  | 10921806 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts installation,vegetation invading the road
1112 | Periodic Maintenance of C33 Jimmys (Wandiaka) Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.527472/34.554083 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44698 |  | 10921806 | 10921806 | 10921806 | County Government of Bungoma |  | 10921806 |  | 10921806 |  | 10921806 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | encroachment and insufficient culverts installaton
1113 | Periodic Maintenance of A104 Salmond Hotel - Lukorito Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.5931898/34.5602799 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44705 |  | 10921806 | 10921806 | 10921806 | County Government of Bungoma |  | 10921806 |  | 10921806 |  | 10921806 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no drainage system,culverts at salmondjunction at the time
1114 | Periodic Maintenance of C33 Cosmas Barasa - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.536555/34.554638 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44691 |  | 10921806 | 10921806 | 10921806 | County Government of Bungoma |  | 10921806 |  | 10921806 |  | 10921806 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts ,poor drainage
1115 | Periodic Maintenance of Roads In Khalaba Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44704 |  | 10921806 | 10921806 | 10921806 | County Government of Bungoma |  | 10921806 |  | 10921806 | 100.0% | 10921806 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1413 | Periodic Maintenance of Kasembeli - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.541472/34.555638 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45062 |  | 6610724 | 6610724 | 6610724 | County Government of Bungoma |  | 6610724 |  | 6610724 |  | 6610724 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | kasembeli was not done
1414 | Periodic Maintenance of Chetambe Posho Mill - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.548277/34.557277 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45068 |  | 6610724 | 6610724 | 6610724 | County Government of Bungoma |  | 6610724 |  | 6610724 |  | 6610724 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor drainage system
1415 | Periodic Maintenance of Grading, Graveling And Culvert Installation Along Kasembeli - R. Khalaba Road, Chetambe Posho Mill - R. Khalaba Road In Khalaba Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | kasembeli 0.541472/34.555638 chetambe 0.548277/34.557277 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45061 |  | 6610724 | 6610724 | 6610724 | County Government of Bungoma |  | 6610724 |  | 6610724 | 99.99% | 6610724 | 0 | 0 | Completed chetambe road | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | kasembeli was not done
1666 | Upgrading of Salmond River Khalaba Road | Road Upgrading to Bitumen works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba | 0.5931898/34.5602799 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45425 |  | 174606810 | 174606810 | 174606810 | County Government of Bungoma |  | 174606810 |  | 174606810 |  | 174606810 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1667 | Upgrading of Salmond River Khalaba Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45432 |  | 174606810 | 174606810 | 174606810 | County Government of Bungoma |  | 174606810 |  | 174606810 |  | 174606810 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1668 | Upgrading of A1 (Salmond) - River Khalaba Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Khalaba |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45429 |  | 174606810 | 174606810 | 174606810 | County Government of Bungoma |  | 174606810 |  | 174606810 | 17.98% | 174606810 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
79 | Land For Khalaba Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | A half an acre of Land For Khalaba Dispensary Purchased | 3110599 | Ward based projects | Kanduyi | Khalaba | 0.647222/35.725 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 | aug2020 | 15/3/2020 | dec2020 | 3000000 | 2000000 | 2000000 | CGB |  | 2000000 |  | 2000000 | 100% | 2500000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete
45 | Proposed Erection And Completion Of Perimiter Wall At Muteremuko Vtc In Khalaba Ward | Construction of perimeter wall fence | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Khalaba | 0.56041/34.566361 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2022/2023 | 44928 | 30/06/2023 |  | 4500000 | 15558370 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 12392200.85 | 79.65% | 12392200.85 | 3166169.15 | 3166169.15 | Complete and in use | 1 | [14 empty] | the wall left out some portions of vct land in some sections
141 | Renovation Of Ablution Block, Construction Of A Chain Link Fence And A Septic Tank At Mteremko Vtc In Khalaba Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Khalaba | 0.56041/34.566361 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2019/2020 | 23/3/2021 | 44049 |  | 4073081.24 | 4062375 | 4073081.24 | County Government of Bungoma | N/A | 4073081.24 | 0 | 1909370.1 | 47% | 1909370.1 | 2153004.9 | 2153004.9 | stalled ablution block $ septic tank | 0.9
1 | CONSTRUCTION OF MARKET STALLS, KITCHEN AND STORES, TOILET BLOCK AND ASSOCIATED EXTERNAL WORKS AT KANDUYI MARKET IN BUNGOMA MUNICIPALITY | BUILDERS WORK,EXTERNAL WORKS,ELECTRICAL AND MECHANICAL WORKS | TO PROVIDE SUITABLE ENVIROMENT FOR TRADING ACTIVITIES | 176 MARKET STALLS | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba | 0.599555/35.130555 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45210 | 22/4/2026 |  | 199219003 | 57,500,000 | 57,500,000 | CGB |  | 57,500,000 | 0 | 57,500,000 | 100% | 51121900 | 0 | 0 | ONGOING | 30 | [5 empty] | YES |  | FREQUENT CHANGE IN TECHNICAL PROJECT MANAGEMENT TEAM | NO |  | YES | REDESIGNING OF DRAINAGE SYSTEMS AND ADJACENT ACCESS ROADS, HIV MITIGATION CAMPAIGN AND SAFETY GEAR TO WORKERS | NO |  | MULTI-YEAR PROJECT
6 | ROUTINE MAINTENANCE OF SOROTI - LUBINDA PORK BUTCHERY ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba | soroti 0.52875/34.553083 lupinda 0.544333/34.557 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 15/4/2024 | 15/4/2024 | 4758204 | 4758204 | 4758204 | CGB |  | 4758204 | 0 | 4758204 | 100% | 0 | 4517504 | 4517504 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL CHALLENGE OF SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | the road did not reach the river
7 | DRILLING AND UPGRADING OF MUPELI D.E.B PRIMARY BOREHOLE | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 5000000 | 4868612 | 5000000 | CGB |  | 5000000 | 0 | 5000000 | 100% | 0 | 4868612 | 4868612 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL CHALLENGE OF SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
8 | INSTALLATION AND REPAIR OF GRID POWERED STREETLIGHTS IN KHALABA WARD | REPAIR EXISTING STREET LIGHTS, INSTALL NEW STREET LIGHTS WHERE APPLICABLE, CONNECT LIGHTS TO SOLAR POWER, SETTING UP OF AUTOMATED LIGHTING SWITCHES | TO PROVIDE LIGHTING AND SECURITY IN URBAN NEIGHBORHOODS | STREET LIGHTING COMPLETE WITH SOLAR INSTALLATION | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 2500000 | 2500000 | 2500000 | CGB |  | 2500000 | 0 | 2500000 | 100% | 0 | 2500000 | 2500000 | COMPLETED | [6 empty] | NO |  | VANDALISM | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
9 | ROUTINE MAINTENANCE OF NELSON MANGOLI - SIO RIVER ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 3581094 | 3581094 | 3581094 | CGB |  | 3581094 | 0 | 3581094 | 100% | 0 | 3320906 | 3320906 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL CHALLENGE OF SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
10 | ERECTION AND COMPLETION OF WORKS FOR DISPENSARY AT NAMUYEMBA VILLAGE UNIT (PHASE 1) | CONSTRUCTION OF SLAB, WALLING, ROOFING AND PLASTERING WORK | TO IMPROVE ACCESS TO HEALTHCARE | DISPENSARY UNIT | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba | 0.647222/35.725 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2023/2024 | 45302 | 45302 |  | 3500000 | 3500000 | 3500000 | CGB |  | 3500000 | 0 | 3500000 | 100% | 0 | 3959380 | 3959380 | COMPLETED | [6 empty] | NO |  | NON-STAFFING AND NON-EQUIPING OF FACILITY | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | several post implementation on the floor and the walls
12 | DRILLING AND UPGRADING OF WAMALWA KIJANA SECONDARY BOREHOLE | DRILLING, SOLAR POWER INSTALLATION | TO IMPROVE ACCESS TO SAFE DRINKING WATER | DRILLED BOREHOLE WITH CLEAN WATER | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba | 3.2/34.6 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 3000000 | 3000000 | 3000000 | CGB |  | 3000000 | 0 | 3000000 | 100% | 0 | 0 | 3000000 | cancelled | 0 | 0 | PROJECT TERMINATED | 2024 | 6 | 3000000 | NO | DEFER | FINANCIAL RISKS | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
13 | ROUTINE MAINTENANCE OF TOTAL - NAMUYEMBA - WAMALWA KIJANA - MEWA ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba | 2.19166/35.4 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2020/2021 | 44229 | 45302 | 44232 | 4739064 | 4739064 | 4739064 | CGB |  | 4739064 | 0 | 4739064 | 100% | 4536760 | 13224 | 13224 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
20 | UPGRADING OF PAMUS- NDENGELWA ROAD IN BUNGOMA MUNICIPALITY TO BITUMEN STANDARDS. | TARMACKING , DRAINAGE WORK | TO IMPROVE ACCESSIBILITY TO URBAN CENTRE | TARMACK ROAD | 2640503 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba |  | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 44568 | 30/06/2023 | 30/06/2023 | 40000000 | 40000000 | 40000000 | WORLD BANK- KUSP I | WORLD BANK | 0 | 40000000 | 40000000 | 10000% | 38812934 | 0 | 0 | COMPLETED | [6 empty] | NO | [8 empty] | PROJECT COMPLETE AND IN USE
23 | UPGRADING OF KANDUYI-MAKUTANO ROAD TO BITUMEN STANDARDS | TARMACKING , DRAINAGE WORK | TO IMPROVE ACCESSIBILITY TO URBAN CENTRE | TARMACK ROAD | 2640503 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Khalaba | 2.205555/35.130555 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 43621 | 43627 | 43627 | 55440229 | 55440229 | 55440229 | WORLD BANK- KUSP I | WORLD BANK | 0 | 55440229 | 55440229 | 100% | 52880518 | 0 | 0 | COMPLETED | [6 empty] | NO | [8 empty] | PROJECT COMPLETE AND IN USE
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | [6 empty] | FLLOCA | N/A |  | 0 |  | 100% |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
33 | Proposed Rehabilitation Of River Khalaba, Khalaba Dam And River Chwele In Tuuti/Marakaru And Bukembe West Wards | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5916000 | 5715000 | 5715000 | FLLOCA | IDA | 0 | 5715000 | 0 | 100% | 0 | 0 |  | On going and not in use | 0.45 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
34 | Proposed Rehabilitation Of Rivers Khalaba B, Chwele, Wabukhonyi And Chwele Dams In Chwele/Kabuchai Ward In Kabuchai Sub County | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5916000 | 5552000 | 5552000 | FLLOCA | IDA | 0 | 5552000 | 0 | 100% | 0 | 0 |  | On going and not in use | 0.3 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
86 | Drilling and Upgrading of Mteremko Borehole in Khalaba Ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba | 0.561194/34.563638 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 | 26/3/24 |  | 45782 | 3000000 | 2951736 | 2951736 | CGB | N/A | 2951736 | 0 | 2951736 | 100% | 0 | 2951736 | 0 | Work in progress | 20% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | PMC yet to be constituted,water being used by car wash
256 | PROTECTION OF 2NO WATER SPRINGS IN KHALABA WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 2 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba | berita 0.525841/34.563 bamboo 0.528305/34.562388 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 | 20/7/2020 |  | 30/9/2020 | 400000 | 319092.8 | 319092.8 |  | N/A | 319092.8 | 0 | 319092.8 | 100% | 319092.8 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | bamboo water spring was personalized
328 | CONSTRUCTION OF KHALABA NZOWASCO PIPELINE WATER PROJECT IN KHALABA WARD | Trenching and laying of water pipeline | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 | 43227 |  | 43232 | 2500000 | 2358300 | 2358300 |  | N/A | 2358300 | 0 | 2358300 | 100% | 2358300 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | pipeline was laid
419 | Extension of Nzowasco Pipeline and Construction of 3 kiosk with 5m3 Plastic tanks | water pipeline laying; construction of water kiosk and construction of plastic tank | To enhance access to clean and safe drinking water | KM of water pipeline constructed and water kiosks construction | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3300000 | 3051900 | 3051900 |  | N/A | 3051900 | 0 | 3051900 | 100% | 3051900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
445 | Extension of Nzowasco pipeline to six Estate. | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2000000 | 1890741.8 | 1890741.8 |  | N/A | 1890741.8 | 0 | 1890741.8 | 100% | 1890741.8 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
452 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1603800 | 1603800 |  | N/A | 1603800 | 0 | 1603800 | 100% | 1603800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
508 | Extension of Nzowasco Pipeline and Construction of 3 kiosk with 5m3 Plastic tanks | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | pipeline constructed, water kiosks and water tank erected | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3200000 | 3051900 | 3051900 |  | N/A | 3051900 | 0 | 3051900 | 100% | 3051900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
577 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1800000 | 1603800 | 1603800 |  | N/A | 1603800 | 0 | 1603800 | 100% | 1603800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
578 | Extension of NZOWASCO pipeline | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Khalaba |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2700000 | 2504420 | 2504420 |  | N/A | 2504420 | 0 | 2504420 | 100% | 2504420 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Supply of marking ink used in inspection of Meat | Supply of marking ink used in inspection of Meat for Bungoma, Webuye East & West, Kimilili and Sirisia Slaughtershouses | To promote meat safety and suitability for human consumption | Marking ink supplied for meat inspection | 2211007 | Agricultural materials, supplies and small equipment | Kanduyi | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 3000000 | 1750000 | 2000000 | County Government of Bungoma |  | 1750000 |  | 1750000 | 100% | 1750000 | 0 | 0 | Completed
| Purchase of soil testing equipment | Purchase of soil testing equipment | To assess soil fertility, nutrient status and identify any deficiencies or imbalances that may affect plant growth | Soil testing equipment purchased | 2640503 | Other Capital grants and transfer (NARGIP) | Kanduyi | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | [5 empty] | 3952000 | 4000000 | Development partner | IDA | 0 | 3952000 | 3952000 |  | 3952000 | 0 | 0 | Completed
| fnamuyemba | Renovation of Bungoma and Webuye Slaughter Houses | To promote meat safety and suitability for human consumption | 2 Slaughterhouses renovated | 3110504 | Other infrastructure and civil works | Kanduyi | Khalaba | 0.561194/34.563638 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45119 | 45478 | 45477 | 5000000 | 4998582 | 5000000 | County Government of Bungoma |  | 4998582 | 0 | 4998582 | 100% | 4998582 | 0 | 0 | Completed
7 | Proposed repair of grid powered streetlights in Khalaba | Repair street lights | Promote security | Grid powered streetlights repaired | BGM/CNTY/TEI/12/OT/2024-2025 1667851-2024/2025 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 3500000 |  |  | CGB | [8 empty] | Works to commence
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
79 | Installation of 30 grid powered streetlights in kanduyi, Tongaren and Mt. Elgon sub counties | of streetlights Tongaren kanduyi and Mt | [5 empty] | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | M/S Eagle Power services Limited | 2021/22 |  | Complete and in use |  | 2278500 |  |  | CGB
93 | Installation of 3 nO grid powered high mast flood lights | of powered mast powered high | [5 empty] | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | MS Zeigham Enterprises limited | 2021/22 |  | Complete and in use |  | 6553500 |  |  | CGB | [8 empty] | Completed | [15 empty] | Juma Bakari high mast is short
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | Khalaba |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Khalaba |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Khalaba |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
19 | Erection and completion works for maternity wing at Butieli dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings erected and completed |  |  | Kanduyi | Tuuti/ Marakaru |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 23-2-2024 |  |  | 3000000 | 2805668.8 | 2805668.8 | CGB |  | 2805668.8 | 0 | 0 | 0% | 0 | 193059 | 2805668.8 | stalled | 25 | [5 empty] | No | complete | Financial | Yes |  |  |  | No |  | slow workmanship
88 | Completion Of Maternity Wing And 2no. Door Pit Latrines Mayanja Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings and 2N0. door pit latrines completed |  |  | Kanduyi | Tuuti/ Marakaru |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 3000000 | 2804500 | 2804500 | CGB |  | 2804500 | 0 | 2507370 | 89.41% | 2507370 |  | 297130 | incomplete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
145 | Completion Of Maternity Wing At Mayanja Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Kanduyi | Tuuti/ Marakaru |  |  | WBPSPCU | Health & Sanitation | 2020-2021 | 26/8/2021 |  | 2024 | 2500000 | 2804500 | 2804500 | CGB |  | 2804500 | 0 | 0 | 0% | 0 |  | 2804500 | Ongoing | 0.85 | [5 empty] | No | complete | Financial | Yes | [5 empty] | 85% done
146 | Construction Of Toilets And Fencing Nabukhisa Dispensary | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors and Fencing | To develop and maintain infrastructure for enhanced access to quality health care services. | toilets constructed and dispensaries fenced |  |  | Kanduyi | Tuuti/ Marakaru |  |  | WBPSPCU | Health & Sanitation | 2020-2021 | 2021 |  | 2021 | 500000 | 483000 | 483000 | CGB |  | 483000 | 0 | 483000 | 100% | 483000 |  | 0 | Completed toilets fencing not started | [6 empty] | No | complete | Financial | Yes | [5 empty] | require fencing
253 | Construction Of Nabukhisa Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Kanduyi | Tuuti/ Marakaru |  |  | CEF | Health & Sanitation | 2017-2018 | 2018 |  | 2018 | 2419344 | 2571511 | 2571511 | CGB |  | 2571511 | 0 | 2571511 | 100% | 2571511 |  | 0 | Completed | [6 empty] | No | complete | Financial | Yes | [5 empty] | in use & need more rooms for lab and maternity
302 | Renovation and Completion of Mayanja Dispensary | Walling,roofing,painting,fixing of doors and windows | To provide accessible and health services within the community | Dispensaries renovated/completed |  |  | Kanduyi | Tuuti/ Marakaru |  |  | Ward Fund | Health & Sanitation | 2014/15 | 41821 | 42185 | 30/6/2015 |  | 2216772 | 2216772 | CGB |  | 2216772 | 0 | 2216772 | 100% | 2216772 |  | 0 | Completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | done
303 | Erection And Completion Of A Maternity Wing And Construction Of 4-Door Pit Latrine. | Walling,roofing,painting,fixing of doors and windows Digging of 20ft deep pit,flooring,walling,painting,roofing anf fitting doors | To provide accessible,affordable maternity services within the community | Maternity wings and 4No.door pit latrine erected and completed |  |  | Kanduyi | Tuuti/ Marakaru |  |  | CEF | Health & Sanitation | 2016/17 | 42856 | 42887 | 43313 |  | 3939621 | 3939621 | CGB |  | 3939621 | 0 | 2814809 | 71.45% | 2814809 |  | 1124812 | completed 4 door pit latrine & maternity wing 85% complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | needs completition and equiping for usage
304 | Completion of Butieli Health Centre | Walling,roofing,painting,fixing doors and windows | To provide accessible,affordable maternity services within the community | health centres completed |  |  | Kanduyi | Tuuti/ Marakaru |  |  | CEF | Health & Sanitation | 2016/17 | 2016 | 42887 | 2017 |  | 3997708 | 3997708 | CGB |  | 3997708 | 0 | 3767390 | 94.24% | 3767390 |  | 230318 | Completed | [6 empty] | No | complete | Financial | Yes | [5 empty] | The project is in use
442 | Periodic Maintenance of Roads In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 2022 | 43606 | 2022 | 5586328 | 5586328 | 5586328 | County Government of Bungoma |  | 5586328 |  | 5586328 | 99.87% | 5586328 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need for installation of culverts and gabros for central walkflow
443 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 2019 | 43608 | 2019 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use $ needs frequent maintenance
539 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
664 | Periodic Maintenance of Kibabii University - Matong'I Primary - River Mayanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 2020 | 43965 | 2020 | 5178631 | 5178631 | 5178631 | County Government of Bungoma |  | 5178631 |  | 5178631 |  | 5178631 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs culverts improve the drainage
665 | Grading of Makutano Primary-Tuuti Market Road | Grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 2019 | 43963 | 2020 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | require installation of culverts
666 | Upgrading of Salmond - Wetangula - Chemwa - Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 2023 | 43967 | 2024 | 7015749.6 | 7015749.6 | 7015749.6 | County Government of Bungoma |  | 7015749.6 |  | 7015749.6 |  | 7015749.6 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs completition.
667 | Upgrading of Salmond - Wetangula - Chemwa - Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43968 |  | 7015749.6 | 7015749.6 | 7015749.6 | County Government of Bungoma |  | 7015749.6 |  | 7015749.6 |  | 7015749.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
668 | Construction of Tuuti Marakaru - West Nalondo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43970 | 44001 | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
669 | Upgrading of Spot Improvement Of Salmond Wetangula Chemwa Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 2023 | 43962 | 2024 | 7015749.6 | 7015749.6 | 7015749.6 | County Government of Bungoma |  | 7015749.6 |  | 7015749.6 | 93.08% | 7015749.6 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs completition.
670 | Periodic Maintenance of Roads In Tuuti-Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43966 |  | 5178631 | 5178631 | 5178631 | County Government of Bungoma |  | 5178631 |  | 5178631 | 93.96% | 5178631 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
983 | Periodic Maintenance of Talent Academy - Mayanja Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 2021 | 44336 | 2021 | 9686964.75 | 9686964.75 | 9686964.75 | County Government of Bungoma |  | 9686964.75 |  | 9686964.75 |  | 9686964.75 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs gravelling,poor drainage,no culverts
984 | Periodic Maintenance of Gardinal Otunga Girls - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 2021 | 44331 | 2021 | 13859622 | 13859622 | 13859622 | County Government of Bungoma |  | 13859622 |  | 13859622 |  | 13859622 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs murraming and gravelling
985 | Periodic Maintenance of Bukusu Junction - Bukusu Primary - Kibabii River - River Mayanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 2020 | 44335 | 2021 | 13859622 | 13859622 | 13859622 | County Government of Bungoma |  | 13859622 |  | 13859622 |  | 13859622 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs culverts and periodic maintainance
986 | Periodic Maintenance of Namikelo Junction - Simon Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 2021 | 44338 | 2021 | 13859622 | 13859622 | 13859622 | County Government of Bungoma |  | 13859622 |  | 13859622 |  | 13859622 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need gravelling and routine maintenance
987 | Periodic Maintenance of Makutano - Tuuti Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 2021 | 44339 | 2021 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs gravelling and culverts
988 | Periodic Maintenance of Roads In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44340 |  | 13859622 | 13859622 | 13859622 | County Government of Bungoma |  | 13859622 |  | 13859622 | 98.41% | 13859622 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
989 | Periodic Maintenance of Talent Academy - Mayanja Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44327 |  | 9686964.75 | 9686964.75 | 9686964.75 | County Government of Bungoma |  | 9686964.75 |  | 9686964.75 | 95.06% | 9686964.75 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1319 | Periodic Maintenance of Kumbuka Junction - Kikwechi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 2022 | 44693 | 2022 | 17456985 | 17456985 | 17456985 | County Government of Bungoma |  | 17456985 |  | 17456985 |  | 17456985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need periodic maintence and installation of culverts.
1320 | Periodic Maintenance of Bukananachi Primary - Lumasa - Kibabii Booster | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 2022 | 44695 | 2022 | 17456985 | 17456985 | 17456985 | County Government of Bungoma |  | 17456985 |  | 17456985 |  | 17456985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need gravelling and murraming
1321 | Periodic Maintenance of Henry Posho Mill - Marofu Junction | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44700 |  | 17456985 | 17456985 | 17456985 | County Government of Bungoma |  | 17456985 |  | 17456985 |  | 17456985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1322 | Periodic Maintenance of Lumasa - Matong'I Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44697 |  | 17456985 | 17456985 | 17456985 | County Government of Bungoma |  | 17456985 |  | 17456985 |  | 17456985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1323 | Periodic Maintenance of Mayanja - Ekholo Junction - Henry Posho Mill - Peter Musemwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 2022 | 44694 | 2022 | 17456985 | 17456985 | 17456985 | County Government of Bungoma |  | 17456985 |  | 17456985 |  | 17456985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs culverts and gravelling
1324 | Periodic Maintenance of Makutano - Wanangali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 2021 | 44699 | 2022 | 5165448.1 | 5165448.1 | 5165448.1 | County Government of Bungoma |  | 5165448.1 |  | 5165448.1 |  | 5165448.1 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor workmanship,no murram,impasable during rainy season
1325 | Periodic Maintenance of Roads In Tuuti - Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 2022 | 44692 | 2020 | 17456985 | 17456985 | 17456985 | County Government of Bungoma |  | 17456985 |  | 17456985 | 100.0% | 17456985 | 0 | 0 | Completed grace community to kikwechi-bisunu junction$kayala to kakichuma | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | culverts required to regulate water movement
1326 | Routine Maintenance Of Makutano - Wanangali - Tuuti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 2022 | 44705 | 2022 | 5165448.1 | 5165448.1 | 5165448.1 | County Government of Bungoma |  | 5165448.1 |  | 5165448.1 | 100.0% | 5165448.1 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs gravelling and culverts installation
1568 | Periodic Maintenance of Bukananachi - Lumasa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 2023 | 45067 | 2023 | 4092596 | 4092596 | 4092596 | County Government of Bungoma |  | 4092596 |  | 4092596 |  | 4092596 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs gravelling
1569 | Periodic Maintenance of Diploma - Maliki Primary - Khalaba River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 2023 | 45068 | 2023 | 4076820 | 4076820 | 4076820 | County Government of Bungoma |  | 4076820 |  | 4076820 |  | 4076820 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs gravelling,grading ,culverts installation and murraming
1570 | Periodic Maintenance of Fana B - Sitoma Primary Main Junction - Kakichuma Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 2023 | 45059 | 2023 | 4120523 | 4120523 | 4120523 | County Government of Bungoma |  | 4120523 |  | 4120523 |  | 4120523 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Needs some repairs as per now
1571 | Periodic Maintenance of Cardinal Otunga Girls - Good Shepherd - Namikelo Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 2023 | 45057 | 2023 | 4980382.74 | 4980382.74 | 4980382.74 | County Government of Bungoma |  | 4980382.74 |  | 4980382.74 |  | 4980382.74 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor state ,need murraming and periodic maintenance
1572 | Periodic Maintenance of Diploma (Dttc) - Maliki Primary - Khalaba River Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 2022 | 45064 | 2023 | 4076820 | 4076820 | 4076820 | County Government of Bungoma |  | 4076820 |  | 4076820 | 100.0% | 4076820 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need for periodic maintenance
1573 | Periodic Maintenance of Fana B - Sitoma Primary - Main Junction - Kakichuma Road In Tuuti/ Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 2023 | 45056 | 2023 | 4120523 | 4120523 | 4120523 | County Government of Bungoma |  | 4120523 |  | 4120523 | 99.82% | 4120523 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1574 | Periodic Maintenance of Bukananachi - Lumasa In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 2023 | 45068 | 2023 | 4092596 | 4092596 | 4092596 | County Government of Bungoma |  | 4092596 |  | 4092596 | 98.17% | 4092596 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1575 | Framework Contracts For Maintenance Of Roads In Kanduyi And Bumula Sub Counties | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45070 |  | 4980382.74 | 4980382.74 | 4980382.74 | County Government of Bungoma |  | 4980382.74 |  | 4980382.74 | 326.25% | 4980382.74 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1812 | Periodic Maintenance of Mwalimu Wetungu - Kumbuka Junction - Nakayonjo Deb Primary - Mungeti River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45422 | 2024 | 3927562.8 | 3927562.8 | 3927562.8 | County Government of Bungoma |  | 3927562.8 |  | 3927562.8 |  | 3927562.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1813 | Periodic Maintenance of Makutano Junction - Chemiati - A104 Malaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45435 | 2024 | 1220436 | 1220436 | 1220436 | County Government of Bungoma |  | 1220436 |  | 1220436 |  | 1220436 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts ,gravellin and its not properly done
1814 | Periodic Maintenance of Hillview - Khalaba - Maliki Primary - Christ Community - Zuri Poa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45432 | 2024 | 3960936 | 3960936 | 3960936 | County Government of Bungoma |  | 3960936 |  | 3960936 |  | 3960936 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | insufficient culverts
1815 | Periodic Maintenance of Kimukung¦I - Onyango - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45434 | 2024 | 2457924 | 2457924 | 2457924 | County Government of Bungoma |  | 2457924 |  | 2457924 |  | 2457924 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project was not completed
1816 | Periodic Maintenance of Tuuti - Namaloko - Kamukunda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2023 | 45427 | 2024 | 4314471 | 4314471 | 4314471 | County Government of Bungoma |  | 4314471 |  | 4314471 |  | 4314471 | 0 | 0 | Complete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | no culverts and no murraming
1817 | Construction of Meli - Mafura Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45428 |  | 7455987 | 7455987 | 7455987 | County Government of Bungoma |  | 7455987 |  | 7455987 |  | 7455987 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1818 | Periodic Maintenance of Hillview - Khalaba - Maliki Primary - Christ Community - Zuri Poa Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45432 | 2024 | 3960936 | 3960936 | 3960936 | County Government of Bungoma |  | 3960936 |  | 3960936 | 99.17% | 3960936 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1819 | Periodic Maintenance of Kimukung'I - Onyango - River Khalaba Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45423 | 2024 | 2457924 | 2457924 | 2457924 | County Government of Bungoma |  | 2457924 |  | 2457924 | 99.96% | 2457924 | 0 | 0 | not completed but in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1820 | Periodic Maintenance of Makutano Junction - Chemiati - A104 Malaba Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45435 | 2024 | 1220436 | 1220436 | 1220436 | County Government of Bungoma |  | 1220436 |  | 1220436 | 99.8% | 1220436 | 0 | 0 | not completed but in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor murraming
1821 | Periodic Maintenance of Tuuti - Namaloko - Kamukunda Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2023 | 45427 | 2024 | 4314471 | 4314471 | 4314471 | County Government of Bungoma |  | 4314471 |  | 4314471 | 101.08% | 4314471 | 0 | 0 | completed | [6 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor murraming
1822 | Proposed Meli - Mafura Box Culvert In Tuuti/Marakaru Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45424 | 2024 | 7455987 | 7455987 | 7455987 | County Government of Bungoma |  | 7455987 |  | 7455987 | 95.44% | 7455987 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1823 | Periodic Maintenance of Mwalimu Wetungu-Kumbuka Junction-Nakayonjo Deb-R.Mungeti Road In Tuuti Marakaru Ward (1465530-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2024 | 45432 | 2024 | 3927562.8 | 3927562.8 | 3927562.8 | County Government of Bungoma |  | 3927562.8 |  | 3927562.8 | 99.95% | 3927562.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1824 | Periodic Maintenance of Pius Osyanju Kibabii University-Kolikho Market-Gospel Church Road In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2023 | 45430 | 2024 | 4953362 | 4953362 | 4953362 | County Government of Bungoma |  | 4953362 |  | 4953362 | 99.99% | 4953362 | 0 | 0 | incomplete | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | did not complete murraming
1825 | Periodic Maintenance of Pius Osyanju Kibabii University-Kolikho Market-Gospel Church Road In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Tuuti/ Marakaru |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2023 | 45430 | 2024 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.99% | 0 | 0 | 0 | not completed but in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | poor murraming
95 | Construction of 1 No.ECDE Classroom Maocho | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Tuuti/ Marakaru |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2019/2020 | 2020 | 30/6/2022 | 2021 | 1500000 | 1495350 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1275171.75 | 85.28% | 1275171.75 | 220178.25 | 220178.25 | completed and not in use | 0.8 | [14 empty] | dillapillated floors need renovation
162 | Proposed Erection And Completion Of 1 No. Ecde At Kikwechi, Makutano And Nabukhisa Primary Schools In Tuuti Marakaru Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Tuuti/ Marakaru |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2019/2020 | 2020 | 44049 | 2021 | 3900000 | 3803200 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 3803200 | 100% | 3803200 | 0 | 0 | Completed | 1 | [14 empty] | need for more class due to surging learners population and floor renovations
181 | Construction Of 1no. Ecde Classroom At Namikelo, Kakichuma, Kimukungi, Bukananachi And Maliki Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Tuuti/ Marakaru |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2019/2020 | 2020 | 43775 | 2021 | 6000000 | 5970325 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 5970325 | 100% | 5970325 | 0 |  | Completed | 1 | [14 empty] | in use and needs some renovation on floors
217 | Construction Of 1 Ecde Classroom At Lumasa, Buema,Bukusu, Munget, Sitama And Nakayonjo | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Tuuti/ Marakaru |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2018/2019 | 2020 | 43410 | 2021 | 7924270 | 7487800 | 7924270 | County Government of Bungoma | N/A | 7924270 |  | 7487800 | 100% | 7487800 | 0 |  | Completed | 100.0% | [14 empty] | in use
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | [7 empty] | FLLOCA | N/A |  | 0 |  | 100% |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
75 | Extension of KOICA Pipeline in Tuuti Marakaru Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 | 2024 |  |  | 5000000 | 4994728 | 4994728 | CGB | N/A | 4994728 | 0 | 4994728 | 100% | 4994728 | 0 | 0 | Ongoing | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | incomplete not in all areas,lumasa village and primary school not accessed to clean water
114 | Drilling of Kabubero Catholic borehole,Rehabilitation of boreholes and well pumps and spring protection in tuuti/marakaru ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole drilled; 1 borehole rehabilitated and 1 water spring constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 | 2023 |  | 2024 | 4000000 | 3852742.8 | 3852742.8 |  | N/A | 3852742.8 | 0 | 3852742.8 | 100% | 3852742.8 | 0 | 0 | complete sibale 1$2 water spring,incomplete sosun waterspring | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | sibale water complete,no water discharged
251 | DRILLING OF 3NO BOREHOLES IN TUUTI/MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 | 2020 |  | 2020 | 5000000 | 4892880 | 4892880 |  | N/A | 4892880 | 0 | 4892880 | 100% | 4892880 | 0 | 0 | incomplete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | kikwechi vct borehole broken down requires repairs and deepening to increase water volume,no water kibabii vct,namikelo borehole function
327 | KIBABII-SASURI WATER PROJECT PHASE 11 | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 34000000 | 32430400 | 32430400 |  | N/A | 32430400 | 1 | 32430400 |  | 26917232 | 5513168 | 0 | incomplete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | need for flooring
336 | DRILLING OF KAKICHUMBA AND MAYANJA BOREHOLES IN TUUTI MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 | 2017 |  | 2018 | 4000000 | 3907483.2 | 3907483.2 |  | N/A | 3907483.2 | 0 | 3907483.2 | 100% | 3907483.2 | 0 | 0 | incomplete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | stalled in kakichuma
337 | DRILLING OF BUTIELI DISPENDARY AND LUMASA BOREHOLE IN TUUTI MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 | 22/1/2019 |  | 43559 | 3300000 | 3222080 | 3222080 |  | N/A | 3222080 | 0 | 3222080 | 100% | 3222080 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | need to be upgraded to solar powered
420 | Protection of 10 water Springs, 2 Shallow wells, and rehabilitate borehole ( Hand pump) and 1 water supply | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump; improvement of a standard apron with drainage tunnel and replacement of Afridev hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed, 1 borehole rehabilitated and2 wells constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 | 2015 |  | 2016 | 1500000 | 1344481 | 1344481 |  | N/A | 1344481 | 0 | 1344481 | 100% | 1344481 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | poor workmanship
580 | Protection of 10 water Springs, 2 Shallow wells, and rehabilitate borehole ( Hand pump) and 1 water supply | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection;Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump;Improvement of a standard apron with drainage tunnel and replacement of Afrdev pump | To enhance access to clean and safe drinking water | 10 water springs constructed, 2 shallow wells constructed and 1 of borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Tuuti/ Marakaru |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3361203 | 3361203 |  | N/A | 3361203 | 0 | 3361203 | 100% | 3361203 | 0 | 0 | incomplete | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes |  | not there
| Construction Coffee drying tables at Kimukung’i | Construction Coffee drying tables at Kimukung’i | To enhance intame generation among dairy farmers | Coffee drying tables constructed at Kimukung'i | 3110504 | Other infrastructure and civil works | Kanduyi | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 2019 | 43739 | 2019 | 3000000 | 1500000 | 1500000 | County Government of Bungoma |  | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Completed | [15 empty] | not enough
| Construction of Kimukung’i Coffee Warehouse | Construction of Kimukung’i Coffee Warehouse | To promote coffee production and income generation | 1 warehouse constructed | 3110504 | Other infrastructure and civil works | Kanduyi | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 27/4/2020 | 27/4/2021 |  | 10000000 | 8623004 | 8000000 | County Government of Bungoma |  | 8623004 | 0 | 2600000 | 30% | 2600000 | 6023004 | 6023004 | incomplete | 0.6 | [14 empty] | need for flooring
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | Tuuti/ Marakaru |  |  |  | Wilkaner Power Solutions Limited | 2020/21 | 2021 | Complete | 2021 | 3634608.65 |  |  | CGG | [8 empty] | Completed bukananachi | [15 empty] | need more along kibabii to bukananachi mkts,lumasa namikelo junctionand kibabii booster
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 2014 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed | [15 empty] | done
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 2014 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed | [15 empty] | worn out needs repairs for both VCT and Joy farmers
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 2015 | 27/1/2015 | 2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed | [15 empty] | done
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed | [15 empty] | lack of follow-up on beneficiaries henceunsustainable
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed | [15 empty] | done
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | [16 empty] | not there
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | [16 empty] | not there
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 2016 |  | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed | [15 empty] | insufficient
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 2016 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed | [15 empty] | insufficient
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed | [15 empty] | done
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed | [15 empty] | increase allocation
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 2017 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed | [15 empty] | done
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed | [15 empty] | done
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed | [15 empty] | increase allocation
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed | [15 empty] | done
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 2019 | 43740 | 2019 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed | [15 empty] | increase allocation
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 2019 | 43740 | 2019 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed | [15 empty] | done
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 2020 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed | [15 empty] | done
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 2020 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed | [15 empty] | done
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed | [15 empty] | done
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed | [15 empty] | done
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 2022 | 44898 | 2022 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed | [15 empty] | done
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 2022 | 44898 | 2022 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed | [15 empty] | done
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 2023 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed | [15 empty] | increase allocation
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 2023 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed | [15 empty] | done
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 2024 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed | [15 empty] | increase allocation
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Tuuti/ Marakaru |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 2024 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed | [15 empty] | increase allocation
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Tuuti/ Marakaru |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| construction of ECDE classroom at kakichuma | [5 empty] | Kanduyi | Tuuti/ Marakaru |  |  | Early Childhood Development Education |  | 2019/2020 | 2020 | 2020 | [13 empty] | completed | [15 empty] | needs renovations at the floor | R
84 | Proposed Extension Works For Siritanyi Dispensary |  |  | Extension works completed |  |  | Kanduyi | Musikoma | 0.4474/34.53 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 1000000 | 964120 | 964120 | CGB |  | 964120 | 0 | 964120 | 100% | 964120 |  | 0 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | maternity wing urgently need completition
175 | Construction Of Pit Latrines At Samoya Dispensary And Fencing | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Pit latrines and fence constructed |  |  | Kanduyi | Musikoma | La:0.54477 Lo34.546236 |  | WBPSPCU | Health & Sanitation | 2019-2020 | 43466 |  | 44177 | 1596440 | 1498731 | 1498731 | CGB |  | 1498731 | 0 | 901031 | 60.12% | 901031 |  | 597700 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | complete
243 | Completion Of Siritanyi Dispensary And Samoya Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Dispensaries completed |  |  | Kanduyi | Musikoma | La:0.5548982 Lo 34.5360498 |  | CEF | Health & Sanitation | 2017-2018 | 42742 |  | 30/12/18 | 4500000 | 3980528.4 | 3980528.4 | CGB |  | 3980528.4 | 0 | 2818128.29 | 70.8% | 2818128.29 |  | 1162400.11 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | complete
301 | Erection and Completion of Pit Latrine and Chain link Fence for Musikoma Dispensary | Digging of 20ft deep pit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the dispensary | pit latrines erected and completed |  |  | Kanduyi | Musikoma | 0.535463/34.545568 |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42185 |  |  | 2594000 | 2594000 | CGB |  | 2594000 | 0 | 2594000 | 100% | 2594000 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
311 | Erection and Completion of Pit Latrine and Chain link Fence for siritanyi Dispensary | Digging of 20ft deep fit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the dispensary | pit latrines and chain link fence erected and completed |  |  | Kanduyi | Musikoma | 0.447/28.52 |  |  |  | 2014/2015 |  |  |  |  | 2485334.8 | 2485334.8 | CGB |  | 2485334.8 | 0 |  | 0% |  |  | 2485334.8 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | need repair
79 | Upgrading of Siritanyi -Namisi-Buema | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.5927/34.5201,0.5798/34.5182 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41654 | 41781 |  | 4937722 | 4937722 | 4937722 | County Government of Bungoma |  | 4937722 |  | 4937722 | 100.0% | 4937722 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs murraming
224 | Construction of Box Culvert On Sio River - Muanda Junction | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.56012/34.53783 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43244 |  | 2502502.8 | 2502502.8 | 2502502.8 | County Government of Bungoma |  | 2502502.8 |  | 2502502.8 |  | 2502502.8 | 0 | 0 | never started | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | unpassable and dangerous to cross
225 | Periodic Maintenance of Oldrex - Sio Primary - Dismas Junction | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.56094/34.55641 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018,Oct 2019 | 22/5/2023 |  | may 2020 | 2502502.8 | 2502502.8 | 2502502.8 | County Government of Bungoma |  | 2502502.8 |  | 2502502.8 |  | 2502502.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | the work was poorly done
226 | Periodic Maintenance of In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43233 |  | 2502502.8 | 2502502.8 | 2502502.8 | County Government of Bungoma |  | 2502502.8 |  | 2502502.8 | 25.59% | 2502502.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
410 | Periodic Maintenance of Roads In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.5360781/34.5010771 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43484 | 43601 |  | 8738048 | 8738048 | 8738048 | County Government of Bungoma |  | 8738048 |  | 8738048 | 99.99% | 8738048 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Done
411 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
412 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
608 | Periodic Maintenance of Rock Gardens - Didmus Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43975 |  | 8429383 | 8429383 | 8429383 | County Government of Bungoma |  | 8429383 |  | 8429383 |  | 8429383 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
609 | Periodic Maintenance of Wanjala Ng'Ombe - Teresa - Swahili Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.55915/34.55423 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | may 2020 | 43963 | june 2020 | 8429383 | 8429383 | 8429383 | County Government of Bungoma |  | 8429383 |  | 8429383 |  | 8429383 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | shaddy work
610 | Periodic Maintenance of Roads In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43967 |  | 8429383 | 8429383 | 8429383 | County Government of Bungoma |  | 8429383 |  | 8429383 | 100.0% | 8429383 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
914 | Periodic Maintenance of Samoya Dispensary - Wekelekha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44326 |  | 8255763.5 | 8255763.5 | 8255763.5 | County Government of Bungoma |  | 8255763.5 |  | 8255763.5 |  | 8255763.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Already done in previous years
915 | Spot Imptovement Of Samoya Dispensary - Wekelekha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 44207 | 44340 |  | 8255763.5 | 8255763.5 | 8255763.5 | County Government of Bungoma |  | 8255763.5 |  | 8255763.5 | 96.78% | 8255763.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Done in previous years
924 | Upgrading of Roads In Musikoma Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44333 |  | 11516799 | 11516799 | 11516799 | County Government of Bungoma |  | 11516799 |  | 11516799 | 42.84% | 11516799 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1223 | Periodic Maintenance of Mlimani - Tulienge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44691 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1224 | Periodic Maintenance of Nambaya Dam - Tulienge Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.533044/34.5554346 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44696 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Done
1225 | Periodic Maintenance of Moca - Millenium - Sio Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.3455641/0.56094 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | may 2022 | 44705 | june 2022 | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | A section of a road has land dispute
1226 | Periodic Maintenance of Moca - Sio Secondary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.56094/34.55641 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | may 2022 | 44697 | june 2022 | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | quality of murram used was poor and never lasted.now almost impassable
1227 | Periodic Maintenance of Siritanyi Dispensary - Siritanyi Children Home Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.570514/34.534895,0.578964/34.518291 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44700 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs murraming
1228 | Periodic Maintenance of Sio - Muanda Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.55984/34.54163 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 17/2/2024 | 44702 | march2024 | 9953617.8 | 9953617.8 | 9953617.8 | County Government of Bungoma |  | 9953617.8 |  | 9953617.8 |  | 9953617.8 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | has no bridge,partialy usable,work poorly done
1229 | Periodic Maintenance of Sacret - Ack - Namisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.5867/34.53,0.578970/34.518285 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44694 |  | 9953617.8 | 9953617.8 | 9953617.8 | County Government of Bungoma |  | 9953617.8 |  | 9953617.8 |  | 9953617.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need murraming, the bridge was washed away
1230 | Periodic Maintenance of Roads In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44702 |  | 9953617.8 | 9953617.8 | 9953617.8 | County Government of Bungoma |  | 9953617.8 |  | 9953617.8 | 100.0% | 9953617.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1231 | Periodic Maintenance of Roads In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44704 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 | 99.99% | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1250 | Upgrading of Roads In Musikoma Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44698 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1507 | Periodic Maintenance of Bhulosi Market - Atemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45056 |  | 2150002 | 2150002 | 2150002 | County Government of Bungoma |  | 2150002 |  | 2150002 |  | 2150002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1508 | Periodic Maintenance of Bhulosi Market - Atemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45070 |  | 2150002 | 2150002 | 2150002 | County Government of Bungoma |  | 2150002 |  | 2150002 |  | 2150002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1509 | Periodic Maintenance of Mwiruti Sec - Lavine Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45062 |  | 7216476 | 7216476 | 7216476 | County Government of Bungoma |  | 7216476 |  | 7216476 |  | 7216476 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good condition
1510 | Periodic Maintenance of Wambiya - Bustani - Sio Primary - Muslim Primary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.55754/34.55346 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | june 2023 | 45062 | june 2023 | 7216476 | 7216476 | 7216476 | County Government of Bungoma |  | 7216476 |  | 7216476 |  | 7216476 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Road is pathetic and impassable during rainny period
1511 | Periodic Maintenance of Mwiruti Sec - Lavine Junction - Wambiya - Bustani - Sio Primary - Muslim Primary Schools In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.55984/34.54163 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | june 2023 | 45065 | june 2023 | 7216476 | 7216476 | 7216476 | County Government of Bungoma |  | 7216476 |  | 7216476 | 98.34% | 7216476 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | its only two years yet the road is impassable,no drainage
1512 | Periodic Maintenance of Bulosi Mkt - Atemba Road In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45056 |  | 2150002 | 2150002 | 2150002 | County Government of Bungoma |  | 2150002 |  | 2150002 | 99.14% | 2150002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | work done was substandard
1762 | Periodic Maintenance of C33 (Dicece) - Marrell - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.516326/34.555004 0.51/34.549 0.521/34.553 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45422 |  | 2931238 | 2931238 | 2931238 | County Government of Bungoma |  | 2931238 |  | 2931238 |  | 2931238 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1763 | Periodic Maintenance of C33 Diocese-Marel-River Khalaba Road In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45422 |  | 2931238 | 2931238 | 2931238 | County Government of Bungoma |  | 2931238 |  | 2931238 | 99.98% | 2931238 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | work done was substandard
179 | Purchase of land for Sacred ECDE centre. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | Zero point two five acres of Land for Sacred ECDE Purchased | 3110599 | Ward based projects | Kanduyi | Musikoma | 0.5930/34.520 | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42585 | 42588 | 42376 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 |  | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
194 | Purchase of land for Sacred ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Sacred E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | Musikoma | 0.5930/34.520 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 42125 | 42128 | 42251 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 100% | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
28 | Contruction of Pit latrine at Dicece | Construction of a pitlatrine. | To provide sanitation facilities | Pit latrine constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | 0.51654/34.54950 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3000000 | 2999670 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0% |  | 2999670 | 2999670 | Completed
90 | construction of 1 no. ECDE Cassroom at samoya, Musikoma, Walala, Muslim, and Siritanyi primary schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | La:0.5534213 Lo:34.5377808 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2020/2021 | 44409 | 30/6/2022 | 44866 | 7000000 | 6971878 | 7000000 | County Government of Bungoma | N/A | 7000000 | 0 | 6971878 | 100% | 6971878 | 0 | 0 | Complete | 1 | [14 empty] | No electricity, Poor workmanship
123 | Construction Of 1 No. Ecde Classroom And 2 No. Door Pit Latrine At St. Joseph Ack, Wekelekha And Namasanda Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2020/2021 | 44044 | 44414 | 44287 | 4200000 | 4044740 | 4200000 | County Government of Bungoma | N/A | 4200000 | 0 | 4044740 | 100% | 4044740 | 0 | 0 | Completed | 1 | [14 empty] | fencing needed
157 | Proposed Erection And Completion Of 1 No. Ecde At Namisi Primary School In Musikoma Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | 0.5798/43.51174 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2021 | 43864 | 44049 | 2022 | 1500000 | 1452580 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1452580 | 100% | 1452580 | 0 | 0 | complete and in use | 1 | [14 empty] | more classrooms needed
207 | Construction Of 3 Classrooms And Toilets At Namamuka Sio And Okanya Primary | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2020/2021 | 44044 | 43410 | 44287 | 4500000 | 4410715 | 4500000 | County Government of Bungoma | N/A | 4500000 |  | 4410715 | 100% | 4410715 | 0 |  | Completed | 100.0% | [14 empty] | Done
2 | DRILLING AND UPGRADING OF SAMOYA DISPENSARY BOREHOLE AND WATER PIPELINE DISTRIBUTION | BOREHOLE DRILLING, RAISED STORAGE TANK INSTALLATION, SOLAR PANELS AND PUMP INSTALLATION, PIPE LAYING AND CONSTRUCTION OF A METRED WATER KIOSK | TO PROVIDE CLEAN AND SAFE DRINKING WATER TO SAMOYA PRIMARY AND SECONDARY SCHOOL, SAMOYA DISPENSARY AND COMMUNITY | BOREHOLE, RAISED WATER STORAGE TANK, LAID WATER PIPES | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | La:0.5548982 Lo:34.5360498 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2024/25 | 45893 | 15/4/2024 | 45985 | Ksh. 7,000,000 | Ksh. 7,000,000 | Ksh. 7,000,000 | CGB |  | Ksh. 7,000,000 | 0 | Ksh. 7,000,000 | 100% | 0 | 6838616 | 6838616 | COMPLETED | [6 empty] | NO |  | NON-PAYMENT BY COUNTY TREASURY FOR COMPLETED PROJECTS | NO | BUDGETARY CONSTRAINS | NO |  | NO | USABILITY OF THE PROJECT TO CITIZENS
5 | ROUTINE MAINTENANCE OF OLDREX - SIO PRIMARY JUNCTION - MUANDA BRIDGE ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.56094/34.55641 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 15/4/2024 | 15/4/2024 | 4126584 | 4126584 | 4126584 | CGB |  | 4126584 | 0 | 4126584 | 100% | 4112664 | 0 | 0 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL CHALLENGE OF SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
15 | ROUTINE MAINTANANCE OF SILOBA PRI. JUNCTION - FORMER ASSISTANT CHIEF OFFICE - NGOLI RIVER ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.570134/34.534959,0.568665/34.534715,0.573007/34.536549 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2023/2024 | 45323 | 45302 | 45352 | 3121734 | 3121734 | 3121734 | CGB |  | 3121734 | 0 | 3121734 | 100% | 0 | 2617946 | 2617946 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | the road was poorly done
16 | ROUTINE MAINTENANCE OF SIRITANYI ASS. CHIEF OFFICE - KISAWAYI - NAMISI ECDE ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.578913/34.518405,0.578980/34.518295,0.578970/34.518285 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2023/2024 | 45302 | 45302 | 2024 | 2537964 | 2537964 | 2537964 | CGB |  | 2537964 | 0 | 2537964 | 100% | 0 | 2432636 | 2432636 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | poor quality murram,poor compression,bridge washed away
17 | ROUTINE MAINTANANCE OF ELMAS - MUKOLWE - NAMASANDA RIVER ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.533044/34.5554346 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 3016464 | 3016464 | 3016464 | CGB |  | 3016464 | 0 | 3016464 | 100% | 0 | 2996512 | 2996512 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | Done in previous years
12 | Upgrading of Siritanyi Dispensary and Namikelo Primary boreholes and pipeline extension in Musikoma/Tuuti Marakaru/Khalaba wards | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45544 | 45546 | 45546 | 10500000 | 10157172 | 10157172 | FLLOCA | N/A | 10157172 | 0 | 0 | 100% | 10157172 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not done in musikoma village
38 | Proposed Tree Growing Within Institutions In Khasoko, Kabula, Musikoma, Bukembe East, West Nalondo And Chesikaki Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Kanduyi | Musikoma | 0.533044/34.5554346 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7101000 | 6960000 | 6960000 | FLLOCA | IDA | 0 | 6960000 | 0 | 100% | 0 | 0 |  | Stalled | 0.2 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not done in musikoma village
97 | Drilling and Equipping of Walala and Siloba Primary Schools Boreholes in Musikoma ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and equipped | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | La:0.53918995 Lo:34.5385569 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 | 45200 |  | 2024 | 5000000 | 4473600 | 4473600 | CGB | N/A | 4473600 | 0 | 4473600 | 100% | 4473600 | 0 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | No water and Not functioning
108 | Upgrading of Namamuka Primary and Namisi primary boreholes in Musikoma ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.51546/34.54946 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 | 2022 |  | 2022 | 6000000 | 5912595.4 | 5912595.4 |  | N/A | 5912595.4 | 0 | 5912595.4 | 100% | 5912595.4 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | project failed,urgent intervension needed since water is a problem to the residents
202 | PROTECTION OF 4 NO. WATER SPRINGS IN MUSIKOMA WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.56216/34.54175 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 | aprill 2021 |  | aprill 2021 | 1000000 | 957600 | 957600 |  | N/A | 957600 | 0 | 957600 | 100% | 957600 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | commendable,has a court dispute risks of loosing the spring
258 | EXTENSION OF MUSIKOMA SECONDARY WATER PROJECT IN MUSIKOMA WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.533888/34.54984 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 | 15/3/2019 |  | 43898 | 2000000 | 1098763 | 1098763 |  | N/A | 1098763 | 0 | 1098763 | 100% | 1098763 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | water valves destroyed , the community can not access the water
333 | DRILLING OF BOREHOLES AND INSTALLATION OF PUMPING SYSTEM AT MUSIKOMA | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled and solarised | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4800000 | 4726639 | 4726639 |  | N/A | 4726639 | 0 | 4726639 | 100% | 4726639 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
334 | EXTENSION OF MUSIKOMA WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2499921 | 2499921 |  | N/A | 2499921 | 0 | 2499921 | 100% | 2499921 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
335 | CONSTRUCTION AND PROTECTION OF 5 NO.WATER SPRINGS IN MUSIKOMA WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.513437/34.53962 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 1000000 | 978500 | 978500 |  | N/A | 978500 | 0 | 978500 | 100% | 978500 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | The project is in use, and in good condition
341 | Construction of 5 Roof Catchment | Construction of 5 Roof Catchment | To enhance access to clean and safe drinking water | 5 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1599502 | 1599502 |  | N/A | 1599502 | 0 | 1599502 | 100% | 1599502 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
448 | Musikoma Pipeline Extension | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works |  | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3500000 | 3298561 | 3298561 |  | N/A | 3298561 | 0 | 3298561 | 100% | 3298561 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
509 | Musikoma Pipeline Extension | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3800000 | 3665068 | 3665068 |  | N/A | 3665068 | 0 | 3665068 | 100% | 3665068 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
579 | Protection of 9 water Springs, Construction of 1 shallow wells and Musikoma water project | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection;Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump;Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 9 water springs constructed, 1 shallow well constructed and KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.56094/34.55641 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 | 2014 |  | 2014 | 4000000 | 3938920 | 3938920 |  | N/A | 3938920 | 0 | 3938920 | 100% | 3938920 | 0 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | commendable though theft took place on projected fence
| Rehabilitation of Namasanda dam | Rehabilitation of Namasanda dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Kanduyi | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 15000000 | 9156000 | 9200000 | County Government of Bungoma |  | 9156000 |  | 9156000 | 100% | 9156000 | 0 | 0 | Complete
| Rehabilitation Of Namasanda Dam | Rehabilitation Of Namasanda Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Kanduyi | Musikoma | 0.533044/34.554346 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43009 | 43014 | 43074 | 15000000 | 9156000 | 9500000 | County Government of Bungoma |  | 9156000 |  | 9156000 | 100% | 9156000 | 0 | 0 | [15 empty] | No activity done
| Provision of improved breeds (meat goats) | Provision of 30 does and 3 Bucks to 3 elite breeders,2 in Bukembe East (BUKONONA SLCA) and 1 in Musikoma (MUSIKOMA SLCA) | To enhance production, productivity and income generation | 30 does and 3 Bucks purchased and issued to 3 elite breeders | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | feb 2023 | 18/7/2024 | aprill 2023 |  | 961980 | 1029280 | Development partner | IFAD | 0 | 961980 | 961980 |  | 961980 | 0 | 0 | Completed | [15 empty] | done
| Provision of improved breeds of chicken | Provision of improved breeds (Indigenous poultry) chicken – day old chicks | To enhance production, productivity and income generation | 14 MOFAG beneffitted by each getting 575 breeds | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Musikoma | La:0.5360781 Lo:34.3010771 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 44958 | 23/6/2024 | 45200 |  | 1387730 | 1447460 | Development partner | IFAD | 0 | 1387730 | 1387730 |  | 1387730 | 0 | 0 | Completed | [15 empty] | done
| Upscaling production of grass seeds | Upscaling production of grass seeds by distrbuting 100 bags of 50kgs of organic fertilizer | To enhance productivity and income generation | 100 bags of 50kg organic fertilizer procured and distributed to 8 farmers. | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Musikoma | La:0.5360781 Lo:34.5010771 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | feb 2023 | 45598 | aprill 2023 |  | 144940 | 145 940 | Development partner | IFAD | 0 | 620398 | 144940 |  | 144940 | 0 | 0 | Not seen | [15 empty] | no evidence
| Purchase and distribution of day old Chicks Rainbow Roosters | Purchase and delivery of 8,050 day old Chicks rainbow roosters to 14 MOFAG Indigenous chicken groups | To enhance poultry production and increase household incomes | 8,050 chicks purchased and delivered to 14 MOFAG indingeneous chicken groups | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Musikoma | La:0.533044 Lo:34.5554346 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45711 | 31/6/2024 | 45200 | [12 empty] | not seen | [15 empty] | not given in musikoma village
4 | Proposed Construction and Commissioning of 4No. Bodaboda Sheds in Samoya,sibembe,siritanyi,Minyali and musikoma | Construction of bodaboda sheds | promotion of MSMEs | Bodaboda sheds constructed | BGM/CNTY/TEI/15/OT/2024-2025 1667858-2024/2025 |  |  | Musikoma | La:0.5455296 Lo:34.5284335 | Trade, Energy and Industrialization | Dept of Trade | MUNGO COMP. LTD | 2024/2025 | aprill 2025 | Awarded in Dec 2024 | may2025 | 1250000 |  |  | CGB | [8 empty] | does not exist | [15 empty] | no bodaboda shed in siritanyi
76 | Installation of 41 grid powered streetlights in Kanduyi Sub-county . | of streetlights Kanduyi streetlights in |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | M/S Mbale Town Electro Works Umeme | 2021/22 |  | Complete and in use |  | 3116001 |  |  | CGB
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | Musikoma |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
129 | Installation of street lights at Sio -Oldrex | of Oldrex street lights | [5 empty] | Musikoma | 34.55641/0.56094 |  |  | KPLC | 2018/19 |  | Project not implemented. KPLC policy requires payment of funds before execution of works. KPLC delayed to submit their quotation to facilitate payment process. The delays were caught up by closure of FY, hence not implemented. |  | 1800000 | 0 |  | CGG | [8 empty] | Stalled | [15 empty] | no existence of such project on site\
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Musikoma |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 |  |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | [16 empty] | No information
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | [16 empty] | No information
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | [16 empty] | No information
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 41852 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed | [15 empty] | Done
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | july2015 | 42312 | aug2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Stalled | [15 empty] | No information
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | [16 empty] | No
| Purchase and delivery of dairy cows at siritanyi | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle at siritanyi | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | mach 2024 | 42585 | mach 2024 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | jan2016 | 42585 | march2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and Delivery of Dairy Cattle at siritanyi | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | may2016 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats at namasanda | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | may2016 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | aprill2017 | 15/3/2017 | may2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed | [15 empty] | community witness
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | aprill2017 | 15/3/2017 | may2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed | [15 empty] | community witness
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed | [15 empty] | community witness
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | aprill2017 | 17/3/2018 | may2017 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | feb 2018 | 17/2/2018 | aprill2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma | 34.54175/0.56216 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | aprill 2018 | 15/04/2018 | june2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Stalled | [15 empty] | No proof
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma | 34.54175/0.56216 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | between july and dec 2018 | 15/1/2018 | 15/04/2018 | dec2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed | [15 empty] | No proof
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | feb 2019 | 43740 | aprill2019 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed | [15 empty] | community witness
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | feb 2019 | 43740 | aprill2019 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | feb 2020 | 23/3/2020 | aprill2020 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | feb 2020 | 23/3/2020 | aprill2020 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | feb 2021 | 20/2/2021 | aprill2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | feb 2021 | 20/2/2021 | aprill2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | feb 2022 | 44898 | aprill2022 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | feb 2022 | 44898 | aprill2022 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | feb 2023 | 45263 | aprill2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | feb 2023 | 45263 | aprill2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed | [15 empty] | community witness
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | sept 2023 | 45387 | aprill2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed | [15 empty] | Done
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 | sept 2023 | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
9 | Erection and completion of Maternity wing at Tulienge dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completion |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 28-2-2024 |  |  | 2000000 | 1967390 | 1967390 | CGB |  | 1967390 | 0 | 0 | 0% | 0 | 1880920 | 1967390 | On-going | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
63 | proposed erection and completion of maternity wing at Lwakhakha dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Sirisia | Lwandanyi |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 45628 |  |  | 4000000 | 3939050 | 3939050 | CGB |  | 3939050 | 0 | 0 | 0% | 0 |  | 3939050 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
167 | Construction Of Septic Tank At Lwandanyi Dispensary | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | Septic tanks constructed |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1050000 | 1161650 | 1161650 | CGB |  | 1161650 | 0 | 1161650 | 100% | 1161650 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | good condition
168 | Construction Of Maternity Wing At Karosisndet Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1963330 | 1963330 | CGB |  | 1963330 | 0 | 878500 | 44.75% | 878500 |  | 1084830 | Complete and in use | [6 empty] | No | complete | Financial | Yes
169 | Renovation Of Health Facility And Staff Quarters At Lwakhakha Dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Staff quarters erected and renovated |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1034983 | 1292924 | 1292924 | CGB |  | 1292924 | 0 | 1163037 | 89.95% | 1163037 |  | 129887 | Complete and in use | [6 empty] | No | complete | Financial | Yes
232 | Construction Of Public Toilets At Wamono And Tulienge Market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Public toilets constructed |  |  | Sirisia | Lwandanyi | Lon:790443 La:34.433693 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 800000 | 876200 | 876200 | CGB |  | 876200 | 0 | 876200 | 100% | 876200 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | good condition
385 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
554 | Periodic Maintenance of Lurare - Bishop Wabukala Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43972 |  | 5111401 | 5111401 | 5111401 | County Government of Bungoma |  | 5111401 |  | 5111401 |  | 5111401 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
555 | Upgrading of Tamulega-Malakisi Bridge (River Malakisi) | Road improvement works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43970 | 44001 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
556 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43964 |  | 5111401 | 5111401 | 5111401 | County Government of Bungoma |  | 5111401 |  | 5111401 | 100.0% | 5111401 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
831 | Periodic Maintenance of Wamono - Khabukoya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44332 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 |  | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need murraming
832 | Periodic Maintenance of Tulienge - Nasala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44335 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 |  | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
833 | Periodic Maintenance of Namosi - Bishop Wabukala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
834 | Construction of Arch. Bishop Wabukala - Namwesi Twin Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
835 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44329 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 | 99.84% | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1146 | Periodic Maintenance of Bukayabi - Kaburweti - Namutokholo - Lwakhakha Border Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44705 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs culverts installatin between bukiabi and kabukweti
1147 | Periodic Maintenance of Katomei Junction - Changara Drift Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44699 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1148 | Periodic Maintenance of Kibindoi - Makwere - Kapkara - Lwandanyi Miracle Church Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44692 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need murraming
1149 | Periodic Maintenance of Nambuya - Tamulega Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44697 | 44728 | 2317424.8 | 2317424.8 | 2317424.8 | County Government of Bungoma |  | 2317424.8 |  | 2317424.8 |  | 2317424.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1150 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44702 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 | 99.62% | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1151 | Routine Maintenance Of Nambuya - Tamulega Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44700 |  | 2317424.8 | 2317424.8 | 2317424.8 | County Government of Bungoma |  | 2317424.8 |  | 2317424.8 | 100.0% | 2317424.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1448 | Periodic Maintenance of St. Paul Lwandanyi - Namundi Tarmac Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45056 |  | 3643608 | 3643608 | 3643608 | County Government of Bungoma |  | 3643608 |  | 3643608 |  | 3643608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good condition
1449 | Periodic Maintenance of Lwakhakha - Township Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45066 |  | 4487867 | 4487867 | 4487867 | County Government of Bungoma |  | 4487867 |  | 4487867 |  | 4487867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1450 | Periodic Maintenance of Mufungu - Namang'Ofulo - Tulienge - Namubila Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45058 |  | 6895712 | 6895712 | 6895712 | County Government of Bungoma |  | 6895712 |  | 6895712 |  | 6895712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1451 | Upgrading of Machakha- Tinga Moja | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45068 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1452 | Periodic Maintenance of Lwakhakha - Township Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45058 |  | 4487867 | 4487867 | 4487867 | County Government of Bungoma |  | 4487867 |  | 4487867 | 99.87% | 4487867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1453 | Periodic Maintenance of Mfungu - Namang'Ofulo - Tulienge - Namubila Primary Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45068 |  | 6895712 | 6895712 | 6895712 | County Government of Bungoma |  | 6895712 |  | 6895712 | 100.0% | 6895712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1454 | Periodic Maintenance of St. Pauls Lwandanyi - Namundi Tarmac Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45064 |  | 3643608 | 3643608 | 3643608 | County Government of Bungoma |  | 3643608 |  | 3643608 | 82.75% | 3643608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good condition
1685 | Periodic Maintenance of Katomei - Allakar - Korosiondet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45427 |  | 4168808 | 4168808 | 4168808 | County Government of Bungoma |  | 4168808 |  | 4168808 |  | 4168808 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1686 | Periodic Maintenance of Kisiero - Wakenda - Kakala Primary - Munialo - Wabomba - Tarmac Road - Oriama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45422 |  | 4092480 | 4092480 | 4092480 | County Government of Bungoma |  | 4092480 |  | 4092480 |  | 4092480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | maintenance to be done
1687 | Periodic Maintenance of Sitabicha - Bukokholo Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45436 |  | 4566282 | 4566282 | 4566282 | County Government of Bungoma |  | 4566282 |  | 4566282 |  | 4566282 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1688 | Periodic Maintenance of Malakisi Health Centre - Rwatama - Malakisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45427 | 45458 | 3112744 | 3112744 | 3112744 | County Government of Bungoma |  | 3112744 |  | 3112744 |  | 3112744 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1689 | Periodic Maintenance of Malakisi Health Center-Rwatama-Malakisi Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45436 |  | 3112744 | 3112744 | 3112744 | County Government of Bungoma |  | 3112744 |  | 3112744 | 99.96% | 3112744 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1690 | Periodic Maintenance of Katomei - Allakar - Korosiondet Sda Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45434 |  | 4168808 | 4168808 | 4168808 | County Government of Bungoma |  | 4168808 |  | 4168808 | 99.97% | 4168808 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1691 | Periodic Maintenance of Kisiero - Wekunda - Kakala - Tarmac - Oriama Road In Lwadanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2023 | 45430 | 2024 | 4092480 | 4092480 | 4092480 | County Government of Bungoma |  | 4092480 |  | 4092480 | 100.0% | 4092480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | maintenance to be done
1692 | Periodic Maintenance of Sitabicha - Bukokholo Junction Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45433 |  | 4566282 | 4566282 | 4566282 | County Government of Bungoma |  | 4566282 |  | 4566282 | 100.0% | 4566282 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
29 | Proposed completion of 1no.ECDE classroom at Marakaru, Londo and Namundi primary schools | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3500000 | 3346250 | 3500000 | County Government of Bungoma | N/A | 3500000 | 0 | 3346250 | 100% | 3346250 | 0 | 0 | Completed
51 | Proposed Erection And Completion Works Of 1no. Ecde Classroom And 2no. Door Pit Latrine At Lwakhakha And Wamono Primary Schools In Lwandanyi Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 4000000 | 3913160 | 4000000 | County Government of Bungoma | N/A | 4000000 | 0 | 2469174.55 | 63.1% | 2469174.55 | 1443985.45 | 1443985.45 | Completed | 1 | [14 empty] | The project is in use and in good condition
116 | Completion Of 1 No. Ecde Classroom At Mukhuyu Primary School | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 1000000 | 1292600 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 0 | 0% | 0 | 1292600 | 1292600 | ongoing. At ring beam. | 0.7
117 | Construction Of 1 No. Ecde Classroom At Marakaru, Londo And Namundi Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4300000 | 4244630 | 4300000 | County Government of Bungoma | N/A | 4300000 | 0 | 876038.95 | 20.64% | 876038.95 | 3368591.05 | 3368591.05 | complete and in use | 1
147 | Proposed Erection And Completion Of 1 No. Ecde At Kibindoi Primary School In Lwandanyi Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1500000 | 1497000 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1497000 | 100% | 1497000 | 0 | 0 | complete and in use | 1 | [14 empty] | The project is in use
174 | Construction Of 08 Ecde Classrooms At Kaburuet, Chebukunyi, Kaprot, Namubila, Namawanga, Tulienge, Kibindoi, And Kapendo Primary Schools | Construction of ECDE classroom and VTC workshop | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 8200000 | 8473660.8 | 8200000 | County Government of Bungoma | N/A | 8200000 | 0 | 8473660.8 | 100% | 8473660.8 | 0 |  | completed kibindoi E.C.D.E | 1 | [14 empty] | The project is in use
175 | Purchase Of 525 Desks For Eight Ecde Classes | Construction of toilets | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 1000000 | 1000000 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 1000000 | 100% | 1000000 | 0 |  | complete and in use | 1
64 | Drilling of Borehole at Kakala Primary School | site identification; geological survey;drilling development(entails casing and gravel use);construction of borehole chamber; construction of water points. | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2000000 | 1999376 | 1999376 | CGB | N/A | 1999376 | 0 | 1999376 | 100% | 1999376 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
174 | Upgrading of Lurare/Namwesi borehole | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4000000 | 3989124 | 3989124 |  | N/A | 3989124 | 0 | 3989124 | 100% | 3989124 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
198 | DRILLING AND EQUIPPING OF BOREHOLE IN TORORO PRIMARY SCHOOL | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1800000 | 1679680 | 1679680 |  | N/A | 1679680 | 0 | 1679680 | 100% | 1679680 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
218 | REHABILITATION AND EXTENSION OF CHESIKAKI-SIRISIA-BUMULA WATER PROJECT PHASE I | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 34000000 | 33391751.4 | 33391751.4 |  | N/A | 33391751.4 | 0 | 33391751.4 | 100% | 23831829 | 9559922 | 0 | Work in progress | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
221 | DRILLING OF 4NO. BOREHOLES IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 4 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 6000000 | 5877482 | 5877482 |  | N/A | 5877482 | 0 | 5877482 | 100% | 2938741 | 2938741 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in use water coated with petroleum
284 | DRILLING OF NASALA AND LURARE BOREHOLES IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3700000 | 3540800 | 3540800 |  | N/A | 3540800 | 0 | 3540800 | 100% | 3540800 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
285 | DRILLING OF MACHAKHA BOREHOLE IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1782000 | 1782000 |  | N/A | 1782000 | 0 | 1782000 | 100% | 1782000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
286 | REHABILITATION OF 3 NO. BOREHOLES AND CONSTRUCTION OF 10 NO. WATER SPRINGS IN LWANDANYI WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 Boreholes rehabilitated and 10 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2499921 | 2499921 |  | N/A | 2499921 | 0 | 2499921 | 100% | 2499921 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
385 | Lwandanyi borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 600000 | 556225 | 556225 |  | N/A | 556225 | 0 | 556225 | 100% | 556225 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
454 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2597616 | 2597616 |  | N/A | 2597616 | 0 | 2597616 | 100% | 2597616 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
545 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points; | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 10000000 | 9277200 | 9277200 |  | N/A | 9277200 | 0 | 9277200 | 100% | 9277200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
561 | Protection of 7 water springs and Construction of 3 Roof catchments | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; construction of roof catchment and storage tank with water points | To enhance access to clean and safe drinking water | 7 water springs constructed and 3 roof catchments | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2498640 | 2498640 |  | N/A | 2498640 | 0 | 2498640 | 100% | 2498640 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
562 | Drill a borehole at Kapkara | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works |  | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2224900 | 2224900 |  | N/A | 2224900 | 0 | 2224900 | 100% | 2224900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
3 | Construction of Lwandanyi ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Lwandanyi ward office constructed | 3111504 | Construction of non- residential buildings | Sirisia | Lwandanyi | Lon:7090325 Lat:34.434112 | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 42879 | 9500000 | 9039375 | 9500000 | County Government of Bungoma | - | 9039375 | - | 9039375 | 100% | 9039375 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Rehabilitation of Kapkara Dam | Rehabilitation of Kapkara Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 10000000 | 7675000 | 8000000 | County Government of Bungoma |  | 7675000 |  | 7675000 | 100% | 7675000 | 0 | 0 | Completed
| Construction of farm ponds at Kabkara watershed | Construction of 20no. farm ponds at Kabkara watershed | To store water for irrigation and flood control | 20 farm ponds constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | [5 empty] | 4999144 | 5000000 | Development partner | IDA | 0 | 4999144 | 4999144 |  | 4999144 | 0 | 0 | stalled
| Construction of Kabkara Earth Dam | Construction of Kabkara Earth Dam | To store water for irrigation and flood control | 1 dam constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 24/5/2022 | 24/11/2022 | 21/3/2024 |  | 50866669 | 50866669 | Development partner | IDA | 0 | 50866669 | 50866669 |  | 50866669 | 0 | 0 | Complete
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
96 | Installation of 2 No high mast flood lights | of lights No high | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Ms Emricon Limited | 2021/22 |  | Complete and in use |  | 1900000 |  |  | CGB | [8 empty] | not traced | [15 empty] | not traced
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Lwandanyi |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
123 | Construction of 3 no. Mama Mboga sheds | sheds of 3 no | [5 empty] | Lwandanyi |  |  |  | Dry Port | 2018/19 |  | Complete |  | 1595174 |  |  | CGG | [8 empty] | Completed | [15 empty] | in use and in good condition
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Lwandanyi |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
133 | Construction of 8 No. Boda Boda Sheds | heds of 8 No | [5 empty] | Lwandanyi |  |  |  | M/S Mamofa Construction Company Limited P.O Box 41658 Bungoma | 2017/18 |  |  |  | 2756979 |  |  | CGB | [8 empty] | Completed | [15 empty] | in use and in good condition
134 | Renovation of Lwakhakha market | [6 empty] | Lwandanyi |  |  | Dept of Trade | Adept General Contractors | 2016/17 |  | Complete |  | 24409776 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Male and female wards lwandanyi health centre | [5 empty] | Sirisia | Lwandanyi | [20 empty] | Completed | [15 empty] | in use and in good condition
45 | Construction of fence, gate and 4NO. Doors pit latrines at cheptais animal sale yard | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Fence, Gate and 4No.door pit latrine constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.811713 LONG 34.469555 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 15/2/2024 |  |  | 2000000 | 1884072 | 1884072 | CGB |  | 1884072 |  |  | 0% |  |  | 1884072 | Completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | good work done
60 | Construction of 9NO. Doors pit latrines with Urinal at Chebwek Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 9no.door pit latrine constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.85111 LONGIT. 34.45362 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 45416 |  |  | 1200000 | 1200000 | 1200000 | CGB |  | 1200000 | 0 | 0 | 0% | 0 |  | 1200000 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | contractor should commence immediately
64 | Construction of fence, gate and 4NO. Doors pit latrines at cheptais animal sale yard | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Fence, Gate and 4No.door pit latrine constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.811713 LONG 34.469555 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 15/2/2024 |  |  | 2000000 | 1884072 | 1884072 | CGB |  | 1884072 | 0 | 0 | 0% | 0 |  | 1884072 | [7 empty] | No | complete | Financial | Yes |  |  |  | No |  | done
72 | Erection And Completion Of Maternity Wing And 4no. Door Pit Latrines Phase 1 At Kimaswa Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wing and 4No.door pit latrine completed |  |  | Mt. Elgon | Cheptais | LAT. 0.8213634 LONG. 34.4577122 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2600000 | 0 | 0 | CGB |  | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Contractor has never stepped on the site
99 | Construction Of Gate, Fence Of Burkweno Land For Dispensary Complition Of Stalled Modern Toilets At Cheptais Market | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services in the area | Fence and Gate constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8286 LONGITU. 34.43178 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1200000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | fencing has neve been undertaken
154 | Construction Of Meternity At Chebkube Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.83532 LONG. 34.4297 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1920400 | 1920400 | CGB |  | 1920400 | 0 | 1804247 | 93.95% | 1804247 |  | 116153 | Incomplete and not in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | Some repairs need to be undertaken esp. doors
155 | Construction Of Meternity Ward In Kang'ang'a Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8093629 LONG. 34.4635973 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1905850 | 1905850 | CGB |  | 1905850 | 0 | 1904417 | 99.92% | 1904417 |  | 1433 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Works not finished
156 | Construction Of Nalondo Dispensary With Pit Latrines, Chain Link Fence And Gate | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8150121 LONG. 34.419669 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2174382 | 4989885 | 4989885 | CGB |  | 4989885 | 0 | 4891180.6 | 98.02% | 4891180.6 |  | 98704.4 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | done
198 | Construction Of A Maternity Ward At Cheptais Health Centre | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wards constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.823191 LONG 34.4620565 |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 3000000 | 2225570 | 2225570 | CGB |  | 2225570 | 0 | 1602820 | 72.02% | 1602820 |  | 622750 | complete but not in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | no equipments
199 | Construction Of A Dispensary At Nalondo | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.815160 LONG. 34.419279 |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 3000000 | 4989885 | 4989885 | CGB |  | 4989885 | 0 | 4891180 | 98.02% | 4891180 |  | 98705 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | in use
218 | Proposed Completion Of Septic Tank At Cheptais Market | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | Septic tanks constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8076761 LONG. 34.4620565 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 500000 | 492269.2 | 492269.2 | CGB |  | 492269.2 | 0 | 492089.4 | 99.96% | 492089.4 |  | 179.8 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Constructed but not in use as its in bad condition
272 | Rehabilitation of public toilet at Cheptais market. | Digging of 20ft deep pit,flooring,walling,painting,roofing and fitting of doors n and installation of water tank | To enhance access to sanitary facilities at the market. | Public toilets constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8076576 LONG 34.4639632 |  | Ward Based | Health & Sanitation | 2015/2016 | 16th March 2015 | 30th Jun 2016 | 16th June 2016 |  | 350000 | 350000 | CGB |  | 350000 | 0 | 286000 | 81.71% | 286000 |  | 64000 | Complete but not in use. | [6 empty] | No | complete | Financial | Yes | [5 empty] | In pathetic state (condenmed for demolition)
273 | Purchase of 2-acre land for construction of Nalondo Health centre. | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Cheptais | LAT. 0.815292 LONG. 34.419057 |  | Ward Based | Health & Sanitation | 2015/2016 | 16th April 2016 | 3rdJun 2016 | 16th June 2016 |  | 460000 | 460000 | CGB |  | 460000 | 0 | 460000 | 100% | 460000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | Land acquired but require sub-division
274 | Purchase of 3/4-acre land | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Cheptais | LAT. 0.8213634 LONG. 34.4577122 |  | Ward Based | Health & Sanitation | 2015/2016 | 42506 | 42551 | 42537 |  | 489000 | 489000 | CGB |  | 489000 | 0 | 489000 | 100% | 489000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | land in dispute, sub-division is needed for full ownership
275 | Construction of Chebwek health centre | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | health centres constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.72243 LONG. 34.4412 |  | CEF | Health & Sanitation | 2016/2017 | 42916 | 43084 | Ongoing. |  | 13191212 | 13191212 | CGB |  | 13191212 | 0 | 2824356 | 21.41% | 2824356 |  | 10366856 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | good workmanship
14 | Upgrading of Cheptais Hosy-Kapsesoipoly-Tembelela-Wasio Mkt | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8032364 LONG. 34.4620589 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41651 | 41778 |  | 4737600 | 4737600 | 4737600 | County Government of Bungoma |  | 4737600 |  | 4737600 | 100.0% | 4737600 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | at the moment, it requires routine maineanance
32 | Upgrading of Periodic Maintanance Of Kamuneru-Masaek | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | not in cheptais ward | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41663 | 41780 |  | 23800030.93 | 23800030.93 | 23800030.93 | County Government of Bungoma |  | 23800030.93 |  | 23800030.93 | 100.0% | 23800030.93 | 0 | 0 |  | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | not in cheptais wad
122 | Upgrading of Cheptais Market Roads | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8090761 LONG. 34.35665 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42759 | 42867 |  | 54263150 | 54263150 | 54263150 | County Government of Bungoma |  | 54263150 |  | 54263150 | 88.4% | 54263150 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | some requires maintenance
156 | Periodic Maintenance of Kwa Kilemba - Kapkwes Forest Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8286 LONGIT. 34.46089 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43232 |  | 8166690 | 8166690 | 8166690 | County Government of Bungoma |  | 8166690 |  | 8166690 |  | 8166690 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | road in pathetic state and impassable
157 | Periodic Maintenance of Chepkube Fcs - Chebwek Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.78869 LONGI. 34.2711699 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43230 |  | 8166690 | 8166690 | 8166690 | County Government of Bungoma |  | 8166690 |  | 8166690 |  | 8166690 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable
158 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8305746 LONG. 34.4580721 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43244 |  | 8166690 | 8166690 | 8166690 | County Government of Bungoma |  | 8166690 |  | 8166690 | 99.94% | 8166690 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
304 | Periodic Maintenance of Cheptais Hospital - Kapsesoi - Tembelela Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8032364 LONG. 34.4620589 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43479 | 43599 |  | 7101670.8 | 7101670.8 | 7101670.8 | County Government of Bungoma |  | 7101670.8 |  | 7101670.8 |  | 7101670.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
305 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43480 | 43606 |  | 7101670.8 | 7101670.8 | 7101670.8 | County Government of Bungoma |  | 7101670.8 |  | 7101670.8 | 99.58% | 7101670.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
306 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
494 | Upgrading of R. Tisi - Burkenwo - Rama Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.8376 LONGI. 34.43267 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43968 |  | 7818342 | 7818342 | 7818342 | County Government of Bungoma |  | 7818342 |  | 7818342 |  | 7818342 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
495 | Periodic Maintenance of Cheptais Backstreet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT 0.8090784 LONG. 34.4635277 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43973 |  | 3475824 | 3475824 | 3475824 | County Government of Bungoma |  | 3475824 |  | 3475824 |  | 3475824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
496 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43962 |  | 3475824 | 3475824 | 3475824 | County Government of Bungoma |  | 3475824 |  | 3475824 | 99.97% | 3475824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
497 | Drainage Works In Elgon,Kabuchai And Sirisia Sub-Counties(Lot 3) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43966 |  | 7818342 | 7818342 | 7818342 | County Government of Bungoma |  | 7818342 |  | 7818342 | 90.53% | 7818342 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
722 | Periodic Maintenance of Peresten - Cheptais Boys - Kiterie - R. Tisi - Rcea Chemorroch Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT 0.8066469 LONG. 34.463665 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44328 |  | 4951837 | 4951837 | 4951837 | County Government of Bungoma |  | 4951837 |  | 4951837 |  | 4951837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
723 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44328 |  | 4951837 | 4951837 | 4951837 | County Government of Bungoma |  | 4951837 |  | 4951837 | 99.79% | 4951837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
1046 | Periodic Maintenance of Chebwek - Chesukum Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.78925 LONG. 34.46089 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44693 | 44724 | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 |  | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | impassable due to non routine mantenance
1047 | Periodic Maintenance of Nairobi B - Chesiro Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.84887 LONG.34.46588 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44693 | 44724 | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 |  | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | road in pathetic state and impassable
1048 | Periodic Maintenance of Wasio - Nalondo - Chepsienya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.820512 LONG. 34.431109 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44695 | 44726 | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 |  | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Complete and passable
1049 | Periodic Maintenance of Kapsesoi - Chepkube Factory | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.8361005 LONG. 34.4504978 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44703 |  | 2513328.5 | 2513328.5 | 2513328.5 | County Government of Bungoma |  | 2513328.5 |  | 2513328.5 |  | 2513328.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | impassable due to non routine mantenance
1050 | Periodic Maintenance of Chepkube - Ack - River Lwakhakha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.83532 LONG. 34.43144 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44702 |  | 2360446.3 | 2360446.3 | 2360446.3 | County Government of Bungoma |  | 2360446.3 |  | 2360446.3 |  | 2360446.3 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
1051 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44695 |  | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 | 19.71% | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
1052 | Routine Maintenance Of Kapsesoi - Chepkube Factory | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.8361005 LONG. 34.4504978 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44701 |  | 2513328.5 | 2513328.5 | 2513328.5 | County Government of Bungoma |  | 2513328.5 |  | 2513328.5 | 100.0% | 2513328.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | repeatation
1053 | Routine Maintenance Of Chepkube - Ack - River Lwakhakha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44700 |  | 2360446.3 | 2360446.3 | 2360446.3 | County Government of Bungoma |  | 2360446.3 |  | 2360446.3 | 100.0% | 2360446.3 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | repeatation
1370 | Construction of Chebwek- Chesiro Twin Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.85244 LONG. 34.46327 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45069 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | bridge passable
1620 | Construction of Cheptais Market (Ochela Junction) - Cheptais Cdf Office Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8130745 LONG 34.4639662 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45428 |  | 8471683 | 8471683 | 8471683 | County Government of Bungoma |  | 8471683 |  | 8471683 |  | 8471683 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
1621 | Periodic Maintenance of Chemoro Rcea Church - Bikhutu Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.83105 LONG. 34.43939 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45434 |  | 3138867 | 3138867 | 3138867 | County Government of Bungoma |  | 3138867 |  | 3138867 |  | 3138867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires maintenance
1622 | Periodic Maintenance of Rama - Busanja - Andrea Walanga Road In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45434 |  | 5003544 | 5003544 | 5003544 | County Government of Bungoma |  | 5003544 |  | 5003544 | 99.94% | 5003544 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1623 | Periodic Maintenance of Kamata - Kang'Ang'A - Cheptiya Road In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8307191 LONG. 34.4506382 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45424 |  | 6377680 | 6377680 | 6377680 | County Government of Bungoma |  | 6377680 |  | 6377680 | 99.92% | 6377680 | 0 | 0 | Incomplete and not in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | impassable an poor work done. No culverts and road completely worn out
1624 | Periodic Maintenance of Chemoro Rcea Church - Bikhutu Primary Road In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.83105 LONG. 34.43939 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45425 |  | 3138867 | 3138867 | 3138867 | County Government of Bungoma |  | 3138867 |  | 3138867 | 98.0% | 3138867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance and culverts for drainage
1625 | Proposed Cheptais Market (Ochela Junction) - Cheptais Cdf Office Box Culvert In Cheptais Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8130745 LONG 34.4639662 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45434 |  | 8471683 | 8471683 | 8471683 | County Government of Bungoma |  | 8471683 |  | 8471683 | 99.81% | 8471683 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
7 | Purchase of 1 Acre for bus terminus and open air market. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of Market and bus terminas | One acre of Land Purchased for bus terminus and open air market | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45200 | 45809 |  | 5000000 | - | 5000000 | CGB | N/A | 5000000 | 0 | 5000000 | 100% | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
74 | Purchase Of Land For Cheswee Ecde | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land For Cheswee Ecde Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 |  |  |  | 3000000 | 2132510.05 | 2132510.05 | CGB |  | 2132510.05 |  | 2132510.05 | 100% |  |  |  | not in existence | [15 empty] | Diverted t buy aplot at a poor site in cheptais market
115 | Purchase Of One Acre For Rama Ecde | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new ECDE centre | One acres of Land for Rama E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT. 0.83993 LONGI. 34.2741770 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 17/9/2017 | 19/11/2017 | 43435 | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 100% | 500000 | 0 |  | Completed | 1 | [14 empty] | school exist at the land purchased
116 | Purchase Of One Acre For Chenomor Coffee Factory | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new Coffee facrory | One acres of Land for Chenomor Coffee Factory Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT. 0.814343 LONG. 34.4574282 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43077 | 43079 | 23/11/2017 | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 100% | 500000 | 0 |  | Completed | 1 | [14 empty] | land in place though require sub-divistion
184 | Purchase of land for Kaamata ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Kaamata yECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT.0.8274209 LONG. 34.453883 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42374 | 42377 | 42377 | 362000 | 362000 | 362000 | CGB | N/A | 362000 |  | 362000 |  | 362000 |  |  | Completed | 1 | [14 empty] | land dispute over boundary, requires sub-division
185 | Purchase of land for Bikhutu ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Bikhutu ECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42014 | 42401 | 25/12/2015 | 300000 | 300000 | 300000 | CGB | N/A | 300000 |  | 300000 |  | 300000 |  |  | Completed | 1 | [14 empty] | land available
192 | Purchase of 1 acre for Rama E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Rama E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT. 0.83993 LONGI. 34.2741770 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 |  |  |  | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 100% | 0 |  |  | Completed | 0 | [14 empty] | school exist at the land purchased
193 | Purchase of 1 acre for Chenomor coffee factory | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new Coffee factory | One acres of Land for Chenomor coffee factory Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 |  |  |  | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 100% | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
35 | Proposed Erection And Completion Works Of Chebwek Polytechnic In Cheptais Ward | Construction of VTC | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.61984 LONG. 33.5263 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2936190 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0% |  | 2936190 | 2936190 | Completed | 1 | [14 empty] | not in use due to unfinished toilets
36 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Kamata and Kipsis Primary Schools In Cheptais Ward | Completion of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.82354 LONG. 34.46955 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3900000 | 3877600 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 1037621.35 | 26.76% | 1037621.35 | 2839978.65 | 2839978.65 | Completed | 1 | [14 empty] | in use by the pupils, though was not officially opened
70 | Construction Of 1no. Classroom At Bulukha Ecde | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.811837 LONG. 34.415907 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1300000 | 1299000 | 1300000 | County Government of Bungoma | N/A | 1300000 | 0 | 0 | 0% | 0 | 1299000 | 1299000 | Stalled | 1 | [14 empty] | construction reached wall plate.
103 | Construction Of 1 No. Ecde At Kuborom And Cheptais Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.61984 LONG. 34.33.50263 LAT. 0.8079479 LONG 34.4563886 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 2600000 | 2501700 | 2600000 | County Government of Bungoma | N/A | 2600000 | 0 | 505561.55 | 20.21% | 505561.55 | 1996138.45 | 1996138.45 | Completed | 0.9 | [14 empty] | in use
32 | Proposed Rehabilitation Of Kuywa, Lwakhakha Rivers And Matere Stream In Chepyuk, Cheptais And Chesikaki Wards Respectively. | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7888000 | 5909325 | 5909325 | FLLOCA | IDA | 0 | 5909325 | 0 | 100% | 0 | 0 |  | Re-tendered | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
47 | Extension of Chebukube Cheptais Water project in Cheptais Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4000000 | 3880780 | 3880780 | CGB | N/A | 3880780 | 0 | 3880780 | 100% | 3880780 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
117 | Expansion of main treatment works at Chebwek-Chepkube | Rehabilitation of treatment plant; flocculation; pre-sedimentation; clear water tank | To enhance access to clean and safe drinking water | 1 Treatment works site expanded | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.78877 LONG. 34.2711772 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 7000000 | 6794730 | 6794730 |  | N/A | 6794730 | 0 | 6794730 | 100% | 6794730 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | water available
118 | Extension of Cheptais Cherendio water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.7965936 LONG. 34.4574282 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2500000 | 2364080 | 2364080 |  | N/A | 2364080 | 0 | 2364080 | 100% | 2364080 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | people enjoy water
181 | Nalondo dispensary - Namatotoa primary water supply project | Trenching ; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.822437 LONG. 34.25968 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 5500000 | 5409231 | 5409231 |  | N/A | 5409231 | 0 | 5409231 | 100% | 5409231 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Not in use due to theft and vandalism
182 | CONSTRUCTION OF INO. WATER IN CHEPTAIS WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8058137 LONG. 34.4637083 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 300000 | 249050 | 249050 |  | N/A | 249050 | 0 | 249050 | 100% | 249050 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
309 | CONSTRUCTION OF WATER PIPELINE PROJECT FROM CHEBWEK –CHEBKUBE MARKET IN CHEPTAIS WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.78877 LONG.34.2711774 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 7400000 | 7296800 | 7296800 |  | N/A | 7296800 | 0 | 7296800 | 100% | 7296800 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
310 | REHABILITATION OF CHEPTAIS LWAKHAKHA WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8048493 LONG. 34.4631076 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 7200000 | 7001470 | 7001470 |  | N/A | 7001470 | 0 | 7001470 | 100% | 7001470 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
454 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8048493 LONG. 34.4631076 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2597616 | 2597616 |  | N/A | 2597616 | 0 | 2597616 | 100% | 2597616 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
545 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points; | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8048493 LONG. 34.4631076 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 10000000 | 9277200 | 9277200 |  | N/A | 9277200 | 0 | 9277200 | 100% | 9277200 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
| Construction Of Coffee Adminstrative Blocks | Construction of Coffee Adminstrative Blocks in Cheswee, Kipsis, Chechoko and Wasio in Cheptais Ward | To support growth of coffee farmers and enhance income generation | 4 Administartion blocks constructed | 3110504 | Other infrastructure and civil works | Mt. Elgon | Cheptais |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 20/2/2022 | 20/7/2022 | 15/5/2022 | 6000000 | 4365000 | 4500000 | County Government of Bungoma |  | 4365000 | 0 | 4365000 | 100% | 4365000 | 0 | 0 | Completed
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
84 | Proposed construction of cabro laying in Cheptais open air market | construction laying in Cheptais |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais | LAT. 0.8066762 LONG. 34.4635277 | Trade, Energy and Industrialization | Dept of Trade | M/S Hertz Investment | 2021/22 |  | Terminated |  | 4782500 |  |  | CGB | [8 empty] | never done | [15 empty] | project never took place
87 | Installation of 2 No solar High mast flood lights | of flood solar High | [5 empty] | Cheptais | LAT. 0.8066762 LONG.34.4636166 | Trade, Energy and Industrialization | Dept of Energy | Bishin Transpoters and Construction Company | 2021/22 |  | Complete and in use |  | 1988000 |  |  | CGB | [8 empty] | Completed | [15 empty] | working
106 | Proposed installation of 25 no. Grid powered street lights in Mt. Elgon Sub County | installation Grid lights street in Mt | [5 empty] | Cheptais |  |  |  | M/S FECAKO Investments Limited | 2020/21 |  | Complete |  | 2434212.5 |  |  | CGG
118 | Construction of 16 door Modern stalls | Of stalls streetlights | [5 empty] | Cheptais | LAT. 0.8066762 LONG. 34.4635277 |  |  | Yonak (Ke) Limited | 2019/20 |  | Project not implemented. The BoQs were reviewed upward in terms of specifications without effecting the same on the budget which resulted to Contractor declining the contract. Additionally, there was no public land for construction of the market stalls. |  | 3096460 |  |  | CGG | [8 empty] | never done | [15 empty] | project never took place
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed | [15 empty] | distribution done and farm production increased
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed | [15 empty] | distribution done and farm production increased
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8066762 LONG. 34.4635277 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
21 | Completion of maternity wing at Kaptalelio dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45478 |  |  | 500000 | 1760000 | 1760000 | CGB |  | 1760000 | 0 | 0 | 0% | 0 |  | 1760000 | On-going | 94 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
32 | Equiping of Kaptama dispensary wards | Equipping with drugs and medical equipment |  | dispensaries equipped |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 750000 | 706880 | 706880 | CGB |  | 706880 | 0 | 0 | 0% | 0 |  | 706880 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
105 | Construction Of 16 No. Door Pit Latrine in Chepkoyaa primary |  |  | 16No. Door pit latrine Constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 3000000 |  |  | CGB |  |  | 0 | 2987924 | #DIV/0! | 2987924 |  | -2987924 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
106 | Construction Of Wards At Kaptama Health Center |  |  | Wards constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2000000 | 1999000 | 1999000 | CGB |  | 1999000 | 0 | 685200 | 34.28% | 685200 |  | 1313800 | stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
161 | Construction Of Toboo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3000000 | 3019790 | 3019790 | CGB |  | 3019790 | 0 | 2574152 | 85.24% | 2574152 |  | 445638 | Complete and in use | [6 empty] | No | complete | Financial | Yes
162 | Construction Of Kaptama Health Center Septic Tank | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | health centres constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1249121 | 984100 | 984100 | CGB |  | 984100 | 0 | 979374 | 99.52% | 979374 |  | 4726 | Complete and in use | [6 empty] | No | complete | Financial | Yes
188 | Construction Of Toboo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3000000 | 3019790 | 3019790 | CGB |  | 3019790 | 0 | 2574152 | 85.24% | 2574152 |  | 445638 | Complete and in use | [6 empty] | No | complete | Financial | Yes
189 | Construction Of Kaptama Health Center Septic Tank | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | health centres constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1249121 | 984100 | 984100 | CGB |  | 984100 | 0 | 979374 | 99.52% | 979374 |  | 4726 | Complete and in use | [6 empty] | No | complete | Financial | Yes
225 | Construction Of Maternity Wing At Kaptalelio Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1500000 | 1790650 | 1790650 | CGB |  | 1790650 | 0 | 520578.72 | 29.07% | 520578.72 |  | 1270071.28 | Stalled at Ringbeam | [6 empty] | No | complete | Financial | Yes |  |  |  | No
226 | Construction Of Maternity Wing At Kaptalelio Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1500000 | 1790650 | 1790650 | CGB |  | 1790650 | 0 | 520578.72 | 29.07% | 520578.72 |  | 1270071.28 | Stalled at Ringbeam | [6 empty] | No | complete | Financial | Yes |  |  |  | No
277 | Purchase of 0.75 acre of land for chemoge Dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | Ward Based | Health & Sanitation | 2015/2016 | 42430 | 42461 | 42522 |  | 300000 | 300000 | CGB |  | 300000 | 0 | 300000 | 100% | 300000 |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
281 | Purchase of 0.5 acre land for Kongit dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | Ward Based | Health & Sanitation | 2015/2016 | 01.01.2016 | 42461 | 15.04.2016 |  | 200000 | 200000 | CGB |  | 200000 | 0 | 200000 | 100% | 200000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
282 | Construction of Kaptama health centre | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windows | To provide accessible and affordable health services within the community | health centres constructed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 |  | Dec – 2016 |  |  | 9741352.9 | 9741352.9 | CGB |  | 9741352.9 | 0 | 8234927 | 84.54% | 8234927 |  | 1506425.9 | Complete | [6 empty] | No | complete | Financial | Yes
283 | Erection and Completion of Kongit dispensary | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 | 42705 | Jan– 2017 | 42767 |  | 3350000 | 3350000 | CGB |  | 3350000 | 0 | 3243724 | 96.83% | 3243724 |  | 106276 | Complete | [6 empty] | No | complete | Financial | Yes
284 | Construction of Chemoge dispensary | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Kaptama |  |  | Ward Based | Health & Sanitation | 2015/2016 | 4th Jan 2016 | 4th Apr 2017 |  |  | 3351566 | 3351566 | CGB |  | 3351566 | 0 | 3034892.3 | 90.55% | 3034892.3 |  | 316673.7 | Complete and in use. | [6 empty] | No | complete | Financial | Yes
285 | Purchase of 1 acre of land for Chemoge dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 |  | 42475 |  |  | 300000 | 300000 | CGB |  | 300000 | 0 | 300000 | 100% | 300000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
286 | Purchase of ½ an acre of land for Kongit dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 | 42370 |  | 15.04.2016 |  | 200000 | 200000 | CGB |  | 200000 | 0 | 200000 | 100% | 200000 |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
288 | Construction of pit latrine at Kaptalelio primary school | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To enhance access to sanitary facilities at the school | pit latrines constructed |  |  | Mt. Elgon | Kaptama | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | [7 empty] | No | complete | Financial | Yes
290 | Renovation of Labot dispensary | Excavation of trenches for foundation,construction of 150mm thick floor slab,walling,roofing,painting,fixing of doors,windows | To provide accessible affordable health services within the community | Dispensaries renovated |  |  | Mt. Elgon | Kaptama | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete but not in use. | [6 empty] | No | complete | Financial | Yes
291 | Renovation of Labot dispensary | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To provide accessible affordable health services within the community | Dispensaries renovated |  |  | Mt. Elgon | Kaptama | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
10 | Fencing of high altitude training centre | Fencing of high altitude training centre | To improve on security | High altitute centre fenced |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2013/14 |  |  |  | 4707483 | 4707483 | 4707483 | County Government of Bungoma | n/a | n/a | n/a | 4707483 | 100% | 4707483 | 0 | 0 | Completed
11 | Erection and completion of high altitude training centre- phase 1 | Erection and completion of high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | High altitute centre erected and completed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2013/14 |  |  |  | 45652160 | 45652160 | 10630020 | County Government of Bungoma | n/a | n/a | n/a | 10630020 | 23.28% | 10630020 | 0 | 35022140 | Stalled | 0.3 | 0.3 | The Contractor was unable to complete works-the contract was terminated and retendered
12 | Erection and completion of high altitude training centre | Erection and completion of high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | High altitute centre erected and completed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015/16 |  |  |  | 37068629 | 37068629 | 37068629 | County Government of Bungoma | n/a | n/a | n/a | 37068629 | 100% | 37068629 | 0 | 0 | Completed
13 | Supply, Delivery, installation and testing of sanitary, fittings, plumbing | Supply, Delivery, installation and testing of sanitary, fittings, plumbing | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Sanitary,fittings and plumbing equipments supplied and installed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015/16 |  |  |  | 3619548 | 3619548 | 3619548 | County Government of Bungoma | n/a | n/a |  | 3619548 | 100% | 3619548 | 0 | 0 | Completed
14 | Supply, installation and commissioning of Kitchen cold Equipment at high altitude training centre | Supply, installation and commissioning of Kitchen cold Equipment at high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Kitchen cold equipment supplied, installed and commissioned |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015-16 |  |  |  | 1847540 | 1847540 | 1350866 | County Government of Bungoma | n/a | n/a |  | 1350866 | 73.12% | 1350866 | 0 | 496674 | Stalled | 0.73 | 0.73 | The supplier supplied equipment but did not test and commission the works-terminated retendered
15 | Supply, installation and commissioning of electrical lighting Equipment at high altitude training centre | Supply, installation and commissioning of electrical lighting Equipment at high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Electrical lighting equipment supplied, installed and commissioned |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015-16 |  |  |  | 7916176 | 7916176 | 5479608 | County Government of Bungoma | n/a | n/a |  | 5479608 | 69.22% | 5479608 | 0 | 2436568 | Stalled | 0.69 | 0.69 | Electrical works were not completed- Terminated, evaluated and retendered
16 | Construction of Hostels at High Altitude Training Centre( phase 11) | Construction of Hostels at High Altitude Training Centre( phase 11) | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Hostels constructed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2018-19 |  |  |  | 25491383 | 25491383 | 25491383 | County Government of Bungoma | n/a | n/a |  | 25491383 | 100% | 25491383 | 0 | 0 | Completed
17 | Supply and Delivery of Gym Equipment and Furniture for High altitude Training centre | To facilitate operationilization of the High altitute centre | To facilitate operationilization of the High altitute centre | Gym Equipment and Furniture supplied and delivered |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2021-22 |  |  |  | 9287164 | 9287164 | 9287164 | County Government of Bungoma | n/a | n/a |  | 9287164 | 100% | 9287164 | 0 | 0 | Completed
18 | Supply and delivery of Kitchen ware equipment for High Altitude training Centre | Supply and delivery of Kitchen ware equipment for High Altitude training Centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Kitchen ware equipment Supplied and delivered |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2021-22 |  |  |  | 480000 | 480000 | 480000 | County Government of Bungoma | n/a | n/a |  | 480000 | 100% | 480000 | 0 | 0 | Completed
19 | Completion of High Altitude Centre | Completion of High Altitude Centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | High Altitude Centre completed | 3110604 | other infrastructure and civil works | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2023/24 | 16/11/2023 | 16/11/2024 |  | 44430681 | 30980230.3 | 19025572 | County Government of Bungoma | n/a | n/a |  | 19025572 | 61.41% | 19025572 | 11954658.3 | 11954658.3 | Ongoing | 0.9
185 | Periodic Maintenance of Kaptama - Kostoi - Chebombai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43123 | 43231 | 43262 | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 |  | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
186 | Periodic Maintenance of Chepkoya - Kapkijana - Kapmuyei Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43235 | 43266 | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 |  | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
187 | Upgrading of Kaptama - Sosio - Chemoge Foot Bridge | Road improvement works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43244 | 43275 | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 |  | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
188 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43240 |  | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 | 82.77% | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
350 | Periodic Maintenance of Kapsamii - Kamatira Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43486 | 43600 |  | 6655152 | 6655152 | 6655152 | County Government of Bungoma |  | 6655152 |  | 6655152 |  | 6655152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
351 | Grading of Chemoge Market Primary School Road | Grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43598 | 43629 | 6655152 | 6655152 | 6655152 | County Government of Bungoma |  | 6655152 |  | 6655152 |  | 6655152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
352 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43604 |  | 6655152 | 6655152 | 6655152 | County Government of Bungoma |  | 6655152 |  | 6655152 | 97.91% | 6655152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
353 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
523 | Periodic Maintenance of Kaptama - Chesito Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43961 |  | 11066433 | 11066433 | 11066433 | County Government of Bungoma |  | 11066433 |  | 11066433 |  | 11066433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
524 | Periodic Maintenance of Chesito - Cheledet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43972 |  | 7393260 | 7393260 | 7393260 | County Government of Bungoma |  | 7393260 |  | 7393260 |  | 7393260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
525 | Periodic Maintenance of Cheledet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43969 |  | 9017463 | 9017463 | 9017463 | County Government of Bungoma |  | 9017463 |  | 9017463 |  | 9017463 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
526 | Periodic Maintenance of Sultan - Kaptengandet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43967 |  | 6780606 | 6780606 | 6780606 | County Government of Bungoma |  | 6780606 |  | 6780606 |  | 6780606 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
527 | Periodic Maintenance of Kaptama - Chesito Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43970 |  | 11066433 | 11066433 | 11066433 | County Government of Bungoma |  | 11066433 |  | 11066433 | 98.61% | 11066433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
528 | Periodic Maintenance of Chesito - Cheldet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43964 |  | 7393260 | 7393260 | 7393260 | County Government of Bungoma |  | 7393260 |  | 7393260 | 95.07% | 7393260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
529 | Periodic Maintenance of Chelindet - Line Maweroad | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43970 |  | 9017463 | 9017463 | 9017463 | County Government of Bungoma |  | 9017463 |  | 9017463 | 98.15% | 9017463 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
530 | Routine Maintenance Of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43975 |  | 6780606 | 6780606 | 6780606 | County Government of Bungoma |  | 6780606 |  | 6780606 | 99.87% | 6780606 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
619 | Upgrading of Roads In Kaptama Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
776 | Periodic Maintenance of Kaptama Market - Kaborom Primary - Ack Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44333 |  | 7397610 | 7397610 | 7397610 | County Government of Bungoma |  | 7397610 |  | 7397610 |  | 7397610 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
777 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44333 |  | 7397610 | 7397610 | 7397610 | County Government of Bungoma |  | 7397610 |  | 7397610 | 99.92% | 7397610 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1103 | Periodic Maintenance of Chemoge Mkt - Kiptiroko Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44697 |  | 8608824 | 8608824 | 8608824 | County Government of Bungoma |  | 8608824 |  | 8608824 |  | 8608824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1104 | Periodic Maintenance of Kaptama Dip - Bondeni - Kabwoyo - Chebombao Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44699 |  | 8608824 | 8608824 | 8608824 | County Government of Bungoma |  | 8608824 |  | 8608824 |  | 8608824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1105 | Upgrading of Kona Tatu - Kongit - Mashambani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44694 | 44725 | 8229451.8 | 8229451.8 | 8229451.8 | County Government of Bungoma |  | 8229451.8 |  | 8229451.8 |  | 8229451.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1106 | Periodic Maintenance of Kaptama Police - Chelinde - Chwele Ndogo Market | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44695 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1107 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44703 |  | 8608824 | 8608824 | 8608824 | County Government of Bungoma |  | 8608824 |  | 8608824 | 40.66% | 8608824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1108 | Upgrading of Spot Improvement Of Kona Tatu - Kongit - Mashambani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44701 |  | 8229451.8 | 8229451.8 | 8229451.8 | County Government of Bungoma |  | 8229451.8 |  | 8229451.8 | 18.23% | 8229451.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1409 | Periodic Maintenance of Kostoi - Chelilde Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45068 |  | 3631101 | 3631101 | 3631101 | County Government of Bungoma |  | 3631101 |  | 3631101 |  | 3631101 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1410 | Periodic Maintenance of Kapsamis - Kongit Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45057 |  | 5331295 | 5331295 | 5331295 | County Government of Bungoma |  | 5331295 |  | 5331295 |  | 5331295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1411 | Periodic Maintenance of Kostoi - Chelindet In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45070 |  | 3631101 | 3631101 | 3631101 | County Government of Bungoma |  | 3631101 |  | 3631101 | 100.0% | 3631101 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1412 | Periodic Maintenance of Kapsami - Kongit Road In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45062 |  | 5331295 | 5331295 | 5331295 | County Government of Bungoma |  | 5331295 |  | 5331295 | 98.85% | 5331295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1661 | Construction of Chepsoingei Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45434 |  | 7187389 | 7187389 | 7187389 | County Government of Bungoma |  | 7187389 |  | 7187389 |  | 7187389 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1662 | Periodic Maintenance of Kostoi Chelilde Chebombai In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45432 |  | 4483400 | 4483400 | 4483400 | County Government of Bungoma |  | 4483400 |  | 4483400 | 99.95% | 4483400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1663 | Periodic Maintenance of Kaptama Chepkerer Road In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45423 |  | 5132043 | 5132043 | 5132043 | County Government of Bungoma |  | 5132043 |  | 5132043 | 99.99% | 5132043 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1664 | Periodic Maintenance of Kiptiroko Sosio River Road In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45424 |  | 2841594 | 2841594 | 2841594 | County Government of Bungoma |  | 2841594 |  | 2841594 | 99.99% | 2841594 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1665 | Proposed Chepsoingei Box Culvert In Kaptama Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45422 |  | 7187389 | 7187389 | 7187389 | County Government of Bungoma |  | 7187389 |  | 7187389 | 99.96% | 7187389 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
2 | Preparation of Local and Physical Land use development Plan for Kaptama | Redesigning of Urban areas | To guide sustainable and inclusive growth of urban areas through land use,infrastructure development and improved service delivery | one Physical and land use plan for Kaptama developed | 2211311 | Development/Physical Planning | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45386 | 45392 |  | 4800000 | 4758900 | 4758900 | CGB | N/A | 4758900 | 0 | 4758900 | 100% | 0 | 4758900 | 0 | Ongoing | 0.5 | N/A | N/A | N/A | N/A | 0 | No | [8 empty] | The project is 50% complete
10 | Purchase of 1 Acre for Chepkitale dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land purchased for Chepkitale dispensary | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 |  |  |  | 1000000 | - | 1000000 | CGB | N/A | 1000000 | 0 | 1000000 | 100% | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2023/24 |  | 0 | No | Compete | [7 empty] | The project is stalled due Lack of documentations(Title deed)
63 | Purchase Of 1/4 Land For Kongta E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One quarter acre of Land For Kongta E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  |  |  | 500000 | 200000 | 200000 | CGB |  | 200000 |  | 200000 | 100% |  |  |  | Stalled | [15 empty] | The project is staled due Lack of documentations(Title deed)
64 | Purchase Of 1 Acre For Tobosom E.C.D.E . | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land For Tobosom E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  |  |  | 500000 | 400000 | 400000 | CGB |  | 400000 |  | 400000 | 100% |  |  |  | Stalled | [15 empty] | The project is staled due Lack of documentations(Title deed)
65 | Purchase Of 1 Acre For Lolongbei E.C.D.E . | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of LandFor Lolongbei E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  |  |  | 500000 | 400000 | 400000 | CGB |  | 400000 |  | 400000 | 100% | 0 |  |  | Stalled | [15 empty] | The project is staled due Lack of documentations(Title deed)
151 | purchase of 1 acre land for Kaboram Sec. School | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Kaboram Sec. School Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 100% | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
197 | purchase of 1/2 acre land for kongit Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | A half an acre of Land for kongit Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 18/08/2014 | 18/11/2014 | 42310 | 200000 | 200000 | 200000 | CGB | N/A | 200000 |  | 200000 | 100% | 200000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
198 | purchase 1/2 acre land Chemoge dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | A half an acre of Land for Chemoge Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 18/08/2014 | 18/11/2014 | 42310 | 300000 | 300000 | 300000 | CGB | N/A | 300000 |  | 300000 | 100% | 300000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
8 | Construction of 1 No. ECDE classroom at Kibei, Sirgoi, Kapchebon and Iya primary Schools in Kaptama Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 6000000 | 5761960 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 4361770.01 | 75.7% | 4361770.01 | 1400189.99 | 1400189.99 | Completed
44 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Tulwo, Kapteganted, Kaboywo And Baptist Primary Schools In Kaptama Ward | Construction of ECDE classroom | To construct perimeter wall fence improving security | Perimeter wall fence constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 6000000 | 5956608 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 4950381.45 | 83.11% | 4950381.45 | 1006226.55 | 1006226.55 | Complete and in use | 1
78 | Construction of 1no ecde classrooms and one pit latrine at chebombai prymary | Construction of ECDE classroom and pit latrine | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1500000 | 1489500 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1202688.1 | 80.74% | 1202688.1 | 286811.9 | 286811.9 | ongoing and not in use | 0.6
79 | Kiptiroko VTC | Construction of VTC | To construct of VTC providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1500000 | 1500000 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 0 | 0% | 0 | 1500000 | 1500000 | Complete and in use | 1
112 | Construction Of `1 No. Ecde Classroom And 2 No. Door Pit Latrine At Kostoi, Cherongos And Chelilde Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4500000 | 3552856 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 0 | 0% | 0 | 3552856 | 3552856 | complete and in use | 1
140 | Proposed Erection And Completionof 1 No. Ecde At Kamenjo Primary School In Kaptama Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1500000 | 1461100 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1461100 | 100% | 1461100 | 0 | 0 | COMPLETE. | 1
194 | Construction Of 01 No.Ecde Classroom At Chepsoikel And Kiptiroko Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2000000 | 3366540 | 2000000 | County Government of Bungoma | N/A | 2000000 |  | 3366540 | 100% | 3366540 | 0 |  | complete and in use | 100.0%
92 | Kongit Water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 1 Water project constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4000000 | 3974856 | 3974856 | CGB | N/A | 3974856 | 0 | 3974856 | 100% | 0 | 3974856 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
191 | REHABILITATION OF CHIKONDI - KAPCHEBON AND KAPTELELIO WATER PROJECTS IN KAPTAMA WARD | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 3500000 | 3393519 | 3393519 |  | N/A | 3393519 | 0 | 3393519 | 100% | 0 | 3393519 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
244 | REHABILITATION AND EXTENSION OF WATER PIPELINE IN KAPTAMA WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1900000 | 1801135 | 1801135 |  | N/A | 1801135 | 0 | 1801135 | 100% | 1801135 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
315 | CONSTRUCTION OF CHESITO KAPTAMA WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 5500000 | 5391680 | 5391680 |  | N/A | 5391680 | 0 | 5391680 | 100% | 5391680 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
363 | Construction of 2 roof Catchment and Construction of a 50m3 Storage Tank (Kaptama Boys) | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 2 roof catchment constructed and 1 tank constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 656848 | 656848 |  | N/A | 656848 | 0 | 656848 | 100% | 656848 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
379 | Construction of roof catchment.(Kaptama Girls) | Erection of storage tank; pipe laying and costruction of water points | To enhance access to clean and safe drinking water | 1 roof catchment constructed; 1 storage tank erected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 699757 | 699757 |  | N/A | 699757 | 0 | 699757 | 100% | 699757 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
412 | Protection of water Springs and drilling of borehole | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 water springs constructed and 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3000000 | 2738110.4 | 2738110.4 |  | N/A | 2738110.4 | 0 | 2738110.4 | 100% | 2738110.4 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
460 | Protection of 3 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 800000 | 794413 | 794413 |  | N/A | 794413 | 0 | 794413 | 100% | 794413 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
541 | Protection of 3 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 794413 | 794413 |  | N/A | 794413 | 0 | 794413 | 100% | 794413 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
542 | Construction of 5 roof Catchment and Construction of a 50m3 Storage Tank (Kaptama Boys) | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchments constructed and 1 water tank constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2300000 | 2189498 | 2189498 |  | N/A | 2189498 | 0 | 2189498 | 100% | 2189498 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
543 | Construction of 2 roof catchment.(Kaptama Girls and Boys) | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 2 roof catchments constructed and 1 water tank constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 699757 | 699757 |  | N/A | 699757 | 0 | 699757 | 100% | 699757 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
617 | Kaptama/Kaborong pipeline rehabilitation and Kaboywo water Project Pipeline extension and 1 roof Catchment | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3422638 | 3422638 |  | N/A | 3422638 | 0 | 3422638 | 100% | 3422638 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
8 | Construction of Kaptama ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Kaptama ward office constructed | 3111504 | Construction of non- residential buildings | Mt. Elgon | Kaptama | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 44131 | 9500000 | 9403690 | 9500000 | County Government of Bungoma | - | 9403690 | - | 9403690 | 100% | 9403690 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Purchase of seedlings for Kaptalelio SLM Project | Purchase of seedlings for Kaptalelio SLM Project | To enhance production, productivity and income generation | Seedlings purchased and distributed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 |  |  |  |  | 1450720 | 1500000 | Development partner | IDA | 0 | 1450720 | 1450720 |  | 1450720 | 0 | 0 | Completed
| Construction of Kaptama dairy technology centre | Construction of Kaptama dairy technology centre in Kaptama ward. | To enhance milk production, productivity, value addition and income among the farmers | 1 dairy technology centre constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44785 |  | 24/4/2024 |  | 9920110 | 10000000 | Development partner | IDA | 0 | 9920110 | 9920110 |  | 9920110 | 0 | 0 | Completed
| Purchase of seedlings for Samita- Kaborom SLM Project | Purchase of seedlings for Samita- Kaborom SLM Project | To enhance fruit production, productity and income generation | Seedlings purchased and distributed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44784 | 45139 | 45079 |  | 1566800 | 1566800 | Development partner | IDA | 0 | 1566800 | 1566800 |  | 1566800 | 0 | 0 | Completed
| Purchase and installation of pond liners, water tanks and solar pump kits | Purchase and installation of pond liners, water tanks and solar pump kits for Samita -Kaborom SLM project | To control loss of water through infiltration | 1,165,117 pcs of pond liners purchased, delivered and installed | 2640503 | Other Capital grants and transfer (NARGIP) |  | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44959 | 44963 | 45266 |  | 4440000 | 4500000 | Development partner | IDA | 0 | 4440000 | 4440000 | 100% | 4440000 | 0 | 0 | Completed
| Supply and delivery of Coffee Seedlings in Kaptama Ward | Supply and delivery of Coffee Seedlings in Kaptama Ward | To promote coffee production and enhance income generation among Coffee farmers | 9,000 Coffee seedlings supplied and delivered | 3110599 | Ward Based projects | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 |  | 1020000 | 1,036,00,000 | County Government of Bungoma |  | 1020000 | 0 | 1020000 |  | 1020000 | 0 | 0 | Completed
| Supply and delivery of Coffee Seedlings | Supply and delivery of Coffee Seedlings | To promote coffee production and enhance income generation among Coffee farmers | 75kgs of coffee seedlings supplied and delivered | 3110599 | Ward Based projects | mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 500000 | 498000 | 500000 | County Government of Bungoma |  | 498000 | 0 | 498000 |  | 498000 | 0 | 0 | Completed
| Supply of coffee seedlings | Supply of coffee seedlings | To promote coffee production and enhance income generation among Coffee farmers | 75kgs of coffee seedlings supplied and delivered | 3110599 | Ward Based projects | mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 500000 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 |  | 500000 | 0 | 0 | Completed
| Supply and delivery of coffee seedlings | Supply and delivery of coffee seedlings | To promote coffee production and enhance income generation among Coffee farmers | 75kgs of coffee seedlings supplied and delivered | 3110599 | Ward Based projects | mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 500000 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 |  | 500000 | 0 | 0 | Completed
| Provision of improved breeds (sheep) | Provision of 30 ewes and 3 Rams to 3 elite breeders,2 in Naitiri/Kabuyefwe (NAKASIMA SLCA) and one in Kaptama (KAPCHEKO SLCA) | To enhance production, productivity and income generation | 30 ewes and 3 Rams purchased and issued to 3 elite breeders | 2640503 | Other Capital grants and transfer (KeLCoP) | Tongaren/Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45630 | 45633 | 45357 |  | 956880 | 1029280 | Development partner | IFAD | 0 | 956880 | 956880 |  | 956880 | 0 | 0 | Complete
| Provision of improved breeds of chicken | Provision of improved breeds (Indigenous poultry) chicken – day old chicks | To enhance production, productivity and income generation | 14 MOFAG beneffitted by each getting 575 breeds | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/3/2024 | 23/6/2024 | 28/5/2024 |  | 1387730 | 1447460 | Development partner | IFAD | 0 | 1387730 | 1387730 |  | 1387730 | 0 | 0 | Complete
| Upscaling production of grass seeds | Upscaling production of grass seeds by distrbuting 100 bags of 50kgs of organic fertilizer | To enhance productivity and income generation | 100 bags of 50kg organic fertilizer procured and distributed to 8 farmers. | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45242 | 45598 | 45444 |  | 144940 | 145 940 | Development partner | IFAD | 0 | 620398 | 144940 |  | 144940 | 0 | 0 | Complete
| Provision of beehives and equipment | Provision of64 langstroth bee hives and 6 bee suits and equipment to 3 groups in KAPCHEKO SLCA |  | 64 Langstroth bee hives and 6 bee suits procured and distributed to 3 groups in KAPCHEKO SLCA | 2640503 | Other Capital grants and transfer (KeLCoP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 31/3/2024 | 31/6/2024 | 45510 |  | 620398 | 701410 | Development partner | IFAD | 0 | 620398 | 620398 |  | 620398 | 0 | 0 | Complete
| Purchase and distribution of day old Chicks Rainbow Roosters | Purchase and delivery of 8,050 day old Chicks rainbow roosters to 14 MOFAG Indigenous chicken groups | To enhance poultry production and increase household incomes | 8,050 chicks purchased and delivered to 14 MOFAG indingeneous chicken groups | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 31/3/2024 | 31/6/2024 | 45510
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
92 | Construction of 3No Bodaboda sheds | Of sheds streetlights | [5 empty] | Kaptama |  | Trade, Energy and Industrialization | Dept of Trade | Gabverox general agencies limited | 2021/22 |  | Complete and in use |  | 970000 | 0 |  | CGB
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A | [5 empty] | Kaptama |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Kaptama |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
28 | Purchase of medical equipment for Milani dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45356 |  |  | 2000000 | 1880920 | 1880920 | CGB |  | 1880920 | 0 | 0 | 0% | 0 | 1880920 | 1880920 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
55 | erection and completion works for male, female and children wards at milani dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Female, male and children wards erected and completed |  |  | Webuye West | Bokoli |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 20/2/24 |  |  | 5000000 | 4901892 | 4901892 | CGB |  | 4901892 | 0 | 2667780 | 54.42% | 2667780 |  | 2234112 | On-going | 91 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
69 | Construction Of Wards At Milani Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2500000 | 2254670 | 2254670 | CGB |  | 2254670 | 0 | 2425000 | 107.6% | 2425000 |  | -170330 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
70 | Construction Of Wards At Machakha Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2500000 | 2303000 | 2303000 | CGB |  | 2303000 | 0 | 545607.69 | 23.69% | 545607.69 |  | 1757392.31 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
94 | Completion Of Milimani Dispensary And Extention Works | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries completed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2100000 | 2060000 | 2060000 | CGB |  | 2060000 | 0 | 0 | 0% | 0 |  | 2060000 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
95 | Construction Of Maternity Wards At Mahanga Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2000000 | 1939880 | 1939880 | CGB |  | 1939880 | 0 | 1531705.24 | 78.96% | 1531705.24 |  | 408174.76 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
121 | Construction Of Milani Dispenary And 2 Pit Latrines | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries and 2no pit latrines constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2700000 | 2599107.6 | 2599107.6 | CGB |  | 2599107.6 | 0 | 1242058.4 | 47.79% | 1242058.4 |  | 1357049.2 | Complete and in use | [6 empty] | No | complete | Financial | Yes
153 | Proposed Erection And Competion Works At Machakha Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2066537 | 1984990 | 1984990 | CGB |  | 1984990 | 0 | 1757803 | 88.55% | 1757803 |  | 227187 | Complete and not in use | [6 empty] | No | complete | Financial | Yes
35 | Construction of Kituni Mkt-R.Kuywa-Miendo Junt With Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41661 | 41783 |  | 16111704 | 16111704 | 16111704 | County Government of Bungoma |  | 16111704 |  | 16111704 | 100.0% | 16111704 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
147 | Periodic Maintenance of Wanyonyi - Mahale-Kaita Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43241 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 |  | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
148 | Periodic Maintenance of Namawanga - Miendo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43233 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 |  | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
149 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43232 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 | 99.24% | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
277 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
278 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
463 | Periodic Maintenance of Sawa- Wanambisi - Kakai Road | Road improvement works | To improve the road condition and enhance accessibility | Road gravelled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43963 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 |  | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
464 | Periodic Maintenance of Mukhale Kaita Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43975 | 44006 | 3137684 | 3137684 | 3137684 | County Government of Bungoma |  | 3137684 |  | 3137684 |  | 3137684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
465 | Periodic Maintenance of Temba-Muchocho Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
466 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43968 |  | 3137684 | 3137684 | 3137684 | County Government of Bungoma |  | 3137684 |  | 3137684 | 99.9% | 3137684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
637 | Routine Maintenance Of Roads In Webuye East And Webuye West Sub- Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
638 | Drainage Works In Webuye East And Webuye West Sub-Counties(Lot 4) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43966 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 | 88.12% | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
688 | Construction of Tuliyonga - Mahanga Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44326 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
689 | Periodic Maintenance of Tuliyonga - Abel - Mahanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44328 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
690 | Periodic Maintenance of Miendo - Chebini Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44326 | 44357 | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
691 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44334 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 | 99.89% | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1024 | Periodic Maintenance of Moyokwe - Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44699 | 44730 | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1025 | Periodic Maintenance of Chebosi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44694 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1026 | Periodic Maintenance of Namilimo - Sitabicha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1027 | Periodic Maintenance of Bruno - Namawanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44701 | 44732 | 5707519.8 | 5707519.8 | 5707519.8 | County Government of Bungoma |  | 5707519.8 |  | 5707519.8 |  | 5707519.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1028 | Periodic Maintenance of Asiba - Kaliwanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44699 | 44730 | 3736012 | 3736012 | 3736012 | County Government of Bungoma |  | 3736012 |  | 3736012 |  | 3736012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1029 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44701 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 | 99.73% | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1030 | Routine Maintenance Of Bruno - Namawanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44697 |  | 5707519.8 | 5707519.8 | 5707519.8 | County Government of Bungoma |  | 5707519.8 |  | 5707519.8 | 100.0% | 5707519.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1031 | Routine Maintenance Of Asiba - Kaliwanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44695 |  | 3736012 | 3736012 | 3736012 | County Government of Bungoma |  | 3736012 |  | 3736012 | 97.38% | 3736012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1253 | Routine Maintenance Of Mahanga Secondary - Chekulo - Sikinga Market Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44693 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1344 | Construction of Chebini Box Culvert On River Bokoli | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45070 |  | 6088985 | 6088985 | 6088985 | County Government of Bungoma |  | 6088985 |  | 6088985 |  | 6088985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1345 | Periodic Maintenance of Nandasaba - Sirwa - Sichai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45064 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 |  | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1346 | Periodic Maintenance of Mlani - Muresia - Mary Kangia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45067 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 |  | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1347 | Construction of Chebini Box Culvert Bokoli River Road In Bokoli Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45063 |  | 6088985 | 6088985 | 6088985 | County Government of Bungoma |  | 6088985 |  | 6088985 | 99.54% | 6088985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1348 | Periodic Maintenance of Nandasaba - Sirwa - Sichai, Mlani - Muresia - Mary Kangia Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45059 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 | 100.0% | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1600 | Periodic Maintenance of Wangwelo - Bokoli River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45431 |  | 3650346 | 3650346 | 3650346 | County Government of Bungoma |  | 3650346 |  | 3650346 |  | 3650346 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1601 | Periodic Maintenance of Wangamati - Malaria - Manga Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45433 |  | 5503411 | 5503411 | 5503411 | County Government of Bungoma |  | 5503411 |  | 5503411 |  | 5503411 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1602 | Periodic Maintenance of Wangwelo - Bokoli River Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45427 |  | 3650346 | 3650346 | 3650346 | County Government of Bungoma |  | 3650346 |  | 3650346 | 99.83% | 3650346 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1603 | Periodic Maintenance of Wangamati - Malaria - Manga Primary Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45435 |  | 5503411 | 5503411 | 5503411 | County Government of Bungoma |  | 5503411 |  | 5503411 | 98.4% | 5503411 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1604 | Periodic Maintenance of Roads In Webuye East And West Sub Counties Chesoli(Mulembe)-John Waswa-R.Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45426 |  | 3883096.4 | 3883096.4 | 3883096.4 | County Government of Bungoma |  | 3883096.4 |  | 3883096.4 | 99.32% | 3883096.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
3 | Purchase of 1 Acre land for Auction ring | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new auction ring | One acre of Land Purchased for auction ring | 3130101 | Purchase of land | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 |  |  |  | 1000000 | - | 1000000 | CGB | N/A | 1000000 | 0 | 1000000 | 100% | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2023/24 |  | 0 | No | Compete | [7 empty] | The project is stalled due Lack of documentations(Title deed)
110 | Purchase Of Land For Proposed Machakha Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new dispensary | One acre of Land for Machakha dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42866 | 18/4/2018 | 30/6/2018 | 700000 | 700000 | 700000 | CGB | N/A | 700000 | 0 | 700000 | 100% | 800000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
111 | Purchase Of Land For Proposed Milani Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new dispensary | One acres of Land for Milani Dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43049 | 15/3/2018 | 18/6/2018 | 700000 | 700000 | 700000 | CGB | N/A | 700000 | 0 | 700000 | 100% | 800000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
165 | Purchase of land-NAMATONDOI ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for NAMATONDOI E.C.D.E Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 750000 | 750000 | 750000 | CGB | N/A | 750000 |  | 750000 | 100% | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
166 | Purchase of 1 acre for milani dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for milani dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 15/8/2015 | 15/11/2015 | 13/12/2015 | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 100% | 1000000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
167 | Purchase of 1 acre for machakha dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for milani dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/01/2016 | 21/03/2016 | 42647 | 475500 | 475500 | 475500 | CGB | N/A | 475500 |  | 475500 | 100% | 475500 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
176 | Purchase of land for Namatondoi ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Namatondoi ECDE Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42461 | 42707 | 42466 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 |  | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
67 | Construction of ECDE classroom at matisi pry school | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1200000 | 1197500 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 0 | 0% | 0 | 1197500 | 1197500 | Complete and not in use | 1
99 | Construction Of 1 No. Ecde Classroom At Chebosi And Miendo Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3000000 | 2895000 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2895000 | 100% | 2895000 | 0 | 0 | complete and in use | 1
130 | Proposed Erection And Completion Of 1 No. Ecde At Sikimbilo Rc, Maloho And Ben Kapten Primary Schools In Bokoli Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 4800000 | 4787390 | 4800000 | County Government of Bungoma | N/A | 4800000 | 0 | 4787190 | 100% | 4787190 | 200 | 200 | complete and in use | 1
165 | Construction Of Ecde Classrooms At Mahanga Primary, Milani, Namilimo Primary And Namatondoi Primary | Construction of ECDE classroom and pit latrine | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli | [5 empty] | 43801 | 43775 |  | 4900000 | 5649840 | 4900000 | County Government of Bungoma | N/A | 4900000 | 0 | 5649840 | 100% | 5649840 | 0 |  | complete and in use | 1
182 | The Proposed Erection And Completion Of 1 N0 Classroom At Lukuku, Bokoli R.C And Sawa Primary School In Bokoli Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4150000 | 3515809 | 4150000 | County Government of Bungoma | N/A | 4150000 |  | 3515809 | 100% | 3515809 | 0 |  | complete and in use | 100.0%
2 | Construction and protection of Sirandafu Spring | Rehabilitation of spring, rehabilitation of sump, installation of solar pumping system, pipelaying; erction of a 30cubic metres, elevated pressed tank; construction of water points. | To enhance access to clean and safe drinking water | 1 Spring constructed and protected | 2640599 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 6000000 | 5812644 | 5812644 | FLLOCA | N/A | 5812644 | 0 | 0 | 100% | 5812644 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
45 | Upgrading of Matunda Borehole in Bokoli Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2960900 | 2960900 | CGB | N/A | 2960900 | 0 | 2960900 | 100% | 2960900 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
53 | Upgrading of Sawa Borehole in Bokoli Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2950000 | 2950000 | CGB | N/A | 2950000 | 0 | 2950000 | 100% | 2950000 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
138 | Drilling of borehole at matunda market ,machakha and bumang'ale | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4945500 | 4945500 |  | N/A | 4945500 | 0 | 4945500 | 100% | 4945500 | 0 | 0 | complete and operational | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
179 | DRILLING AND EQUIPPING OF NAMILIMO BOREHOLE | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2000000 | 1795680 | 1795680 |  | N/A | 1795680 | 0 | 1795680 | 100% | 1795680 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
234 | DRILLING OF SAWA AND SIKILIMBO MARKET BOREHOLES IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 3800000 | 3678824 | 3678824 |  | N/A | 3678824 | 0 | 3678824 | 100% | 3678824 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
235 | DRILLING OF NAMATONDOI PRIMARY BOREHOLE IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1800000 | 1789880 | 1789880 |  | N/A | 1789880 | 0 | 1789880 | 100% | 1789880 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
274 | DRILLING OF KAG CHURCH BOREHOLE IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1800000 | 1699900 | 1699900 |  | N/A | 1699900 | 0 | 1699900 | 100% | 1699900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
275 | DRILLING OF CHEBINI AND MAKUNDA BOREHOLES IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 3500000 | 3398000 | 3398000 |  | N/A | 3398000 | 0 | 3398000 | 100% | 3398000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
297 | CONSTRUCTION OF 4NO. SPRINGS AND DRILLING OF 1 BOREHOLE IN BOKOLI WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection;site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes rehabilitated and 4 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2458624 | 2458624 |  | N/A | 2458624 | 0 | 2458624 | 100% | 2458624 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
351 | Construction of 5Roof catchments and supply 10m3 Plastic tank at stikho youth polytechnic. | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 696710 | 696710 |  | N/A | 696710 | 0 | 696710 | 100% | 696710 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
368 | Nzowasco pipeline extension to Matulo | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1200000 | 1116520 | 1116520 |  | N/A | 1116520 | 0 | 1116520 | 100% | 1116520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
411 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1421260 | 1421260 |  | N/A | 1421260 | 0 | 1421260 | 100% | 1421260 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
516 | Protection of 8 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1300000 | 1116520 | 1116520 |  | N/A | 1116520 | 0 | 1116520 | 100% | 1116520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
517 | Drilling of Borehole and equipping with handpump at Sirwa | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1881065 | 1881065 |  | N/A | 1881065 | 0 | 1881065 | 100% | 1881065 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
595 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1421260 | 1421260 |  | N/A | 1421260 | 0 | 1421260 | 100% | 1421260 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
596 | Miendo piped scheme | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2363240 | 2363240 |  | N/A | 2363240 | 0 | 2363240 | 100% | 2363240 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
4 | Construction of Bokoli ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Bokoli ward office constructed | 3111504 | Construction of non- residential buildings | Webuye West | Bokoli | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43060 | 9500000 | 8960963 | 9500000 | County Government of Bungoma | - | 8960963 | - | 8960963 | 100% | 8960963 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Construction of Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | Construction of 20 Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | To support growth of coffee farmers and enhance income generation | 20 Coffee drying tables constructed | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44900 | 44838 | 10000000 | 3087863.88 | 3100000 | County Government of Bungoma |  | 3087863.88 | 0 | 3087863.88 | 100% | 3087863.88 | 0 | 0 | Completed
| Construction of Coffee Drying Tables at Sirandafu FCS in Bokoli Ward | Construction of 20 Coffee Drying Tables at Sirandafu FCS in Bokoli Ward | To support growth of coffee farmers and enhance income generation | 20 Coffee Drying tables constructed at Sirandafu FCS | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 21/1/2024 | 21/5/2024 | 15/6/2024 |  | 1997000 | 2000000 | County Government of Bungoma |  | 1997000 | 0 | 1997000 | 100% | 1997000 | 0 | 0 | Completed
46 | Proposed installation and commissioning of 3NO. 15M high solar powered floodlights | installation of M M high | promotion of MSMEs and security | Solar flood lights installed | 1358968/2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Project is complete | Complete and in use | 3000000 | 2909990 |  | CGB | [8 empty] | Complete | 100 | 3
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye |  |  |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A |  |  |  |  | Webuye West | Bokoli |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of |  |  |  |  | Webuye West | Bokoli |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
137 | Renovation of Matisi market | [5 empty] | Webuye West | Bokoli |  |  |  | Dynamic General Construction | 2016/17 |  | Complete |  | 12422753.2 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights |  |  |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
53 | Construction of 4NO.Doors Pit Latrines with urinal at Khaoya Recreational Centre. | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Kanduyi | Bukembe west |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 13/2/2024 |  |  | 800000 | 697650 | 697650 | CGB |  | 697650 | 0 | 0 | 0% | 0 |  | 697650 | On-going | 92 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
97 | Construction Of 2no Door Pit Latrines At Matumbufu primary school |  |  | 2No. Door pit latrines constructed |  |  | Kanduyi | Bukembe west |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 500000 | 495820 | 495820 | CGB |  | 495820 | 0 |  | 0% |  |  | 495820 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
196 | Construction Of Namirembe Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Kanduyi | Bukembe west |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 3500000 | 3321729.6 | 3321729.6 | CGB |  | 3321729.6 | 0 | 3321729.6 | 100% | 3321729.6 |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes
197 | Construction of 2no Ecosan pit latrines at Ndengelwa and Ekitale Markets | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Ecosan pit latrines constructed |  |  | Kanduyi | Bukembe west |  |  | WBPSPCU | Health & Sanitation | 2018-2019 | [6 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes
215 | Purchase Of Land For Namirembe Dispensary | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services in the area | acres of land purchased |  |  | Kanduyi | Bukembe west |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2000000 | 1200000 | 1200000 | CGB |  | 1200000 | 0 |  | 0% |  |  | 1200000 | Complete and in use | [6 empty] | No | complete | Financial | Yes
216 | Completion Of Ndengelwa Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries completed |  |  | Kanduyi | Bukembe west |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1169707 | 1344086.2 | 1344086.2 | CGB |  | 1344086.2 | 0 | 1343297.4 | 99.94% | 1343297.4 |  | 788.8 | Complete and in Use | [6 empty] | No | complete | Financial | Yes
283 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
284 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
472 | Periodic Maintenance of Mabanga - Ekitale Centre Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43967 |  | 11899433 | 11899433 | 11899433 | County Government of Bungoma |  | 11899433 |  | 11899433 |  | 11899433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
473 | Upgrading of Makotelo - Namiremembe Market Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43970 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
474 | Periodic Maintenance of Kisuluni - Serikali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43961 |  | 4665056 | 4665056 | 4665056 | County Government of Bungoma |  | 4665056 |  | 4665056 |  | 4665056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
475 | Periodic Maintenance of Kwa Mukunga - Nalutiri Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43971 |  | 4665056 | 4665056 | 4665056 | County Government of Bungoma |  | 4665056 |  | 4665056 |  | 4665056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
476 | Periodic Maintenance of Roads In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43972 |  | 4665056 | 4665056 | 4665056 | County Government of Bungoma |  | 4665056 |  | 4665056 | 93.12% | 4665056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
477 | Periodic Maintenance of Mabanga-Ekitale Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43963 |  | 11899433 | 11899433 | 11899433 | County Government of Bungoma |  | 11899433 |  | 11899433 | 97.31% | 11899433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
663 | Drainage Works In Kanduyi And Bumula Sub-Counties(Lot 2) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 | 96.54% | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
699 | Periodic Maintenance of Makayo - Matumbufu Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44326 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 |  | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
700 | Construction of Lutaso - Maniafu Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44336 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 |  | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
701 | Construction of Lutaso - Matumbufu Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44326 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 |  | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
702 | Periodic Maintenance of Roads In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44335 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 | 100.0% | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1034 | Periodic Maintenance of Muyayi - Noco Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44692 | 44723 | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 |  | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1035 | Periodic Maintenance of Bishop Siabuta Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44693 | 44724 | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 |  | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1036 | Periodic Maintenance of Puloti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44692 | 44723 | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 |  | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1037 | Upgrading of Lumoro - Namirembe Dispensary | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44698 | 44729 | 9072423.8 | 9072423.8 | 9072423.8 | County Government of Bungoma |  | 9072423.8 |  | 9072423.8 |  | 9072423.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1038 | Periodic Maintenance of Roads In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44696 |  | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 | 7.36% | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1039 | Spot Improvement Of Lumoro - Sichekereni Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 |  | 9072423.8 | 9072423.8 | 9072423.8 | County Government of Bungoma |  | 9072423.8 |  | 9072423.8 | 100.0% | 9072423.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1252 | Upgrading of Roads In Bukembe West Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44694 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1351 | Periodic Maintenance of Muyayi Primary Sch. - Bulafu - Misiko - Wilbroda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45062 |  | 3899572 | 3899572 | 3899572 | County Government of Bungoma |  | 3899572 |  | 3899572 |  | 3899572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1352 | Periodic Maintenance of Muyayi Primary School - Bulafu - Misiko - Wilbroda Road In Bukembe West | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45060 |  | 3899572 | 3899572 | 3899572 | County Government of Bungoma |  | 3899572 |  | 3899572 | 96.29% | 3899572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1606 | Periodic Maintenance of Ndengelwa - Marabi Road And Maniafu Road In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45422 |  | 5361336 | 5361336 | 5361336 | County Government of Bungoma |  | 5361336 |  | 5361336 | 100.0% | 5361336 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1607 | Periodic Maintenance of Marufutu - Khaoya Road, Khaoya Primary - Lifecare Road And Lambert - River Khalaba Road In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45435 |  | 4586196 | 4586196 | 4586196 | County Government of Bungoma |  | 4586196 |  | 4586196 | 99.82% | 4586196 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1608 | Periodic Maintenance of Gannaps Petrol Station - Ndengelwa Primary Road In Bukembe West Ward (1450749-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45434 |  | 5045565 | 5045565 | 5045565 | County Government of Bungoma |  | 5045565 |  | 5045565 | 100.0% | 5045565 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
33 | Proposed Erection And Completion Works Of 2no. Ecde Classroom At Kisuluni Primary School In Bukembe West Ward | Completion of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2781500 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2311226.6 | 83.09% | 2311226.6 | 470273.4 | 470273.4 | Complete and in use | 1
101 | Construction Of Community Resorce Centre At Ndengelwa | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 6000000 | 12705020 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 4406239.05 | 34.68% | 4406239.05 | 8298780.95 | 8298780.95 | complete and in use | 1
166 | Construction Of 1 Classroom At Namirembe Vtc And 2 Classrooms At Muyayi Vtc. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  |  |  |  | 3600000 | 3594460 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3594460 | 100% | 3594460 | 0 |  | complete and in use | 1
185 | Construction Of 1no. Ecde Classroom At Khaoya, Namirembe And Muyayi Vtc In Bukembe West Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3169708 | 3434230 | 3169708 | County Government of Bungoma | N/A | 3169708 |  | 3434230 | 100% | 3434230 | 0 |  | complete and in use | 100.0%
186 | Construction Of 1no. Ecde Classroom At Matumbufu And Chemche Primary Schools In Bukembe West Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3169708 | 3165858 | 3169708 | County Government of Bungoma | N/A | 3169708 |  | 3165858 | 100% | 3165858 | 0 |  | complete and in use | 100.0%
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | Water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 |  |  |  | FLLOCA | N/A |  | 0 |  | 100% |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
40 | Proposed Supply And Installation Of Combustion Chamber For Improved Stoves And Energy Centre For Research On Training Of Energy Technologies In Khasoko And Bukembe West Wards | 1.construction of combustion chamber (Kiln) for production of clean energy saving jikos. 2.Provision and Assemblying of production materials for the two burner / saving jikos. 3.Training of youths and women on installation of single /two burner jikos to the community. | To promote climate change mitigation and adaptation | Construction of combustion chambers in 2 wards | 2640599 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 6000000 | 5950005 | 5950005 | FLLOCA | IDA | 0 | 5950005 | 0 | 100% | 0 | 0 |  | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
46 | Lutaso-Matumbufu Water Project in Bukembe West Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 1 Water project upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 9000000 | 8550000 | 8550000 | CGB | N/A | 8550000 | 0 | 8550000 | 100% | 8550000 | 0 | 0 | Complete and in use | 100% complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
54 | Protection of 5no. Water springs in Bukembe West ward | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 1000000 | 968890 | 968890 | CGB | N/A | 968890 | 0 | 968890 | 100% | 968890 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
55 | Pipeline Extension at Namirembe and Khaoya in Bukembe West Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2768000 | 2768000 | CGB | N/A | 2768000 | 0 | 2768000 | 100% | 2768000 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
99 | Upgrading of Namirembe dispensary borehole in bukembe west ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 3800000 | 3581280 | 3581280 |  | N/A | 3581280 | 0 | 3581280 | 100% | 3581280 |  | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
139 | drilling and equipping of khaoya primary school | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4700000 | 4620396 | 4620396 |  | N/A | 4620396 | 0 | 4620396 | 100% | 4620396 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
140 | extension of pipeline in bukembe west ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2800000 | 2614524 | 2614524 |  | N/A | 2614524 | 0 | 2614524 | 100% | 2614524 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
180 | EXTENSION OF MAKOTELO AND LUTASO NZOWASCO PIPELINE IN WEST BUKEMBE WARD | Trenching ; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1950000 | 1921679.8 | 1921679.8 |  | N/A | 1921679.8 | 0 | 1921679.8 | 100% | 1921679.8 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
262 | LAYING OF PIPELINES IN BUKEMBE WEST WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1200000 | 1053280 | 1053280 |  | N/A | 1053280 | 0 | 1053280 | 100% | 1053280 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
10 | Construction of Bukembe West ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Bukembe West ward office constructed | 3111504 | Construction of non- residential buildings | Kanduyi | Bukembe west | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43300 | 9500000 | 10361120 | 9500000 | County Government of Bungoma | - | 10361120 | - | 10361120 | 100% | 10361120 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Purchase of tree seedlings for planting in institutions | Purchase of tree seedlings for planting at Hututu Primary, Bukembe S.A, Chief’s Office, Kongoli dispensary, Bukembe Mkt, and Nandolia Mkt | To improve the environment and create awareness on importance of trees | Tree seedlings purchased and distributed | 3111301 | Purchased of certified crop seed | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 43375 | 5000000 | 400000 | 400000 | County Government of Bungoma |  | 400000 | 0 | 400000 | 100% | 400000 | 0 | 0 | Completed
| Rehabilitation of cattle dips | Rehabilitation of cattle dips in Luuya, Kibisi, Bukembe, Lutaso, Tulumba, and Myanga Cattle Dips | To improve animal health and productivity | 6 Cattle dips rehabiliatated | 3110504 | Other infrastructure and civil works | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44136 | 44139 | 14/3/2020 | 5000000 | 3486950 | 3548016 | County Government of Bungoma |  | 3486950 | 0 | 3486950 | 100% | 3486950 | 0 | 0 | Completed
| Tree Planting in public schools | Tree Planting in public schools | To preserve the environment and create awareness of tree plantation | 3,230 tree supplied and planted | 3110599 | Ward Based projects | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 15/11/2020 | 15/2/2021 | 22/12/2021 | 500000 | 485250 | 500000 | County Government of Bungoma |  | 485250 | 0 | 485250 | 100% | 485250 | 0 | 0 | Completed
| Purchase of Dairy cows for women groups across the ward | Purchase of Dairy cows for women groups across the ward | To increase dairy production, value addition and income generation | 29 Dairy cows purchased | 3110599 | Ward Based projects | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 44287 | 44290 | 44472 | 3000000 | 2900000 | 3000000 | County Government of Bungoma |  | 2900000 | 0 | 2900000 | 100% | 2900000 | 0 | 0 | Completed
| Planting of assorted tree seedlings in public places | Planting of assorted tree seedlings in public places | To promote environmental awareness | Assorted seedlings planted in public institutions | 3111301 | Purchase of Certified Crop seed | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 45232 | 3000000 | 2999999 | 3000000 | County Government of Bungoma |  | 2999999 | 0 | 2999999 | 100% | 2999999 | 0 | 0 | Completed
| Provision of improved breeds of chicken | Provision of improved breeds (Indigenous poultry) chicken – day old chicks | To enhance production, productivity and income generation | 14 MOFAG beneffitted by each getting 575 breeds | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/3/2024 | 23/6/2024 | 28/5/2024 |  | 1387730 | 1447460 | Development partner | IFAD | 0 | 1387730 | 1387730 |  | 1387730 | 0 | 0 | Complete
| Upscaling production of grass seeds | Upscaling production of grass seeds by distrbuting 100 bags of 50kgs of organic fertilizer | To enhance productivity and income generation | 100 bags of 50kg organic fertilizer procured and distributed to 8 farmers. | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45242 | 45598 | 45444 |  | 144940 | 145 940 | Development partner | IFAD | 0 | 620398 | 144940 |  | 144940 | 0 | 0 | Complete
| Purchase and distribution of day old Chicks Rainbow Roosters | Purchase and delivery of 8,050 day old Chicks rainbow roosters to 14 MOFAG Indigenous chicken groups | To enhance poultry production and increase household incomes | 8,050 chicks purchased and delivered to 14 MOFAG indingeneous chicken groups | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 31/3/2024 | 31/6/2024 | 45510
37 | Proposed construction of 3 NO. bodaboda sheds | sheds construction of | promotion of MSMEs | Bodaboda sheds constructed | 1357197/2023-24 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Trade | MEGAWIDE BUILDING AND CIVILENGINEERING LIMITED | 2023/2024 |  | Completed | Complete and in use | 1000000 |  |  | CGB | [8 empty] | Complete | 100 | 3
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
86 | Installation of 2 No solar flood lights | lights of 2 No | [5 empty] | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Modular Development enterprise Limited | 2021/22 |  | Complete and in use |  | 1940000 |  |  | CGB
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Bukembe west |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
119 | Rennovation Of Staff Hause At Bulondo Dispensary |  |  | Staff quarters erected and renovated |  |  | Kanduyi | West Sang'alo |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 3500000 |  |  | CGB |  |  | 0 | 3499499 | #DIV/0! | 3499499 |  | -3499499 | Complete and in use | [6 empty] | No | complete | Financial | Yes
120 | Rennovation Of Ranje Dispensary |  |  | dispensaries renovated |  |  | Kanduyi | West Sang'alo |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2500000 | 2479000 | 2479000 | CGB |  | 2479000 | 0 | 2479688.1 | 100% | 2479688.1 |  | -688.1 | Complete and in use | [6 empty] | No | complete | Financial | Yes
256 | Completion Of Male Ward/Rehabilitation At Bulondo Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Male ward completed/Rehabilitated |  |  | Kanduyi | West Sang'alo |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 4150000 | 3900660 | 3900660 | CGB |  | 3900660 | 0 | 3899039.4 | 99.96% | 3899039.4 |  | 1620.6 | Complete and in use | [6 empty] | No | complete | Financial | Yes
9 | Upgrading of Ekitale-Sangalo-Namwacha-Bulondo R.Khalaba | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41661 | 41769 |  | 21492706 | 21492706 | 21492706 | County Government of Bungoma |  | 21492706 |  | 21492706 | 100.0% | 21492706 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
42 | Upgrading of Felix,Mang'Ale-Lutungu-Nyange | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41657 | 41780 |  | 6314112 | 6314112 | 6314112 | County Government of Bungoma |  | 6314112 |  | 6314112 | 100.0% | 6314112 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
49 | Upgrading of Nyangali-Javan | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41659 | 41781 |  | 4239858 | 4239858 | 4239858 | County Government of Bungoma |  | 4239858 |  | 4239858 | 100.0% | 4239858 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
50 | Upgrading of Kongoli-Babuya-Paile Spring Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41656 | 41781 |  | 4450572 | 4450572 | 4450572 | County Government of Bungoma |  | 4450572 |  | 4450572 | 100.0% | 4450572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
77 | Upgrading of Kcc-R.Khalaba-Ranje Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41658 | 41776 |  | 4106024.16 | 4106024.16 | 4106024.16 | County Government of Bungoma |  | 4106024.16 |  | 4106024.16 | 100.0% | 4106024.16 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
273 | Periodic Maintenance of Lancaster - Luyekhe - R. Chemululuchi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43230 |  | 3816968 | 3816968 | 3816968 | County Government of Bungoma |  | 3816968 |  | 3816968 |  | 3816968 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
274 | Periodic Maintenance of Namisi -Ndakaru - Bulondo Dispensary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43243 |  | 9846433.8 | 9846433.8 | 9846433.8 | County Government of Bungoma |  | 9846433.8 |  | 9846433.8 |  | 9846433.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
275 | Periodic Maintenance of Roads In West Sangalo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43243 |  | 9846433.8 | 9846433.8 | 9846433.8 | County Government of Bungoma |  | 9846433.8 |  | 9846433.8 | 86.56% | 9846433.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
276 | Periodic Maintenance of Roads In West Sangalo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43236 |  | 3816968 | 3816968 | 3816968 | County Government of Bungoma |  | 3816968 |  | 3816968 | 91.76% | 3816968 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
459 | Periodic Maintenance of Roads In West Sangalo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43478 | 43596 |  | 9806060 | 9806060 | 9806060 | County Government of Bungoma |  | 9806060 |  | 9806060 | 100.0% | 9806060 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
460 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
461 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
617 | Upgrading of Spot Improvement Of Mteremko - Ekitale Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43966 |  | 6818480 | 6818480 | 6818480 | County Government of Bungoma |  | 6818480 |  | 6818480 | 100.0% | 6818480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
684 | Periodic Maintenance of Ekitale Centre - Lwanda Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43975 |  | 6912440 | 6912440 | 6912440 | County Government of Bungoma |  | 6912440 |  | 6912440 |  | 6912440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
685 | Periodic Maintenance of Lwanda Girls - Kisochele River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43965 |  | 6780153 | 6780153 | 6780153 | County Government of Bungoma |  | 6780153 |  | 6780153 |  | 6780153 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
686 | Periodic Maintenance of Roads In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43966 |  | 6780153 | 6780153 | 6780153 | County Government of Bungoma |  | 6780153 |  | 6780153 | 98.31% | 6780153 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
687 | Periodic Maintenance of Ekitale Centre-Lwanda Junction | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43970 |  | 6912440 | 6912440 | 6912440 | County Government of Bungoma |  | 6912440 |  | 6912440 | 99.32% | 6912440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1020 | Periodic Maintenance of Bulondo Dispensary - Bulondo Secondary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44338 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 |  | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1021 | Periodic Maintenance of Luyekhe Junction - Kitinda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44338 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 |  | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1022 | Periodic Maintenance of Musikiti - Namanga Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44333 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 |  | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1023 | Periodic Maintenance of Roads In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44330 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 | 88.27% | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1342 | Periodic Maintenance of Mutoto Junction - Luyekhe - Namwacha Market - Kachomba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44698 |  | 7109466 | 7109466 | 7109466 | County Government of Bungoma |  | 7109466 |  | 7109466 |  | 7109466 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1343 | Periodic Maintenance of Roads In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44702 |  | 7109466 | 7109466 | 7109466 | County Government of Bungoma |  | 7109466 |  | 7109466 | 100.0% | 7109466 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1598 | Periodic Maintenance of Kamba Primary Junction - Chwele Bridge -Kachomba - Bulondo Market - Bumba Pri Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45068 |  | 11392012 | 11392012 | 11392012 | County Government of Bungoma |  | 11392012 |  | 11392012 |  | 11392012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1599 | Periodic Maintenance of Kamba Primary Junction - Chwele Bridge - Kachomba - Bulondo Mkt - Bumba Primary Road In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45064 |  | 11392012 | 11392012 | 11392012 | County Government of Bungoma |  | 11392012 |  | 11392012 | 99.61% | 11392012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1843 | Periodic Maintenance of Kona Mbaya - Buteyo Miti Park - Luanda Junction Road In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45429 |  | 5975508 | 5975508 | 5975508 | County Government of Bungoma |  | 5975508 |  | 5975508 | 85.14% | 5975508 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1844 | Periodic Maintenance of Musikiti - Lancaster - Kitinda Secondary Road In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45436 |  | 10141068 | 10141068 | 10141068 | County Government of Bungoma |  | 10141068 |  | 10141068 | 100.0% | 10141068 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1845 | Periodic Maintenance of Msikiti Junction - Lancaster - Kitinda Secondary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45429 |  | 10141068 | 10141068 | 10141068 | County Government of Bungoma |  | 10141068 |  | 10141068 |  | 10141068 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1846 | Periodic Maintenance of Kona Mbaya - Buteyo Miti Park - Luanda Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45428 |  | 5975508 | 5975508 | 5975508 | County Government of Bungoma |  | 5975508 |  | 5975508 |  | 5975508 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1847 | Periodic Maintenance of Khalaba Bridge - Luyekhe - Sang'Alo Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.3KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45434 |  | 3198468 | 3198468 | 3198468 | County Government of Bungoma |  | 3198468 |  | 3198468 |  | 3198468 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1848 | Periodic Maintenance of Khalaba Bridge - Luyekhe - Sang'Alo Junction In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.3KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45427 |  | 3198468 | 3198468 | 3198468 | County Government of Bungoma |  | 3198468 |  | 3198468 | 99.99% | 3198468 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
131 | Purchase Of 1/2 An Acre For Ndakaru E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for expansion of ECDE centre | One acres of Land for Ndakaru E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | West Sang'alo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43079 | 43051 | 23/2/2018 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 100% | 0 | 0 | [17 empty] | The project is 100% complete and not in use
195 | Purchase of 1 acre for Ndakaru E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Ndakaru E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | West Sang'alo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 |  |  |  | 350000 | 350000 | 350000 | CGB | N/A | 350000 |  | 350000 | 100% | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
98 | Construction of 2no ecde classroom and toilets at NAMWACHA and Siaka primary | Construction of ECDE classroom n tollet | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | West Sang'alo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3500000 | 3493490 | 3500000 | County Government of Bungoma | N/A | 3500000 | 0 | 0 | 0% | 0 | 3493490 | 3493490 | complete and in use | 1
219 | Construction Of 1no. Ecde Classroom And Pit Latrine At Siangwe, Bulondo Polytechnic, Sang'alo Ecde And Kamba Primary Schools In West Sangalo Ward | Construction of ECDE classroom and VTC workshop | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | West Sang'alo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2800000 | 3364200 | 2800000 | County Government of Bungoma | N/A | 2800000 |  | 3364200 | 100% | 3364200 | 0 |  | complete and in use | 100.0%
116 | Drilling of Kitinda Pri borehole and upgrading of Bulondo market,Ekitale dispensary and Kitinda Pri boreholes in west sangalo ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 2 boreholes rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 7000000 | 6874028 | 6874028 |  | N/A | 6874028 | 0 | 6874028 | 100% | 6874028 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
259 | Drilling of Borehole and protection of 4no. Water springs | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled and 4 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2800000 | 2776698 | 2776698 |  | N/A | 2776698 | 0 | 2776698 | 100% | 2776698 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
263 | DRILLING OF SANGALO MARKET BOREHOLE IN WEST SANGALO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 2000000 | 1925600 | 1925600 |  | N/A | 1925600 | 0 | 1925600 | 100% | 1925600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
329 | CONSTRUCTION AND DRILLING OF BOREHOLE IN WEST SANG’ALO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1922400 | 1922400 |  | N/A | 1922400 | 0 | 1922400 | 100% | 1922400 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
331 | CONSTRUCTION AND PROTECTION OF 5 WATER SPRINGS IN WEST SANG’ALO WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 1000000 | 900000 | 900000 |  | N/A | 900000 | 0 | 900000 | 100% | 900000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
332 | EXTENSION OF LWANDA WATER PROJECT PHASE II | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3500000 | 3481745 | 3481745 |  | N/A | 3481745 | 0 | 3481745 | 100% | 3481745 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
408 | Construction of 5 Roof catchments and Upgrading of Bulondo Health Centre Borehole | Construction of roof catchment and Improvement of a standard apron with drainage tunnel and replacement of 1 Afrdev hand pump | To enhance access to clean and safe drinking water | 1 borehole rehabilitated and 5 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2711581 | 2711581 |  | N/A | 2711581 | 0 | 2711581 | 100% | 2711581 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
442 | Protection of 4 water Springs. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs. constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 800000 | 619800 | 619800 |  | N/A | 619800 | 0 | 619800 | 100% | 619800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
512 | Protection of 4 water Springs. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 619800 | 619800 |  | N/A | 619800 | 0 | 619800 | 100% | 619800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
513 | Construction of 5 Roof catchments and Upgrading of Bulondo Health Centre Borehole | Construction of roof catchment; storage tank and water points; Improvement of a standard apron with standard drainage tunnel and replacement of 1 A fridev handpump | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 of borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3500000 | 3389476 | 3389476 |  | N/A | 3389476 | 0 | 3389476 | 100% | 3389476 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
583 | Construction of Lwanda community water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2200000 | 2094000 | 2094000 |  | N/A | 2094000 | 0 | 2094000 | 100% | 2094000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
584 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 of water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1445210 | 1445210 |  | N/A | 1445210 | 0 | 1445210 | 100% | 1445210 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
15 | Proposed installation and Commissioning of Solar backup system at Bulond Dispensary and installation of 10 No solar streetlights. | installation of system Dispensary backup installation of | Promotion of health care | Solar strret lights and solar back up system installed | BGM/CNTY/TEI/04/OT/2024-2025 1667818-2024-2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | GERRICK TECHNICAL AND HYGIENE SERVICE LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 6000000 |  |  | CGB | [8 empty] | Works to commence |  | 10
27 | Propose supply and installation of 16NO.Solar powered streetlights | supply of Solar of 16NO | promotion of MSMEs and security | solar powered street lights installed | 1362963-2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | GERRICK TECHNICAL AND HYGIENE SERVICES LIMITED | 2023/2024 |  | Completed | Complete and in use | 5000000 |  |  | CGB | [8 empty] | Complete | 100 | 16
51 | Proposed construction of county aggregation and industrial park in Bungoma county at Sang’alo | construction aggregation park industrial Bungoma county | Promotion of industrialization | County Aggregated Industrial Park Established | Bgm/cnty/tei/24/2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Industry | M/S Quest Civil Engineers Limited | 2023/24 |  | Works ongoing | Ongoing and not in use | 80000000 | 474153713.83 |  | CGB | [8 empty] | Works on schedule |  | 1
76 | Installation of 41 grid powered streetlights in Kanduyi Sub-county . | of streetlights Kanduyi streetlights in |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S Mbale Town Electro Works Umeme | 2021/22 |  | Complete and in use |  | 3116001 |  |  | CGB
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | West Sang'alo |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
13 | Construction of sentry and gate for Webuye health centre |  |  | Sentry and gate constructed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21-2-2024 |  |  | 1000000 | 947093.6 | 947093.6 | CGB |  | 947093.6 | 0 | 0 | 0% | 0 | 1485230 | 947093.6 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
19 | Erection and completion works for maternity wing at Butieli dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings erected and completed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 23-2-2024 |  |  | 3000000 | 2805668.8 | 2805668.8 | CGB |  | 2805668.8 | 0 | 0 | 0% | 0 | 193059 | 2805668.8 | On-going | 25 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
88 | Completion Of Maternity Wing And 2no. Door Pit Latrines Mayanja Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings and 2N0. door pit latrines completed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 3000000 | 2804500 | 2804500 | CGB |  | 2804500 | 0 | 2507370 | 89.41% | 2507370 |  | 297130 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
112 | Muji Centre Dispensary And Power Installation |  |  | power installed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 3300000 | 3496800 | 3496800 | CGB |  | 3496800 | 0 | 0 | 0% | 0 |  | 3496800 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No
145 | Completion Of Maternity Wing At Mayanja Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2500000 | 2804500 | 2804500 | CGB |  | 2804500 | 0 | 0 | 0% | 0 |  | 2804500 | Complete and in use | [6 empty] | No | complete | Financial | Yes
146 | Construction Of Toilets And Fencing Nabukhisa Dispensary | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors and Fencing | To develop and maintain infrastructure for enhanced access to quality health care services. | toilets constructed and dispensaries fenced |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 500000 | 483000 | 483000 | CGB |  | 483000 | 0 | 483000 | 100% | 483000 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
206 | Completion Of Lukhoba Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries constructed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 4200000 | 7150000 | 7150000 | CGB |  | 7150000 | 0 | 4200000 | 58.74% | 4200000 |  | 2950000 | complete and in use | [6 empty] | No | complete | Financial | Yes
207 | Construction Of Public Toilet At Sango Juntion,Nzoia Rc Ecde And Webuye Main Bus Park | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Public toilets constructed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 10000000 | 10,741,368 | 10,741,368 | CGB |  | 10,741,368 | 0 | 9,022,323 | 84% | 9,022,323 |  | 1719045 | complete and in use | [6 empty] | No | complete | Financial | Yes
234 | Construction Of A Maternity Wing At Lurare And Lukhoba Health Cente | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2000000 | 2243520 | 2243520 | CGB |  | 2243520 | 0 | 2243520 | 100% | 2243520 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
253 | Construction Of Nabukhisa Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2419344 | 2571511 | 2571511 | CGB |  | 2571511 | 0 | 2571511 | 100% | 2571511 |  | 0 | Complete and not use | [6 empty] | No | complete | Financial | Yes
302 | Renovation and Completion of Mayanja Dispensary | Walling,roofing,painting,fixing of doors and windows | To provide accessible and health services within the community | Dispensaries renovated/completed |  |  | Webuye East | Maraka |  |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42185 |  |  | 2216772 | 2216772 | CGB |  | 2216772 | 0 | 2216772 | 100% | 2216772 |  | 0 | Stalled and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
303 | Erection And Completion Of A Maternity Wing And Construction Of 4-Door Pit Latrine. | Walling,roofing,painting,fixing of doors and windows Digging of 20ft deep pit,flooring,walling,painting,roofing anf fitting doors | To provide accessible,affordable maternity services within the community | Maternity wings and 4No.door pit latrine erected and completed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2016/17 | 42856 | 42887 |  |  | 3939621 | 3939621 | CGB |  | 3939621 | 0 | 2814809 | 71.45% | 2814809 |  | 1124812 | Stalled and not in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
304 | Completion of Butieli Health Centre | Walling,roofing,painting,fixing doors and windows | To provide accessible,affordable maternity services within the community | health centres completed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2016/17 |  | 42887 |  |  | 3997708 | 3997708 | CGB |  | 3997708 | 0 | 3767390 | 94.24% | 3767390 |  | 230318 | Complete | [6 empty] | No | complete | Financial | Yes
341 | Construction of pit latrine | Digging of 20ft deep pit,flooring,walling,painting,roofing,fitting of doors | To enhance access to sanitary facilities at the market | pit latrines constructed |  |  | Webuye East | Maraka | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete and in use. | [6 empty] | No | complete | Financial | Yes
5 | Construction of 6 NO. door pit latrines and landscaping at Maraka stadium | Construction of 6NO. door pit latrines and landscaping | To improve sanitation | 6 NO.Pit latrines constructed | 3111504 | Other infrastructure and civil works | Webuye East | Maraka |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2023/24 | 45475 | 45481 |  | 5000000 | 4978550 | 0 | County Government of Bungoma | n/a | n/a | n/a | 0 | 0% | 0 | 4978550 | 4978550 | Ongoing | 0.7
44 | Upgrading of Kamasielo-Kikwechi | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41656 | 41772 |  | 4468842 | 4468842 | 4468842 | County Government of Bungoma |  | 4468842 |  | 4468842 | 100.0% | 4468842 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
72 | Upgrading of Gravelling Of Sango Market-Maraka Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41658 | 41770 |  | 11677308.2 | 11677308.2 | 11677308.2 | County Government of Bungoma |  | 11677308.2 |  | 11677308.2 | 100.0% | 11677308.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
74 | Construction of Box Culvert Over R.Sasuri | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41657 | 41782 |  | 5914062.8 | 5914062.8 | 5914062.8 | County Government of Bungoma |  | 5914062.8 |  | 5914062.8 | 100.0% | 5914062.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
83 | Construction of Makuselwa-Lugusi-Lugulu With Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41659 | 41770 |  | 32020002 | 32020002 | 32020002 | County Government of Bungoma |  | 32020002 |  | 32020002 | 100.0% | 32020002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
84 | Upgrading of Mayanja-Kikwechi-Bisuni Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41650 | 41779 |  | 8599080 | 8599080 | 8599080 | County Government of Bungoma |  | 8599080 |  | 8599080 | 100.0% | 8599080 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
391 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
392 | Periodic Maintenance of Roads In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43606 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.87% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
393 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
561 | Construction of Maliki Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43969 |  | 6777317 | 6777317 | 6777317 | County Government of Bungoma |  | 6777317 |  | 6777317 |  | 6777317 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
562 | Grading of Cpb-Public Works Road | Grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43968 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
563 | Upgrading of Masoni - Sambu Central - Mukhuyu Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43971 |  | 3731140 | 3731140 | 3731140 | County Government of Bungoma |  | 3731140 |  | 3731140 |  | 3731140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
564 | Construction of Wamoyo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43967 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
565 | Upgrading of Spot Improvement Of Masoni - Sambu Central -Mukhuyu Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43971 |  | 3731140 | 3731140 | 3731140 | County Government of Bungoma |  | 3731140 |  | 3731140 | 95.4% | 3731140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
566 | Construction of Roads In Maraka Ward With A Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43973 |  | 6777317 | 6777317 | 6777317 | County Government of Bungoma |  | 6777317 |  | 6777317 | 100.0% | 6777317 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
567 | Periodic Maintenance of Kibabii University - Matong'I Primary - River Mayanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
568 | Grading of Makutano Primary-Tuuti Market Road | Grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
569 | Upgrading of Salmond - Wetangula - Chemwa - Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43967 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
570 | Upgrading of Salmond - Wetangula - Chemwa - Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43968 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
571 | Construction of Tuuti Marakaru - West Nalondo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43970 | 44001 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
572 | Upgrading of Spot Improvement Of Salmond Wetangula Chemwa Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43962 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 93.08% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
573 | Periodic Maintenance of Roads In Tuuti-Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43966 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 93.96% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
574 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
637 | Routine Maintenance Of Roads In Webuye East And Webuye West Sub- Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
851 | Periodic Maintenance of Sajan - Lukhoba - Butchery Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44334 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 |  | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
852 | Periodic Maintenance of Sango - Maraka - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44328 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 |  | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
853 | Periodic Maintenance of Nangili - Ngachi Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44330 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 |  | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
854 | Periodic Maintenance of Muji River - Simala Bandu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
855 | Upgrading of St. Joseph - Reliance Road | Road improvement works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
856 | Periodic Maintenance of Roads In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44326 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 | 99.86% | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
857 | Periodic Maintenance of Talent Academy - Mayanja Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
858 | Periodic Maintenance of Gardinal Otunga Girls - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44331 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
859 | Periodic Maintenance of Bukusu Junction - Bukusu Primary - Kibabii River - River Mayanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44335 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
860 | Periodic Maintenance of Namikelo Junction - Simon Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44338 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
861 | Periodic Maintenance of Makutano - Tuuti Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44339 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
862 | Periodic Maintenance of Roads In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 98.41% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
863 | Periodic Maintenance of Talent Academy - Mayanja Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44327 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 95.06% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1158 | Periodic Maintenance of Sunrise - Muji River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44699 |  | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 |  | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1159 | Periodic Maintenance of Muji - Woodhill Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44697 | 44728 | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 |  | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1160 | Periodic Maintenance of Sikolia - Mukonambi - St. Teresa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44692 |  | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 |  | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1161 | Periodic Maintenance of Muji Sec - Pharis Maikuma - Showmap Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44704 | 44735 | 6099825.2 | 6099825.2 | 6099825.2 | County Government of Bungoma |  | 6099825.2 |  | 6099825.2 |  | 6099825.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1162 | Periodic Maintenance of Roads In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44698 |  | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 | 95.86% | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1163 | Routine Maintenance Of Muji Secondary - Pharis Maikuma - Showmap Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44701 |  | 6099825.2 | 6099825.2 | 6099825.2 | County Government of Bungoma |  | 6099825.2 |  | 6099825.2 | 100.0% | 6099825.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1164 | Periodic Maintenance of Kumbuka Junction - Kikwechi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44693 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1165 | Periodic Maintenance of Bukananachi Primary - Lumasa - Kibabii Booster | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44695 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1166 | Periodic Maintenance of Henry Posho Mill - Marofu Junction | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44700 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1167 | Periodic Maintenance of Lumasa - Matong'I Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44697 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1168 | Periodic Maintenance of Mayanja - Ekholo Junction - Henry Posho Mill - Peter Musemwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44694 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1169 | Periodic Maintenance of Makutano - Wanangali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44699 | 44730 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1170 | Periodic Maintenance of Roads In Tuuti - Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44692 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1171 | Routine Maintenance Of Makutano - Wanangali - Tuuti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44705 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1459 | Periodic Maintenance of Sunrise - Muchi River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45065 | 45096 | 2836780 | 2836780 | 2836780 | County Government of Bungoma |  | 2836780 |  | 2836780 |  | 2836780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1460 | Periodic Maintenance of Muji Primary - Muji River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45056 | 45087 | 2836780 | 2836780 | 2836780 | County Government of Bungoma |  | 2836780 |  | 2836780 |  | 2836780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1461 | Construction of Site And Service And National Estate Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45065 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1462 | Periodic Maintenance of Sunrise - Muji River Road, Muji Primary - Muji River Road In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45061 |  | 2836780 | 2836780 | 2836780 | County Government of Bungoma |  | 2836780 |  | 2836780 | 90.85% | 2836780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1463 | Periodic Maintenance of Bukananachi - Lumasa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45067 | 45098 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1464 | Periodic Maintenance of Diploma - Maliki Primary - Khalaba River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45068 | 45099 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1465 | Periodic Maintenance of Fana B - Sitoma Primary Main Junction - Kakichuma Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45059 | 45090 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1466 | Periodic Maintenance of Cardinal Otunga Girls - Good Shepherd - Namikelo Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45057 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1467 | Periodic Maintenance of Diploma (Dttc) - Maliki Primary - Khalaba River Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45064 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1468 | Periodic Maintenance of Fana B - Sitoma Primary - Main Junction - Kakichuma Road In Tuuti/ Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45056 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.82% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1469 | Periodic Maintenance of Bukananachi - Lumasa In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45068 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 98.17% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1470 | Framework Contracts For Maintenance Of Roads In Kanduyi And Bumula Sub Counties | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45070 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 326.25% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1695 | Periodic Maintenance of Makuma - Nangili - Muji River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45431 | 45462 | 6795709 | 6795709 | 6795709 | County Government of Bungoma |  | 6795709 |  | 6795709 |  | 6795709 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1696 | Periodic Maintenance of Sango - Maraka - River Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45426 | 45457 | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 |  | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1697 | Periodic Maintenance of Webuye River -Kizinji -Makuma - Nangili - Muji River | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45422 | 45453 | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 |  | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1698 | Periodic Maintenance of Mufunje - Boilo - Pombo - Kakimanyi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45434 | 45465 | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 |  | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1699 | Periodic Maintenance of Mufunje - Boilo - Pombo - Kakimanyi River Road, Sango - Maraka - River Nzoia - Kizinji - Webuye Road In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45434 |  | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 | 93.88% | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1700 | Periodic Maintenance of Webuye River - Kizinji - Makuma - Nangili - Muji River Road In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45433 |  | 6795709 | 6795709 | 6795709 | County Government of Bungoma |  | 6795709 |  | 6795709 | 99.81% | 6795709 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1701 | Periodic Maintenance of Mwalimu Wetungu - Kumbuka Junction - Nakayonjo Deb Primary - Mungeti River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45422 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1702 | Periodic Maintenance of Makutano Junction - Chemiati - A104 Malaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45435 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1703 | Periodic Maintenance of Hillview - Khalaba - Maliki Primary - Christ Community - Zuri Poa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45432 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1704 | Periodic Maintenance of Kimukung¦I - Onyango - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45434 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1705 | Periodic Maintenance of Tuuti - Namaloko - Kamukunda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45427 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1706 | Construction of Meli - Mafura Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45428 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1707 | Periodic Maintenance of Hillview - Khalaba - Maliki Primary - Christ Community - Zuri Poa Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45432 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.17% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1708 | Periodic Maintenance of Kimukung'I - Onyango - River Khalaba Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45423 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.96% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1709 | Periodic Maintenance of Makutano Junction - Chemiati - A104 Malaba Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45435 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.8% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1710 | Periodic Maintenance of Tuuti - Namaloko - Kamukunda Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45427 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 101.08% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1711 | Proposed Meli - Mafura Box Culvert In Tuuti/Marakaru Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45424 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 95.44% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1712 | Periodic Maintenance of Mwalimu Wetungu-Kumbuka Junction-Nakayonjo Deb-R.Mungeti Road In Tuuti Marakaru Ward (1465530-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45432 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.95% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1824 | Periodic Maintenance of Pius Osyanju Kibabii University-Kolikho Market-Gospel Church Road In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45430 |  | 4953362 | 4953362 | 4953362 | County Government of Bungoma |  | 4953362 |  | 4953362 | 99.99% | 4953362 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1825 | Periodic Maintenance of Pius Osyanju Kibabii University-Kolikho Market-Gospel Church Road In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45430 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.99% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1 | Review of Physical and development plan for Webuye Urban Area | Document review,Desktop research, Gaps analysis, Report Writing and formulation of new maps, Stakeholder engagement for new vision and direction of the urban area | To guide sustainable and inclusive growth of urban areas through land use,infrastructure development and improved service delivery | One Physical and land use plan for Webuye Urban Area developed | 2211311 | Development/Physical Planning | Webuye East | Maraka |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 15/5/2024 | 15/11/2024 | 15/11/2024 | 2600000 | 2567080 | 2567080 | CGB | N/A | 2567080 | 0 | 2567080 | 100% | 513416 | 2053664 | 0 | Completed | 1 | N/A | N/A | N/A | N/A | 0 | No |  |  | No |  | No |  |  |  | The project is 100% complete and in use
94 | Purchase Of Land For Catholic Market | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new market | One acre of Land For Catholic Market Purchased | 3110599 | Ward based projects | Webuye East | Maraka |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 26/6/2019 | 27/12/2019 | 16/1/2020 | 4500000 | 4150000 | 4150000 | CGB |  | 4150000 |  | 4150000 |  | 3900000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
177 | Purchase of land for Cheloti ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land forCheloti ECDE Purchased | 3110599 | Ward based projects | Webuye East | Maraka |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42286 | 42289 | 42014 | 260000 | 260000 | 260000 | CGB | N/A | 260000 |  | 260000 |  | 260000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
53 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Nzoia Pefa Primary School In Maraka Ward | Completion of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 1500000 | 1410000 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 0 | 0% | 0 | 1410000 | 1410000 | Complete and not in use | 1
87 | Construction Of 1no Ecde Classrooms At Maraka,Nang'eni,Mukhuyu,Nzoia Pefa,St.Joseph Rc,Sda Kakimanyi Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 9600000 | 9594200 | 9600000 | County Government of Bungoma | N/A | 9600000 | 0 | 7884776.75 | 82.18% | 7884776.75 | 1709423.25 | 1709423.25 | ongoing and not in use | 0.5
95 | Construction of 1 No.ECDE Classroom Maocho | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1500000 | 1495350 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1275171.75 | 85.28% | 1275171.75 | 220178.25 | 220178.25 | ongoing and not in use | 0.8
118 | Construction Of 1 No. Ecde Classroom At Ack And Pag Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3900000 | 2612796 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 2612796 | 100% | 2612796 | 0 | 0 | complete and in use | 1
150 | Proposed Erection And Completion Of 1 No. Ecde At Khamoto,Nabuyole, Muji And Webuye Sub-County Hq In Maraka Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 5062905.59 | 4726394.4 | 5062905.59 | County Government of Bungoma | N/A | 5062905.59 | 0 | 4726394.4 | 100% | 4460736.02 | 265658.38 | 0 | complete and in use | 1
162 | Proposed Erection And Completion Of 1 No. Ecde At Kikwechi, Makutano And Nabukhisa Primary Schools In Tuuti Marakaru Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3900000 | 3803200 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 3803200 | 100% | 3803200 | 0 | 0 | complete and in use | 1
181 | Construction Of 1no. Ecde Classroom At Namikelo, Kakichuma, Kimukungi, Bukananachi And Maliki Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 6000000 | 5970325 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 5970325 | 100% | 5970325 | 0 |  | complete and in use | 1
217 | Construction Of 1 Ecde Classroom At Lumasa, Buema,Bukusu, Munget, Sitama And Nakayonjo | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 7924270 | 7487800 | 7924270 | County Government of Bungoma | N/A | 7924270 |  | 7487800 | 100% | 7487800 | 0 |  | complete and in use | 100.0%
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | [7 empty] | FLLOCA | N/A |  | 0 |  | 100% |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
41 | Proposed Supply And Installation Of Combustion Chamber For Improved Stoves And Energy Centre For Research On Training Of Energy Technologies In Maraka And Kabuchai | 1.construction of combustion chamber (Kiln) for production of clean energy saving jikos. 2.Provision and Assemblying of production materials for the two burner / saving jikos. 3.Training of youths and women on installation of single /two burner jikos to the community. | To promote climate change mitigation and adaptation | Construction of combustion chambers in 2 wards | 2640599 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 6000000 | 5955480 | 5955480 | FLLOCA | IDA | 0 | 5955480 | 0 | 100% | 0 | 0 |  | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
75 | Extension of KOICA Pipeline in Tuuti Marakaru Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4994728 | 4994728 | CGB | N/A | 4994728 | 0 | 4994728 | 100% | 4994728 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
106 | Drilling and equipping of ward stadium borehole in Maraka ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2000000 | 1975046.4 | 1975046.4 |  | N/A | 1975046.4 | 0 | 1975046.4 | 100% | 1975046.4 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
114 | Drilling of Kabubero Catholic borehole,Rehabilitation of boreholes and well pumps and spring protection in tuuti/marakaru ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole drilled; 1 borehole rehabilitated and 1 water spring constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4000000 | 3852742.8 | 3852742.8 |  | N/A | 3852742.8 | 0 | 3852742.8 | 100% | 3852742.8 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
251 | DRILLING OF 3NO BOREHOLES IN TUUTI/MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 5000000 | 4892880 | 4892880 |  | N/A | 4892880 | 0 | 4892880 | 100% | 4892880 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
289 | DRILLING OF SERVICE ESTATE AND MAKUMA BOREHOLES IN MARAKA WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3900000 | 3830320 | 3830320 |  | N/A | 3830320 | 0 | 3830320 | 100% | 3830320 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
290 | DRILLING OF MARAKA WARD OFFICE AND LUKHOVA BOREHOLES IN MARAKA WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3990400 | 3990400 |  | N/A | 3990400 | 0 | 3990400 | 100% | 3990400 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
291 | DRILLING OF MUCHI YOUTH POLYTECHNIC AND NANGOTO BOREHOLES IN MARAKA WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3962560 | 3962560 |  | N/A | 3962560 | 0 | 3962560 | 100% | 3962560 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
327 | KIBABII-SASURI WATER PROJECT PHASE 11 | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 34000000 | 32430400 | 32430400 |  | N/A | 32430400 | 1 | 32430400 |  | 26917232 | 5513168 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
336 | DRILLING OF KAKICHUMBA AND MAYANJA BOREHOLES IN TUUTI MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3907483.2 | 3907483.2 |  | N/A | 3907483.2 | 0 | 3907483.2 | 100% | 3907483.2 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
337 | DRILLING OF BUTIELI DISPENDARY AND LUMASA BOREHOLE IN TUUTI MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3300000 | 3222080 | 3222080 |  | N/A | 3222080 | 0 | 3222080 | 100% | 3222080 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
344 | Protection of 9 water Springs and rehabilitation of borehole pump | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; improvement of a standard apron with drainage tunnel and replacement of Afridev hand pump | To enhance access to clean and safe drinking water | 9 water springs constructed and a borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 756670 | 756670 |  | N/A | 756670 | 0 | 756670 | 100% | 756670 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
386 | Construction of 5 Roof catchments and 50m3 Masonry tank at Mayanja market | Construction of roof catchment and erection of water tank plus provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 tank constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1545130 | 1545130 |  | N/A | 1545130 | 0 | 1545130 | 100% | 1545130 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
405 | Protection of 10 water Springs and 2 shallow wells. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed and 2 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2500000 | 2322090 | 2322090 |  | N/A | 2322090 | 0 | 2322090 | 100% | 2322090 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
420 | Protection of 10 water Springs, 2 Shallow wells, and rehabilitate borehole ( Hand pump) and 1 water supply | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump; improvement of a standard apron with drainage tunnel and replacement of Afridev hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed, 1 borehole rehabilitated and2 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1344481 | 1344481 |  | N/A | 1344481 | 0 | 1344481 | 100% | 1344481 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
462 | Piped water scheme in Maraka | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1478900 | 1478900 |  | N/A | 1478900 | 0 | 1478900 | 100% | 1478900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
510 | Protection of 9 water Springs and rehabilitation of borehole pump | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; improvement of a standard apron with drainage tunnel and replacement of Afridev hand pump | To enhance access to clean and safe drinking water | 9 water springs and 1 borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1513340 | 1513340 |  | N/A | 1513340 | 0 | 1513340 | 100% | 1513340 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
511 | Construction of 5 Roof catchments and 50m3 Masonry tank at Mayanja market | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and tank constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1545130 | 1545130 |  | N/A | 1545130 | 0 | 1545130 | 100% | 1545130 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
523 | Protection of 10 water Springs and Construction of 1Shallow wells | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed and 1 shallow well drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1928755 | 1928755 |  | N/A | 1928755 | 0 | 1928755 | 100% | 1928755 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
580 | Protection of 10 water Springs, 2 Shallow wells, and rehabilitate borehole ( Hand pump) and 1 water supply | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection;Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump;Improvement of a standard apron with drainage tunnel and replacement of Afrdev pump | To enhance access to clean and safe drinking water | 10 water springs constructed, 2 shallow wells constructed and 1 of borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3361203 | 3361203 |  | N/A | 3361203 | 0 | 3361203 | 100% | 3361203 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
581 | Construction of 2 roof Catchment | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 2 of roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 600000 | 518320 | 518320 |  | N/A | 518320 | 0 | 518320 | 100% | 518320 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
582 | Construction of 1 roof catchment Cardinal otunga | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 1 of roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 400000 | 373500 | 373500 |  | N/A | 373500 | 0 | 373500 | 100% | 373500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
585 | Protection of 10 water Springs and 2 shallow wells. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection;digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed and 2 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2322090 | 2322090 |  | N/A | 2322090 | 0 | 2322090 | 100% | 2322090 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
586 | Piped water scheme in Maraka | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1478900 | 1478900 |  | N/A | 1478900 | 0 | 1478900 | 100% | 1478900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
12 | Construction of Maraka ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Maraka ward office constructed | 3111504 | Construction of non- residential buildings | Webuye East | Maraka | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43159 | 9500000 | 9859968 | 9500000 | County Government of Bungoma | - | 9859968 | - | 9859968 | 100% | 9859968 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Supply of marking ink used in inspection of Meat | Supply of marking ink used in inspection of Meat for Bungoma, Webuye East & West, Kimilili and Sirisia Slaughtershouses | To promote meat safety and suitability for human consumption | Marking ink supplied for meat inspection | 2211007 | Agricultural materials, supplies and small equipment | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 3000000 | 1750000 | 2000000 | County Government of Bungoma |  | 1750000 |  | 1750000 | 100% | 1750000 | 0 | 0 | Completed
| Establishment of a County Dairy Processing Plant | Establishment of a County Dairy Processing Plant | To enhance indame generation among dairy farmers | 1 County dairy Processing plant established | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43800 | 44531 | 2021 | 160000000 | 157648000 | 60,000,000 (multi-year) | County Government of Bungoma |  | 157648000 | 0 | 147710110.37 | 94% | 147710110.37 | 9937889.63 | 9937889.63 | Completed
| Construction Coffee drying tables at Kimukung’i | Construction Coffee drying tables at Kimukung’i | To enhance intame generation among dairy farmers | Coffee drying tables constructed at Kimukung'i | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43384 | 43739 | 43586 | 3000000 | 1500000 | 1500000 | County Government of Bungoma |  | 1500000 | 0 | 1500000 | 100% | 1500000 | 0 | 0 | Completed
| Construction of Kimukung’i Coffee Warehouse | Construction of Kimukung’i Coffee Warehouse | To promote coffee production and income generation | 1 warehouse constructed | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 27/4/2020 | 27/4/2021 |  | 10000000 | 8623004 | 8000000 | County Government of Bungoma |  | 8623004 | 0 | 2600000 | 30% | 2600000 | 6023004 | 6023004 | Ongoing | 0.6
| Renovation of Auction Rings | Renovation of Auction Rings | To centralize and enhance access to animal trading services | 2 Auction rings renovated | 3110599 | Ward Based projects | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44835 | 44837 | 16/2/2022 | 4000000 | 3919176 | 4000000 | County Government of Bungoma |  | 3919176 | 0 | 3919176 | 100% | 3919176 | 0 | 0 | Completed
| Renovation of Slaughter Houses | Renovation of Bungoma and Webuye Slaughter Houses | To promote meat safety and suitability for human consumption | 2 Slaughterhouses renovated | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45119 | 45478 | 45477 | 5000000 | 4998582 | 5000000 | County Government of Bungoma |  | 4998582 | 0 | 4998582 | 100% | 4998582 | 0 | 0 | Completed
10 | Proposed installation and Commissioning of electrical works at catholic market | installation of electrical works | promotion of MSMEs and security | Electrical works installed | BGM/CNTY/TEI/09/OT/2024-2025 1667845-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 1500000 |  |  | CGB | [8 empty] | Works to commence |  | 1
33 | Proposed installation and commissioning of 5 NO. 15M high solar powered floodlights | installation of M M high | promotion of MSMEs and security | High solar powered flood light installed | 1358617/2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 5000000 |  |  | CGB | [8 empty] | Complete | 100 | 5
42 | Proposed supply, installation and commissioning of 30 NO. metallic stalls | Supply taled stalls | promotion of MSMEs | Mettalic stalls instaled | 1363449/2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Trade | SINAWA ENTER | 2023/2024 |  | Ongoing | Ongoing and not in use | 2500000 | 2400000 |  | CGB | [8 empty] | Project is ongoing |  | 30
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
104 | Proposed installation of 35 no. Grid powered street lights in Webuye East, Webuye West, Kimilili and Bumula Sub Counties | installation Grid lights East Kimilili street Kimilili and | [5 empty] | Maraka |  |  |  | M/S Rygeo Tech Solution | 2020/21 |  | Complete |  | 3232265 |  |  | CGG
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | Maraka |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
127 | Proposed supply and installation of 2 solar powered high flood mast lights | supply of powered powered high | [5 empty] | Maraka |  |  |  | Bishin Transporters and Construction Company Ltd | 2018/19 |  | Complete |  | 2478200 |  |  | CGG
131 | Development of Industrial park (Feasibility study) | study of Industrial | [5 empty] | Maraka |  |  |  | ICDC | 2018/19 |  | Feasibility study complete, the report to be disseminated to relevant stakeholders by ICDC upon full payment. |  | 9970000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
2 | Erection and completion of maternity wing at Ndalu health centre | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completion |  |  | Tongaren | NDALU/ TABANI |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 23-2-2024 |  |  | 5000000 | 4743000.2 | 4743000.2 | CGB |  | 4743000.2 | 0 | 0 | 0% | 0 |  | 4743000.2 | On-going | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
38 | Purchase of medical equipment for Ndalu dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Tongaren | NDALU/ TABANI |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21/5/24 |  |  | 2000000 | 1904200 | 1904200 | CGB |  | 1904200 | 0 | 0 | 0% | 0 | 1904200 | 1904200 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
8 | Purchase of tailoring machines for Ndalu Taban ward | Purchase of tailoring machines | To improve skills | 48 tailoring machines purchased |  |  | Tongaren | NDALU/ TABANI |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Gender and Culture | 2022/23 | 45235 | 45241 |  | 1000000 | 959040 | 959040 | County Government of Bungoma | n/a | n/a | n/a | 959040 | 100% | 959040 | 0 | 0 | Completed
236 | Periodic Maintenance of Roads In Ndalu/Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43241 |  | 12463185 | 12463185 | 12463185 | County Government of Bungoma |  | 12463185 |  | 12463185 | 97.74% | 12463185 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
255 | Periodic Maintenance of Milimani Pag - Soko Mjinga - Young Life Academy - T/Junction - Tali Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43243 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
256 | Periodic Maintenance of Maisha Mapya - Wanyama - Lavissa Cattle Dip Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43243 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
257 | Periodic Maintenance of Nuru Academy - Sawa Deb Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43234 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
418 | Periodic Maintenance of Roads In Ndalu Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43604 |  | 6965742 | 6965742 | 6965742 | County Government of Bungoma |  | 6965742 |  | 6965742 | 100.0% | 6965742 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
492 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
626 | Periodic Maintenance of Roads In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43963 |  | 6649062 | 6649062 | 6649062 | County Government of Bungoma |  | 6649062 |  | 6649062 | 88.27% | 6649062 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
627 | Periodic Maintenance of Bunyasi-Ndalu-Nangabo-Lunani Rc Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43962 |  | 7005021 | 7005021 | 7005021 | County Government of Bungoma |  | 7005021 |  | 7005021 | 96.92% | 7005021 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
628 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
654 | Periodic Maintenance of Lukhuna Junction - Agevi - Malari/Mutoro Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43971 | 44002 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
655 | Periodic Maintenance of Ndalu Rc - Bunyasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43962 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
928 | Periodic Maintenance of Roads In Ndalu Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44336 |  | 3784105.6 | 3784105.6 | 3784105.6 | County Government of Bungoma |  | 3784105.6 |  | 3784105.6 | 100.0% | 3784105.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
967 | Periodic Maintenance of Nuru Academy - Sawa Deb Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
968 | Periodic Maintenance of Oindo - Kaliwanga - Duka Moja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44328 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1260 | Periodic Maintenance of Roads In Ndalu- Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44705 |  | 10384811.2 | 10384811.2 | 10384811.2 | County Government of Bungoma |  | 10384811.2 |  | 10384811.2 | 100.0% | 10384811.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1261 | Routine Maintenance Of Prof. Sifuna - Tabani - Sis Metrine Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 |  | 7251305 | 7251305 | 7251305 | County Government of Bungoma |  | 7251305 |  | 7251305 | 97.74% | 7251305 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1300 | Periodic Maintenance of Dr. Kisia Musangura Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44699 | 44730 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1301 | Periodic Maintenance of Saidi - Ligodi - Nyabera - Chege - Charles - Ibrahim - Georgina Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44697 | 44728 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1302 | Periodic Maintenance of Prof. Sifuna - Tabani - Sis Metrine Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44705 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1303 | Periodic Maintenance of Omindo - Duka Moja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44697 | 44728 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1304 | Routine Maintenance Of Omindo - Duka Moja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44704 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 95.51% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1523 | Periodic Maintenance of Namunwa - Bunyasi - Glory Academy - Musese - Faith Academy Road In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45060 |  | 4639861 | 4639861 | 4639861 | County Government of Bungoma |  | 4639861 |  | 4639861 | 89.38% | 4639861 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1524 | Periodic Maintenance of Sinoko Primary School Road In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45069 |  | 2811787 | 2811787 | 2811787 | County Government of Bungoma |  | 2811787 |  | 2811787 | 100.0% | 2811787 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1551 | Periodic Maintenance of Namunwa - Bunyasi - Glory Academy - Musese Faith Academy Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45061 | 45092 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1801 | Periodic Maintenance of Omido - Mwangi - Minyali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45430 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1802 | Periodic Maintenance of Omindo - Mwangi Minyali - God'S Favor Filling Station - Sawa Road In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45436 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
96 | Purchase Of 5acre Land For Expansion Of Ndalu Market | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of Market | Five acres of Land For Expansion Of Ndalu Market Purchased | 3110599 | Ward based projects | Tongaren | NDALU/ TABANI |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 |  |  |  | 2000000 | 1800000 | 1800000 | CGB |  | 1800000 |  | 1800000 |  |  |  |  | Stalled | 0 | [14 empty] | The project is staled due Lack of documentations(Title deed)
99 | Purchase of one acre of land for shikuku primary school | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of ECDE centre | One acre of Land for shikuku primary school Purchased | 3110599 | Ward based projects | Tongaren | NDALU/ TABANI |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 |  |  |  | 1000000 | 900000 | 900000 | CGB |  | 900000 |  | 900000 |  |  |  |  | Stalled | 0 | [14 empty] | The project is staled due Lack of documentations(Title deed)
149 | Purchase of land for Buyofu ECDE centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Buyofu ECDE Purchased | 3110599 | Ward based projects | Tongaren | NDALU/ TABANI |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 21/01/2017 | 21/03/2017 | 30/06/2017 | 1100000 | 1100000 | 1100000 | CGB | N/A | 1100000 |  | 1100000 |  | 1100000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
59 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Ndalu, Muliro, Taabani And Shikuku Primary Schools In Ndalu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 6000000 | 5784750 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 0 | 0% | 0 | 5784750 | 5784750 | ongoing, at walling stage. | 0.4
125 | Construction Of 1 No. Ecde Classroom And 2 No. Pit Latrine At Ngoya Buyofu, Tabani Fym, Sawa, Minyali, Kiminini And Sinoko Primary Schools And Tabani Vtc. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 10000000 | 9587260 | 10000000 | County Government of Bungoma | N/A | 10000000 | 0 | 4916511.55 | 51.28% | 4916511.55 | 4670748.45 | 4670748.45 | complete and in use | 1
159 | Proposed Erection And Completion Of 1 No. Ecde At Musembe And Mapera Primary Schools In Ndalu Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 2580910.18 | 2339880 | 2580910.18 | County Government of Bungoma | N/A | 2580910.18 | 0 | 2339880 | 100% | 2339880 | 0 | 0 | complete and in use | 1
210 | Construction Of 1no. Ecde Classroom And Pit Latrine At Musangura And Nzoia Primary Schools In Ndalu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3000000 | 3536770 | 3000000 | County Government of Bungoma | N/A | 3000000 |  | 3536770 | 100% | 3536770 | 0 |  | complete and in use | 100.0%
44 | Construction and Protection of 10no. Water Springs in Ndalu ward | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2500000 | 2042760 | 2042760 | CGB | N/A | 2042760 | 0 | 2042760 | 100% | 2042760 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
83 | Muliro Water Project In Ndalu Taban Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Water project constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4500000 | 4270585 | 4270585 | CGB | N/A | 4270585 | 0 | 4270585 | 100% | 0 | 4270585 | 0 | Work in progress | 15% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
135 | Tabani secondary water project in Ndalu Tabani ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4000000 | 3813840 | 3813840 |  | N/A | 3813840 | 0 | 3813840 | 100% | 3813840 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
205 | CONSTRUCTION AND PROTECTION OF 10 NO. WATER SPRINGS IN NDALU- TABANI WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2000000 | 1856348 | 1856348 |  | N/A | 1856348 | 0 | 1856348 | 100% | 1856348 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
206 | REHABILITATION AND UPGRADING OF NDALU MARKET WATER PROJECT IN NDALU / TABAN WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 800000 | 759200 | 759200 |  | N/A | 759200 | 0 | 759200 | 100% | 759200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Purchase of chicken for farmer groups | Purchase and delivery of 4,000 chicken for farmer groups in Ndalu Tabani Ward | To enhance poultry production and increase household incomes | 4,000 chicken birds purchased and delivered to farmer groups | 3110599 | Ward Based projects | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44166 | 44169 | 18/3/2020 | 3000000 | 3000000 | 3000000 | County Government of Bungoma |  | 3000000 | 0 | 3000000 | 100% | 3000000 | 0 | 0 | Completed
| Purchase of drip irrigation kits for farmer groups (Ward Based) | Purchase and delivery of drip irrigation kits for farmer groups (Ward Based) | To enhance production, productivity and income generation | Assorted drip irrigation kits purchased and delivered | 3110599 | Ward Based projects | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 43952 | 43955 | 30/3/2020 | 4000000 | 3185000 | 3, 381,882 | County Government of Bungoma |  | 3185000 | 0 | 3185000 | 100% | 3185000 | 0 | 0 | Completed
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 100% | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 100% | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 100% | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 100% | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 100% | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 100% | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 100% | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 100% | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 73% | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
35 | Purchase of medical equipment for Eluya dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 20/5/24 |  |  | 2000000 | 1890125 | 1890125 | CGB |  | 1890125 | 0 | 0 | 0% | 0 |  | 1890125 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
134 | Constuction Of Male And Female Ward At Mukuyuni Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | male and female wards constructed |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2500000 | 2904700 | 2904700 | CGB |  | 2904700 | 0 | 2904700 | 100% | 2904700 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
135 | Construction Of Maternity Wing And 4door Pit Latrine At Mukuyuni Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2425000 | 2425000 | CGB |  | 2425000 | 0 | 2255239 | 93% | 2255239 |  | 169761 | Complete and in use | [6 empty] | No | complete | Financial | Yes
136 | Expansion Of Eluhya Dispansary Construction Of Pit Latrine Electricity Connection And Fencing | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries expanded |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2869955 | 2869955 | CGB |  | 2869955 | 0 | 2869955 | 100% | 2869955 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
239 | Erection And Completion Of Eluuya And Mukuyuni Dispensaries | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Tongaren | Milima |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 4800000 | 4729946.4 | 4729946.4 | CGB |  | 4729946.4 | 0 | 4729946.4 | 100% | 4729946.4 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
313 | Equipping of Lukhokhwe Dispensary. | Equipping of Lukhokhwe Dispensary with drugs and medical equipment | To provide accesswible health services within the community | dispensaries equipped |  |  | Tongaren | Milima |  |  | Ward Based | Health & Sanitation | 2015/16 |  | 42430 |  |  | 386335 | 386335 | CGB |  | 386335 | 0 | 386335 | 100% | 386335 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
315 | Purchase of one acre of land | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health facilities. | acres of land purchased |  |  | Tongaren | Milima | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
401 | Periodic Maintenance of Roads In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43481 | 43608 |  | 3946668 | 3946668 | 3946668 | County Government of Bungoma |  | 3946668 |  | 3946668 | 96.07% | 3946668 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
492 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
590 | Periodic Maintenance of Naitiri Slaughterhouse Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43963 | 43994 | 8399171 | 8399171 | 8399171 | County Government of Bungoma |  | 8399171 |  | 8399171 |  | 8399171 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
591 | Periodic Maintenance of Roads In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43969 |  | 8399171 | 8399171 | 8399171 | County Government of Bungoma |  | 8399171 |  | 8399171 | 30.05% | 8399171 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
598 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
883 | Periodic Maintenance of Maliki S.A - Wabukhonyi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44329 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
884 | Periodic Maintenance of Kwa Area - Nabing'Eng'E Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44326 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1191 | Construction of Walubengo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44691 |  | 6165151 | 6165151 | 6165151 | County Government of Bungoma |  | 6165151 |  | 6165151 |  | 6165151 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1192 | Periodic Maintenance of Bondeni - Utubora - Mukuyuni Girls Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44698 | 44729 | 15566963.73 | 15566963.73 | 15566963.73 | County Government of Bungoma |  | 15566963.73 |  | 15566963.73 |  | 15566963.73 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1193 | Periodic Maintenance of Namuininia - Munialo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44703 | 44734 | 15566963.73 | 15566963.73 | 15566963.73 | County Government of Bungoma |  | 15566963.73 |  | 15566963.73 |  | 15566963.73 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1194 | Periodic Maintenance of Maliki Pag - Maliki School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44700 | 44731 | 5146618 | 5146618 | 5146618 | County Government of Bungoma |  | 5146618 |  | 5146618 |  | 5146618 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1195 | Periodic Maintenance of Roads In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44704 |  | 15566963.73 | 15566963.73 | 15566963.73 | County Government of Bungoma |  | 15566963.73 |  | 15566963.73 | 78.48% | 15566963.73 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1196 | Upgrading of Roads In Milima Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44692 |  | 6165151 | 6165151 | 6165151 | County Government of Bungoma |  | 6165151 |  | 6165151 | 48.66% | 6165151 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1197 | Routine Maintenance Of Maliki P.A.G - Maliki Secondary School | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44695 |  | 5146618 | 5146618 | 5146618 | County Government of Bungoma |  | 5146618 |  | 5146618 | 100.0% | 5146618 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1734 | Periodic Maintenance of Namboko Primary - Mbakalo River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45430 | 45461 | 4586013 | 4586013 | 4586013 | County Government of Bungoma |  | 4586013 |  | 4586013 |  | 4586013 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1735 | Periodic Maintenance of Festo - Hamsini - Wangala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45433 | 45464 | 7342408.5 | 7342408.5 | 7342408.5 | County Government of Bungoma |  | 7342408.5 |  | 7342408.5 |  | 7342408.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1736 | Periodic Maintenance of Mama Agoi Road - Wataka Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45425 | 45456 | 7342408.5 | 7342408.5 | 7342408.5 | County Government of Bungoma |  | 7342408.5 |  | 7342408.5 |  | 7342408.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1737 | Periodic Maintenance of Mama Agoi - Wataka Road And Festo - Hamusini - Wangala Road In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45429 |  | 7342408.5 | 7342408.5 | 7342408.5 | County Government of Bungoma |  | 7342408.5 |  | 7342408.5 | 100.0% | 7342408.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1738 | Periodic Maintenance of Namboko Primary - Mbakalo River Road In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45428 |  | 4586013 | 4586013 | 4586013 | County Government of Bungoma |  | 4586013 |  | 4586013 | 100.0% | 4586013 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
95 | Purchase Of 01 Acre Land For Auction Ring At Maliki Market | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new auction ring | One acre of Land For Auction Ring At Maliki Market Purchased | 3110599 | Ward based projects | Tongaren | Milima |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 26/6/2019 | 27/12/2019 | 16/1/2020 | 1500000 | 1200000 | 1200000 | CGB |  | 1200000 |  | 1200000 |  | 1099060 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
140 | Purchase of 1 acre of land for health centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of health centre | One acres of Land for a health centre Purchased | 3110599 | Ward based projects | Tongaren | Milima |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 20/07/2016 | 20/9/2016 | 24/8/2016 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 100% | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
56 | Proposed Completion Of Works For Lukhokhwe Vocational Training Center | Construction of VTC | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 0 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 |  | 0 | 0 | 0 | ongoing and not in use | Funds Channeled To Existing Project
121 | Construction Of 1 No. Ecde Classroom At Luuya Deb, Bilibili And Kegode Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4500000 | 4364390 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 4364390 | 100% | 4364390 | 0 | 0 | complete and in use | 1
153 | Proposed Erection And Completion Of Works For Lukhokhwe Vocational Training Centre In Milima Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 5500000 | 13983515.08 | 5500000 | County Government of Bungoma | N/A | 5500000 | 0 | 13983515.08 | 100% | 7755924.95 | 6227590.13 | 0 | ONGOING. At roofing level | 0.8
154 | Proposed Erection And Completion Of 1 No Ecde At Nabinge'nge Primary School In Milima Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1300000 | 1999980 | 1300000 | County Government of Bungoma | N/A | 1300000 | 0 | 1999980 | 100% | 1114500 | 885480 | 0 | complete and in use | 1
178 | Construction Of 1no Ecde Classroom At Mukhuyu, Milima Riverside And Mufupi Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 4500000 | 3908654.8 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 3908654.8 | 100% | 3908654.8 | 0 |  | complete and in use | 1
204 | Construction Of 1no. Ecde Classroom At Milima, Mukuyuni And Maliki Primary Schools In Milima Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4500000 | 3881352 | 4500000 | County Government of Bungoma | N/A | 4500000 |  | 3881352 | 100% | 3881352 | 0 |  | complete and in use | 100.0%
36 | Proposed Rehabilitation Of Rivers Kibisi, Magemo Dam, And Nabingenge Dam In Ndivisi, And Milima Wards | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers |  | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5916000 | 5820000 | 5820000 | FLLOCA | IDA | 0 | 5820000 | 0 | 100% | 0 | 0 |  | On going and not in use | 0.4 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
88 | Construction and Protection of 8no. Water Springs in Milima ward | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 Water springs constructed and equipped | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2000000 | 1997009.6 | 1997009.6 | CGB | N/A | 1997009.6 | 0 | 1997009.6 | 100% | 0 | 1997009.6 | 0 | Complete and in use | 100% complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
132 | Construction of Maliki Primary water project in Milima ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 6850000 | 6749526 | 6749526 |  | N/A | 6749526 | 0 | 6749526 | 100% | 6749526 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
133 | Upgrading of Mukuyuni Dispensary borehole and protection of 3no. Water springs in Milima ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and 3 water springs constructed and proctected | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4500000 | 4397339.6 | 4397339.6 |  | N/A | 4397339.6 | 0 | 4397339.6 | 100% | 4397339.6 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
154 | protection of 5no water springs in milima ward | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 1300000 | 1138656 | 1138656 |  | N/A | 1138656 | 0 | 1138656 | 100% | 1138656 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
266 | PROTECTION OF 4NO. WATER SPRINGS IN MILIMA WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 800000 | 709000 | 709000 |  | N/A | 709000 | 0 | 709000 | 100% | 709000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
317 | INSTALLATION OF SOLAR PUMPING UNIT AT MALIKI AND MAKUNGA BOREHOLES IN MILIMA WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded and solarised | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3500000 | 3113714 | 3113714 |  | N/A | 3113714 | 0 | 3113714 | 100% | 3113714 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
367 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1533538 | 1533538 |  | N/A | 1533538 | 0 | 1533538 | 100% | 1533538 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
398 | Central Division Water Project pipeline Extension. mfupi – Bilibili | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1000000 | 946990 | 946990 |  | N/A | 946990 | 0 | 946990 | 100% | 946990 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
401 | Central Division Water Project Drill a borehole at Mukuyuni market and equip with hand pump | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1468600 | 1468600 |  | N/A | 1468600 | 0 | 1468600 | 100% | 1468600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
413 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1435500 | 1435500 |  | N/A | 1435500 | 0 | 1435500 | 100% | 1435500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
450 | Pipeline Extention and Construction of Water project | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1300000 | 1175300.4 | 1175300.4 |  | N/A | 1175300.4 | 0 | 1175300.4 | 100% | 1175300.4 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
474 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1533538 | 1533538 |  | N/A | 1533538 | 0 | 1533538 | 100% | 1533538 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
475 | Construction of 5 roof Catchments and 50m3 Masonry tank | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1956000 | 1956000 |  | N/A | 1956000 | 0 | 1956000 | 100% | 1956000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
476 | Drilling of borehole at Makunga Market | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1575000 | 1575000 |  | N/A | 1575000 | 0 | 1575000 | 100% | 1575000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
477 | Upgrading of Mukuyuni Makunga pipeline | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2700000 | 2598720 | 2598720 |  | N/A | 2598720 | 0 | 2598720 | 100% | 2598720 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
555 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | No. 10 of water springs constructed | 3110599 | Other Infrastructure &Civil Works |  | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1435500 | 1435500 |  | N/A | 1435500 | 0 | 1435500 | 100% | 1435500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
556 | Central Division Water Project pipeline Extension. mfupi – Bilibili | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1000000 | 946990 | 946990 |  | N/A | 946990 | 0 | 946990 | 100% | 946990 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
557 | Central Division Water Project Drill a borehole at Mukuyuni market and equip with hand pump | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1468600 | 1468600 |  | N/A | 1468600 | 0 | 1468600 | 100% | 1468600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
16 | Construction of Milima ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Milima ward office constructed | 3111504 | Construction of non- residential buildings | Tongaren | Milima | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2023/24 | 45300 | 45415 | - | 9500000 | 9453590 | 9500000 | County Government of Bungoma | - | 9453590 | - | 9453590 | 100% | 0 | 0 | 0 | Ongoing | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | Dite dispute delayed project implementation. No resolved.
| Supply and delivery of young dairy animals(Heifers) 18 to 24 months | Supply and delivery of young dairy animals(Heifers) 18 to 24 months | To enhance dairy production, value addition and income generation | 20 Dairy animals (heifers) supplied and delivered to farmer groups | 3110599 | Ward Based projects | Tongaren | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 2000000 | 1960000 | 2000000 | County Government of Bungoma |  | 1960000 | 0 | 1960000 | 100% | 1960000 | 0 | 0 | Completed
29 | Proposed Installation and commissioning of 5No. Solar powered Floodlight | Installation of Solar of 5No | promotion of MSMEs and security | Solar powered floodligts installed | 1358429-2023-24 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 5000000 |  |  | CGB | [8 empty] | Complete | 100 | 5
100 | Installation of 2No high mast flood lights solar powered | of mast lights mast flood | [5 empty] | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Eagle Power Services limited | 2021/22 |  | Complete and in use |  | 786500 |  |  | CGB
101 | Construction of 4 No Bodaboda sheds | Of sheds streetlights | [5 empty] | Milima |  | Trade, Energy and Industrialization | Dept of Trade | Newark Holdings limited | 2021/22 |  | Complete and in use |  | 1192480 |  |  | CGB
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Milima |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
110 | Construction of 4 no. Bodaboda sheds at Maliki stage,Nabingenge stage,Wabukhonyi stage and Lukhokhwe stage | of sheds stage Wabukhonyi Maliki Wabukhonyi stage | [5 empty] | Milima |  |  |  | Namwaya Enterprises Ltd | 2019/20 |  | Complete |  | 1080000 |  |  | CGG
130 | Construction of 3 boda boda sheds | Of sheds streetlights | [5 empty] | Milima |  |  |  | Dry Logistic ltd | 2018/19 |  | Complete |  | 897880.59 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Milima |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 100% | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 100% | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 100% | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 100% | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 100% | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 100% | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 100% | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 100% | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 100% | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 100% | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 100% | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 100% | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 100% | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 100% | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 100% | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 100% | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 100% | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 100% | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 100% | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 100% | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 100% | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 100% | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 100% | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 100% | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 100% | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 100% | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 100% | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 100% | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 100% | 79184782 | 0 | 0 | Completed