611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
914 | Periodic Maintenance of Samoya Dispensary - Wekelekha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44326 |  | 8255763.5 | 8255763.5 | 8255763.5 | County Government of Bungoma |  | 8255763.5 |  | 8255763.5 |  | 8255763.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Already done in previous years
915 | Spot Imptovement Of Samoya Dispensary - Wekelekha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 44207 | 44340 |  | 8255763.5 | 8255763.5 | 8255763.5 | County Government of Bungoma |  | 8255763.5 |  | 8255763.5 | 96.78% | 8255763.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Done in previous years
924 | Upgrading of Roads In Musikoma Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44333 |  | 11516799 | 11516799 | 11516799 | County Government of Bungoma |  | 11516799 |  | 11516799 | 42.84% | 11516799 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1223 | Periodic Maintenance of Mlimani - Tulienge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44691 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1224 | Periodic Maintenance of Nambaya Dam - Tulienge Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.533044/34.5554346 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44696 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Done
1225 | Periodic Maintenance of Moca - Millenium - Sio Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.3455641/0.56094 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | may 2022 | 44705 | june 2022 | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | A section of a road has land dispute
1226 | Periodic Maintenance of Moca - Sio Secondary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.56094/34.55641 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | may 2022 | 44697 | june 2022 | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | quality of murram used was poor and never lasted.now almost impassable
1227 | Periodic Maintenance of Siritanyi Dispensary - Siritanyi Children Home Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.570514/34.534895,0.578964/34.518291 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44700 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 |  | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs murraming
1228 | Periodic Maintenance of Sio - Muanda Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.55984/34.54163 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 17/2/2024 | 44702 | march2024 | 9953617.8 | 9953617.8 | 9953617.8 | County Government of Bungoma |  | 9953617.8 |  | 9953617.8 |  | 9953617.8 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | has no bridge,partialy usable,work poorly done
1229 | Periodic Maintenance of Sacret - Ack - Namisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.5867/34.53,0.578970/34.518285 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44694 |  | 9953617.8 | 9953617.8 | 9953617.8 | County Government of Bungoma |  | 9953617.8 |  | 9953617.8 |  | 9953617.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need murraming, the bridge was washed away
1230 | Periodic Maintenance of Roads In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44702 |  | 9953617.8 | 9953617.8 | 9953617.8 | County Government of Bungoma |  | 9953617.8 |  | 9953617.8 | 100.0% | 9953617.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1231 | Periodic Maintenance of Roads In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44704 |  | 7770840 | 7770840 | 7770840 | County Government of Bungoma |  | 7770840 |  | 7770840 | 99.99% | 7770840 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1250 | Upgrading of Roads In Musikoma Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44698 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1507 | Periodic Maintenance of Bhulosi Market - Atemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45056 |  | 2150002 | 2150002 | 2150002 | County Government of Bungoma |  | 2150002 |  | 2150002 |  | 2150002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1508 | Periodic Maintenance of Bhulosi Market - Atemba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45070 |  | 2150002 | 2150002 | 2150002 | County Government of Bungoma |  | 2150002 |  | 2150002 |  | 2150002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1509 | Periodic Maintenance of Mwiruti Sec - Lavine Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45062 |  | 7216476 | 7216476 | 7216476 | County Government of Bungoma |  | 7216476 |  | 7216476 |  | 7216476 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good condition
1510 | Periodic Maintenance of Wambiya - Bustani - Sio Primary - Muslim Primary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.55754/34.55346 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | june 2023 | 45062 | june 2023 | 7216476 | 7216476 | 7216476 | County Government of Bungoma |  | 7216476 |  | 7216476 |  | 7216476 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Road is pathetic and impassable during rainny period
1511 | Periodic Maintenance of Mwiruti Sec - Lavine Junction - Wambiya - Bustani - Sio Primary - Muslim Primary Schools In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.55984/34.54163 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | june 2023 | 45065 | june 2023 | 7216476 | 7216476 | 7216476 | County Government of Bungoma |  | 7216476 |  | 7216476 | 98.34% | 7216476 | 0 | 0 | Stalled | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | its only two years yet the road is impassable,no drainage
1512 | Periodic Maintenance of Bulosi Mkt - Atemba Road In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45056 |  | 2150002 | 2150002 | 2150002 | County Government of Bungoma |  | 2150002 |  | 2150002 | 99.14% | 2150002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | work done was substandard
1762 | Periodic Maintenance of C33 (Dicece) - Marrell - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Musikoma | 0.516326/34.555004 0.51/34.549 0.521/34.553 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45422 |  | 2931238 | 2931238 | 2931238 | County Government of Bungoma |  | 2931238 |  | 2931238 |  | 2931238 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1763 | Periodic Maintenance of C33 Diocese-Marel-River Khalaba Road In Musikoma Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Musikoma |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45422 |  | 2931238 | 2931238 | 2931238 | County Government of Bungoma |  | 2931238 |  | 2931238 | 99.98% | 2931238 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | work done was substandard
179 | Purchase of land for Sacred ECDE centre. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | Zero point two five acres of Land for Sacred ECDE Purchased | 3110599 | Ward based projects | Kanduyi | Musikoma | 0.5930/34.520 | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42585 | 42588 | 42376 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 |  | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
194 | Purchase of land for Sacred ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Sacred E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | Musikoma | 0.5930/34.520 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 42125 | 42128 | 42251 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 | 1 | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
28 | Contruction of Pit latrine at Dicece | Construction of a pitlatrine. | To provide sanitation facilities | Pit latrine constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | 0.51654/34.54950 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3000000 | 2999670 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0 |  | 2999670 | 2999670 | Completed
90 | construction of 1 no. ECDE Cassroom at samoya, Musikoma, Walala, Muslim, and Siritanyi primary schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | La:0.5534213 Lo:34.5377808 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2020/2021 | 44409 | 30/6/2022 | 44866 | 7000000 | 6971878 | 7000000 | County Government of Bungoma | N/A | 7000000 | 0 | 6971878 | 1 | 6971878 | 0 | 0 | Complete | 1 | [14 empty] | No electricity, Poor workmanship
123 | Construction Of 1 No. Ecde Classroom And 2 No. Door Pit Latrine At St. Joseph Ack, Wekelekha And Namasanda Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2020/2021 | 44044 | 44414 | 44287 | 4200000 | 4044740 | 4200000 | County Government of Bungoma | N/A | 4200000 | 0 | 4044740 | 1 | 4044740 | 0 | 0 | Completed | 1 | [14 empty] | fencing needed
157 | Proposed Erection And Completion Of 1 No. Ecde At Namisi Primary School In Musikoma Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | 0.5798/43.51174 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2021 | 43864 | 44049 | 2022 | 1500000 | 1452580 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1452580 | 1 | 1452580 | 0 | 0 | complete and in use | 1 | [14 empty] | more classrooms needed
207 | Construction Of 3 Classrooms And Toilets At Namamuka Sio And Okanya Primary | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training | 2020/2021 | 44044 | 43410 | 44287 | 4500000 | 4410715 | 4500000 | County Government of Bungoma | N/A | 4500000 |  | 4410715 | 1 | 4410715 | 0 |  | Completed | 100.0% | [14 empty] | Done
2 | DRILLING AND UPGRADING OF SAMOYA DISPENSARY BOREHOLE AND WATER PIPELINE DISTRIBUTION | BOREHOLE DRILLING, RAISED STORAGE TANK INSTALLATION, SOLAR PANELS AND PUMP INSTALLATION, PIPE LAYING AND CONSTRUCTION OF A METRED WATER KIOSK | TO PROVIDE CLEAN AND SAFE DRINKING WATER TO SAMOYA PRIMARY AND SECONDARY SCHOOL, SAMOYA DISPENSARY AND COMMUNITY | BOREHOLE, RAISED WATER STORAGE TANK, LAID WATER PIPES | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | La:0.5548982 Lo:34.5360498 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2024/25 | 45893 | 15/4/2024 | 45985 | Ksh. 7,000,000 | Ksh. 7,000,000 | Ksh. 7,000,000 | CGB |  | Ksh. 7,000,000 | 0 | Ksh. 7,000,000 | 1 | 0 | 6838616 | 6838616 | COMPLETED | [6 empty] | NO |  | NON-PAYMENT BY COUNTY TREASURY FOR COMPLETED PROJECTS | NO | BUDGETARY CONSTRAINS | NO |  | NO | USABILITY OF THE PROJECT TO CITIZENS
5 | ROUTINE MAINTENANCE OF OLDREX - SIO PRIMARY JUNCTION - MUANDA BRIDGE ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.56094/34.55641 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 15/4/2024 | 15/4/2024 | 4126584 | 4126584 | 4126584 | CGB |  | 4126584 | 0 | 4126584 | 1 | 4112664 | 0 | 0 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL CHALLENGE OF SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY
15 | ROUTINE MAINTANANCE OF SILOBA PRI. JUNCTION - FORMER ASSISTANT CHIEF OFFICE - NGOLI RIVER ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.570134/34.534959,0.568665/34.534715,0.573007/34.536549 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2023/2024 | 45323 | 45302 | 45352 | 3121734 | 3121734 | 3121734 | CGB |  | 3121734 | 0 | 3121734 | 1 | 0 | 2617946 | 2617946 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | the road was poorly done
16 | ROUTINE MAINTENANCE OF SIRITANYI ASS. CHIEF OFFICE - KISAWAYI - NAMISI ECDE ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.578913/34.518405,0.578980/34.518295,0.578970/34.518285 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY | 2023/2024 | 45302 | 45302 | 2024 | 2537964 | 2537964 | 2537964 | CGB |  | 2537964 | 0 | 2537964 | 1 | 0 | 2432636 | 2432636 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | poor quality murram,poor compression,bridge washed away
17 | ROUTINE MAINTANANCE OF ELMAS - MUKOLWE - NAMASANDA RIVER ROAD | EARTH WORKS, DUMPING AND GRADING WORK | TO ENHANCE ACCESSIBILITY | GRAVEL ROAD | 3110504 | INFRASTRUCTURE AND CIVIL WORKS | Kanduyi | Musikoma | 0.533044/34.5554346 | AGRICULTURE, URBAN AND RURAL DEVELOPMENT | LANDS,URBAN,PHYSICAL PLANNING,HOUSING AND MUNICIPALITIES | BUNGOMA MUNICIPALITY |  | 45302 | 45302 |  | 3016464 | 3016464 | 3016464 | CGB |  | 3016464 | 0 | 3016464 | 1 | 0 | 2996512 | 2996512 | COMPLETED | [6 empty] | NO |  | ENVIRONMENTAL RISK I.E SOIL EROSION | NO | BUDGETARY CONSTRAINS | NO |  | NO | PROJECT UTILITY TO THE CITIZENRY | Done in previous years
12 | Upgrading of Siritanyi Dispensary and Namikelo Primary boreholes and pipeline extension in Musikoma/Tuuti Marakaru/Khalaba wards | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45544 | 45546 | 45546 | 10500000 | 10157172 | 10157172 | FLLOCA | N/A | 10157172 | 0 | 0 | 1 | 10157172 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not done in musikoma village
38 | Proposed Tree Growing Within Institutions In Khasoko, Kabula, Musikoma, Bukembe East, West Nalondo And Chesikaki Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Kanduyi | Musikoma | 0.533044/34.5554346 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7101000 | 6960000 | 6960000 | FLLOCA | IDA | 0 | 6960000 | 0 | 1 | 0 | 0 |  | Stalled | 0.2 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not done in musikoma village
97 | Drilling and Equipping of Walala and Siloba Primary Schools Boreholes in Musikoma ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and equipped | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | La:0.53918995 Lo:34.5385569 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 | 45200 |  | 2024 | 5000000 | 4473600 | 4473600 | CGB | N/A | 4473600 | 0 | 4473600 | 1 | 4473600 | 0 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | No water and Not functioning
108 | Upgrading of Namamuka Primary and Namisi primary boreholes in Musikoma ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.51546/34.54946 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 | 2022 |  | 2022 | 6000000 | 5912595.4 | 5912595.4 |  | N/A | 5912595.4 | 0 | 5912595.4 | 1 | 5912595.4 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | project failed,urgent intervension needed since water is a problem to the residents
202 | PROTECTION OF 4 NO. WATER SPRINGS IN MUSIKOMA WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.56216/34.54175 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 | aprill 2021 |  | aprill 2021 | 1000000 | 957600 | 957600 |  | N/A | 957600 | 0 | 957600 | 1 | 957600 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | commendable,has a court dispute risks of loosing the spring
258 | EXTENSION OF MUSIKOMA SECONDARY WATER PROJECT IN MUSIKOMA WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.533888/34.54984 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 | 15/3/2019 |  | 43898 | 2000000 | 1098763 | 1098763 |  | N/A | 1098763 | 0 | 1098763 | 1 | 1098763 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | water valves destroyed , the community can not access the water
333 | DRILLING OF BOREHOLES AND INSTALLATION OF PUMPING SYSTEM AT MUSIKOMA | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled and solarised | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4800000 | 4726639 | 4726639 |  | N/A | 4726639 | 0 | 4726639 | 1 | 4726639 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
334 | EXTENSION OF MUSIKOMA WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2499921 | 2499921 |  | N/A | 2499921 | 0 | 2499921 | 1 | 2499921 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
335 | CONSTRUCTION AND PROTECTION OF 5 NO.WATER SPRINGS IN MUSIKOMA WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.513437/34.53962 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 1000000 | 978500 | 978500 |  | N/A | 978500 | 0 | 978500 | 1 | 978500 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | The project is in use, and in good condition
341 | Construction of 5 Roof Catchment | Construction of 5 Roof Catchment | To enhance access to clean and safe drinking water | 5 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1599502 | 1599502 |  | N/A | 1599502 | 0 | 1599502 | 1 | 1599502 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
448 | Musikoma Pipeline Extension | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works |  | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3500000 | 3298561 | 3298561 |  | N/A | 3298561 | 0 | 3298561 | 1 | 3298561 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
509 | Musikoma Pipeline Extension | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3800000 | 3665068 | 3665068 |  | N/A | 3665068 | 0 | 3665068 | 1 | 3665068 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in musikoma village
579 | Protection of 9 water Springs, Construction of 1 shallow wells and Musikoma water project | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection;Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump;Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 9 water springs constructed, 1 shallow well constructed and KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Musikoma | 0.56094/34.55641 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 | 2014 |  | 2014 | 4000000 | 3938920 | 3938920 |  | N/A | 3938920 | 0 | 3938920 | 1 | 3938920 | 0 | 0 | Stalled | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | commendable though theft took place on projected fence
| Rehabilitation of Namasanda dam | Rehabilitation of Namasanda dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Kanduyi | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 15000000 | 9156000 | 9200000 | County Government of Bungoma |  | 9156000 |  | 9156000 | 1 | 9156000 | 0 | 0 | Complete
| Rehabilitation Of Namasanda Dam | Rehabilitation Of Namasanda Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Kanduyi | Musikoma | 0.533044/34.554346 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43009 | 43014 | 43074 | 15000000 | 9156000 | 9500000 | County Government of Bungoma |  | 9156000 |  | 9156000 | 1 | 9156000 | 0 | 0 | [15 empty] | No activity done
| Provision of improved breeds (meat goats) | Provision of 30 does and 3 Bucks to 3 elite breeders,2 in Bukembe East (BUKONONA SLCA) and 1 in Musikoma (MUSIKOMA SLCA) | To enhance production, productivity and income generation | 30 does and 3 Bucks purchased and issued to 3 elite breeders | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Musikoma | La:0.5360781 Lo:34.5010771 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | feb 2023 | 18/7/2024 | aprill 2023 |  | 961980 | 1029280 | Development partner | IFAD | 0 | 961980 | 961980 |  | 961980 | 0 | 0 | Completed | [15 empty] | done
| Provision of improved breeds of chicken | Provision of improved breeds (Indigenous poultry) chicken – day old chicks | To enhance production, productivity and income generation | 14 MOFAG beneffitted by each getting 575 breeds | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Musikoma | La:0.5360781 Lo:34.3010771 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 44958 | 23/6/2024 | 45200 |  | 1387730 | 1447460 | Development partner | IFAD | 0 | 1387730 | 1387730 |  | 1387730 | 0 | 0 | Completed | [15 empty] | done
| Upscaling production of grass seeds | Upscaling production of grass seeds by distrbuting 100 bags of 50kgs of organic fertilizer | To enhance productivity and income generation | 100 bags of 50kg organic fertilizer procured and distributed to 8 farmers. | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Musikoma | La:0.5360781 Lo:34.5010771 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | feb 2023 | 45598 | aprill 2023 |  | 144940 | 145 940 | Development partner | IFAD | 0 | 620398 | 144940 |  | 144940 | 0 | 0 | Not seen | [15 empty] | no evidence
| Purchase and distribution of day old Chicks Rainbow Roosters | Purchase and delivery of 8,050 day old Chicks rainbow roosters to 14 MOFAG Indigenous chicken groups | To enhance poultry production and increase household incomes | 8,050 chicks purchased and delivered to 14 MOFAG indingeneous chicken groups | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Musikoma | La:0.533044 Lo:34.5554346 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45711 | 31/6/2024 | 45200 | [12 empty] | not seen | [15 empty] | not given in musikoma village
4 | Proposed Construction and Commissioning of 4No. Bodaboda Sheds in Samoya,sibembe,siritanyi,Minyali and musikoma | Construction of bodaboda sheds | promotion of MSMEs | Bodaboda sheds constructed | BGM/CNTY/TEI/15/OT/2024-2025 1667858-2024/2025 |  |  | Musikoma | La:0.5455296 Lo:34.5284335 | Trade, Energy and Industrialization | Dept of Trade | MUNGO COMP. LTD | 2024/2025 | aprill 2025 | Awarded in Dec 2024 | may2025 | 1250000 |  |  | CGB | [8 empty] | does not exist | [15 empty] | no bodaboda shed in siritanyi
76 | Installation of 41 grid powered streetlights in Kanduyi Sub-county . | of streetlights Kanduyi streetlights in |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | M/S Mbale Town Electro Works Umeme | 2021/22 |  | Complete and in use |  | 3116001 |  |  | CGB
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | Musikoma |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
129 | Installation of street lights at Sio -Oldrex | of Oldrex street lights | [5 empty] | Musikoma | 34.55641/0.56094 |  |  | KPLC | 2018/19 |  | Project not implemented. KPLC policy requires payment of funds before execution of works. KPLC delayed to submit their quotation to facilitate payment process. The delays were caught up by closure of FY, hence not implemented. |  | 1800000 | 0 |  | CGG | [8 empty] | Stalled | [15 empty] | no existence of such project on site\
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Musikoma |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 |  |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | [16 empty] | No information
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | [16 empty] | No information
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | [16 empty] | No information
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 41852 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed | [15 empty] | Done
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | july2015 | 42312 | aug2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Stalled | [15 empty] | No information
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | [16 empty] | No
| Purchase and delivery of dairy cows at siritanyi | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle at siritanyi | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | mach 2024 | 42585 | mach 2024 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | jan2016 | 42585 | march2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and Delivery of Dairy Cattle at siritanyi | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | may2016 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats at namasanda | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | may2016 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | aprill2017 | 15/3/2017 | may2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed | [15 empty] | community witness
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | aprill2017 | 15/3/2017 | may2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed | [15 empty] | community witness
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed | [15 empty] | community witness
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | aprill2017 | 17/3/2018 | may2017 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | feb 2018 | 17/2/2018 | aprill2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma | 34.54175/0.56216 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | aprill 2018 | 15/04/2018 | june2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Stalled | [15 empty] | No proof
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma | 34.54175/0.56216 | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | between july and dec 2018 | 15/1/2018 | 15/04/2018 | dec2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed | [15 empty] | No proof
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | feb 2019 | 43740 | aprill2019 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed | [15 empty] | community witness
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | feb 2019 | 43740 | aprill2019 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | feb 2020 | 23/3/2020 | aprill2020 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | feb 2020 | 23/3/2020 | aprill2020 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | feb 2021 | 20/2/2021 | aprill2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | feb 2021 | 20/2/2021 | aprill2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | feb 2022 | 44898 | aprill2022 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed | [15 empty] | community witness
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | feb 2022 | 44898 | aprill2022 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | feb 2023 | 45263 | aprill2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed | [15 empty] | community witness
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | feb 2023 | 45263 | aprill2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed | [15 empty] | community witness
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Musikoma |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | sept 2023 | 45387 | aprill2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed | [15 empty] | Done
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 | sept 2023 | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Musikoma |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
9 | Erection and completion of Maternity wing at Tulienge dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completion |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 28-2-2024 |  |  | 2000000 | 1967390 | 1967390 | CGB |  | 1967390 | 0 | 0 | 0 | 0 | 1880920 | 1967390 | On-going | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
63 | proposed erection and completion of maternity wing at Lwakhakha dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completed |  |  | Sirisia | Lwandanyi |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 45628 |  |  | 4000000 | 3939050 | 3939050 | CGB |  | 3939050 | 0 | 0 | 0 | 0 |  | 3939050 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
167 | Construction Of Septic Tank At Lwandanyi Dispensary | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | Septic tanks constructed |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1050000 | 1161650 | 1161650 | CGB |  | 1161650 | 0 | 1161650 | 1 | 1161650 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | good condition
168 | Construction Of Maternity Wing At Karosisndet Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1963330 | 1963330 | CGB |  | 1963330 | 0 | 878500 | 0.44745 | 878500 |  | 1084830 | Complete and in use | [6 empty] | No | complete | Financial | Yes
169 | Renovation Of Health Facility And Staff Quarters At Lwakhakha Dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Staff quarters erected and renovated |  |  | Sirisia | Lwandanyi |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1034983 | 1292924 | 1292924 | CGB |  | 1292924 | 0 | 1163037 | 0.89954 | 1163037 |  | 129887 | Complete and in use | [6 empty] | No | complete | Financial | Yes
232 | Construction Of Public Toilets At Wamono And Tulienge Market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Public toilets constructed |  |  | Sirisia | Lwandanyi | Lon:790443 La:34.433693 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 800000 | 876200 | 876200 | CGB |  | 876200 | 0 | 876200 | 1 | 876200 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | good condition
385 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
493 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 44.73% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
554 | Periodic Maintenance of Lurare - Bishop Wabukala Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43972 |  | 5111401 | 5111401 | 5111401 | County Government of Bungoma |  | 5111401 |  | 5111401 |  | 5111401 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
555 | Upgrading of Tamulega-Malakisi Bridge (River Malakisi) | Road improvement works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43970 | 44001 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
556 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43964 |  | 5111401 | 5111401 | 5111401 | County Government of Bungoma |  | 5111401 |  | 5111401 | 100.0% | 5111401 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
831 | Periodic Maintenance of Wamono - Khabukoya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44332 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 |  | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need murraming
832 | Periodic Maintenance of Tulienge - Nasala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44335 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 |  | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
833 | Periodic Maintenance of Namosi - Bishop Wabukala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
834 | Construction of Arch. Bishop Wabukala - Namwesi Twin Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
835 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44329 |  | 8764728 | 8764728 | 8764728 | County Government of Bungoma |  | 8764728 |  | 8764728 | 99.84% | 8764728 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1146 | Periodic Maintenance of Bukayabi - Kaburweti - Namutokholo - Lwakhakha Border Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44705 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | needs culverts installatin between bukiabi and kabukweti
1147 | Periodic Maintenance of Katomei Junction - Changara Drift Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44699 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1148 | Periodic Maintenance of Kibindoi - Makwere - Kapkara - Lwandanyi Miracle Church Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44692 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 |  | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | need murraming
1149 | Periodic Maintenance of Nambuya - Tamulega Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44697 | 44728 | 2317424.8 | 2317424.8 | 2317424.8 | County Government of Bungoma |  | 2317424.8 |  | 2317424.8 |  | 2317424.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1150 | Periodic Maintenance of Roads In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44702 |  | 16472018.85 | 16472018.85 | 16472018.85 | County Government of Bungoma |  | 16472018.85 |  | 16472018.85 | 99.62% | 16472018.85 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1151 | Routine Maintenance Of Nambuya - Tamulega Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44700 |  | 2317424.8 | 2317424.8 | 2317424.8 | County Government of Bungoma |  | 2317424.8 |  | 2317424.8 | 100.0% | 2317424.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1448 | Periodic Maintenance of St. Paul Lwandanyi - Namundi Tarmac Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45056 |  | 3643608 | 3643608 | 3643608 | County Government of Bungoma |  | 3643608 |  | 3643608 |  | 3643608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good condition
1449 | Periodic Maintenance of Lwakhakha - Township Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45066 |  | 4487867 | 4487867 | 4487867 | County Government of Bungoma |  | 4487867 |  | 4487867 |  | 4487867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1450 | Periodic Maintenance of Mufungu - Namang'Ofulo - Tulienge - Namubila Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45058 |  | 6895712 | 6895712 | 6895712 | County Government of Bungoma |  | 6895712 |  | 6895712 |  | 6895712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1451 | Upgrading of Machakha- Tinga Moja | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45068 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1452 | Periodic Maintenance of Lwakhakha - Township Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45058 |  | 4487867 | 4487867 | 4487867 | County Government of Bungoma |  | 4487867 |  | 4487867 | 99.87% | 4487867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1453 | Periodic Maintenance of Mfungu - Namang'Ofulo - Tulienge - Namubila Primary Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45068 |  | 6895712 | 6895712 | 6895712 | County Government of Bungoma |  | 6895712 |  | 6895712 | 100.0% | 6895712 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1454 | Periodic Maintenance of St. Pauls Lwandanyi - Namundi Tarmac Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44948 | 45064 |  | 3643608 | 3643608 | 3643608 | County Government of Bungoma |  | 3643608 |  | 3643608 | 82.75% | 3643608 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use and in good condition
1685 | Periodic Maintenance of Katomei - Allakar - Korosiondet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45427 |  | 4168808 | 4168808 | 4168808 | County Government of Bungoma |  | 4168808 |  | 4168808 |  | 4168808 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1686 | Periodic Maintenance of Kisiero - Wakenda - Kakala Primary - Munialo - Wabomba - Tarmac Road - Oriama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45422 |  | 4092480 | 4092480 | 4092480 | County Government of Bungoma |  | 4092480 |  | 4092480 |  | 4092480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | maintenance to be done
1687 | Periodic Maintenance of Sitabicha - Bukokholo Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45436 |  | 4566282 | 4566282 | 4566282 | County Government of Bungoma |  | 4566282 |  | 4566282 |  | 4566282 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1688 | Periodic Maintenance of Malakisi Health Centre - Rwatama - Malakisi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45427 | 45458 | 3112744 | 3112744 | 3112744 | County Government of Bungoma |  | 3112744 |  | 3112744 |  | 3112744 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1689 | Periodic Maintenance of Malakisi Health Center-Rwatama-Malakisi Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45436 |  | 3112744 | 3112744 | 3112744 | County Government of Bungoma |  | 3112744 |  | 3112744 | 99.96% | 3112744 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1690 | Periodic Maintenance of Katomei - Allakar - Korosiondet Sda Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45434 |  | 4168808 | 4168808 | 4168808 | County Government of Bungoma |  | 4168808 |  | 4168808 | 99.97% | 4168808 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1691 | Periodic Maintenance of Kisiero - Wekunda - Kakala - Tarmac - Oriama Road In Lwadanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 2023 | 45430 | 2024 | 4092480 | 4092480 | 4092480 | County Government of Bungoma |  | 4092480 |  | 4092480 | 100.0% | 4092480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | maintenance to be done
1692 | Periodic Maintenance of Sitabicha - Bukokholo Junction Road In Lwandanyi Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Sirisia | Lwandanyi |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45433 |  | 4566282 | 4566282 | 4566282 | County Government of Bungoma |  | 4566282 |  | 4566282 | 100.0% | 4566282 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
29 | Proposed completion of 1no.ECDE classroom at Marakaru, Londo and Namundi primary schools | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3500000 | 3346250 | 3500000 | County Government of Bungoma | N/A | 3500000 | 0 | 3346250 | 1 | 3346250 | 0 | 0 | Completed
51 | Proposed Erection And Completion Works Of 1no. Ecde Classroom And 2no. Door Pit Latrine At Lwakhakha And Wamono Primary Schools In Lwandanyi Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 4000000 | 3913160 | 4000000 | County Government of Bungoma | N/A | 4000000 | 0 | 2469174.55 | 0.63099 | 2469174.55 | 1443985.45 | 1443985.45 | Completed | 1 | [14 empty] | The project is in use and in good condition
116 | Completion Of 1 No. Ecde Classroom At Mukhuyu Primary School | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 1000000 | 1292600 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 0 | 0 | 0 | 1292600 | 1292600 | ongoing. At ring beam. | 0.7
117 | Construction Of 1 No. Ecde Classroom At Marakaru, Londo And Namundi Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4300000 | 4244630 | 4300000 | County Government of Bungoma | N/A | 4300000 | 0 | 876038.95 | 0.20639 | 876038.95 | 3368591.05 | 3368591.05 | complete and in use | 1
147 | Proposed Erection And Completion Of 1 No. Ecde At Kibindoi Primary School In Lwandanyi Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1500000 | 1497000 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1497000 | 1 | 1497000 | 0 | 0 | complete and in use | 1 | [14 empty] | The project is in use
174 | Construction Of 08 Ecde Classrooms At Kaburuet, Chebukunyi, Kaprot, Namubila, Namawanga, Tulienge, Kibindoi, And Kapendo Primary Schools | Construction of ECDE classroom and VTC workshop | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 8200000 | 8473660.8 | 8200000 | County Government of Bungoma | N/A | 8200000 | 0 | 8473660.8 | 1 | 8473660.8 | 0 |  | completed kibindoi E.C.D.E | 1 | [14 empty] | The project is in use
175 | Purchase Of 525 Desks For Eight Ecde Classes | Construction of toilets | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Sirisia | Lwandanyi |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 1000000 | 1000000 | 1000000 | County Government of Bungoma | N/A | 1000000 | 0 | 1000000 | 1 | 1000000 | 0 |  | complete and in use | 1
64 | Drilling of Borehole at Kakala Primary School | site identification; geological survey;drilling development(entails casing and gravel use);construction of borehole chamber; construction of water points. | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2000000 | 1999376 | 1999376 | CGB | N/A | 1999376 | 0 | 1999376 | 1 | 1999376 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
174 | Upgrading of Lurare/Namwesi borehole | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4000000 | 3989124 | 3989124 |  | N/A | 3989124 | 0 | 3989124 | 1 | 3989124 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
198 | DRILLING AND EQUIPPING OF BOREHOLE IN TORORO PRIMARY SCHOOL | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1800000 | 1679680 | 1679680 |  | N/A | 1679680 | 0 | 1679680 | 1 | 1679680 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
218 | REHABILITATION AND EXTENSION OF CHESIKAKI-SIRISIA-BUMULA WATER PROJECT PHASE I | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 34000000 | 33391751.4 | 33391751.4 |  | N/A | 33391751.4 | 0 | 33391751.4 | 1 | 23831829 | 9559922 | 0 | Work in progress | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
221 | DRILLING OF 4NO. BOREHOLES IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 4 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 6000000 | 5877482 | 5877482 |  | N/A | 5877482 | 0 | 5877482 | 1 | 2938741 | 2938741 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | not in use water coated with petroleum
284 | DRILLING OF NASALA AND LURARE BOREHOLES IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3700000 | 3540800 | 3540800 |  | N/A | 3540800 | 0 | 3540800 | 1 | 3540800 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
285 | DRILLING OF MACHAKHA BOREHOLE IN LWANDANYI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1782000 | 1782000 |  | N/A | 1782000 | 0 | 1782000 | 1 | 1782000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
286 | REHABILITATION OF 3 NO. BOREHOLES AND CONSTRUCTION OF 10 NO. WATER SPRINGS IN LWANDANYI WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 Boreholes rehabilitated and 10 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2499921 | 2499921 |  | N/A | 2499921 | 0 | 2499921 | 1 | 2499921 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
385 | Lwandanyi borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 600000 | 556225 | 556225 |  | N/A | 556225 | 0 | 556225 | 1 | 556225 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
454 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2597616 | 2597616 |  | N/A | 2597616 | 0 | 2597616 | 1 | 2597616 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
545 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points; | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 10000000 | 9277200 | 9277200 |  | N/A | 9277200 | 0 | 9277200 | 1 | 9277200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
561 | Protection of 7 water springs and Construction of 3 Roof catchments | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; construction of roof catchment and storage tank with water points | To enhance access to clean and safe drinking water | 7 water springs constructed and 3 roof catchments | 3110599 | Other Infrastructure &Civil Works | Sirisia | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2498640 | 2498640 |  | N/A | 2498640 | 0 | 2498640 | 1 | 2498640 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
562 | Drill a borehole at Kapkara | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works |  | Lwandanyi |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2224900 | 2224900 |  | N/A | 2224900 | 0 | 2224900 | 1 | 2224900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
3 | Construction of Lwandanyi ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Lwandanyi ward office constructed | 3111504 | Construction of non- residential buildings | Sirisia | Lwandanyi | Lon:7090325 Lat:34.434112 | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 42879 | 9500000 | 9039375 | 9500000 | County Government of Bungoma | - | 9039375 | - | 9039375 | 1 | 9039375 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Rehabilitation of Kapkara Dam | Rehabilitation of Kapkara Dam | To store water for irrigation and flood control | 1 dam rehabilitated | 3110504 | Other infrastructure and civil works | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41699 | 10000000 | 7675000 | 8000000 | County Government of Bungoma |  | 7675000 |  | 7675000 | 1 | 7675000 | 0 | 0 | Completed
| Construction of farm ponds at Kabkara watershed | Construction of 20no. farm ponds at Kabkara watershed | To store water for irrigation and flood control | 20 farm ponds constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | [5 empty] | 4999144 | 5000000 | Development partner | IDA | 0 | 4999144 | 4999144 |  | 4999144 | 0 | 0 | stalled
| Construction of Kabkara Earth Dam | Construction of Kabkara Earth Dam | To store water for irrigation and flood control | 1 dam constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Sirisia | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 24/5/2022 | 24/11/2022 | 21/3/2024 |  | 50866669 | 50866669 | Development partner | IDA | 0 | 50866669 | 50866669 |  | 50866669 | 0 | 0 | Complete
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
96 | Installation of 2 No high mast flood lights | of lights No high | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Ms Emricon Limited | 2021/22 |  | Complete and in use |  | 1900000 |  |  | CGB | [8 empty] | not traced | [15 empty] | not traced
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | Lwandanyi |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
123 | Construction of 3 no. Mama Mboga sheds | sheds of 3 no | [5 empty] | Lwandanyi |  |  |  | Dry Port | 2018/19 |  | Complete |  | 1595174 |  |  | CGG | [8 empty] | Completed | [15 empty] | in use and in good condition
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Lwandanyi |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
133 | Construction of 8 No. Boda Boda Sheds | heds of 8 No | [5 empty] | Lwandanyi |  |  |  | M/S Mamofa Construction Company Limited P.O Box 41658 Bungoma | 2017/18 |  |  |  | 2756979 |  |  | CGB | [8 empty] | Completed | [15 empty] | in use and in good condition
134 | Renovation of Lwakhakha market | [6 empty] | Lwandanyi |  |  | Dept of Trade | Adept General Contractors | 2016/17 |  | Complete |  | 24409776 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Lwandanyi |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Lwandanyi |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Male and female wards lwandanyi health centre | [5 empty] | Sirisia | Lwandanyi | [20 empty] | Completed | [15 empty] | in use and in good condition
45 | Construction of fence, gate and 4NO. Doors pit latrines at cheptais animal sale yard | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Fence, Gate and 4No.door pit latrine constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.811713 LONG 34.469555 |  | WBPSPCU | Health & Sanitation | 2023-2024 | 15/2/2024 |  |  | 2000000 | 1884072 | 1884072 | CGB |  | 1884072 |  |  | 0 |  |  | 1884072 | Completed | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | good work done
60 | Construction of 9NO. Doors pit latrines with Urinal at Chebwek Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 9no.door pit latrine constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.85111 LONGIT. 34.45362 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 45416 |  |  | 1200000 | 1200000 | 1200000 | CGB |  | 1200000 | 0 | 0 | 0 | 0 |  | 1200000 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | contractor should commence immediately
64 | Construction of fence, gate and 4NO. Doors pit latrines at cheptais animal sale yard | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Fence, Gate and 4No.door pit latrine constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.811713 LONG 34.469555 |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 15/2/2024 |  |  | 2000000 | 1884072 | 1884072 | CGB |  | 1884072 | 0 | 0 | 0 | 0 |  | 1884072 | [7 empty] | No | complete | Financial | Yes |  |  |  | No |  | done
72 | Erection And Completion Of Maternity Wing And 4no. Door Pit Latrines Phase 1 At Kimaswa Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wing and 4No.door pit latrine completed |  |  | Mt. Elgon | Cheptais | LAT. 0.8213634 LONG. 34.4577122 |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2600000 | 0 | 0 | CGB |  | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Contractor has never stepped on the site
99 | Construction Of Gate, Fence Of Burkweno Land For Dispensary Complition Of Stalled Modern Toilets At Cheptais Market | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services in the area | Fence and Gate constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8286 LONGITU. 34.43178 |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 1200000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | fencing has neve been undertaken
154 | Construction Of Meternity At Chebkube Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.83532 LONG. 34.4297 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1920400 | 1920400 | CGB |  | 1920400 | 0 | 1804247 | 0.93952 | 1804247 |  | 116153 | Incomplete and not in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | Some repairs need to be undertaken esp. doors
155 | Construction Of Meternity Ward In Kang'ang'a Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8093629 LONG. 34.4635973 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 1905850 | 1905850 | CGB |  | 1905850 | 0 | 1904417 | 0.99925 | 1904417 |  | 1433 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Works not finished
156 | Construction Of Nalondo Dispensary With Pit Latrines, Chain Link Fence And Gate | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8150121 LONG. 34.419669 |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2174382 | 4989885 | 4989885 | CGB |  | 4989885 | 0 | 4891180.6 | 0.98022 | 4891180.6 |  | 98704.4 | Complete and in use | [6 empty] | No | complete | Financial | Yes | [5 empty] | done
198 | Construction Of A Maternity Ward At Cheptais Health Centre | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wards constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.823191 LONG 34.4620565 |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 3000000 | 2225570 | 2225570 | CGB |  | 2225570 | 0 | 1602820 | 0.72018 | 1602820 |  | 622750 | complete but not in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | no equipments
199 | Construction Of A Dispensary At Nalondo | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.815160 LONG. 34.419279 |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 3000000 | 4989885 | 4989885 | CGB |  | 4989885 | 0 | 4891180 | 0.98022 | 4891180 |  | 98705 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | in use
218 | Proposed Completion Of Septic Tank At Cheptais Market | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | Septic tanks constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8076761 LONG. 34.4620565 |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 500000 | 492269.2 | 492269.2 | CGB |  | 492269.2 | 0 | 492089.4 | 0.99963 | 492089.4 |  | 179.8 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No |  | Constructed but not in use as its in bad condition
272 | Rehabilitation of public toilet at Cheptais market. | Digging of 20ft deep pit,flooring,walling,painting,roofing and fitting of doors n and installation of water tank | To enhance access to sanitary facilities at the market. | Public toilets constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.8076576 LONG 34.4639632 |  | Ward Based | Health & Sanitation | 2015/2016 | 16th March 2015 | 30th Jun 2016 | 16th June 2016 |  | 350000 | 350000 | CGB |  | 350000 | 0 | 286000 | 0.81714 | 286000 |  | 64000 | Complete but not in use. | [6 empty] | No | complete | Financial | Yes | [5 empty] | In pathetic state (condenmed for demolition)
273 | Purchase of 2-acre land for construction of Nalondo Health centre. | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Cheptais | LAT. 0.815292 LONG. 34.419057 |  | Ward Based | Health & Sanitation | 2015/2016 | 16th April 2016 | 3rdJun 2016 | 16th June 2016 |  | 460000 | 460000 | CGB |  | 460000 | 0 | 460000 | 1 | 460000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | Land acquired but require sub-division
274 | Purchase of 3/4-acre land | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Cheptais | LAT. 0.8213634 LONG. 34.4577122 |  | Ward Based | Health & Sanitation | 2015/2016 | 42506 | 42551 | 42537 |  | 489000 | 489000 | CGB |  | 489000 | 0 | 489000 | 1 | 489000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | land in dispute, sub-division is needed for full ownership
275 | Construction of Chebwek health centre | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | health centres constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.72243 LONG. 34.4412 |  | CEF | Health & Sanitation | 2016/2017 | 42916 | 43084 | Ongoing. |  | 13191212 | 13191212 | CGB |  | 13191212 | 0 | 2824356 | 0.21411 | 2824356 |  | 10366856 | Complete | [6 empty] | No | complete | Financial | Yes | [5 empty] | good workmanship
14 | Upgrading of Cheptais Hosy-Kapsesoipoly-Tembelela-Wasio Mkt | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8032364 LONG. 34.4620589 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41651 | 41778 |  | 4737600 | 4737600 | 4737600 | County Government of Bungoma |  | 4737600 |  | 4737600 | 100.0% | 4737600 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | at the moment, it requires routine maineanance
32 | Upgrading of Periodic Maintanance Of Kamuneru-Masaek | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | not in cheptais ward | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41663 | 41780 |  | 23800030.93 | 23800030.93 | 23800030.93 | County Government of Bungoma |  | 23800030.93 |  | 23800030.93 | 100.0% | 23800030.93 | 0 | 0 |  | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | not in cheptais wad
122 | Upgrading of Cheptais Market Roads | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8090761 LONG. 34.35665 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2016/2017 | 42759 | 42867 |  | 54263150 | 54263150 | 54263150 | County Government of Bungoma |  | 54263150 |  | 54263150 | 88.4% | 54263150 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | some requires maintenance
156 | Periodic Maintenance of Kwa Kilemba - Kapkwes Forest Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8286 LONGIT. 34.46089 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43232 |  | 8166690 | 8166690 | 8166690 | County Government of Bungoma |  | 8166690 |  | 8166690 |  | 8166690 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | road in pathetic state and impassable
157 | Periodic Maintenance of Chepkube Fcs - Chebwek Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.78869 LONGI. 34.2711699 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43115 | 43230 |  | 8166690 | 8166690 | 8166690 | County Government of Bungoma |  | 8166690 |  | 8166690 |  | 8166690 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable
158 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8305746 LONG. 34.4580721 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43244 |  | 8166690 | 8166690 | 8166690 | County Government of Bungoma |  | 8166690 |  | 8166690 | 99.94% | 8166690 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
304 | Periodic Maintenance of Cheptais Hospital - Kapsesoi - Tembelela Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8032364 LONG. 34.4620589 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43479 | 43599 |  | 7101670.8 | 7101670.8 | 7101670.8 | County Government of Bungoma |  | 7101670.8 |  | 7101670.8 |  | 7101670.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
305 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43480 | 43606 |  | 7101670.8 | 7101670.8 | 7101670.8 | County Government of Bungoma |  | 7101670.8 |  | 7101670.8 | 99.58% | 7101670.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
306 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
494 | Upgrading of R. Tisi - Burkenwo - Rama Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.8376 LONGI. 34.43267 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43968 |  | 7818342 | 7818342 | 7818342 | County Government of Bungoma |  | 7818342 |  | 7818342 |  | 7818342 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
495 | Periodic Maintenance of Cheptais Backstreet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT 0.8090784 LONG. 34.4635277 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43973 |  | 3475824 | 3475824 | 3475824 | County Government of Bungoma |  | 3475824 |  | 3475824 |  | 3475824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance
496 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43962 |  | 3475824 | 3475824 | 3475824 | County Government of Bungoma |  | 3475824 |  | 3475824 | 99.97% | 3475824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
497 | Drainage Works In Elgon,Kabuchai And Sirisia Sub-Counties(Lot 3) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43966 |  | 7818342 | 7818342 | 7818342 | County Government of Bungoma |  | 7818342 |  | 7818342 | 90.53% | 7818342 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
722 | Periodic Maintenance of Peresten - Cheptais Boys - Kiterie - R. Tisi - Rcea Chemorroch Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT 0.8066469 LONG. 34.463665 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44328 |  | 4951837 | 4951837 | 4951837 | County Government of Bungoma |  | 4951837 |  | 4951837 |  | 4951837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
723 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44328 |  | 4951837 | 4951837 | 4951837 | County Government of Bungoma |  | 4951837 |  | 4951837 | 99.79% | 4951837 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
1046 | Periodic Maintenance of Chebwek - Chesukum Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.78925 LONG. 34.46089 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44693 | 44724 | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 |  | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | impassable due to non routine mantenance
1047 | Periodic Maintenance of Nairobi B - Chesiro Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.84887 LONG.34.46588 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44693 | 44724 | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 |  | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | road in pathetic state and impassable
1048 | Periodic Maintenance of Wasio - Nalondo - Chepsienya Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.820512 LONG. 34.431109 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44695 | 44726 | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 |  | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | Complete and passable
1049 | Periodic Maintenance of Kapsesoi - Chepkube Factory | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.8361005 LONG. 34.4504978 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44703 |  | 2513328.5 | 2513328.5 | 2513328.5 | County Government of Bungoma |  | 2513328.5 |  | 2513328.5 |  | 2513328.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | impassable due to non routine mantenance
1050 | Periodic Maintenance of Chepkube - Ack - River Lwakhakha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.83532 LONG. 34.43144 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44702 |  | 2360446.3 | 2360446.3 | 2360446.3 | County Government of Bungoma |  | 2360446.3 |  | 2360446.3 |  | 2360446.3 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
1051 | Periodic Maintenance of Roads In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44695 |  | 10149304 | 10149304 | 10149304 | County Government of Bungoma |  | 10149304 |  | 10149304 | 19.71% | 10149304 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | most of the feeder roads are in pathetic state and needs maintenance
1052 | Routine Maintenance Of Kapsesoi - Chepkube Factory | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais | LAT. 0.8361005 LONG. 34.4504978 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44701 |  | 2513328.5 | 2513328.5 | 2513328.5 | County Government of Bungoma |  | 2513328.5 |  | 2513328.5 | 100.0% | 2513328.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | repeatation
1053 | Routine Maintenance Of Chepkube - Ack - River Lwakhakha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.3KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44700 |  | 2360446.3 | 2360446.3 | 2360446.3 | County Government of Bungoma |  | 2360446.3 |  | 2360446.3 | 100.0% | 2360446.3 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | repeatation
1370 | Construction of Chebwek- Chesiro Twin Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Mt. Elgon | Cheptais | LAT. 0.85244 LONG. 34.46327 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44942 | 45069 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | bridge passable
1620 | Construction of Cheptais Market (Ochela Junction) - Cheptais Cdf Office Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8130745 LONG 34.4639662 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45428 |  | 8471683 | 8471683 | 8471683 | County Government of Bungoma |  | 8471683 |  | 8471683 |  | 8471683 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
1621 | Periodic Maintenance of Chemoro Rcea Church - Bikhutu Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.83105 LONG. 34.43939 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45434 |  | 3138867 | 3138867 | 3138867 | County Government of Bungoma |  | 3138867 |  | 3138867 |  | 3138867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires maintenance
1622 | Periodic Maintenance of Rama - Busanja - Andrea Walanga Road In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45434 |  | 5003544 | 5003544 | 5003544 | County Government of Bungoma |  | 5003544 |  | 5003544 | 99.94% | 5003544 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1623 | Periodic Maintenance of Kamata - Kang'Ang'A - Cheptiya Road In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8307191 LONG. 34.4506382 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45424 |  | 6377680 | 6377680 | 6377680 | County Government of Bungoma |  | 6377680 |  | 6377680 | 99.92% | 6377680 | 0 | 0 | Incomplete and not in use | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | impassable an poor work done. No culverts and road completely worn out
1624 | Periodic Maintenance of Chemoro Rcea Church - Bikhutu Primary Road In Cheptais Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.83105 LONG. 34.43939 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45425 |  | 3138867 | 3138867 | 3138867 | County Government of Bungoma |  | 3138867 |  | 3138867 | 98.0% | 3138867 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | requires periodic maintenance and culverts for drainage
1625 | Proposed Cheptais Market (Ochela Junction) - Cheptais Cdf Office Box Culvert In Cheptais Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Cheptais | LAT. 0.8130745 LONG 34.4639662 | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45434 |  | 8471683 | 8471683 | 8471683 | County Government of Bungoma |  | 8471683 |  | 8471683 | 99.81% | 8471683 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | passable and in good condition
7 | Purchase of 1 Acre for bus terminus and open air market. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of Market and bus terminas | One acre of Land Purchased for bus terminus and open air market | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45200 | 45809 |  | 5000000 | - | 5000000 | CGB | N/A | 5000000 | 0 | 5000000 | 1 | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
74 | Purchase Of Land For Cheswee Ecde | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land For Cheswee Ecde Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 |  |  |  | 3000000 | 2132510.05 | 2132510.05 | CGB |  | 2132510.05 |  | 2132510.05 | 1 |  |  |  | not in existence | [15 empty] | Diverted t buy aplot at a poor site in cheptais market
115 | Purchase Of One Acre For Rama Ecde | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new ECDE centre | One acres of Land for Rama E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT. 0.83993 LONGI. 34.2741770 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 17/9/2017 | 19/11/2017 | 43435 | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 1 | 500000 | 0 |  | Completed | 1 | [14 empty] | school exist at the land purchased
116 | Purchase Of One Acre For Chenomor Coffee Factory | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new Coffee facrory | One acres of Land for Chenomor Coffee Factory Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT. 0.814343 LONG. 34.4574282 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43077 | 43079 | 23/11/2017 | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 1 | 500000 | 0 |  | Completed | 1 | [14 empty] | land in place though require sub-divistion
184 | Purchase of land for Kaamata ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Kaamata yECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT.0.8274209 LONG. 34.453883 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42374 | 42377 | 42377 | 362000 | 362000 | 362000 | CGB | N/A | 362000 |  | 362000 |  | 362000 |  |  | Completed | 1 | [14 empty] | land dispute over boundary, requires sub-division
185 | Purchase of land for Bikhutu ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acre of Land for Bikhutu ECDE Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 42014 | 42401 | 25/12/2015 | 300000 | 300000 | 300000 | CGB | N/A | 300000 |  | 300000 |  | 300000 |  |  | Completed | 1 | [14 empty] | land available
192 | Purchase of 1 acre for Rama E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Rama E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais | LAT. 0.83993 LONGI. 34.2741770 | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 |  |  |  | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 1 | 0 |  |  | Completed | 0 | [14 empty] | school exist at the land purchased
193 | Purchase of 1 acre for Chenomor coffee factory | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new Coffee factory | One acres of Land for Chenomor coffee factory Purchased | 3110599 | Ward based projects | Mt. Elgon | Cheptais |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 |  |  |  | 500000 | 500000 | 500000 | CGB | N/A | 500000 |  | 500000 | 1 | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
35 | Proposed Erection And Completion Works Of Chebwek Polytechnic In Cheptais Ward | Construction of VTC | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.61984 LONG. 33.5263 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2936190 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0 |  | 2936190 | 2936190 | Completed | 1 | [14 empty] | not in use due to unfinished toilets
36 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Kamata and Kipsis Primary Schools In Cheptais Ward | Completion of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.82354 LONG. 34.46955 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3900000 | 3877600 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 1037621.35 | 0.26759 | 1037621.35 | 2839978.65 | 2839978.65 | Completed | 1 | [14 empty] | in use by the pupils, though was not officially opened
70 | Construction Of 1no. Classroom At Bulukha Ecde | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.811837 LONG. 34.415907 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1300000 | 1299000 | 1300000 | County Government of Bungoma | N/A | 1300000 | 0 | 0 | 0 | 0 | 1299000 | 1299000 | Stalled | 1 | [14 empty] | construction reached wall plate.
103 | Construction Of 1 No. Ecde At Kuborom And Cheptais Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Cheptais | LAT. 0.61984 LONG. 34.33.50263 LAT. 0.8079479 LONG 34.4563886 | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 2600000 | 2501700 | 2600000 | County Government of Bungoma | N/A | 2600000 | 0 | 505561.55 | 0.20209 | 505561.55 | 1996138.45 | 1996138.45 | Completed | 0.9 | [14 empty] | in use
32 | Proposed Rehabilitation Of Kuywa, Lwakhakha Rivers And Matere Stream In Chepyuk, Cheptais And Chesikaki Wards Respectively. | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | Cheptais |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7888000 | 5909325 | 5909325 | FLLOCA | IDA | 0 | 5909325 | 0 | 1 | 0 | 0 |  | Re-tendered | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
47 | Extension of Chebukube Cheptais Water project in Cheptais Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4000000 | 3880780 | 3880780 | CGB | N/A | 3880780 | 0 | 3880780 | 1 | 3880780 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
117 | Expansion of main treatment works at Chebwek-Chepkube | Rehabilitation of treatment plant; flocculation; pre-sedimentation; clear water tank | To enhance access to clean and safe drinking water | 1 Treatment works site expanded | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.78877 LONG. 34.2711772 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 7000000 | 6794730 | 6794730 |  | N/A | 6794730 | 0 | 6794730 | 1 | 6794730 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | water available
118 | Extension of Cheptais Cherendio water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.7965936 LONG. 34.4574282 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2500000 | 2364080 | 2364080 |  | N/A | 2364080 | 0 | 2364080 | 1 | 2364080 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | people enjoy water
181 | Nalondo dispensary - Namatotoa primary water supply project | Trenching ; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.822437 LONG. 34.25968 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 5500000 | 5409231 | 5409231 |  | N/A | 5409231 | 0 | 5409231 | 1 | 5409231 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Not in use due to theft and vandalism
182 | CONSTRUCTION OF INO. WATER IN CHEPTAIS WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8058137 LONG. 34.4637083 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 300000 | 249050 | 249050 |  | N/A | 249050 | 0 | 249050 | 1 | 249050 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
309 | CONSTRUCTION OF WATER PIPELINE PROJECT FROM CHEBWEK –CHEBKUBE MARKET IN CHEPTAIS WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.78877 LONG.34.2711774 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 7400000 | 7296800 | 7296800 |  | N/A | 7296800 | 0 | 7296800 | 1 | 7296800 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
310 | REHABILITATION OF CHEPTAIS LWAKHAKHA WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline rehabilitated and extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8048493 LONG. 34.4631076 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 7200000 | 7001470 | 7001470 |  | N/A | 7001470 | 0 | 7001470 | 1 | 7001470 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
454 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8048493 LONG. 34.4631076 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2597616 | 2597616 |  | N/A | 2597616 | 0 | 2597616 | 1 | 2597616 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
545 | CHEPTAIS LWAKHAKA WATER PROJECT | Trenching; laying of water pipeline and water points; | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Cheptais | LAT. 0.8048493 LONG. 34.4631076 | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 10000000 | 9277200 | 9277200 |  | N/A | 9277200 | 0 | 9277200 | 1 | 9277200 | 0 | 0 | Completed | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | in use
| Construction Of Coffee Adminstrative Blocks | Construction of Coffee Adminstrative Blocks in Cheswee, Kipsis, Chechoko and Wasio in Cheptais Ward | To support growth of coffee farmers and enhance income generation | 4 Administartion blocks constructed | 3110504 | Other infrastructure and civil works | Mt. Elgon | Cheptais |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 20/2/2022 | 20/7/2022 | 15/5/2022 | 6000000 | 4365000 | 4500000 | County Government of Bungoma |  | 4365000 | 0 | 4365000 | 1 | 4365000 | 0 | 0 | Completed
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
84 | Proposed construction of cabro laying in Cheptais open air market | construction laying in Cheptais |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais | LAT. 0.8066762 LONG. 34.4635277 | Trade, Energy and Industrialization | Dept of Trade | M/S Hertz Investment | 2021/22 |  | Terminated |  | 4782500 |  |  | CGB | [8 empty] | never done | [15 empty] | project never took place
87 | Installation of 2 No solar High mast flood lights | of flood solar High | [5 empty] | Cheptais | LAT. 0.8066762 LONG.34.4636166 | Trade, Energy and Industrialization | Dept of Energy | Bishin Transpoters and Construction Company | 2021/22 |  | Complete and in use |  | 1988000 |  |  | CGB | [8 empty] | Completed | [15 empty] | working
106 | Proposed installation of 25 no. Grid powered street lights in Mt. Elgon Sub County | installation Grid lights street in Mt | [5 empty] | Cheptais |  |  |  | M/S FECAKO Investments Limited | 2020/21 |  | Complete |  | 2434212.5 |  |  | CGG
118 | Construction of 16 door Modern stalls | Of stalls streetlights | [5 empty] | Cheptais | LAT. 0.8066762 LONG. 34.4635277 |  |  | Yonak (Ke) Limited | 2019/20 |  | Project not implemented. The BoQs were reviewed upward in terms of specifications without effecting the same on the budget which resulted to Contractor declining the contract. Additionally, there was no public land for construction of the market stalls. |  | 3096460 |  |  | CGG | [8 empty] | never done | [15 empty] | project never took place
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed | [15 empty] | distribution done and farm production increased
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed | [15 empty] | distribution done and farm production increased
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8047113 LONG. 34.4631014 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Cheptais | LAT. 0.8066762 LONG. 34.4635277 | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed | [15 empty] | distribution done and food production increased
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Cheptais |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Cheptais |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
21 | Completion of maternity wing at Kaptalelio dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45478 |  |  | 500000 | 1760000 | 1760000 | CGB |  | 1760000 | 0 | 0 | 0 | 0 |  | 1760000 | On-going | 94 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
32 | Equiping of Kaptama dispensary wards | Equipping with drugs and medical equipment |  | dispensaries equipped |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 750000 | 706880 | 706880 | CGB |  | 706880 | 0 | 0 | 0 | 0 |  | 706880 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
105 | Construction Of 16 No. Door Pit Latrine in Chepkoyaa primary |  |  | 16No. Door pit latrine Constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 3000000 |  |  | CGB |  |  | 0 | 2987924 | #DIV/0! | 2987924 |  | -2987924 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
106 | Construction Of Wards At Kaptama Health Center |  |  | Wards constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2000000 | 1999000 | 1999000 | CGB |  | 1999000 | 0 | 685200 | 0.34277 | 685200 |  | 1313800 | stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
161 | Construction Of Toboo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3000000 | 3019790 | 3019790 | CGB |  | 3019790 | 0 | 2574152 | 0.85243 | 2574152 |  | 445638 | Complete and in use | [6 empty] | No | complete | Financial | Yes
162 | Construction Of Kaptama Health Center Septic Tank | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | health centres constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1249121 | 984100 | 984100 | CGB |  | 984100 | 0 | 979374 | 0.9952 | 979374 |  | 4726 | Complete and in use | [6 empty] | No | complete | Financial | Yes
188 | Construction Of Toboo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3000000 | 3019790 | 3019790 | CGB |  | 3019790 | 0 | 2574152 | 0.85243 | 2574152 |  | 445638 | Complete and in use | [6 empty] | No | complete | Financial | Yes
189 | Construction Of Kaptama Health Center Septic Tank | Digging of 20ft deep pit,flooring,walling,roofing | To develop and maintain infrastructure for enhanced access to quality health care services. | health centres constructed |  |  | Mt. Elgon | Kaptama |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1249121 | 984100 | 984100 | CGB |  | 984100 | 0 | 979374 | 0.9952 | 979374 |  | 4726 | Complete and in use | [6 empty] | No | complete | Financial | Yes
225 | Construction Of Maternity Wing At Kaptalelio Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1500000 | 1790650 | 1790650 | CGB |  | 1790650 | 0 | 520578.72 | 0.29072 | 520578.72 |  | 1270071.28 | Stalled at Ringbeam | [6 empty] | No | complete | Financial | Yes |  |  |  | No
226 | Construction Of Maternity Wing At Kaptalelio Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1500000 | 1790650 | 1790650 | CGB |  | 1790650 | 0 | 520578.72 | 0.29072 | 520578.72 |  | 1270071.28 | Stalled at Ringbeam | [6 empty] | No | complete | Financial | Yes |  |  |  | No
277 | Purchase of 0.75 acre of land for chemoge Dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | Ward Based | Health & Sanitation | 2015/2016 | 42430 | 42461 | 42522 |  | 300000 | 300000 | CGB |  | 300000 | 0 | 300000 | 1 | 300000 |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
281 | Purchase of 0.5 acre land for Kongit dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | Ward Based | Health & Sanitation | 2015/2016 | 01.01.2016 | 42461 | 15.04.2016 |  | 200000 | 200000 | CGB |  | 200000 | 0 | 200000 | 1 | 200000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
282 | Construction of Kaptama health centre | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windows | To provide accessible and affordable health services within the community | health centres constructed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 |  | Dec – 2016 |  |  | 9741352.9 | 9741352.9 | CGB |  | 9741352.9 | 0 | 8234927 | 0.84536 | 8234927 |  | 1506425.9 | Complete | [6 empty] | No | complete | Financial | Yes
283 | Erection and Completion of Kongit dispensary | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 | 42705 | Jan– 2017 | 42767 |  | 3350000 | 3350000 | CGB |  | 3350000 | 0 | 3243724 | 0.96828 | 3243724 |  | 106276 | Complete | [6 empty] | No | complete | Financial | Yes
284 | Construction of Chemoge dispensary | Excavation of trenches for foundation,construction of 150mm thick slab,walling,roofing,painting,fixing of doors,windors | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | Kaptama |  |  | Ward Based | Health & Sanitation | 2015/2016 | 4th Jan 2016 | 4th Apr 2017 |  |  | 3351566 | 3351566 | CGB |  | 3351566 | 0 | 3034892.3 | 0.90551 | 3034892.3 |  | 316673.7 | Complete and in use. | [6 empty] | No | complete | Financial | Yes
285 | Purchase of 1 acre of land for Chemoge dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 |  | 42475 |  |  | 300000 | 300000 | CGB |  | 300000 | 0 | 300000 | 1 | 300000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
286 | Purchase of ½ an acre of land for Kongit dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services within the community | acres of land purchased |  |  | Mt. Elgon | Kaptama |  |  | CEF | Health & Sanitation | 2016/2017 | 42370 |  | 15.04.2016 |  | 200000 | 200000 | CGB |  | 200000 | 0 | 200000 | 1 | 200000 |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
288 | Construction of pit latrine at Kaptalelio primary school | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To enhance access to sanitary facilities at the school | pit latrines constructed |  |  | Mt. Elgon | Kaptama | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | [7 empty] | No | complete | Financial | Yes
290 | Renovation of Labot dispensary | Excavation of trenches for foundation,construction of 150mm thick floor slab,walling,roofing,painting,fixing of doors,windows | To provide accessible affordable health services within the community | Dispensaries renovated |  |  | Mt. Elgon | Kaptama | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete but not in use. | [6 empty] | No | complete | Financial | Yes
291 | Renovation of Labot dispensary | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To provide accessible affordable health services within the community | Dispensaries renovated |  |  | Mt. Elgon | Kaptama | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete. | [6 empty] | No | complete | Financial | Yes
10 | Fencing of high altitude training centre | Fencing of high altitude training centre | To improve on security | High altitute centre fenced |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2013/14 |  |  |  | 4707483 | 4707483 | 4707483 | County Government of Bungoma | n/a | n/a | n/a | 4707483 | 1 | 4707483 | 0 | 0 | Completed
11 | Erection and completion of high altitude training centre- phase 1 | Erection and completion of high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | High altitute centre erected and completed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2013/14 |  |  |  | 45652160 | 45652160 | 10630020 | County Government of Bungoma | n/a | n/a | n/a | 10630020 | 0.23285 | 10630020 | 0 | 35022140 | Stalled | 0.3 | 0.3 | The Contractor was unable to complete works-the contract was terminated and retendered
12 | Erection and completion of high altitude training centre | Erection and completion of high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | High altitute centre erected and completed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015/16 |  |  |  | 37068629 | 37068629 | 37068629 | County Government of Bungoma | n/a | n/a | n/a | 37068629 | 1 | 37068629 | 0 | 0 | Completed
13 | Supply, Delivery, installation and testing of sanitary, fittings, plumbing | Supply, Delivery, installation and testing of sanitary, fittings, plumbing | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Sanitary,fittings and plumbing equipments supplied and installed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015/16 |  |  |  | 3619548 | 3619548 | 3619548 | County Government of Bungoma | n/a | n/a |  | 3619548 | 1 | 3619548 | 0 | 0 | Completed
14 | Supply, installation and commissioning of Kitchen cold Equipment at high altitude training centre | Supply, installation and commissioning of Kitchen cold Equipment at high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Kitchen cold equipment supplied, installed and commissioned |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015-16 |  |  |  | 1847540 | 1847540 | 1350866 | County Government of Bungoma | n/a | n/a |  | 1350866 | 0.73117 | 1350866 | 0 | 496674 | Stalled | 0.73 | 0.73 | The supplier supplied equipment but did not test and commission the works-terminated retendered
15 | Supply, installation and commissioning of electrical lighting Equipment at high altitude training centre | Supply, installation and commissioning of electrical lighting Equipment at high altitude training centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Electrical lighting equipment supplied, installed and commissioned |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2015-16 |  |  |  | 7916176 | 7916176 | 5479608 | County Government of Bungoma | n/a | n/a |  | 5479608 | 0.6922 | 5479608 | 0 | 2436568 | Stalled | 0.69 | 0.69 | Electrical works were not completed- Terminated, evaluated and retendered
16 | Construction of Hostels at High Altitude Training Centre( phase 11) | Construction of Hostels at High Altitude Training Centre( phase 11) | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Hostels constructed |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2018-19 |  |  |  | 25491383 | 25491383 | 25491383 | County Government of Bungoma | n/a | n/a |  | 25491383 | 1 | 25491383 | 0 | 0 | Completed
17 | Supply and Delivery of Gym Equipment and Furniture for High altitude Training centre | To facilitate operationilization of the High altitute centre | To facilitate operationilization of the High altitute centre | Gym Equipment and Furniture supplied and delivered |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2021-22 |  |  |  | 9287164 | 9287164 | 9287164 | County Government of Bungoma | n/a | n/a |  | 9287164 | 1 | 9287164 | 0 | 0 | Completed
18 | Supply and delivery of Kitchen ware equipment for High Altitude training Centre | Supply and delivery of Kitchen ware equipment for High Altitude training Centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | Kitchen ware equipment Supplied and delivered |  |  | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2021-22 |  |  |  | 480000 | 480000 | 480000 | County Government of Bungoma | n/a | n/a |  | 480000 | 1 | 480000 | 0 | 0 | Completed
19 | Completion of High Altitude Centre | Completion of High Altitude Centre | To identify and nuture all forms and talents and sports for social cohesion and economic growth. | High Altitude Centre completed | 3110604 | other infrastructure and civil works | Mt. Elgon | Kaptama |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2023/24 | 16/11/2023 | 16/11/2024 |  | 44430681 | 30980230.3 | 19025572 | County Government of Bungoma | n/a | n/a |  | 19025572 | 0.61412 | 19025572 | 11954658.3 | 11954658.3 | Ongoing | 0.9
185 | Periodic Maintenance of Kaptama - Kostoi - Chebombai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43123 | 43231 | 43262 | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 |  | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
186 | Periodic Maintenance of Chepkoya - Kapkijana - Kapmuyei Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43235 | 43266 | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 |  | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
187 | Upgrading of Kaptama - Sosio - Chemoge Foot Bridge | Road improvement works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43244 | 43275 | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 |  | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
188 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43240 |  | 7040100.9 | 7040100.9 | 7040100.9 | County Government of Bungoma |  | 7040100.9 |  | 7040100.9 | 82.77% | 7040100.9 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
350 | Periodic Maintenance of Kapsamii - Kamatira Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43486 | 43600 |  | 6655152 | 6655152 | 6655152 | County Government of Bungoma |  | 6655152 |  | 6655152 |  | 6655152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
351 | Grading of Chemoge Market Primary School Road | Grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43598 | 43629 | 6655152 | 6655152 | 6655152 | County Government of Bungoma |  | 6655152 |  | 6655152 |  | 6655152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
352 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43604 |  | 6655152 | 6655152 | 6655152 | County Government of Bungoma |  | 6655152 |  | 6655152 | 97.91% | 6655152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
353 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
523 | Periodic Maintenance of Kaptama - Chesito Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43961 |  | 11066433 | 11066433 | 11066433 | County Government of Bungoma |  | 11066433 |  | 11066433 |  | 11066433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
524 | Periodic Maintenance of Chesito - Cheledet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43972 |  | 7393260 | 7393260 | 7393260 | County Government of Bungoma |  | 7393260 |  | 7393260 |  | 7393260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
525 | Periodic Maintenance of Cheledet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43969 |  | 9017463 | 9017463 | 9017463 | County Government of Bungoma |  | 9017463 |  | 9017463 |  | 9017463 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
526 | Periodic Maintenance of Sultan - Kaptengandet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43967 |  | 6780606 | 6780606 | 6780606 | County Government of Bungoma |  | 6780606 |  | 6780606 |  | 6780606 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
527 | Periodic Maintenance of Kaptama - Chesito Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43970 |  | 11066433 | 11066433 | 11066433 | County Government of Bungoma |  | 11066433 |  | 11066433 | 98.61% | 11066433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
528 | Periodic Maintenance of Chesito - Cheldet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43964 |  | 7393260 | 7393260 | 7393260 | County Government of Bungoma |  | 7393260 |  | 7393260 | 95.07% | 7393260 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
529 | Periodic Maintenance of Chelindet - Line Maweroad | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43970 |  | 9017463 | 9017463 | 9017463 | County Government of Bungoma |  | 9017463 |  | 9017463 | 98.15% | 9017463 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
530 | Routine Maintenance Of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43975 |  | 6780606 | 6780606 | 6780606 | County Government of Bungoma |  | 6780606 |  | 6780606 | 99.87% | 6780606 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
619 | Upgrading of Roads In Kaptama Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43961 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
776 | Periodic Maintenance of Kaptama Market - Kaborom Primary - Ack Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44333 |  | 7397610 | 7397610 | 7397610 | County Government of Bungoma |  | 7397610 |  | 7397610 |  | 7397610 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
777 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44333 |  | 7397610 | 7397610 | 7397610 | County Government of Bungoma |  | 7397610 |  | 7397610 | 99.92% | 7397610 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1103 | Periodic Maintenance of Chemoge Mkt - Kiptiroko Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44697 |  | 8608824 | 8608824 | 8608824 | County Government of Bungoma |  | 8608824 |  | 8608824 |  | 8608824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1104 | Periodic Maintenance of Kaptama Dip - Bondeni - Kabwoyo - Chebombao Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44699 |  | 8608824 | 8608824 | 8608824 | County Government of Bungoma |  | 8608824 |  | 8608824 |  | 8608824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1105 | Upgrading of Kona Tatu - Kongit - Mashambani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44694 | 44725 | 8229451.8 | 8229451.8 | 8229451.8 | County Government of Bungoma |  | 8229451.8 |  | 8229451.8 |  | 8229451.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1106 | Periodic Maintenance of Kaptama Police - Chelinde - Chwele Ndogo Market | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44695 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1107 | Periodic Maintenance of Roads In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44703 |  | 8608824 | 8608824 | 8608824 | County Government of Bungoma |  | 8608824 |  | 8608824 | 40.66% | 8608824 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1108 | Upgrading of Spot Improvement Of Kona Tatu - Kongit - Mashambani Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44701 |  | 8229451.8 | 8229451.8 | 8229451.8 | County Government of Bungoma |  | 8229451.8 |  | 8229451.8 | 18.23% | 8229451.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1409 | Periodic Maintenance of Kostoi - Chelilde Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45068 |  | 3631101 | 3631101 | 3631101 | County Government of Bungoma |  | 3631101 |  | 3631101 |  | 3631101 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1410 | Periodic Maintenance of Kapsamis - Kongit Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45057 |  | 5331295 | 5331295 | 5331295 | County Government of Bungoma |  | 5331295 |  | 5331295 |  | 5331295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1411 | Periodic Maintenance of Kostoi - Chelindet In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45070 |  | 3631101 | 3631101 | 3631101 | County Government of Bungoma |  | 3631101 |  | 3631101 | 100.0% | 3631101 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1412 | Periodic Maintenance of Kapsami - Kongit Road In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45062 |  | 5331295 | 5331295 | 5331295 | County Government of Bungoma |  | 5331295 |  | 5331295 | 98.85% | 5331295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1661 | Construction of Chepsoingei Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45434 |  | 7187389 | 7187389 | 7187389 | County Government of Bungoma |  | 7187389 |  | 7187389 |  | 7187389 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1662 | Periodic Maintenance of Kostoi Chelilde Chebombai In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45432 |  | 4483400 | 4483400 | 4483400 | County Government of Bungoma |  | 4483400 |  | 4483400 | 99.95% | 4483400 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1663 | Periodic Maintenance of Kaptama Chepkerer Road In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45423 |  | 5132043 | 5132043 | 5132043 | County Government of Bungoma |  | 5132043 |  | 5132043 | 99.99% | 5132043 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1664 | Periodic Maintenance of Kiptiroko Sosio River Road In Kaptama Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45424 |  | 2841594 | 2841594 | 2841594 | County Government of Bungoma |  | 2841594 |  | 2841594 | 99.99% | 2841594 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1665 | Proposed Chepsoingei Box Culvert In Kaptama Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | Kaptama |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45422 |  | 7187389 | 7187389 | 7187389 | County Government of Bungoma |  | 7187389 |  | 7187389 | 99.96% | 7187389 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
2 | Preparation of Local and Physical Land use development Plan for Kaptama | Redesigning of Urban areas | To guide sustainable and inclusive growth of urban areas through land use,infrastructure development and improved service delivery | one Physical and land use plan for Kaptama developed | 2211311 | Development/Physical Planning | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45386 | 45392 |  | 4800000 | 4758900 | 4758900 | CGB | N/A | 4758900 | 0 | 4758900 | 1 | 0 | 4758900 | 0 | Ongoing | 0.5 | N/A | N/A | N/A | N/A | 0 | No | [8 empty] | The project is 50% complete
10 | Purchase of 1 Acre for Chepkitale dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | One acre of Land purchased for Chepkitale dispensary | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 |  |  |  | 1000000 | - | 1000000 | CGB | N/A | 1000000 | 0 | 1000000 | 1 | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2023/24 |  | 0 | No | Compete | [7 empty] | The project is stalled due Lack of documentations(Title deed)
63 | Purchase Of 1/4 Land For Kongta E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One quarter acre of Land For Kongta E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  |  |  | 500000 | 200000 | 200000 | CGB |  | 200000 |  | 200000 | 1 |  |  |  | Stalled | [15 empty] | The project is staled due Lack of documentations(Title deed)
64 | Purchase Of 1 Acre For Tobosom E.C.D.E . | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of Land For Tobosom E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  |  |  | 500000 | 400000 | 400000 | CGB |  | 400000 |  | 400000 | 1 |  |  |  | Stalled | [15 empty] | The project is staled due Lack of documentations(Title deed)
65 | Purchase Of 1 Acre For Lolongbei E.C.D.E . | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | One acre of LandFor Lolongbei E.C.D.E Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2020/21 |  |  |  | 500000 | 400000 | 400000 | CGB |  | 400000 |  | 400000 | 1 | 0 |  |  | Stalled | [15 empty] | The project is staled due Lack of documentations(Title deed)
151 | purchase of 1 acre land for Kaboram Sec. School | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Kaboram Sec. School Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
197 | purchase of 1/2 acre land for kongit Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | A half an acre of Land for kongit Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 18/08/2014 | 18/11/2014 | 42310 | 200000 | 200000 | 200000 | CGB | N/A | 200000 |  | 200000 | 1 | 200000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
198 | purchase 1/2 acre land Chemoge dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | A half an acre of Land for Chemoge Dispensary Purchased | 3110599 | Ward based projects | Mt. Elgon | Kaptama |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 | 18/08/2014 | 18/11/2014 | 42310 | 300000 | 300000 | 300000 | CGB | N/A | 300000 |  | 300000 | 1 | 300000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
8 | Construction of 1 No. ECDE classroom at Kibei, Sirgoi, Kapchebon and Iya primary Schools in Kaptama Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 6000000 | 5761960 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 4361770.01 | 0.75699 | 4361770.01 | 1400189.99 | 1400189.99 | Completed
44 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Tulwo, Kapteganted, Kaboywo And Baptist Primary Schools In Kaptama Ward | Construction of ECDE classroom | To construct perimeter wall fence improving security | Perimeter wall fence constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 6000000 | 5956608 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 4950381.45 | 0.83107 | 4950381.45 | 1006226.55 | 1006226.55 | Complete and in use | 1
78 | Construction of 1no ecde classrooms and one pit latrine at chebombai prymary | Construction of ECDE classroom and pit latrine | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1500000 | 1489500 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1202688.1 | 0.80744 | 1202688.1 | 286811.9 | 286811.9 | ongoing and not in use | 0.6
79 | Kiptiroko VTC | Construction of VTC | To construct of VTC providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1500000 | 1500000 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | Complete and in use | 1
112 | Construction Of `1 No. Ecde Classroom And 2 No. Door Pit Latrine At Kostoi, Cherongos And Chelilde Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4500000 | 3552856 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 0 | 0 | 0 | 3552856 | 3552856 | complete and in use | 1
140 | Proposed Erection And Completionof 1 No. Ecde At Kamenjo Primary School In Kaptama Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1500000 | 1461100 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1461100 | 1 | 1461100 | 0 | 0 | COMPLETE. | 1
194 | Construction Of 01 No.Ecde Classroom At Chepsoikel And Kiptiroko Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | Kaptama |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2000000 | 3366540 | 2000000 | County Government of Bungoma | N/A | 2000000 |  | 3366540 | 1 | 3366540 | 0 |  | complete and in use | 100.0%
92 | Kongit Water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 1 Water project constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4000000 | 3974856 | 3974856 | CGB | N/A | 3974856 | 0 | 3974856 | 1 | 0 | 3974856 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
191 | REHABILITATION OF CHIKONDI - KAPCHEBON AND KAPTELELIO WATER PROJECTS IN KAPTAMA WARD | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 3500000 | 3393519 | 3393519 |  | N/A | 3393519 | 0 | 3393519 | 1 | 0 | 3393519 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
244 | REHABILITATION AND EXTENSION OF WATER PIPELINE IN KAPTAMA WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1900000 | 1801135 | 1801135 |  | N/A | 1801135 | 0 | 1801135 | 1 | 1801135 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
315 | CONSTRUCTION OF CHESITO KAPTAMA WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 5500000 | 5391680 | 5391680 |  | N/A | 5391680 | 0 | 5391680 | 1 | 5391680 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
363 | Construction of 2 roof Catchment and Construction of a 50m3 Storage Tank (Kaptama Boys) | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 2 roof catchment constructed and 1 tank constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 656848 | 656848 |  | N/A | 656848 | 0 | 656848 | 1 | 656848 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
379 | Construction of roof catchment.(Kaptama Girls) | Erection of storage tank; pipe laying and costruction of water points | To enhance access to clean and safe drinking water | 1 roof catchment constructed; 1 storage tank erected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 699757 | 699757 |  | N/A | 699757 | 0 | 699757 | 1 | 699757 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
412 | Protection of water Springs and drilling of borehole | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 water springs constructed and 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 3000000 | 2738110.4 | 2738110.4 |  | N/A | 2738110.4 | 0 | 2738110.4 | 1 | 2738110.4 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
460 | Protection of 3 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 800000 | 794413 | 794413 |  | N/A | 794413 | 0 | 794413 | 1 | 794413 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
541 | Protection of 3 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 794413 | 794413 |  | N/A | 794413 | 0 | 794413 | 1 | 794413 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
542 | Construction of 5 roof Catchment and Construction of a 50m3 Storage Tank (Kaptama Boys) | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchments constructed and 1 water tank constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2300000 | 2189498 | 2189498 |  | N/A | 2189498 | 0 | 2189498 | 1 | 2189498 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
543 | Construction of 2 roof catchment.(Kaptama Girls and Boys) | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 2 roof catchments constructed and 1 water tank constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 699757 | 699757 |  | N/A | 699757 | 0 | 699757 | 1 | 699757 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
617 | Kaptama/Kaborong pipeline rehabilitation and Kaboywo water Project Pipeline extension and 1 roof Catchment | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | Kaptama |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3422638 | 3422638 |  | N/A | 3422638 | 0 | 3422638 | 1 | 3422638 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
8 | Construction of Kaptama ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Kaptama ward office constructed | 3111504 | Construction of non- residential buildings | Mt. Elgon | Kaptama | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 44131 | 9500000 | 9403690 | 9500000 | County Government of Bungoma | - | 9403690 | - | 9403690 | 1 | 9403690 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Purchase of seedlings for Kaptalelio SLM Project | Purchase of seedlings for Kaptalelio SLM Project | To enhance production, productivity and income generation | Seedlings purchased and distributed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 |  |  |  |  | 1450720 | 1500000 | Development partner | IDA | 0 | 1450720 | 1450720 |  | 1450720 | 0 | 0 | Completed
| Construction of Kaptama dairy technology centre | Construction of Kaptama dairy technology centre in Kaptama ward. | To enhance milk production, productivity, value addition and income among the farmers | 1 dairy technology centre constructed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44785 |  | 24/4/2024 |  | 9920110 | 10000000 | Development partner | IDA | 0 | 9920110 | 9920110 |  | 9920110 | 0 | 0 | Completed
| Purchase of seedlings for Samita- Kaborom SLM Project | Purchase of seedlings for Samita- Kaborom SLM Project | To enhance fruit production, productity and income generation | Seedlings purchased and distributed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44784 | 45139 | 45079 |  | 1566800 | 1566800 | Development partner | IDA | 0 | 1566800 | 1566800 |  | 1566800 | 0 | 0 | Completed
| Purchase and installation of pond liners, water tanks and solar pump kits | Purchase and installation of pond liners, water tanks and solar pump kits for Samita -Kaborom SLM project | To control loss of water through infiltration | 1,165,117 pcs of pond liners purchased, delivered and installed | 2640503 | Other Capital grants and transfer (NARGIP) |  | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44959 | 44963 | 45266 |  | 4440000 | 4500000 | Development partner | IDA | 0 | 4440000 | 4440000 | 1 | 4440000 | 0 | 0 | Completed
| Supply and delivery of Coffee Seedlings in Kaptama Ward | Supply and delivery of Coffee Seedlings in Kaptama Ward | To promote coffee production and enhance income generation among Coffee farmers | 9,000 Coffee seedlings supplied and delivered | 3110599 | Ward Based projects | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 |  | 1020000 | 1,036,00,000 | County Government of Bungoma |  | 1020000 | 0 | 1020000 |  | 1020000 | 0 | 0 | Completed
| Supply and delivery of Coffee Seedlings | Supply and delivery of Coffee Seedlings | To promote coffee production and enhance income generation among Coffee farmers | 75kgs of coffee seedlings supplied and delivered | 3110599 | Ward Based projects | mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 500000 | 498000 | 500000 | County Government of Bungoma |  | 498000 | 0 | 498000 |  | 498000 | 0 | 0 | Completed
| Supply of coffee seedlings | Supply of coffee seedlings | To promote coffee production and enhance income generation among Coffee farmers | 75kgs of coffee seedlings supplied and delivered | 3110599 | Ward Based projects | mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 500000 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 |  | 500000 | 0 | 0 | Completed
| Supply and delivery of coffee seedlings | Supply and delivery of coffee seedlings | To promote coffee production and enhance income generation among Coffee farmers | 75kgs of coffee seedlings supplied and delivered | 3110599 | Ward Based projects | mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 500000 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 |  | 500000 | 0 | 0 | Completed
| Provision of improved breeds (sheep) | Provision of 30 ewes and 3 Rams to 3 elite breeders,2 in Naitiri/Kabuyefwe (NAKASIMA SLCA) and one in Kaptama (KAPCHEKO SLCA) | To enhance production, productivity and income generation | 30 ewes and 3 Rams purchased and issued to 3 elite breeders | 2640503 | Other Capital grants and transfer (KeLCoP) | Tongaren/Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45630 | 45633 | 45357 |  | 956880 | 1029280 | Development partner | IFAD | 0 | 956880 | 956880 |  | 956880 | 0 | 0 | Complete
| Provision of improved breeds of chicken | Provision of improved breeds (Indigenous poultry) chicken – day old chicks | To enhance production, productivity and income generation | 14 MOFAG beneffitted by each getting 575 breeds | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/3/2024 | 23/6/2024 | 28/5/2024 |  | 1387730 | 1447460 | Development partner | IFAD | 0 | 1387730 | 1387730 |  | 1387730 | 0 | 0 | Complete
| Upscaling production of grass seeds | Upscaling production of grass seeds by distrbuting 100 bags of 50kgs of organic fertilizer | To enhance productivity and income generation | 100 bags of 50kg organic fertilizer procured and distributed to 8 farmers. | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45242 | 45598 | 45444 |  | 144940 | 145 940 | Development partner | IFAD | 0 | 620398 | 144940 |  | 144940 | 0 | 0 | Complete
| Provision of beehives and equipment | Provision of64 langstroth bee hives and 6 bee suits and equipment to 3 groups in KAPCHEKO SLCA |  | 64 Langstroth bee hives and 6 bee suits procured and distributed to 3 groups in KAPCHEKO SLCA | 2640503 | Other Capital grants and transfer (KeLCoP) | Mt. Elgon | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 31/3/2024 | 31/6/2024 | 45510 |  | 620398 | 701410 | Development partner | IFAD | 0 | 620398 | 620398 |  | 620398 | 0 | 0 | Complete
| Purchase and distribution of day old Chicks Rainbow Roosters | Purchase and delivery of 8,050 day old Chicks rainbow roosters to 14 MOFAG Indigenous chicken groups | To enhance poultry production and increase household incomes | 8,050 chicks purchased and delivered to 14 MOFAG indingeneous chicken groups | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi/Mt. Elgon/Tongaren | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 31/3/2024 | 31/6/2024 | 45510
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
92 | Construction of 3No Bodaboda sheds | Of sheds streetlights | [5 empty] | Kaptama |  | Trade, Energy and Industrialization | Dept of Trade | Gabverox general agencies limited | 2021/22 |  | Complete and in use |  | 970000 | 0 |  | CGB
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A | [5 empty] | Kaptama |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Kaptama |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Kaptama |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Kaptama |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
28 | Purchase of medical equipment for Milani dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45356 |  |  | 2000000 | 1880920 | 1880920 | CGB |  | 1880920 | 0 | 0 | 0 | 0 | 1880920 | 1880920 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
55 | erection and completion works for male, female and children wards at milani dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Female, male and children wards erected and completed |  |  | Webuye West | Bokoli |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 20/2/24 |  |  | 5000000 | 4901892 | 4901892 | CGB |  | 4901892 | 0 | 2667780 | 0.54423 | 2667780 |  | 2234112 | On-going | 91 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
69 | Construction Of Wards At Milani Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2500000 | 2254670 | 2254670 | CGB |  | 2254670 | 0 | 2425000 | 1.0755 | 2425000 |  | -170330 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
70 | Construction Of Wards At Machakha Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2500000 | 2303000 | 2303000 | CGB |  | 2303000 | 0 | 545607.69 | 0.23691 | 545607.69 |  | 1757392.31 | On-going | [6 empty] | No | complete | Financial | Yes |  |  |  | No
94 | Completion Of Milimani Dispensary And Extention Works | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries completed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2100000 | 2060000 | 2060000 | CGB |  | 2060000 | 0 | 0 | 0 | 0 |  | 2060000 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
95 | Construction Of Maternity Wards At Mahanga Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wards constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2000000 | 1939880 | 1939880 | CGB |  | 1939880 | 0 | 1531705.24 | 0.78959 | 1531705.24 |  | 408174.76 | Ongoing | [6 empty] | No | complete | Financial | Yes |  |  |  | No
121 | Construction Of Milani Dispenary And 2 Pit Latrines | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries and 2no pit latrines constructed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2700000 | 2599107.6 | 2599107.6 | CGB |  | 2599107.6 | 0 | 1242058.4 | 0.47788 | 1242058.4 |  | 1357049.2 | Complete and in use | [6 empty] | No | complete | Financial | Yes
153 | Proposed Erection And Competion Works At Machakha Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Webuye West | Bokoli |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2066537 | 1984990 | 1984990 | CGB |  | 1984990 | 0 | 1757803 | 0.88555 | 1757803 |  | 227187 | Complete and not in use | [6 empty] | No | complete | Financial | Yes
35 | Construction of Kituni Mkt-R.Kuywa-Miendo Junt With Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41661 | 41783 |  | 16111704 | 16111704 | 16111704 | County Government of Bungoma |  | 16111704 |  | 16111704 | 100.0% | 16111704 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
147 | Periodic Maintenance of Wanyonyi - Mahale-Kaita Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43120 | 43241 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 |  | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
148 | Periodic Maintenance of Namawanga - Miendo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43233 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 |  | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
149 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43232 |  | 9174828 | 9174828 | 9174828 | County Government of Bungoma |  | 9174828 |  | 9174828 | 99.24% | 9174828 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
277 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
278 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
463 | Periodic Maintenance of Sawa- Wanambisi - Kakai Road | Road improvement works | To improve the road condition and enhance accessibility | Road gravelled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43963 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 |  | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
464 | Periodic Maintenance of Mukhale Kaita Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43975 | 44006 | 3137684 | 3137684 | 3137684 | County Government of Bungoma |  | 3137684 |  | 3137684 |  | 3137684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
465 | Periodic Maintenance of Temba-Muchocho Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
466 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43968 |  | 3137684 | 3137684 | 3137684 | County Government of Bungoma |  | 3137684 |  | 3137684 | 99.9% | 3137684 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
637 | Routine Maintenance Of Roads In Webuye East And Webuye West Sub- Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
638 | Drainage Works In Webuye East And Webuye West Sub-Counties(Lot 4) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43966 |  | 4941426 | 4941426 | 4941426 | County Government of Bungoma |  | 4941426 |  | 4941426 | 88.12% | 4941426 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
688 | Construction of Tuliyonga - Mahanga Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44326 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
689 | Periodic Maintenance of Tuliyonga - Abel - Mahanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44328 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
690 | Periodic Maintenance of Miendo - Chebini Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44326 | 44357 | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 |  | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
691 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44334 |  | 8838538.8 | 8838538.8 | 8838538.8 | County Government of Bungoma |  | 8838538.8 |  | 8838538.8 | 99.89% | 8838538.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1024 | Periodic Maintenance of Moyokwe - Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44699 | 44730 | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1025 | Periodic Maintenance of Chebosi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44694 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1026 | Periodic Maintenance of Namilimo - Sitabicha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 |  | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1027 | Periodic Maintenance of Bruno - Namawanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44701 | 44732 | 5707519.8 | 5707519.8 | 5707519.8 | County Government of Bungoma |  | 5707519.8 |  | 5707519.8 |  | 5707519.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1028 | Periodic Maintenance of Asiba - Kaliwanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44699 | 44730 | 3736012 | 3736012 | 3736012 | County Government of Bungoma |  | 3736012 |  | 3736012 |  | 3736012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1029 | Periodic Maintenance of Roads In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44701 |  | 8095437 | 8095437 | 8095437 | County Government of Bungoma |  | 8095437 |  | 8095437 | 99.73% | 8095437 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1030 | Routine Maintenance Of Bruno - Namawanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44697 |  | 5707519.8 | 5707519.8 | 5707519.8 | County Government of Bungoma |  | 5707519.8 |  | 5707519.8 | 100.0% | 5707519.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1031 | Routine Maintenance Of Asiba - Kaliwanga Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44695 |  | 3736012 | 3736012 | 3736012 | County Government of Bungoma |  | 3736012 |  | 3736012 | 97.38% | 3736012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1253 | Routine Maintenance Of Mahanga Secondary - Chekulo - Sikinga Market Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44693 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1344 | Construction of Chebini Box Culvert On River Bokoli | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45070 |  | 6088985 | 6088985 | 6088985 | County Government of Bungoma |  | 6088985 |  | 6088985 |  | 6088985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1345 | Periodic Maintenance of Nandasaba - Sirwa - Sichai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45064 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 |  | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1346 | Periodic Maintenance of Mlani - Muresia - Mary Kangia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45067 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 |  | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1347 | Construction of Chebini Box Culvert Bokoli River Road In Bokoli Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45063 |  | 6088985 | 6088985 | 6088985 | County Government of Bungoma |  | 6088985 |  | 6088985 | 99.54% | 6088985 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1348 | Periodic Maintenance of Nandasaba - Sirwa - Sichai, Mlani - Muresia - Mary Kangia Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45059 |  | 7221626 | 7221626 | 7221626 | County Government of Bungoma |  | 7221626 |  | 7221626 | 100.0% | 7221626 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1600 | Periodic Maintenance of Wangwelo - Bokoli River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45431 |  | 3650346 | 3650346 | 3650346 | County Government of Bungoma |  | 3650346 |  | 3650346 |  | 3650346 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1601 | Periodic Maintenance of Wangamati - Malaria - Manga Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45433 |  | 5503411 | 5503411 | 5503411 | County Government of Bungoma |  | 5503411 |  | 5503411 |  | 5503411 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1602 | Periodic Maintenance of Wangwelo - Bokoli River Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45427 |  | 3650346 | 3650346 | 3650346 | County Government of Bungoma |  | 3650346 |  | 3650346 | 99.83% | 3650346 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1603 | Periodic Maintenance of Wangamati - Malaria - Manga Primary Road In Bokoli Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45435 |  | 5503411 | 5503411 | 5503411 | County Government of Bungoma |  | 5503411 |  | 5503411 | 98.4% | 5503411 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1604 | Periodic Maintenance of Roads In Webuye East And West Sub Counties Chesoli(Mulembe)-John Waswa-R.Kuywa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye West | Bokoli |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45426 |  | 3883096.4 | 3883096.4 | 3883096.4 | County Government of Bungoma |  | 3883096.4 |  | 3883096.4 | 99.32% | 3883096.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
3 | Purchase of 1 Acre land for Auction ring | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new auction ring | One acre of Land Purchased for auction ring | 3130101 | Purchase of land | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 |  |  |  | 1000000 | - | 1000000 | CGB | N/A | 1000000 | 0 | 1000000 | 1 | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2023/24 |  | 0 | No | Compete | [7 empty] | The project is stalled due Lack of documentations(Title deed)
110 | Purchase Of Land For Proposed Machakha Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new dispensary | One acre of Land for Machakha dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42866 | 18/4/2018 | 30/6/2018 | 700000 | 700000 | 700000 | CGB | N/A | 700000 | 0 | 700000 | 1 | 800000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
111 | Purchase Of Land For Proposed Milani Dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a new dispensary | One acres of Land for Milani Dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43049 | 15/3/2018 | 18/6/2018 | 700000 | 700000 | 700000 | CGB | N/A | 700000 | 0 | 700000 | 1 | 800000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
165 | Purchase of land-NAMATONDOI ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for NAMATONDOI E.C.D.E Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 750000 | 750000 | 750000 | CGB | N/A | 750000 |  | 750000 | 1 | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
166 | Purchase of 1 acre for milani dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for milani dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 15/8/2015 | 15/11/2015 | 13/12/2015 | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 1 | 1000000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
167 | Purchase of 1 acre for machakha dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for milani dispensary Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/01/2016 | 21/03/2016 | 42647 | 475500 | 475500 | 475500 | CGB | N/A | 475500 |  | 475500 | 1 | 475500 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
176 | Purchase of land for Namatondoi ECDE Centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Namatondoi ECDE Purchased | 3110599 | Ward based projects | Webuye West | Bokoli |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42461 | 42707 | 42466 | 700000 | 700000 | 700000 | CGB | N/A | 700000 |  | 700000 |  | 700000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
67 | Construction of ECDE classroom at matisi pry school | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1200000 | 1197500 | 1200000 | County Government of Bungoma | N/A | 1200000 | 0 | 0 | 0 | 0 | 1197500 | 1197500 | Complete and not in use | 1
99 | Construction Of 1 No. Ecde Classroom At Chebosi And Miendo Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3000000 | 2895000 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2895000 | 1 | 2895000 | 0 | 0 | complete and in use | 1
130 | Proposed Erection And Completion Of 1 No. Ecde At Sikimbilo Rc, Maloho And Ben Kapten Primary Schools In Bokoli Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 4800000 | 4787390 | 4800000 | County Government of Bungoma | N/A | 4800000 | 0 | 4787190 | 0.99996 | 4787190 | 200 | 200 | complete and in use | 1
165 | Construction Of Ecde Classrooms At Mahanga Primary, Milani, Namilimo Primary And Namatondoi Primary | Construction of ECDE classroom and pit latrine | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli | [5 empty] | 43801 | 43775 |  | 4900000 | 5649840 | 4900000 | County Government of Bungoma | N/A | 4900000 | 0 | 5649840 | 1 | 5649840 | 0 |  | complete and in use | 1
182 | The Proposed Erection And Completion Of 1 N0 Classroom At Lukuku, Bokoli R.C And Sawa Primary School In Bokoli Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye West | Bokoli |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4150000 | 3515809 | 4150000 | County Government of Bungoma | N/A | 4150000 |  | 3515809 | 1 | 3515809 | 0 |  | complete and in use | 100.0%
2 | Construction and protection of Sirandafu Spring | Rehabilitation of spring, rehabilitation of sump, installation of solar pumping system, pipelaying; erction of a 30cubic metres, elevated pressed tank; construction of water points. | To enhance access to clean and safe drinking water | 1 Spring constructed and protected | 2640599 | Other Capital Grants and Transfers | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 6000000 | 5812644 | 5812644 | FLLOCA | N/A | 5812644 | 0 | 0 | 1 | 5812644 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
45 | Upgrading of Matunda Borehole in Bokoli Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2960900 | 2960900 | CGB | N/A | 2960900 | 0 | 2960900 | 1 | 2960900 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
53 | Upgrading of Sawa Borehole in Bokoli Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2950000 | 2950000 | CGB | N/A | 2950000 | 0 | 2950000 | 1 | 2950000 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
138 | Drilling of borehole at matunda market ,machakha and bumang'ale | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4945500 | 4945500 |  | N/A | 4945500 | 0 | 4945500 | 1 | 4945500 | 0 | 0 | complete and operational | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
179 | DRILLING AND EQUIPPING OF NAMILIMO BOREHOLE | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2000000 | 1795680 | 1795680 |  | N/A | 1795680 | 0 | 1795680 | 1 | 1795680 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
234 | DRILLING OF SAWA AND SIKILIMBO MARKET BOREHOLES IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 3800000 | 3678824 | 3678824 |  | N/A | 3678824 | 0 | 3678824 | 1 | 3678824 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
235 | DRILLING OF NAMATONDOI PRIMARY BOREHOLE IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 1800000 | 1789880 | 1789880 |  | N/A | 1789880 | 0 | 1789880 | 1 | 1789880 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
274 | DRILLING OF KAG CHURCH BOREHOLE IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1800000 | 1699900 | 1699900 |  | N/A | 1699900 | 0 | 1699900 | 1 | 1699900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
275 | DRILLING OF CHEBINI AND MAKUNDA BOREHOLES IN BOKOLI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 3500000 | 3398000 | 3398000 |  | N/A | 3398000 | 0 | 3398000 | 1 | 3398000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
297 | CONSTRUCTION OF 4NO. SPRINGS AND DRILLING OF 1 BOREHOLE IN BOKOLI WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection;site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Boreholes rehabilitated and 4 water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2500000 | 2458624 | 2458624 |  | N/A | 2458624 | 0 | 2458624 | 1 | 2458624 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
351 | Construction of 5Roof catchments and supply 10m3 Plastic tank at stikho youth polytechnic. | Erection of a storage tank;pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 696710 | 696710 |  | N/A | 696710 | 0 | 696710 | 1 | 696710 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
368 | Nzowasco pipeline extension to Matulo | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1200000 | 1116520 | 1116520 |  | N/A | 1116520 | 0 | 1116520 | 1 | 1116520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
411 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1421260 | 1421260 |  | N/A | 1421260 | 0 | 1421260 | 1 | 1421260 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
516 | Protection of 8 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1300000 | 1116520 | 1116520 |  | N/A | 1116520 | 0 | 1116520 | 1 | 1116520 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
517 | Drilling of Borehole and equipping with handpump at Sirwa | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1881065 | 1881065 |  | N/A | 1881065 | 0 | 1881065 | 1 | 1881065 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
595 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1421260 | 1421260 |  | N/A | 1421260 | 0 | 1421260 | 1 | 1421260 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
596 | Miendo piped scheme | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye West | Bokoli |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2363240 | 2363240 |  | N/A | 2363240 | 0 | 2363240 | 1 | 2363240 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
4 | Construction of Bokoli ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Bokoli ward office constructed | 3111504 | Construction of non- residential buildings | Webuye West | Bokoli | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43060 | 9500000 | 8960963 | 9500000 | County Government of Bungoma | - | 8960963 | - | 8960963 | 1 | 8960963 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Construction of Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | Construction of 20 Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | To support growth of coffee farmers and enhance income generation | 20 Coffee drying tables constructed | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44900 | 44838 | 10000000 | 3087863.88 | 3100000 | County Government of Bungoma |  | 3087863.88 | 0 | 3087863.88 | 1 | 3087863.88 | 0 | 0 | Completed
| Construction of Coffee Drying Tables at Sirandafu FCS in Bokoli Ward | Construction of 20 Coffee Drying Tables at Sirandafu FCS in Bokoli Ward | To support growth of coffee farmers and enhance income generation | 20 Coffee Drying tables constructed at Sirandafu FCS | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 21/1/2024 | 21/5/2024 | 15/6/2024 |  | 1997000 | 2000000 | County Government of Bungoma |  | 1997000 | 0 | 1997000 | 1 | 1997000 | 0 | 0 | Completed
46 | Proposed installation and commissioning of 3NO. 15M high solar powered floodlights | installation of M M high | promotion of MSMEs and security | Solar flood lights installed | 1358968/2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Project is complete | Complete and in use | 3000000 | 2909990 |  | CGB | [8 empty] | Complete | 100 | 3
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye |  |  |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A |  |  |  |  | Webuye West | Bokoli |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of |  |  |  |  | Webuye West | Bokoli |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
137 | Renovation of Matisi market | [5 empty] | Webuye West | Bokoli |  |  |  | Dynamic General Construction | 2016/17 |  | Complete |  | 12422753.2 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | Webuye West | Bokoli |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights |  |  |  |  | Webuye West | Bokoli |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
53 | Construction of 4NO.Doors Pit Latrines with urinal at Khaoya Recreational Centre. | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Kanduyi | Bukembe west |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 13/2/2024 |  |  | 800000 | 697650 | 697650 | CGB |  | 697650 | 0 | 0 | 0 | 0 |  | 697650 | On-going | 92 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
97 | Construction Of 2no Door Pit Latrines At Matumbufu primary school |  |  | 2No. Door pit latrines constructed |  |  | Kanduyi | Bukembe west |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 500000 | 495820 | 495820 | CGB |  | 495820 | 0 |  | 0 |  |  | 495820 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
196 | Construction Of Namirembe Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Kanduyi | Bukembe west |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 3500000 | 3321729.6 | 3321729.6 | CGB |  | 3321729.6 | 0 | 3321729.6 | 1 | 3321729.6 |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes
197 | Construction of 2no Ecosan pit latrines at Ndengelwa and Ekitale Markets | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Ecosan pit latrines constructed |  |  | Kanduyi | Bukembe west |  |  | WBPSPCU | Health & Sanitation | 2018-2019 | [6 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes
215 | Purchase Of Land For Namirembe Dispensary | Land identification, search,survey, signing of sell agreements,payment and transfer of ownership of the title. | To provide physical space for construction of health services in the area | acres of land purchased |  |  | Kanduyi | Bukembe west |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2000000 | 1200000 | 1200000 | CGB |  | 1200000 | 0 |  | 0 |  |  | 1200000 | Complete and in use | [6 empty] | No | complete | Financial | Yes
216 | Completion Of Ndengelwa Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries completed |  |  | Kanduyi | Bukembe west |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1169707 | 1344086.2 | 1344086.2 | CGB |  | 1344086.2 | 0 | 1343297.4 | 0.99941 | 1343297.4 |  | 788.8 | Complete and in Use | [6 empty] | No | complete | Financial | Yes
283 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
284 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
472 | Periodic Maintenance of Mabanga - Ekitale Centre Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43967 |  | 11899433 | 11899433 | 11899433 | County Government of Bungoma |  | 11899433 |  | 11899433 |  | 11899433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
473 | Upgrading of Makotelo - Namiremembe Market Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43970 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
474 | Periodic Maintenance of Kisuluni - Serikali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43961 |  | 4665056 | 4665056 | 4665056 | County Government of Bungoma |  | 4665056 |  | 4665056 |  | 4665056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
475 | Periodic Maintenance of Kwa Mukunga - Nalutiri Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43971 |  | 4665056 | 4665056 | 4665056 | County Government of Bungoma |  | 4665056 |  | 4665056 |  | 4665056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
476 | Periodic Maintenance of Roads In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43972 |  | 4665056 | 4665056 | 4665056 | County Government of Bungoma |  | 4665056 |  | 4665056 | 93.12% | 4665056 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
477 | Periodic Maintenance of Mabanga-Ekitale Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.9KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43963 |  | 11899433 | 11899433 | 11899433 | County Government of Bungoma |  | 11899433 |  | 11899433 | 97.31% | 11899433 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
663 | Drainage Works In Kanduyi And Bumula Sub-Counties(Lot 2) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 | 96.54% | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
699 | Periodic Maintenance of Makayo - Matumbufu Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44326 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 |  | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
700 | Construction of Lutaso - Maniafu Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44219 | 44336 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 |  | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
701 | Construction of Lutaso - Matumbufu Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44326 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 |  | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
702 | Periodic Maintenance of Roads In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44335 |  | 3900036 | 3900036 | 3900036 | County Government of Bungoma |  | 3900036 |  | 3900036 | 100.0% | 3900036 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1034 | Periodic Maintenance of Muyayi - Noco Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44692 | 44723 | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 |  | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1035 | Periodic Maintenance of Bishop Siabuta Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44693 | 44724 | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 |  | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1036 | Periodic Maintenance of Puloti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44692 | 44723 | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 |  | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1037 | Upgrading of Lumoro - Namirembe Dispensary | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44698 | 44729 | 9072423.8 | 9072423.8 | 9072423.8 | County Government of Bungoma |  | 9072423.8 |  | 9072423.8 |  | 9072423.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1038 | Periodic Maintenance of Roads In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44696 |  | 6792542.4 | 6792542.4 | 6792542.4 | County Government of Bungoma |  | 6792542.4 |  | 6792542.4 | 7.36% | 6792542.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1039 | Spot Improvement Of Lumoro - Sichekereni Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 |  | 9072423.8 | 9072423.8 | 9072423.8 | County Government of Bungoma |  | 9072423.8 |  | 9072423.8 | 100.0% | 9072423.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1252 | Upgrading of Roads In Bukembe West Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44694 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1351 | Periodic Maintenance of Muyayi Primary Sch. - Bulafu - Misiko - Wilbroda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45062 |  | 3899572 | 3899572 | 3899572 | County Government of Bungoma |  | 3899572 |  | 3899572 |  | 3899572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1352 | Periodic Maintenance of Muyayi Primary School - Bulafu - Misiko - Wilbroda Road In Bukembe West | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45060 |  | 3899572 | 3899572 | 3899572 | County Government of Bungoma |  | 3899572 |  | 3899572 | 96.29% | 3899572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1606 | Periodic Maintenance of Ndengelwa - Marabi Road And Maniafu Road In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45422 |  | 5361336 | 5361336 | 5361336 | County Government of Bungoma |  | 5361336 |  | 5361336 | 100.0% | 5361336 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1607 | Periodic Maintenance of Marufutu - Khaoya Road, Khaoya Primary - Lifecare Road And Lambert - River Khalaba Road In Bukembe West Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45435 |  | 4586196 | 4586196 | 4586196 | County Government of Bungoma |  | 4586196 |  | 4586196 | 99.82% | 4586196 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1608 | Periodic Maintenance of Gannaps Petrol Station - Ndengelwa Primary Road In Bukembe West Ward (1450749-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | Bukembe west |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45434 |  | 5045565 | 5045565 | 5045565 | County Government of Bungoma |  | 5045565 |  | 5045565 | 100.0% | 5045565 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
33 | Proposed Erection And Completion Works Of 2no. Ecde Classroom At Kisuluni Primary School In Bukembe West Ward | Completion of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2781500 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2311226.6 | 0.83093 | 2311226.6 | 470273.4 | 470273.4 | Complete and in use | 1
101 | Construction Of Community Resorce Centre At Ndengelwa | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 6000000 | 12705020 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 4406239.05 | 0.34681 | 4406239.05 | 8298780.95 | 8298780.95 | complete and in use | 1
166 | Construction Of 1 Classroom At Namirembe Vtc And 2 Classrooms At Muyayi Vtc. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  |  |  |  | 3600000 | 3594460 | 3600000 | County Government of Bungoma | N/A | 3600000 | 0 | 3594460 | 1 | 3594460 | 0 |  | complete and in use | 1
185 | Construction Of 1no. Ecde Classroom At Khaoya, Namirembe And Muyayi Vtc In Bukembe West Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3169708 | 3434230 | 3169708 | County Government of Bungoma | N/A | 3169708 |  | 3434230 | 1 | 3434230 | 0 |  | complete and in use | 100.0%
186 | Construction Of 1no. Ecde Classroom At Matumbufu And Chemche Primary Schools In Bukembe West Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | Bukembe west |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3169708 | 3165858 | 3169708 | County Government of Bungoma | N/A | 3169708 |  | 3165858 | 1 | 3165858 | 0 |  | complete and in use | 100.0%
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | Water pipeline extended | 2640599 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 |  |  |  | FLLOCA | N/A |  | 0 |  | 1 |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
40 | Proposed Supply And Installation Of Combustion Chamber For Improved Stoves And Energy Centre For Research On Training Of Energy Technologies In Khasoko And Bukembe West Wards | 1.construction of combustion chamber (Kiln) for production of clean energy saving jikos. 2.Provision and Assemblying of production materials for the two burner / saving jikos. 3.Training of youths and women on installation of single /two burner jikos to the community. | To promote climate change mitigation and adaptation | Construction of combustion chambers in 2 wards | 2640599 | Other Capital Grants and Transfers | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 6000000 | 5950005 | 5950005 | FLLOCA | IDA | 0 | 5950005 | 0 | 1 | 0 | 0 |  | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
46 | Lutaso-Matumbufu Water Project in Bukembe West Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 1 Water project upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 9000000 | 8550000 | 8550000 | CGB | N/A | 8550000 | 0 | 8550000 | 1 | 8550000 | 0 | 0 | Complete and in use | 100% complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
54 | Protection of 5no. Water springs in Bukembe West ward | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 1000000 | 968890 | 968890 | CGB | N/A | 968890 | 0 | 968890 | 1 | 968890 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
55 | Pipeline Extension at Namirembe and Khaoya in Bukembe West Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3000000 | 2768000 | 2768000 | CGB | N/A | 2768000 | 0 | 2768000 | 1 | 2768000 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
99 | Upgrading of Namirembe dispensary borehole in bukembe west ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 3800000 | 3581280 | 3581280 |  | N/A | 3581280 | 0 | 3581280 | 1 | 3581280 |  | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
139 | drilling and equipping of khaoya primary school | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 4700000 | 4620396 | 4620396 |  | N/A | 4620396 | 0 | 4620396 | 1 | 4620396 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
140 | extension of pipeline in bukembe west ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2800000 | 2614524 | 2614524 |  | N/A | 2614524 | 0 | 2614524 | 1 | 2614524 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
180 | EXTENSION OF MAKOTELO AND LUTASO NZOWASCO PIPELINE IN WEST BUKEMBE WARD | Trenching ; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1950000 | 1921679.8 | 1921679.8 |  | N/A | 1921679.8 | 0 | 1921679.8 | 1 | 1921679.8 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
262 | LAYING OF PIPELINES IN BUKEMBE WEST WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | Bukembe west |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1200000 | 1053280 | 1053280 |  | N/A | 1053280 | 0 | 1053280 | 1 | 1053280 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
10 | Construction of Bukembe West ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Bukembe West ward office constructed | 3111504 | Construction of non- residential buildings | Kanduyi | Bukembe west | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43300 | 9500000 | 10361120 | 9500000 | County Government of Bungoma | - | 10361120 | - | 10361120 | 1 | 10361120 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Purchase of tree seedlings for planting in institutions | Purchase of tree seedlings for planting at Hututu Primary, Bukembe S.A, Chief’s Office, Kongoli dispensary, Bukembe Mkt, and Nandolia Mkt | To improve the environment and create awareness on importance of trees | Tree seedlings purchased and distributed | 3111301 | Purchased of certified crop seed | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 43375 | 5000000 | 400000 | 400000 | County Government of Bungoma |  | 400000 | 0 | 400000 | 1 | 400000 | 0 | 0 | Completed
| Rehabilitation of cattle dips | Rehabilitation of cattle dips in Luuya, Kibisi, Bukembe, Lutaso, Tulumba, and Myanga Cattle Dips | To improve animal health and productivity | 6 Cattle dips rehabiliatated | 3110504 | Other infrastructure and civil works | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44136 | 44139 | 14/3/2020 | 5000000 | 3486950 | 3548016 | County Government of Bungoma |  | 3486950 | 0 | 3486950 | 1 | 3486950 | 0 | 0 | Completed
| Tree Planting in public schools | Tree Planting in public schools | To preserve the environment and create awareness of tree plantation | 3,230 tree supplied and planted | 3110599 | Ward Based projects | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 15/11/2020 | 15/2/2021 | 22/12/2021 | 500000 | 485250 | 500000 | County Government of Bungoma |  | 485250 | 0 | 485250 | 1 | 485250 | 0 | 0 | Completed
| Purchase of Dairy cows for women groups across the ward | Purchase of Dairy cows for women groups across the ward | To increase dairy production, value addition and income generation | 29 Dairy cows purchased | 3110599 | Ward Based projects | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 44287 | 44290 | 44472 | 3000000 | 2900000 | 3000000 | County Government of Bungoma |  | 2900000 | 0 | 2900000 | 1 | 2900000 | 0 | 0 | Completed
| Planting of assorted tree seedlings in public places | Planting of assorted tree seedlings in public places | To promote environmental awareness | Assorted seedlings planted in public institutions | 3111301 | Purchase of Certified Crop seed | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 45232 | 3000000 | 2999999 | 3000000 | County Government of Bungoma |  | 2999999 | 0 | 2999999 | 1 | 2999999 | 0 | 0 | Completed
| Provision of improved breeds of chicken | Provision of improved breeds (Indigenous poultry) chicken – day old chicks | To enhance production, productivity and income generation | 14 MOFAG beneffitted by each getting 575 breeds | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/3/2024 | 23/6/2024 | 28/5/2024 |  | 1387730 | 1447460 | Development partner | IFAD | 0 | 1387730 | 1387730 |  | 1387730 | 0 | 0 | Complete
| Upscaling production of grass seeds | Upscaling production of grass seeds by distrbuting 100 bags of 50kgs of organic fertilizer | To enhance productivity and income generation | 100 bags of 50kg organic fertilizer procured and distributed to 8 farmers. | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45242 | 45598 | 45444 |  | 144940 | 145 940 | Development partner | IFAD | 0 | 620398 | 144940 |  | 144940 | 0 | 0 | Complete
| Purchase and distribution of day old Chicks Rainbow Roosters | Purchase and delivery of 8,050 day old Chicks rainbow roosters to 14 MOFAG Indigenous chicken groups | To enhance poultry production and increase household incomes | 8,050 chicks purchased and delivered to 14 MOFAG indingeneous chicken groups | 2640503 | Other Capital grants and transfer (KeLCoP) | Kanduyi | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services-KeLCoP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 31/3/2024 | 31/6/2024 | 45510
37 | Proposed construction of 3 NO. bodaboda sheds | sheds construction of | promotion of MSMEs | Bodaboda sheds constructed | 1357197/2023-24 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Trade | MEGAWIDE BUILDING AND CIVILENGINEERING LIMITED | 2023/2024 |  | Completed | Complete and in use | 1000000 |  |  | CGB | [8 empty] | Complete | 100 | 3
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
86 | Installation of 2 No solar flood lights | lights of 2 No | [5 empty] | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Modular Development enterprise Limited | 2021/22 |  | Complete and in use |  | 1940000 |  |  | CGB
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Bukembe west |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Bukembe west |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Bukembe west |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
119 | Rennovation Of Staff Hause At Bulondo Dispensary |  |  | Staff quarters erected and renovated |  |  | Kanduyi | West Sang'alo |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 3500000 |  |  | CGB |  |  | 0 | 3499499 | #DIV/0! | 3499499 |  | -3499499 | Complete and in use | [6 empty] | No | complete | Financial | Yes
120 | Rennovation Of Ranje Dispensary |  |  | dispensaries renovated |  |  | Kanduyi | West Sang'alo |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 2500000 | 2479000 | 2479000 | CGB |  | 2479000 | 0 | 2479688.1 | 1.0003 | 2479688.1 |  | -688.1 | Complete and in use | [6 empty] | No | complete | Financial | Yes
256 | Completion Of Male Ward/Rehabilitation At Bulondo Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Male ward completed/Rehabilitated |  |  | Kanduyi | West Sang'alo |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 4150000 | 3900660 | 3900660 | CGB |  | 3900660 | 0 | 3899039.4 | 0.99958 | 3899039.4 |  | 1620.6 | Complete and in use | [6 empty] | No | complete | Financial | Yes
9 | Upgrading of Ekitale-Sangalo-Namwacha-Bulondo R.Khalaba | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41661 | 41769 |  | 21492706 | 21492706 | 21492706 | County Government of Bungoma |  | 21492706 |  | 21492706 | 100.0% | 21492706 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
42 | Upgrading of Felix,Mang'Ale-Lutungu-Nyange | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41657 | 41780 |  | 6314112 | 6314112 | 6314112 | County Government of Bungoma |  | 6314112 |  | 6314112 | 100.0% | 6314112 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
49 | Upgrading of Nyangali-Javan | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41659 | 41781 |  | 4239858 | 4239858 | 4239858 | County Government of Bungoma |  | 4239858 |  | 4239858 | 100.0% | 4239858 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
50 | Upgrading of Kongoli-Babuya-Paile Spring Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41656 | 41781 |  | 4450572 | 4450572 | 4450572 | County Government of Bungoma |  | 4450572 |  | 4450572 | 100.0% | 4450572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
77 | Upgrading of Kcc-R.Khalaba-Ranje Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41658 | 41776 |  | 4106024.16 | 4106024.16 | 4106024.16 | County Government of Bungoma |  | 4106024.16 |  | 4106024.16 | 100.0% | 4106024.16 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
273 | Periodic Maintenance of Lancaster - Luyekhe - R. Chemululuchi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43230 |  | 3816968 | 3816968 | 3816968 | County Government of Bungoma |  | 3816968 |  | 3816968 |  | 3816968 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
274 | Periodic Maintenance of Namisi -Ndakaru - Bulondo Dispensary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43110 | 43243 |  | 9846433.8 | 9846433.8 | 9846433.8 | County Government of Bungoma |  | 9846433.8 |  | 9846433.8 |  | 9846433.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
275 | Periodic Maintenance of Roads In West Sangalo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.4KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43118 | 43243 |  | 9846433.8 | 9846433.8 | 9846433.8 | County Government of Bungoma |  | 9846433.8 |  | 9846433.8 | 86.56% | 9846433.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
276 | Periodic Maintenance of Roads In West Sangalo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43122 | 43236 |  | 3816968 | 3816968 | 3816968 | County Government of Bungoma |  | 3816968 |  | 3816968 | 91.76% | 3816968 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
459 | Periodic Maintenance of Roads In West Sangalo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43478 | 43596 |  | 9806060 | 9806060 | 9806060 | County Government of Bungoma |  | 9806060 |  | 9806060 | 100.0% | 9806060 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
460 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
461 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
617 | Upgrading of Spot Improvement Of Mteremko - Ekitale Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43966 |  | 6818480 | 6818480 | 6818480 | County Government of Bungoma |  | 6818480 |  | 6818480 | 100.0% | 6818480 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
684 | Periodic Maintenance of Ekitale Centre - Lwanda Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43975 |  | 6912440 | 6912440 | 6912440 | County Government of Bungoma |  | 6912440 |  | 6912440 |  | 6912440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
685 | Periodic Maintenance of Lwanda Girls - Kisochele River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43965 |  | 6780153 | 6780153 | 6780153 | County Government of Bungoma |  | 6780153 |  | 6780153 |  | 6780153 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
686 | Periodic Maintenance of Roads In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43966 |  | 6780153 | 6780153 | 6780153 | County Government of Bungoma |  | 6780153 |  | 6780153 | 98.31% | 6780153 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
687 | Periodic Maintenance of Ekitale Centre-Lwanda Junction | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43970 |  | 6912440 | 6912440 | 6912440 | County Government of Bungoma |  | 6912440 |  | 6912440 | 99.32% | 6912440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1020 | Periodic Maintenance of Bulondo Dispensary - Bulondo Secondary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44338 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 |  | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1021 | Periodic Maintenance of Luyekhe Junction - Kitinda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44338 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 |  | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1022 | Periodic Maintenance of Musikiti - Namanga Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44333 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 |  | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1023 | Periodic Maintenance of Roads In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44330 |  | 13057203.6 | 13057203.6 | 13057203.6 | County Government of Bungoma |  | 13057203.6 |  | 13057203.6 | 88.27% | 13057203.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1342 | Periodic Maintenance of Mutoto Junction - Luyekhe - Namwacha Market - Kachomba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44698 |  | 7109466 | 7109466 | 7109466 | County Government of Bungoma |  | 7109466 |  | 7109466 |  | 7109466 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1343 | Periodic Maintenance of Roads In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44702 |  | 7109466 | 7109466 | 7109466 | County Government of Bungoma |  | 7109466 |  | 7109466 | 100.0% | 7109466 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1598 | Periodic Maintenance of Kamba Primary Junction - Chwele Bridge -Kachomba - Bulondo Market - Bumba Pri Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45068 |  | 11392012 | 11392012 | 11392012 | County Government of Bungoma |  | 11392012 |  | 11392012 |  | 11392012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1599 | Periodic Maintenance of Kamba Primary Junction - Chwele Bridge - Kachomba - Bulondo Mkt - Bumba Primary Road In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45064 |  | 11392012 | 11392012 | 11392012 | County Government of Bungoma |  | 11392012 |  | 11392012 | 99.61% | 11392012 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1843 | Periodic Maintenance of Kona Mbaya - Buteyo Miti Park - Luanda Junction Road In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45429 |  | 5975508 | 5975508 | 5975508 | County Government of Bungoma |  | 5975508 |  | 5975508 | 85.14% | 5975508 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1844 | Periodic Maintenance of Musikiti - Lancaster - Kitinda Secondary Road In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45436 |  | 10141068 | 10141068 | 10141068 | County Government of Bungoma |  | 10141068 |  | 10141068 | 100.0% | 10141068 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1845 | Periodic Maintenance of Msikiti Junction - Lancaster - Kitinda Secondary School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45429 |  | 10141068 | 10141068 | 10141068 | County Government of Bungoma |  | 10141068 |  | 10141068 |  | 10141068 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1846 | Periodic Maintenance of Kona Mbaya - Buteyo Miti Park - Luanda Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45428 |  | 5975508 | 5975508 | 5975508 | County Government of Bungoma |  | 5975508 |  | 5975508 |  | 5975508 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1847 | Periodic Maintenance of Khalaba Bridge - Luyekhe - Sang'Alo Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.3KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45434 |  | 3198468 | 3198468 | 3198468 | County Government of Bungoma |  | 3198468 |  | 3198468 |  | 3198468 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1848 | Periodic Maintenance of Khalaba Bridge - Luyekhe - Sang'Alo Junction In West Sang'Alo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.3KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kanduyi | West Sang'alo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45427 |  | 3198468 | 3198468 | 3198468 | County Government of Bungoma |  | 3198468 |  | 3198468 | 99.99% | 3198468 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
131 | Purchase Of 1/2 An Acre For Ndakaru E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for expansion of ECDE centre | One acres of Land for Ndakaru E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | West Sang'alo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 43079 | 43051 | 23/2/2018 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 0 | 0 | [17 empty] | The project is 100% complete and not in use
195 | Purchase of 1 acre for Ndakaru E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Ndakaru E.C.D.E Purchased | 3110599 | Ward based projects | Kanduyi | West Sang'alo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 |  |  |  | 350000 | 350000 | 350000 | CGB | N/A | 350000 |  | 350000 | 1 | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
98 | Construction of 2no ecde classroom and toilets at NAMWACHA and Siaka primary | Construction of ECDE classroom n tollet | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | West Sang'alo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3500000 | 3493490 | 3500000 | County Government of Bungoma | N/A | 3500000 | 0 | 0 | 0 | 0 | 3493490 | 3493490 | complete and in use | 1
219 | Construction Of 1no. Ecde Classroom And Pit Latrine At Siangwe, Bulondo Polytechnic, Sang'alo Ecde And Kamba Primary Schools In West Sangalo Ward | Construction of ECDE classroom and VTC workshop | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kanduyi | West Sang'alo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 2800000 | 3364200 | 2800000 | County Government of Bungoma | N/A | 2800000 |  | 3364200 | 1 | 3364200 | 0 |  | complete and in use | 100.0%
116 | Drilling of Kitinda Pri borehole and upgrading of Bulondo market,Ekitale dispensary and Kitinda Pri boreholes in west sangalo ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and 2 boreholes rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 7000000 | 6874028 | 6874028 |  | N/A | 6874028 | 0 | 6874028 | 1 | 6874028 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
259 | Drilling of Borehole and protection of 4no. Water springs | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled and 4 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2800000 | 2776698 | 2776698 |  | N/A | 2776698 | 0 | 2776698 | 1 | 2776698 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
263 | DRILLING OF SANGALO MARKET BOREHOLE IN WEST SANGALO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 2000000 | 1925600 | 1925600 |  | N/A | 1925600 | 0 | 1925600 | 1 | 1925600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
329 | CONSTRUCTION AND DRILLING OF BOREHOLE IN WEST SANG’ALO WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 2000000 | 1922400 | 1922400 |  | N/A | 1922400 | 0 | 1922400 | 1 | 1922400 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
331 | CONSTRUCTION AND PROTECTION OF 5 WATER SPRINGS IN WEST SANG’ALO WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 1000000 | 900000 | 900000 |  | N/A | 900000 | 0 | 900000 | 1 | 900000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
332 | EXTENSION OF LWANDA WATER PROJECT PHASE II | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3500000 | 3481745 | 3481745 |  | N/A | 3481745 | 0 | 3481745 | 1 | 3481745 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
408 | Construction of 5 Roof catchments and Upgrading of Bulondo Health Centre Borehole | Construction of roof catchment and Improvement of a standard apron with drainage tunnel and replacement of 1 Afrdev hand pump | To enhance access to clean and safe drinking water | 1 borehole rehabilitated and 5 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2800000 | 2711581 | 2711581 |  | N/A | 2711581 | 0 | 2711581 | 1 | 2711581 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
442 | Protection of 4 water Springs. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs. constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 800000 | 619800 | 619800 |  | N/A | 619800 | 0 | 619800 | 1 | 619800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
512 | Protection of 4 water Springs. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 800000 | 619800 | 619800 |  | N/A | 619800 | 0 | 619800 | 1 | 619800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
513 | Construction of 5 Roof catchments and Upgrading of Bulondo Health Centre Borehole | Construction of roof catchment; storage tank and water points; Improvement of a standard apron with standard drainage tunnel and replacement of 1 A fridev handpump | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 of borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3500000 | 3389476 | 3389476 |  | N/A | 3389476 | 0 | 3389476 | 1 | 3389476 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
583 | Construction of Lwanda community water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2200000 | 2094000 | 2094000 |  | N/A | 2094000 | 0 | 2094000 | 1 | 2094000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
584 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 of water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kanduyi | West Sang'alo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1445210 | 1445210 |  | N/A | 1445210 | 0 | 1445210 | 1 | 1445210 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
15 | Proposed installation and Commissioning of Solar backup system at Bulond Dispensary and installation of 10 No solar streetlights. | installation of system Dispensary backup installation of | Promotion of health care | Solar strret lights and solar back up system installed | BGM/CNTY/TEI/04/OT/2024-2025 1667818-2024-2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | GERRICK TECHNICAL AND HYGIENE SERVICE LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 6000000 |  |  | CGB | [8 empty] | Works to commence |  | 10
27 | Propose supply and installation of 16NO.Solar powered streetlights | supply of Solar of 16NO | promotion of MSMEs and security | solar powered street lights installed | 1362963-2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | GERRICK TECHNICAL AND HYGIENE SERVICES LIMITED | 2023/2024 |  | Completed | Complete and in use | 5000000 |  |  | CGB | [8 empty] | Complete | 100 | 16
51 | Proposed construction of county aggregation and industrial park in Bungoma county at Sang’alo | construction aggregation park industrial Bungoma county | Promotion of industrialization | County Aggregated Industrial Park Established | Bgm/cnty/tei/24/2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Industry | M/S Quest Civil Engineers Limited | 2023/24 |  | Works ongoing | Ongoing and not in use | 80000000 | 474153713.83 |  | CGB | [8 empty] | Works on schedule |  | 1
76 | Installation of 41 grid powered streetlights in Kanduyi Sub-county . | of streetlights Kanduyi streetlights in |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S Mbale Town Electro Works Umeme | 2021/22 |  | Complete and in use |  | 3116001 |  |  | CGB
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | West Sang'alo |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Sang'alo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | West Sang'alo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
13 | Construction of sentry and gate for Webuye health centre |  |  | Sentry and gate constructed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21-2-2024 |  |  | 1000000 | 947093.6 | 947093.6 | CGB |  | 947093.6 | 0 | 0 | 0 | 0 | 1485230 | 947093.6 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
19 | Erection and completion works for maternity wing at Butieli dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | maternity wings erected and completed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 23-2-2024 |  |  | 3000000 | 2805668.8 | 2805668.8 | CGB |  | 2805668.8 | 0 | 0 | 0 | 0 | 193059 | 2805668.8 | On-going | 25 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
88 | Completion Of Maternity Wing And 2no. Door Pit Latrines Mayanja Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings and 2N0. door pit latrines completed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 3000000 | 2804500 | 2804500 | CGB |  | 2804500 | 0 | 2507370 | 0.89405 | 2507370 |  | 297130 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
112 | Muji Centre Dispensary And Power Installation |  |  | power installed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 3300000 | 3496800 | 3496800 | CGB |  | 3496800 | 0 | 0 | 0 | 0 |  | 3496800 | Yet to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No
145 | Completion Of Maternity Wing At Mayanja Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2500000 | 2804500 | 2804500 | CGB |  | 2804500 | 0 | 0 | 0 | 0 |  | 2804500 | Complete and in use | [6 empty] | No | complete | Financial | Yes
146 | Construction Of Toilets And Fencing Nabukhisa Dispensary | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors and Fencing | To develop and maintain infrastructure for enhanced access to quality health care services. | toilets constructed and dispensaries fenced |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 500000 | 483000 | 483000 | CGB |  | 483000 | 0 | 483000 | 1 | 483000 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
206 | Completion Of Lukhoba Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries constructed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 4200000 | 7150000 | 7150000 | CGB |  | 7150000 | 0 | 4200000 | 0.58741 | 4200000 |  | 2950000 | complete and in use | [6 empty] | No | complete | Financial | Yes
207 | Construction Of Public Toilet At Sango Juntion,Nzoia Rc Ecde And Webuye Main Bus Park | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | Public toilets constructed |  |  | Webuye East | Maraka |  |  | WBPSPCU | Health & Sanitation | 2018-2019 |  |  |  | 10000000 | 10,741,368 | 10,741,368 | CGB |  | 10,741,368 | 0 | 9,022,323 | 0.83996 | 9,022,323 |  | 1719045 | complete and in use | [6 empty] | No | complete | Financial | Yes
234 | Construction Of A Maternity Wing At Lurare And Lukhoba Health Cente | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2000000 | 2243520 | 2243520 | CGB |  | 2243520 | 0 | 2243520 | 1 | 2243520 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
253 | Construction Of Nabukhisa Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2419344 | 2571511 | 2571511 | CGB |  | 2571511 | 0 | 2571511 | 1 | 2571511 |  | 0 | Complete and not use | [6 empty] | No | complete | Financial | Yes
302 | Renovation and Completion of Mayanja Dispensary | Walling,roofing,painting,fixing of doors and windows | To provide accessible and health services within the community | Dispensaries renovated/completed |  |  | Webuye East | Maraka |  |  | Ward Fund | Health & Sanitation | 2014/15 |  | 42185 |  |  | 2216772 | 2216772 | CGB |  | 2216772 | 0 | 2216772 | 1 | 2216772 |  | 0 | Stalled and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
303 | Erection And Completion Of A Maternity Wing And Construction Of 4-Door Pit Latrine. | Walling,roofing,painting,fixing of doors and windows Digging of 20ft deep pit,flooring,walling,painting,roofing anf fitting doors | To provide accessible,affordable maternity services within the community | Maternity wings and 4No.door pit latrine erected and completed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2016/17 | 42856 | 42887 |  |  | 3939621 | 3939621 | CGB |  | 3939621 | 0 | 2814809 | 0.71449 | 2814809 |  | 1124812 | Stalled and not in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
304 | Completion of Butieli Health Centre | Walling,roofing,painting,fixing doors and windows | To provide accessible,affordable maternity services within the community | health centres completed |  |  | Webuye East | Maraka |  |  | CEF | Health & Sanitation | 2016/17 |  | 42887 |  |  | 3997708 | 3997708 | CGB |  | 3997708 | 0 | 3767390 | 0.94239 | 3767390 |  | 230318 | Complete | [6 empty] | No | complete | Financial | Yes
341 | Construction of pit latrine | Digging of 20ft deep pit,flooring,walling,painting,roofing,fitting of doors | To enhance access to sanitary facilities at the market | pit latrines constructed |  |  | Webuye East | Maraka | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete and in use. | [6 empty] | No | complete | Financial | Yes
5 | Construction of 6 NO. door pit latrines and landscaping at Maraka stadium | Construction of 6NO. door pit latrines and landscaping | To improve sanitation | 6 NO.Pit latrines constructed | 3111504 | Other infrastructure and civil works | Webuye East | Maraka |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2023/24 | 45475 | 45481 |  | 5000000 | 4978550 | 0 | County Government of Bungoma | n/a | n/a | n/a | 0 | 0 | 0 | 4978550 | 4978550 | Ongoing | 0.7
44 | Upgrading of Kamasielo-Kikwechi | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41656 | 41772 |  | 4468842 | 4468842 | 4468842 | County Government of Bungoma |  | 4468842 |  | 4468842 | 100.0% | 4468842 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
72 | Upgrading of Gravelling Of Sango Market-Maraka Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41658 | 41770 |  | 11677308.2 | 11677308.2 | 11677308.2 | County Government of Bungoma |  | 11677308.2 |  | 11677308.2 | 100.0% | 11677308.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
74 | Construction of Box Culvert Over R.Sasuri | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41657 | 41782 |  | 5914062.8 | 5914062.8 | 5914062.8 | County Government of Bungoma |  | 5914062.8 |  | 5914062.8 | 100.0% | 5914062.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
83 | Construction of Makuselwa-Lugusi-Lugulu With Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41659 | 41770 |  | 32020002 | 32020002 | 32020002 | County Government of Bungoma |  | 32020002 |  | 32020002 | 100.0% | 32020002 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
84 | Upgrading of Mayanja-Kikwechi-Bisuni Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41650 | 41779 |  | 8599080 | 8599080 | 8599080 | County Government of Bungoma |  | 8599080 |  | 8599080 | 100.0% | 8599080 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
391 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
392 | Periodic Maintenance of Roads In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43487 | 43606 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.87% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
393 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
561 | Construction of Maliki Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43969 |  | 6777317 | 6777317 | 6777317 | County Government of Bungoma |  | 6777317 |  | 6777317 |  | 6777317 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
562 | Grading of Cpb-Public Works Road | Grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43968 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
563 | Upgrading of Masoni - Sambu Central - Mukhuyu Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43971 |  | 3731140 | 3731140 | 3731140 | County Government of Bungoma |  | 3731140 |  | 3731140 |  | 3731140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
564 | Construction of Wamoyo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43967 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
565 | Upgrading of Spot Improvement Of Masoni - Sambu Central -Mukhuyu Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43971 |  | 3731140 | 3731140 | 3731140 | County Government of Bungoma |  | 3731140 |  | 3731140 | 95.4% | 3731140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
566 | Construction of Roads In Maraka Ward With A Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43973 |  | 6777317 | 6777317 | 6777317 | County Government of Bungoma |  | 6777317 |  | 6777317 | 100.0% | 6777317 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
567 | Periodic Maintenance of Kibabii University - Matong'I Primary - River Mayanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
568 | Grading of Makutano Primary-Tuuti Market Road | Grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
569 | Upgrading of Salmond - Wetangula - Chemwa - Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43967 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
570 | Upgrading of Salmond - Wetangula - Chemwa - Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43968 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
571 | Construction of Tuuti Marakaru - West Nalondo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43970 | 44001 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
572 | Upgrading of Spot Improvement Of Salmond Wetangula Chemwa Sikata Primary Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43845 | 43962 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 93.08% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
573 | Periodic Maintenance of Roads In Tuuti-Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43966 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 93.96% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
574 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
637 | Routine Maintenance Of Roads In Webuye East And Webuye West Sub- Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43963 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
851 | Periodic Maintenance of Sajan - Lukhoba - Butchery Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44334 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 |  | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
852 | Periodic Maintenance of Sango - Maraka - R. Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44328 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 |  | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
853 | Periodic Maintenance of Nangili - Ngachi Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44330 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 |  | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
854 | Periodic Maintenance of Muji River - Simala Bandu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
855 | Upgrading of St. Joseph - Reliance Road | Road improvement works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
856 | Periodic Maintenance of Roads In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44326 |  | 11049696 | 11049696 | 11049696 | County Government of Bungoma |  | 11049696 |  | 11049696 | 99.86% | 11049696 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
857 | Periodic Maintenance of Talent Academy - Mayanja Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44336 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
858 | Periodic Maintenance of Gardinal Otunga Girls - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44331 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
859 | Periodic Maintenance of Bukusu Junction - Bukusu Primary - Kibabii River - River Mayanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44335 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
860 | Periodic Maintenance of Namikelo Junction - Simon Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44212 | 44338 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
861 | Periodic Maintenance of Makutano - Tuuti Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44339 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
862 | Periodic Maintenance of Roads In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 98.41% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
863 | Periodic Maintenance of Talent Academy - Mayanja Mkt Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.8KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44327 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 95.06% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1158 | Periodic Maintenance of Sunrise - Muji River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44699 |  | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 |  | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1159 | Periodic Maintenance of Muji - Woodhill Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44697 | 44728 | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 |  | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1160 | Periodic Maintenance of Sikolia - Mukonambi - St. Teresa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44692 |  | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 |  | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1161 | Periodic Maintenance of Muji Sec - Pharis Maikuma - Showmap Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44704 | 44735 | 6099825.2 | 6099825.2 | 6099825.2 | County Government of Bungoma |  | 6099825.2 |  | 6099825.2 |  | 6099825.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1162 | Periodic Maintenance of Roads In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44698 |  | 4599168 | 4599168 | 4599168 | County Government of Bungoma |  | 4599168 |  | 4599168 | 95.86% | 4599168 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1163 | Routine Maintenance Of Muji Secondary - Pharis Maikuma - Showmap Bridge | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44701 |  | 6099825.2 | 6099825.2 | 6099825.2 | County Government of Bungoma |  | 6099825.2 |  | 6099825.2 | 100.0% | 6099825.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1164 | Periodic Maintenance of Kumbuka Junction - Kikwechi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44693 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1165 | Periodic Maintenance of Bukananachi Primary - Lumasa - Kibabii Booster | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44695 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1166 | Periodic Maintenance of Henry Posho Mill - Marofu Junction | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44700 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1167 | Periodic Maintenance of Lumasa - Matong'I Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44697 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1168 | Periodic Maintenance of Mayanja - Ekholo Junction - Henry Posho Mill - Peter Musemwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44694 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1169 | Periodic Maintenance of Makutano - Wanangali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44699 | 44730 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1170 | Periodic Maintenance of Roads In Tuuti - Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44578 | 44692 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1171 | Routine Maintenance Of Makutano - Wanangali - Tuuti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44705 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1459 | Periodic Maintenance of Sunrise - Muchi River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45065 | 45096 | 2836780 | 2836780 | 2836780 | County Government of Bungoma |  | 2836780 |  | 2836780 |  | 2836780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1460 | Periodic Maintenance of Muji Primary - Muji River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45056 | 45087 | 2836780 | 2836780 | 2836780 | County Government of Bungoma |  | 2836780 |  | 2836780 |  | 2836780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1461 | Construction of Site And Service And National Estate Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed |  |  | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45065 |  | 10177641460.34 | 10177641460.34 | 10177641460.34 | County Government of Bungoma |  | 10177641460.34 |  | 10177641460.34 |  | 10177641460.34 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1462 | Periodic Maintenance of Sunrise - Muji River Road, Muji Primary - Muji River Road In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45061 |  | 2836780 | 2836780 | 2836780 | County Government of Bungoma |  | 2836780 |  | 2836780 | 90.85% | 2836780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1463 | Periodic Maintenance of Bukananachi - Lumasa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45067 | 45098 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1464 | Periodic Maintenance of Diploma - Maliki Primary - Khalaba River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45068 | 45099 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1465 | Periodic Maintenance of Fana B - Sitoma Primary Main Junction - Kakichuma Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45059 | 45090 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1466 | Periodic Maintenance of Cardinal Otunga Girls - Good Shepherd - Namikelo Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45057 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1467 | Periodic Maintenance of Diploma (Dttc) - Maliki Primary - Khalaba River Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45064 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1468 | Periodic Maintenance of Fana B - Sitoma Primary - Main Junction - Kakichuma Road In Tuuti/ Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.1KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45056 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.82% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1469 | Periodic Maintenance of Bukananachi - Lumasa In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44936 | 45068 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 98.17% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1470 | Framework Contracts For Maintenance Of Roads In Kanduyi And Bumula Sub Counties | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45070 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 326.25% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1695 | Periodic Maintenance of Makuma - Nangili - Muji River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45431 | 45462 | 6795709 | 6795709 | 6795709 | County Government of Bungoma |  | 6795709 |  | 6795709 |  | 6795709 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1696 | Periodic Maintenance of Sango - Maraka - River Nzoia Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45309 | 45426 | 45457 | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 |  | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1697 | Periodic Maintenance of Webuye River -Kizinji -Makuma - Nangili - Muji River | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45422 | 45453 | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 |  | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1698 | Periodic Maintenance of Mufunje - Boilo - Pombo - Kakimanyi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45434 | 45465 | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 |  | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1699 | Periodic Maintenance of Mufunje - Boilo - Pombo - Kakimanyi River Road, Sango - Maraka - River Nzoia - Kizinji - Webuye Road In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45434 |  | 6957216 | 6957216 | 6957216 | County Government of Bungoma |  | 6957216 |  | 6957216 | 93.88% | 6957216 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1700 | Periodic Maintenance of Webuye River - Kizinji - Makuma - Nangili - Muji River Road In Maraka Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45433 |  | 6795709 | 6795709 | 6795709 | County Government of Bungoma |  | 6795709 |  | 6795709 | 99.81% | 6795709 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1701 | Periodic Maintenance of Mwalimu Wetungu - Kumbuka Junction - Nakayonjo Deb Primary - Mungeti River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45422 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1702 | Periodic Maintenance of Makutano Junction - Chemiati - A104 Malaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45435 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1703 | Periodic Maintenance of Hillview - Khalaba - Maliki Primary - Christ Community - Zuri Poa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45432 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1704 | Periodic Maintenance of Kimukung¦I - Onyango - River Khalaba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45434 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1705 | Periodic Maintenance of Tuuti - Namaloko - Kamukunda Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45427 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1706 | Construction of Meli - Mafura Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45428 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1707 | Periodic Maintenance of Hillview - Khalaba - Maliki Primary - Christ Community - Zuri Poa Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45432 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.17% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1708 | Periodic Maintenance of Kimukung'I - Onyango - River Khalaba Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45423 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.96% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1709 | Periodic Maintenance of Makutano Junction - Chemiati - A104 Malaba Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45435 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.8% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1710 | Periodic Maintenance of Tuuti - Namaloko - Kamukunda Road In Tuuti/Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.8KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45427 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 101.08% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1711 | Proposed Meli - Mafura Box Culvert In Tuuti/Marakaru Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45424 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 95.44% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1712 | Periodic Maintenance of Mwalimu Wetungu-Kumbuka Junction-Nakayonjo Deb-R.Mungeti Road In Tuuti Marakaru Ward (1465530-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45432 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.95% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1824 | Periodic Maintenance of Pius Osyanju Kibabii University-Kolikho Market-Gospel Church Road In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45430 |  | 4953362 | 4953362 | 4953362 | County Government of Bungoma |  | 4953362 |  | 4953362 | 99.99% | 4953362 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1825 | Periodic Maintenance of Pius Osyanju Kibabii University-Kolikho Market-Gospel Church Road In Tuuti Marakaru Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Webuye East | Maraka |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45430 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 99.99% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1 | Review of Physical and development plan for Webuye Urban Area | Document review,Desktop research, Gaps analysis, Report Writing and formulation of new maps, Stakeholder engagement for new vision and direction of the urban area | To guide sustainable and inclusive growth of urban areas through land use,infrastructure development and improved service delivery | One Physical and land use plan for Webuye Urban Area developed | 2211311 | Development/Physical Planning | Webuye East | Maraka |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 15/5/2024 | 15/11/2024 | 15/11/2024 | 2600000 | 2567080 | 2567080 | CGB | N/A | 2567080 | 0 | 2567080 | 1 | 513416 | 2053664 | 0 | Completed | 1 | N/A | N/A | N/A | N/A | 0 | No |  |  | No |  | No |  |  |  | The project is 100% complete and in use
94 | Purchase Of Land For Catholic Market | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new market | One acre of Land For Catholic Market Purchased | 3110599 | Ward based projects | Webuye East | Maraka |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 26/6/2019 | 27/12/2019 | 16/1/2020 | 4500000 | 4150000 | 4150000 | CGB |  | 4150000 |  | 4150000 |  | 3900000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
177 | Purchase of land for Cheloti ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land forCheloti ECDE Purchased | 3110599 | Ward based projects | Webuye East | Maraka |  | Lands,Urban/Physical Planning,Housing and Municipalities | Housing,Urban areas and Municipalities | Housing | 2015/16 | 42286 | 42289 | 42014 | 260000 | 260000 | 260000 | CGB | N/A | 260000 |  | 260000 |  | 260000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
53 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Nzoia Pefa Primary School In Maraka Ward | Completion of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 1500000 | 1410000 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 0 | 0 | 0 | 1410000 | 1410000 | Complete and not in use | 1
87 | Construction Of 1no Ecde Classrooms At Maraka,Nang'eni,Mukhuyu,Nzoia Pefa,St.Joseph Rc,Sda Kakimanyi Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 9600000 | 9594200 | 9600000 | County Government of Bungoma | N/A | 9600000 | 0 | 7884776.75 | 0.82183 | 7884776.75 | 1709423.25 | 1709423.25 | ongoing and not in use | 0.5
95 | Construction of 1 No.ECDE Classroom Maocho | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 1500000 | 1495350 | 1500000 | County Government of Bungoma | N/A | 1500000 | 0 | 1275171.75 | 0.85276 | 1275171.75 | 220178.25 | 220178.25 | ongoing and not in use | 0.8
118 | Construction Of 1 No. Ecde Classroom At Ack And Pag Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3900000 | 2612796 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 2612796 | 1 | 2612796 | 0 | 0 | complete and in use | 1
150 | Proposed Erection And Completion Of 1 No. Ecde At Khamoto,Nabuyole, Muji And Webuye Sub-County Hq In Maraka Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 5062905.59 | 4726394.4 | 5062905.59 | County Government of Bungoma | N/A | 5062905.59 | 0 | 4726394.4 | 1 | 4460736.02 | 265658.38 | 0 | complete and in use | 1
162 | Proposed Erection And Completion Of 1 No. Ecde At Kikwechi, Makutano And Nabukhisa Primary Schools In Tuuti Marakaru Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3900000 | 3803200 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 3803200 | 1 | 3803200 | 0 | 0 | complete and in use | 1
181 | Construction Of 1no. Ecde Classroom At Namikelo, Kakichuma, Kimukungi, Bukananachi And Maliki Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 6000000 | 5970325 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 5970325 | 1 | 5970325 | 0 |  | complete and in use | 1
217 | Construction Of 1 Ecde Classroom At Lumasa, Buema,Bukusu, Munget, Sitama And Nakayonjo | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Webuye East | Maraka |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 7924270 | 7487800 | 7924270 | County Government of Bungoma | N/A | 7924270 |  | 7487800 | 1 | 7487800 | 0 |  | complete and in use | 100.0%
|  | Erection of a storage tank; installation of solar pumping system; pipe laying and construction of community water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and water pipeline extended | 2640599 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | [7 empty] | FLLOCA | N/A |  | 0 |  | 1 |  | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
41 | Proposed Supply And Installation Of Combustion Chamber For Improved Stoves And Energy Centre For Research On Training Of Energy Technologies In Maraka And Kabuchai | 1.construction of combustion chamber (Kiln) for production of clean energy saving jikos. 2.Provision and Assemblying of production materials for the two burner / saving jikos. 3.Training of youths and women on installation of single /two burner jikos to the community. | To promote climate change mitigation and adaptation | Construction of combustion chambers in 2 wards | 2640599 | Other Capital Grants and Transfers | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 6000000 | 5955480 | 5955480 | FLLOCA | IDA | 0 | 5955480 | 0 | 1 | 0 | 0 |  | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
75 | Extension of KOICA Pipeline in Tuuti Marakaru Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4994728 | 4994728 | CGB | N/A | 4994728 | 0 | 4994728 | 1 | 4994728 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
106 | Drilling and equipping of ward stadium borehole in Maraka ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2000000 | 1975046.4 | 1975046.4 |  | N/A | 1975046.4 | 0 | 1975046.4 | 1 | 1975046.4 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
114 | Drilling of Kabubero Catholic borehole,Rehabilitation of boreholes and well pumps and spring protection in tuuti/marakaru ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole drilled; 1 borehole rehabilitated and 1 water spring constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4000000 | 3852742.8 | 3852742.8 |  | N/A | 3852742.8 | 0 | 3852742.8 | 1 | 3852742.8 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
251 | DRILLING OF 3NO BOREHOLES IN TUUTI/MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 5000000 | 4892880 | 4892880 |  | N/A | 4892880 | 0 | 4892880 | 1 | 4892880 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
289 | DRILLING OF SERVICE ESTATE AND MAKUMA BOREHOLES IN MARAKA WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3900000 | 3830320 | 3830320 |  | N/A | 3830320 | 0 | 3830320 | 1 | 3830320 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
290 | DRILLING OF MARAKA WARD OFFICE AND LUKHOVA BOREHOLES IN MARAKA WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3990400 | 3990400 |  | N/A | 3990400 | 0 | 3990400 | 1 | 3990400 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
291 | DRILLING OF MUCHI YOUTH POLYTECHNIC AND NANGOTO BOREHOLES IN MARAKA WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3962560 | 3962560 |  | N/A | 3962560 | 0 | 3962560 | 1 | 3962560 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
327 | KIBABII-SASURI WATER PROJECT PHASE 11 | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 34000000 | 32430400 | 32430400 |  | N/A | 32430400 | 1 | 32430400 |  | 26917232 | 5513168 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
336 | DRILLING OF KAKICHUMBA AND MAYANJA BOREHOLES IN TUUTI MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3907483.2 | 3907483.2 |  | N/A | 3907483.2 | 0 | 3907483.2 | 1 | 3907483.2 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
337 | DRILLING OF BUTIELI DISPENDARY AND LUMASA BOREHOLE IN TUUTI MARAKARU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3300000 | 3222080 | 3222080 |  | N/A | 3222080 | 0 | 3222080 | 1 | 3222080 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
344 | Protection of 9 water Springs and rehabilitation of borehole pump | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; improvement of a standard apron with drainage tunnel and replacement of Afridev hand pump | To enhance access to clean and safe drinking water | 9 water springs constructed and a borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 756670 | 756670 |  | N/A | 756670 | 0 | 756670 | 1 | 756670 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
386 | Construction of 5 Roof catchments and 50m3 Masonry tank at Mayanja market | Construction of roof catchment and erection of water tank plus provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 tank constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1545130 | 1545130 |  | N/A | 1545130 | 0 | 1545130 | 1 | 1545130 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
405 | Protection of 10 water Springs and 2 shallow wells. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed and 2 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2500000 | 2322090 | 2322090 |  | N/A | 2322090 | 0 | 2322090 | 1 | 2322090 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
420 | Protection of 10 water Springs, 2 Shallow wells, and rehabilitate borehole ( Hand pump) and 1 water supply | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump; improvement of a standard apron with drainage tunnel and replacement of Afridev hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed, 1 borehole rehabilitated and2 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1344481 | 1344481 |  | N/A | 1344481 | 0 | 1344481 | 1 | 1344481 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
462 | Piped water scheme in Maraka | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1478900 | 1478900 |  | N/A | 1478900 | 0 | 1478900 | 1 | 1478900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
510 | Protection of 9 water Springs and rehabilitation of borehole pump | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; improvement of a standard apron with drainage tunnel and replacement of Afridev hand pump | To enhance access to clean and safe drinking water | 9 water springs and 1 borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1513340 | 1513340 |  | N/A | 1513340 | 0 | 1513340 | 1 | 1513340 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
511 | Construction of 5 Roof catchments and 50m3 Masonry tank at Mayanja market | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and tank constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1545130 | 1545130 |  | N/A | 1545130 | 0 | 1545130 | 1 | 1545130 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
523 | Protection of 10 water Springs and Construction of 1Shallow wells | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; digging of a 15ft shallow well; walling using bricks; installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed and 1 shallow well drilled | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1928755 | 1928755 |  | N/A | 1928755 | 0 | 1928755 | 1 | 1928755 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
580 | Protection of 10 water Springs, 2 Shallow wells, and rehabilitate borehole ( Hand pump) and 1 water supply | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection;Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump;Improvement of a standard apron with drainage tunnel and replacement of Afrdev pump | To enhance access to clean and safe drinking water | 10 water springs constructed, 2 shallow wells constructed and 1 of borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3500000 | 3361203 | 3361203 |  | N/A | 3361203 | 0 | 3361203 | 1 | 3361203 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
581 | Construction of 2 roof Catchment | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 2 of roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 600000 | 518320 | 518320 |  | N/A | 518320 | 0 | 518320 | 1 | 518320 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
582 | Construction of 1 roof catchment Cardinal otunga | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 1 of roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 400000 | 373500 | 373500 |  | N/A | 373500 | 0 | 373500 | 1 | 373500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
585 | Protection of 10 water Springs and 2 shallow wells. | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection;digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 10 water springs constructed and 2 wells constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2322090 | 2322090 |  | N/A | 2322090 | 0 | 2322090 | 1 | 2322090 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
586 | Piped water scheme in Maraka | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Webuye East | Maraka |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1478900 | 1478900 |  | N/A | 1478900 | 0 | 1478900 | 1 | 1478900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
12 | Construction of Maraka ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Maraka ward office constructed | 3111504 | Construction of non- residential buildings | Webuye East | Maraka | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43159 | 9500000 | 9859968 | 9500000 | County Government of Bungoma | - | 9859968 | - | 9859968 | 1 | 9859968 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Supply of marking ink used in inspection of Meat | Supply of marking ink used in inspection of Meat for Bungoma, Webuye East & West, Kimilili and Sirisia Slaughtershouses | To promote meat safety and suitability for human consumption | Marking ink supplied for meat inspection | 2211007 | Agricultural materials, supplies and small equipment | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 3000000 | 1750000 | 2000000 | County Government of Bungoma |  | 1750000 |  | 1750000 | 1 | 1750000 | 0 | 0 | Completed
| Establishment of a County Dairy Processing Plant | Establishment of a County Dairy Processing Plant | To enhance indame generation among dairy farmers | 1 County dairy Processing plant established | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43800 | 44531 | 2021 | 160000000 | 157648000 | 60,000,000 (multi-year) | County Government of Bungoma |  | 157648000 | 0 | 147710110.37 | 0.94 | 147710110.37 | 9937889.63 | 9937889.63 | Completed
| Construction Coffee drying tables at Kimukung’i | Construction Coffee drying tables at Kimukung’i | To enhance intame generation among dairy farmers | Coffee drying tables constructed at Kimukung'i | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43384 | 43739 | 43586 | 3000000 | 1500000 | 1500000 | County Government of Bungoma |  | 1500000 | 0 | 1500000 | 1 | 1500000 | 0 | 0 | Completed
| Construction of Kimukung’i Coffee Warehouse | Construction of Kimukung’i Coffee Warehouse | To promote coffee production and income generation | 1 warehouse constructed | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 27/4/2020 | 27/4/2021 |  | 10000000 | 8623004 | 8000000 | County Government of Bungoma |  | 8623004 | 0 | 2600000 | 0.3 | 2600000 | 6023004 | 6023004 | Ongoing | 0.6
| Renovation of Auction Rings | Renovation of Auction Rings | To centralize and enhance access to animal trading services | 2 Auction rings renovated | 3110599 | Ward Based projects | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44835 | 44837 | 16/2/2022 | 4000000 | 3919176 | 4000000 | County Government of Bungoma |  | 3919176 | 0 | 3919176 | 1 | 3919176 | 0 | 0 | Completed
| Renovation of Slaughter Houses | Renovation of Bungoma and Webuye Slaughter Houses | To promote meat safety and suitability for human consumption | 2 Slaughterhouses renovated | 3110504 | Other infrastructure and civil works | Webuye East | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45119 | 45478 | 45477 | 5000000 | 4998582 | 5000000 | County Government of Bungoma |  | 4998582 | 0 | 4998582 | 1 | 4998582 | 0 | 0 | Completed
10 | Proposed installation and Commissioning of electrical works at catholic market | installation of electrical works | promotion of MSMEs and security | Electrical works installed | BGM/CNTY/TEI/09/OT/2024-2025 1667845-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 1500000 |  |  | CGB | [8 empty] | Works to commence |  | 1
33 | Proposed installation and commissioning of 5 NO. 15M high solar powered floodlights | installation of M M high | promotion of MSMEs and security | High solar powered flood light installed | 1358617/2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 5000000 |  |  | CGB | [8 empty] | Complete | 100 | 5
42 | Proposed supply, installation and commissioning of 30 NO. metallic stalls | Supply taled stalls | promotion of MSMEs | Mettalic stalls instaled | 1363449/2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Trade | SINAWA ENTER | 2023/2024 |  | Ongoing | Ongoing and not in use | 2500000 | 2400000 |  | CGB | [8 empty] | Project is ongoing |  | 30
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
104 | Proposed installation of 35 no. Grid powered street lights in Webuye East, Webuye West, Kimilili and Bumula Sub Counties | installation Grid lights East Kimilili street Kimilili and | [5 empty] | Maraka |  |  |  | M/S Rygeo Tech Solution | 2020/21 |  | Complete |  | 3232265 |  |  | CGG
107 | Proposed installation of 40 no. Grid powered street lights in Kanduyi Sub County | installation Grid lights street lights in | [5 empty] | Maraka |  |  |  | Wilkaner Power Solutions Limited | 2020/21 |  | Complete |  | 3634608.65 |  |  | CGG
127 | Proposed supply and installation of 2 solar powered high flood mast lights | supply of powered powered high | [5 empty] | Maraka |  |  |  | Bishin Transporters and Construction Company Ltd | 2018/19 |  | Complete |  | 2478200 |  |  | CGG
131 | Development of Industrial park (Feasibility study) | study of Industrial | [5 empty] | Maraka |  |  |  | ICDC | 2018/19 |  | Feasibility study complete, the report to be disseminated to relevant stakeholders by ICDC upon full payment. |  | 9970000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maraka |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Maraka |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
2 | Erection and completion of maternity wing at Ndalu health centre | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings erected and completion |  |  | Tongaren | NDALU/ TABANI |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 23-2-2024 |  |  | 5000000 | 4743000.2 | 4743000.2 | CGB |  | 4743000.2 | 0 | 0 | 0 | 0 |  | 4743000.2 | On-going | 70 | [5 empty] | No | complete | Financial | Yes |  |  |  | No
38 | Purchase of medical equipment for Ndalu dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Tongaren | NDALU/ TABANI |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21/5/24 |  |  | 2000000 | 1904200 | 1904200 | CGB |  | 1904200 | 0 | 0 | 0 | 0 | 1904200 | 1904200 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
8 | Purchase of tailoring machines for Ndalu Taban ward | Purchase of tailoring machines | To improve skills | 48 tailoring machines purchased |  |  | Tongaren | NDALU/ TABANI |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Gender and Culture | 2022/23 | 45235 | 45241 |  | 1000000 | 959040 | 959040 | County Government of Bungoma | n/a | n/a | n/a | 959040 | 1 | 959040 | 0 | 0 | Completed
236 | Periodic Maintenance of Roads In Ndalu/Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43241 |  | 12463185 | 12463185 | 12463185 | County Government of Bungoma |  | 12463185 |  | 12463185 | 97.74% | 12463185 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
255 | Periodic Maintenance of Milimani Pag - Soko Mjinga - Young Life Academy - T/Junction - Tali Bridge Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43243 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
256 | Periodic Maintenance of Maisha Mapya - Wanyama - Lavissa Cattle Dip Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43119 | 43243 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
257 | Periodic Maintenance of Nuru Academy - Sawa Deb Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43111 | 43234 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
418 | Periodic Maintenance of Roads In Ndalu Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43604 |  | 6965742 | 6965742 | 6965742 | County Government of Bungoma |  | 6965742 |  | 6965742 | 100.0% | 6965742 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
492 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
626 | Periodic Maintenance of Roads In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43963 |  | 6649062 | 6649062 | 6649062 | County Government of Bungoma |  | 6649062 |  | 6649062 | 88.27% | 6649062 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
627 | Periodic Maintenance of Bunyasi-Ndalu-Nangabo-Lunani Rc Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43962 |  | 7005021 | 7005021 | 7005021 | County Government of Bungoma |  | 7005021 |  | 7005021 | 96.92% | 7005021 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
628 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
654 | Periodic Maintenance of Lukhuna Junction - Agevi - Malari/Mutoro Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43971 | 44002 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
655 | Periodic Maintenance of Ndalu Rc - Bunyasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43962 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
928 | Periodic Maintenance of Roads In Ndalu Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44336 |  | 3784105.6 | 3784105.6 | 3784105.6 | County Government of Bungoma |  | 3784105.6 |  | 3784105.6 | 100.0% | 3784105.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
967 | Periodic Maintenance of Nuru Academy - Sawa Deb Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
968 | Periodic Maintenance of Oindo - Kaliwanga - Duka Moja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44328 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1260 | Periodic Maintenance of Roads In Ndalu- Tabani Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44705 |  | 10384811.2 | 10384811.2 | 10384811.2 | County Government of Bungoma |  | 10384811.2 |  | 10384811.2 | 100.0% | 10384811.2 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1261 | Routine Maintenance Of Prof. Sifuna - Tabani - Sis Metrine Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44573 | 44702 |  | 7251305 | 7251305 | 7251305 | County Government of Bungoma |  | 7251305 |  | 7251305 | 97.74% | 7251305 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1300 | Periodic Maintenance of Dr. Kisia Musangura Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44699 | 44730 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1301 | Periodic Maintenance of Saidi - Ligodi - Nyabera - Chege - Charles - Ibrahim - Georgina Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44697 | 44728 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1302 | Periodic Maintenance of Prof. Sifuna - Tabani - Sis Metrine Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44705 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1303 | Periodic Maintenance of Omindo - Duka Moja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44697 | 44728 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1304 | Routine Maintenance Of Omindo - Duka Moja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44704 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 95.51% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1523 | Periodic Maintenance of Namunwa - Bunyasi - Glory Academy - Musese - Faith Academy Road In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45060 |  | 4639861 | 4639861 | 4639861 | County Government of Bungoma |  | 4639861 |  | 4639861 | 89.38% | 4639861 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1524 | Periodic Maintenance of Sinoko Primary School Road In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45069 |  | 2811787 | 2811787 | 2811787 | County Government of Bungoma |  | 2811787 |  | 2811787 | 100.0% | 2811787 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1551 | Periodic Maintenance of Namunwa - Bunyasi - Glory Academy - Musese Faith Academy Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45061 | 45092 | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1801 | Periodic Maintenance of Omido - Mwangi - Minyali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45430 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1802 | Periodic Maintenance of Omindo - Mwangi Minyali - God'S Favor Filling Station - Sawa Road In Ndalu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | NDALU/ TABANI |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45436 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
96 | Purchase Of 5acre Land For Expansion Of Ndalu Market | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of Market | Five acres of Land For Expansion Of Ndalu Market Purchased | 3110599 | Ward based projects | Tongaren | NDALU/ TABANI |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 |  |  |  | 2000000 | 1800000 | 1800000 | CGB |  | 1800000 |  | 1800000 |  |  |  |  | Stalled | 0 | [14 empty] | The project is staled due Lack of documentations(Title deed)
99 | Purchase of one acre of land for shikuku primary school | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of ECDE centre | One acre of Land for shikuku primary school Purchased | 3110599 | Ward based projects | Tongaren | NDALU/ TABANI |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 |  |  |  | 1000000 | 900000 | 900000 | CGB |  | 900000 |  | 900000 |  |  |  |  | Stalled | 0 | [14 empty] | The project is staled due Lack of documentations(Title deed)
149 | Purchase of land for Buyofu ECDE centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Buyofu ECDE Purchased | 3110599 | Ward based projects | Tongaren | NDALU/ TABANI |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 21/01/2017 | 21/03/2017 | 30/06/2017 | 1100000 | 1100000 | 1100000 | CGB | N/A | 1100000 |  | 1100000 |  | 1100000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
59 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Ndalu, Muliro, Taabani And Shikuku Primary Schools In Ndalu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 6000000 | 5784750 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 0 | 0 | 0 | 5784750 | 5784750 | ongoing, at walling stage. | 0.4
125 | Construction Of 1 No. Ecde Classroom And 2 No. Pit Latrine At Ngoya Buyofu, Tabani Fym, Sawa, Minyali, Kiminini And Sinoko Primary Schools And Tabani Vtc. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 10000000 | 9587260 | 10000000 | County Government of Bungoma | N/A | 10000000 | 0 | 4916511.55 | 0.51282 | 4916511.55 | 4670748.45 | 4670748.45 | complete and in use | 1
159 | Proposed Erection And Completion Of 1 No. Ecde At Musembe And Mapera Primary Schools In Ndalu Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 2580910.18 | 2339880 | 2580910.18 | County Government of Bungoma | N/A | 2580910.18 | 0 | 2339880 | 1 | 2339880 | 0 | 0 | complete and in use | 1
210 | Construction Of 1no. Ecde Classroom And Pit Latrine At Musangura And Nzoia Primary Schools In Ndalu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | NDALU/ TABANI |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 3000000 | 3536770 | 3000000 | County Government of Bungoma | N/A | 3000000 |  | 3536770 | 1 | 3536770 | 0 |  | complete and in use | 100.0%
44 | Construction and Protection of 10no. Water Springs in Ndalu ward | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2500000 | 2042760 | 2042760 | CGB | N/A | 2042760 | 0 | 2042760 | 1 | 2042760 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
83 | Muliro Water Project In Ndalu Taban Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Water project constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 4500000 | 4270585 | 4270585 | CGB | N/A | 4270585 | 0 | 4270585 | 1 | 0 | 4270585 | 0 | Work in progress | 15% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
135 | Tabani secondary water project in Ndalu Tabani ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4000000 | 3813840 | 3813840 |  | N/A | 3813840 | 0 | 3813840 | 1 | 3813840 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
205 | CONSTRUCTION AND PROTECTION OF 10 NO. WATER SPRINGS IN NDALU- TABANI WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2000000 | 1856348 | 1856348 |  | N/A | 1856348 | 0 | 1856348 | 1 | 1856348 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
206 | REHABILITATION AND UPGRADING OF NDALU MARKET WATER PROJECT IN NDALU / TABAN WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Tongaren | NDALU/ TABANI |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 800000 | 759200 | 759200 |  | N/A | 759200 | 0 | 759200 | 1 | 759200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Purchase of chicken for farmer groups | Purchase and delivery of 4,000 chicken for farmer groups in Ndalu Tabani Ward | To enhance poultry production and increase household incomes | 4,000 chicken birds purchased and delivered to farmer groups | 3110599 | Ward Based projects | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44166 | 44169 | 18/3/2020 | 3000000 | 3000000 | 3000000 | County Government of Bungoma |  | 3000000 | 0 | 3000000 | 1 | 3000000 | 0 | 0 | Completed
| Purchase of drip irrigation kits for farmer groups (Ward Based) | Purchase and delivery of drip irrigation kits for farmer groups (Ward Based) | To enhance production, productivity and income generation | Assorted drip irrigation kits purchased and delivered | 3110599 | Ward Based projects | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 43952 | 43955 | 30/3/2020 | 4000000 | 3185000 | 3, 381,882 | County Government of Bungoma |  | 3185000 | 0 | 3185000 | 1 | 3185000 | 0 | 0 | Completed
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | Tongaren | NDALU/ TABANI |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | NDALU/ TABANI |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
35 | Purchase of medical equipment for Eluya dispensary | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 20/5/24 |  |  | 2000000 | 1890125 | 1890125 | CGB |  | 1890125 | 0 | 0 | 0 | 0 |  | 1890125 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
134 | Constuction Of Male And Female Ward At Mukuyuni Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | male and female wards constructed |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 2500000 | 2904700 | 2904700 | CGB |  | 2904700 | 0 | 2904700 | 1 | 2904700 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
135 | Construction Of Maternity Wing And 4door Pit Latrine At Mukuyuni Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2425000 | 2425000 | CGB |  | 2425000 | 0 | 2255239 | 0.93 | 2255239 |  | 169761 | Complete and in use | [6 empty] | No | complete | Financial | Yes
136 | Expansion Of Eluhya Dispansary Construction Of Pit Latrine Electricity Connection And Fencing | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries expanded |  |  | Tongaren | Milima |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 3000000 | 2869955 | 2869955 | CGB |  | 2869955 | 0 | 2869955 | 1 | 2869955 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
239 | Erection And Completion Of Eluuya And Mukuyuni Dispensaries | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries erected and completed |  |  | Tongaren | Milima |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 4800000 | 4729946.4 | 4729946.4 | CGB |  | 4729946.4 | 0 | 4729946.4 | 1 | 4729946.4 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
313 | Equipping of Lukhokhwe Dispensary. | Equipping of Lukhokhwe Dispensary with drugs and medical equipment | To provide accesswible health services within the community | dispensaries equipped |  |  | Tongaren | Milima |  |  | Ward Based | Health & Sanitation | 2015/16 |  | 42430 |  |  | 386335 | 386335 | CGB |  | 386335 | 0 | 386335 | 1 | 386335 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
315 | Purchase of one acre of land | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health facilities. | acres of land purchased |  |  | Tongaren | Milima | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
401 | Periodic Maintenance of Roads In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43481 | 43608 |  | 3946668 | 3946668 | 3946668 | County Government of Bungoma |  | 3946668 |  | 3946668 | 96.07% | 3946668 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
492 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
590 | Periodic Maintenance of Naitiri Slaughterhouse Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43963 | 43994 | 8399171 | 8399171 | 8399171 | County Government of Bungoma |  | 8399171 |  | 8399171 |  | 8399171 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
591 | Periodic Maintenance of Roads In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43969 |  | 8399171 | 8399171 | 8399171 | County Government of Bungoma |  | 8399171 |  | 8399171 | 30.05% | 8399171 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
598 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
883 | Periodic Maintenance of Maliki S.A - Wabukhonyi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44329 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
884 | Periodic Maintenance of Kwa Area - Nabing'Eng'E Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44218 | 44326 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1191 | Construction of Walubengo Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44691 |  | 6165151 | 6165151 | 6165151 | County Government of Bungoma |  | 6165151 |  | 6165151 |  | 6165151 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1192 | Periodic Maintenance of Bondeni - Utubora - Mukuyuni Girls Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44698 | 44729 | 15566963.73 | 15566963.73 | 15566963.73 | County Government of Bungoma |  | 15566963.73 |  | 15566963.73 |  | 15566963.73 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1193 | Periodic Maintenance of Namuininia - Munialo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44703 | 44734 | 15566963.73 | 15566963.73 | 15566963.73 | County Government of Bungoma |  | 15566963.73 |  | 15566963.73 |  | 15566963.73 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1194 | Periodic Maintenance of Maliki Pag - Maliki School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44700 | 44731 | 5146618 | 5146618 | 5146618 | County Government of Bungoma |  | 5146618 |  | 5146618 |  | 5146618 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1195 | Periodic Maintenance of Roads In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.3KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44704 |  | 15566963.73 | 15566963.73 | 15566963.73 | County Government of Bungoma |  | 15566963.73 |  | 15566963.73 | 78.48% | 15566963.73 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1196 | Upgrading of Roads In Milima Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44692 |  | 6165151 | 6165151 | 6165151 | County Government of Bungoma |  | 6165151 |  | 6165151 | 48.66% | 6165151 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1197 | Routine Maintenance Of Maliki P.A.G - Maliki Secondary School | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44695 |  | 5146618 | 5146618 | 5146618 | County Government of Bungoma |  | 5146618 |  | 5146618 | 100.0% | 5146618 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1734 | Periodic Maintenance of Namboko Primary - Mbakalo River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45312 | 45430 | 45461 | 4586013 | 4586013 | 4586013 | County Government of Bungoma |  | 4586013 |  | 4586013 |  | 4586013 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1735 | Periodic Maintenance of Festo - Hamsini - Wangala Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45308 | 45433 | 45464 | 7342408.5 | 7342408.5 | 7342408.5 | County Government of Bungoma |  | 7342408.5 |  | 7342408.5 |  | 7342408.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1736 | Periodic Maintenance of Mama Agoi Road - Wataka Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45425 | 45456 | 7342408.5 | 7342408.5 | 7342408.5 | County Government of Bungoma |  | 7342408.5 |  | 7342408.5 |  | 7342408.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1737 | Periodic Maintenance of Mama Agoi - Wataka Road And Festo - Hamusini - Wangala Road In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45429 |  | 7342408.5 | 7342408.5 | 7342408.5 | County Government of Bungoma |  | 7342408.5 |  | 7342408.5 | 100.0% | 7342408.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1738 | Periodic Maintenance of Namboko Primary - Mbakalo River Road In Milima Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Tongaren | Milima |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45428 |  | 4586013 | 4586013 | 4586013 | County Government of Bungoma |  | 4586013 |  | 4586013 | 100.0% | 4586013 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
95 | Purchase Of 01 Acre Land For Auction Ring At Maliki Market | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new auction ring | One acre of Land For Auction Ring At Maliki Market Purchased | 3110599 | Ward based projects | Tongaren | Milima |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 | 26/6/2019 | 27/12/2019 | 16/1/2020 | 1500000 | 1200000 | 1200000 | CGB |  | 1200000 |  | 1200000 |  | 1099060 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
140 | Purchase of 1 acre of land for health centre | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of health centre | One acres of Land for a health centre Purchased | 3110599 | Ward based projects | Tongaren | Milima |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 20/07/2016 | 20/9/2016 | 24/8/2016 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 800000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
56 | Proposed Completion Of Works For Lukhokhwe Vocational Training Center | Construction of VTC | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 0 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 |  | 0 | 0 | 0 | ongoing and not in use | Funds Channeled To Existing Project
121 | Construction Of 1 No. Ecde Classroom At Luuya Deb, Bilibili And Kegode Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4500000 | 4364390 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 4364390 | 1 | 4364390 | 0 | 0 | complete and in use | 1
153 | Proposed Erection And Completion Of Works For Lukhokhwe Vocational Training Centre In Milima Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 5500000 | 13983515.08 | 5500000 | County Government of Bungoma | N/A | 5500000 | 0 | 13983515.08 | 1 | 7755924.95 | 6227590.13 | 0 | ONGOING. At roofing level | 0.8
154 | Proposed Erection And Completion Of 1 No Ecde At Nabinge'nge Primary School In Milima Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1300000 | 1999980 | 1300000 | County Government of Bungoma | N/A | 1300000 | 0 | 1999980 | 1 | 1114500 | 885480 | 0 | complete and in use | 1
178 | Construction Of 1no Ecde Classroom At Mukhuyu, Milima Riverside And Mufupi Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 4500000 | 3908654.8 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 3908654.8 | 1 | 3908654.8 | 0 |  | complete and in use | 1
204 | Construction Of 1no. Ecde Classroom At Milima, Mukuyuni And Maliki Primary Schools In Milima Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Tongaren | Milima |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4500000 | 3881352 | 4500000 | County Government of Bungoma | N/A | 4500000 |  | 3881352 | 1 | 3881352 | 0 |  | complete and in use | 100.0%
36 | Proposed Rehabilitation Of Rivers Kibisi, Magemo Dam, And Nabingenge Dam In Ndivisi, And Milima Wards | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers |  | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 5916000 | 5820000 | 5820000 | FLLOCA | IDA | 0 | 5820000 | 0 | 1 | 0 | 0 |  | On going and not in use | 0.4 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
88 | Construction and Protection of 8no. Water Springs in Milima ward | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 Water springs constructed and equipped | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 2000000 | 1997009.6 | 1997009.6 | CGB | N/A | 1997009.6 | 0 | 1997009.6 | 1 | 0 | 1997009.6 | 0 | Complete and in use | 100% complete | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS IN PROGRESS
132 | Construction of Maliki Primary water project in Milima ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 6850000 | 6749526 | 6749526 |  | N/A | 6749526 | 0 | 6749526 | 1 | 6749526 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
133 | Upgrading of Mukuyuni Dispensary borehole and protection of 3no. Water springs in Milima ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded and 3 water springs constructed and proctected | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 4500000 | 4397339.6 | 4397339.6 |  | N/A | 4397339.6 | 0 | 4397339.6 | 1 | 4397339.6 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
154 | protection of 5no water springs in milima ward | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 1300000 | 1138656 | 1138656 |  | N/A | 1138656 | 0 | 1138656 | 1 | 1138656 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
266 | PROTECTION OF 4NO. WATER SPRINGS IN MILIMA WARD | Excavation, construction of wing walls; fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 800000 | 709000 | 709000 |  | N/A | 709000 | 0 | 709000 | 1 | 709000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
317 | INSTALLATION OF SOLAR PUMPING UNIT AT MALIKI AND MAKUNGA BOREHOLES IN MILIMA WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes upgraded and solarised | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3500000 | 3113714 | 3113714 |  | N/A | 3113714 | 0 | 3113714 | 1 | 3113714 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
367 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1533538 | 1533538 |  | N/A | 1533538 | 0 | 1533538 | 1 | 1533538 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
398 | Central Division Water Project pipeline Extension. mfupi – Bilibili | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1000000 | 946990 | 946990 |  | N/A | 946990 | 0 | 946990 | 1 | 946990 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
401 | Central Division Water Project Drill a borehole at Mukuyuni market and equip with hand pump | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1468600 | 1468600 |  | N/A | 1468600 | 0 | 1468600 | 1 | 1468600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
413 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1435500 | 1435500 |  | N/A | 1435500 | 0 | 1435500 | 1 | 1435500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
450 | Pipeline Extention and Construction of Water project | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1300000 | 1175300.4 | 1175300.4 |  | N/A | 1175300.4 | 0 | 1175300.4 | 1 | 1175300.4 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
474 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1533538 | 1533538 |  | N/A | 1533538 | 0 | 1533538 | 1 | 1533538 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
475 | Construction of 5 roof Catchments and 50m3 Masonry tank | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2000000 | 1956000 | 1956000 |  | N/A | 1956000 | 0 | 1956000 | 1 | 1956000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
476 | Drilling of borehole at Makunga Market | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1800000 | 1575000 | 1575000 |  | N/A | 1575000 | 0 | 1575000 | 1 | 1575000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
477 | Upgrading of Mukuyuni Makunga pipeline | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2700000 | 2598720 | 2598720 |  | N/A | 2598720 | 0 | 2598720 | 1 | 2598720 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
555 | Protection of 10 water springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | No. 10 of water springs constructed | 3110599 | Other Infrastructure &Civil Works |  | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1435500 | 1435500 |  | N/A | 1435500 | 0 | 1435500 | 1 | 1435500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
556 | Central Division Water Project pipeline Extension. mfupi – Bilibili | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1000000 | 946990 | 946990 |  | N/A | 946990 | 0 | 946990 | 1 | 946990 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
557 | Central Division Water Project Drill a borehole at Mukuyuni market and equip with hand pump | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled | 3110599 | Other Infrastructure &Civil Works | Tongaren | Milima |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1468600 | 1468600 |  | N/A | 1468600 | 0 | 1468600 | 1 | 1468600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
16 | Construction of Milima ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Milima ward office constructed | 3111504 | Construction of non- residential buildings | Tongaren | Milima | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2023/24 | 45300 | 45415 | - | 9500000 | 9453590 | 9500000 | County Government of Bungoma | - | 9453590 | - | 9453590 | 1 | 0 | 0 | 0 | Ongoing | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | Dite dispute delayed project implementation. No resolved.
| Supply and delivery of young dairy animals(Heifers) 18 to 24 months | Supply and delivery of young dairy animals(Heifers) 18 to 24 months | To enhance dairy production, value addition and income generation | 20 Dairy animals (heifers) supplied and delivered to farmer groups | 3110599 | Ward Based projects | Tongaren | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 2000000 | 1960000 | 2000000 | County Government of Bungoma |  | 1960000 | 0 | 1960000 | 1 | 1960000 | 0 | 0 | Completed
29 | Proposed Installation and commissioning of 5No. Solar powered Floodlight | Installation of Solar of 5No | promotion of MSMEs and security | Solar powered floodligts installed | 1358429-2023-24 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 5000000 |  |  | CGB | [8 empty] | Complete | 100 | 5
100 | Installation of 2No high mast flood lights solar powered | of mast lights mast flood | [5 empty] | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Eagle Power Services limited | 2021/22 |  | Complete and in use |  | 786500 |  |  | CGB
101 | Construction of 4 No Bodaboda sheds | Of sheds streetlights | [5 empty] | Milima |  | Trade, Energy and Industrialization | Dept of Trade | Newark Holdings limited | 2021/22 |  | Complete and in use |  | 1192480 |  |  | CGB
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Milima |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
110 | Construction of 4 no. Bodaboda sheds at Maliki stage,Nabingenge stage,Wabukhonyi stage and Lukhokhwe stage | of sheds stage Wabukhonyi Maliki Wabukhonyi stage | [5 empty] | Milima |  |  |  | Namwaya Enterprises Ltd | 2019/20 |  | Complete |  | 1080000 |  |  | CGG
130 | Construction of 3 boda boda sheds | Of sheds streetlights | [5 empty] | Milima |  |  |  | Dry Logistic ltd | 2018/19 |  | Complete |  | 897880.59 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Milima |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Milima |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Milima |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
44 | construction of maeni youth empowerment ablution block | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Ablution blocks constructed |  |  | Kimilili | Maeni |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 |  |  |  | 2000000 | 1933845 | 1933845 | CGB |  | 1933845 | 0 | 0 | 0 | 0 |  | 1933845 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
82 | Construction Of Maeni Youth Empowerment Ablution Block |  |  | Ablution blocks constructed |  |  | Kimilili | Maeni |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 2000000 | 1933845 | 1933845 | CGB |  | 1933845 | 0 | 1940000 | 1.0032 | 1940000 |  | -6155 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
170 | Construction Of Kamasielo Dispensary Maternity Wing With Toilets And Tiles Inside | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries with toilets constructed |  |  | Kimilili | Maeni |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 3307190 | 3440040 | 3440040 | CGB |  | 3440040 | 0 | 1414290 | 0.41113 | 1414290 |  | 2025750 | Complete and not in use | [6 empty] | No | complete | Financial | Yes
171 | Construction Of Male Ward At Maeni Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Male wards constructed |  |  | Kimilili | Maeni |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 2000000 | 2075240 | 2075240 | CGB |  | 2075240 | 0 | 1662431 | 0.80108 | 1662431 |  | 412809 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
233 | Construction Of Kamasielo 4 Door Pit Latrines | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Kimilili | Maeni |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 1500000 | 1405660 | 1405660 | CGB |  | 1405660 | 0 | 1405660 | 1 | 1405660 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
319 | Construction of Public Toilets | Digging of 20ft deep fit,flooring,walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the market | public toilets constructed |  |  | Kimilili | Maeni | [11 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete and not in use. | [6 empty] | No | complete | Financial | Yes
320 | Purchase of Land for Kamasielo dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services in the area | acres of land purchased |  |  | Kimilili | Maeni |  |  | Ward Based | Health & Sanitation | 2015/16 | 03.06.2016 |  | 03.07.2016 |  | 1000000 | 1000000 | CGB |  | 1000000 | 0 | 1000000 | 1 | 1000000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
325 | Purchase of 1 acre land for construction of Kamasielo Dispensary | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | acres of land purchased |  |  | Kimilili | Maeni |  |  | Ward Based | Health & Sanitation | 2015/2016 | 42522 |  | 42552 |  | 1000000 | 1000000 | CGB |  | 1000000 | 0 | 1000000 | 1 | 1000000 |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
326 | Proposed Erection & Completion of Kamasielo dispensary | Excavation of trenches for foundation,construction of thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health service within the community | dispensaries erected and completed |  |  | Kimilili | Maeni |  |  | CEF | Health & Sanitation | 2016/2017 | 42644 |  | 42552 |  | 2101280 | 2101280 | CGB |  | 2101280 | 0 | 1830830.2 | 0.87129 | 1830830.2 |  | 270449.8 | 98% complete. | [6 empty] | No | complete | Financial | Yes
327 | ERECTION AND COMPLETION OF KAMUSINDE HEALTH CENTRE | Excavation of trenches for foundation,construction of thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health service in the community | health centres erected and completed |  |  | Kimilili | Maeni |  |  | CEF | Health & Sanitation | 2016/2017 | 42675 |  | 42736 |  | 5588479 | 5588479 | CGB |  | 5588479 | 0 | 4395700 | 0.78656 | 4395700 |  | 1192779 | Complete | [6 empty] | No | complete | Financial | Yes
328 | Completion of a male ward at Nasusi dispensary | Walling,roofing,painting,fixing of doors and windows | To reduce congestion at the male ward. | Male ward completed |  |  | Kimilili | Maeni |  |  | CEF | Health & Sanitation | 2016/2017 | 42374 |  | 42743 |  | 3183248 | 3183248 | CGB |  | 3183248 | 0 | 1041054 | 0.32704 | 1041054 |  | 2142194 | Complete | [6 empty] | No | complete | Financial | Yes
332 | Purchase of land for Kamusinde Health Center | Land identification,search,survey,signing of sale agreement,payment and transfer of ownership of the title deed | To provide physical space for construction of health services in the area | acres of land purchased |  |  | Kimilili | Maeni |  |  | Ward Based | Health & Sanitation | 2015/2016 | [6 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete | [6 empty] | No | complete | Financial | Yes
333 | Construction of standard hall at Kamusinde R.C dispensary | excavation of trenches for foundation,construction of thick slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Standard halls constructed |  |  | Kimilili | Maeni |  |  | Ward Based | Health & Sanitation | 2015/2016 |  | 42747 |  |  | 998539.6 | 998539.6 | CGB |  | 998539.6 | 0 | - | #VALUE! | - |  | #VALUE! | Contract terminated. | [6 empty] | No | complete | Financial | Yes |  |  |  | No
6 | Erection and completion of Maeni Youth empowerment centre | Erection and completion of youth empowerment centre | To narture talents | Youth centre constructed | 3111504 | Other infrastructure and civil works | Kimilili | Maeni |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Youths and Sports | 2018/19 |  |  |  | 5671170 | 5671170 | 5671170 | County Government of Bungoma | n/a | n/a | n/a | 5671170 | 1 | 5671170 | 0 | 0 | Completed
7 | Equiping of Maeni Youth Empowerment Centre | Equipping of maeni Youth Empowerment Centre | To narture talents | Equipments purchased |  |  | Kimilili | Maeni |  | Recreation, Culture and Youth and Sports | Gender,Culture, Youth and Sports | Gender and Culture | 2022/23 | 25/04/2023 | 23/07/2023 |  | 1000000 | 959094 | 959094 | County Government of Bungoma | n/a | n/a | n/a | 959094 | 1 | 959094 | 0 | 0 | Completed
207 | Periodic Maintenance of Komolo - Teso Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43121 | 43231 |  | 2665593 | 2665593 | 2665593 | County Government of Bungoma |  | 2665593 |  | 2665593 |  | 2665593 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
208 | Periodic Maintenance of Roads In Maeni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.9KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43124 | 43231 |  | 2665593 | 2665593 | 2665593 | County Government of Bungoma |  | 2665593 |  | 2665593 | 79.95% | 2665593 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
303 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 86.67% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
386 | Grading of Kibisi - Kamasielo Road | Grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43600 | 43631 | 8473660.8 | 8473660.8 | 8473660.8 | County Government of Bungoma |  | 8473660.8 |  | 8473660.8 |  | 8473660.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
387 | Grading of Yembe Road | Grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43477 | 43598 | 43629 | 8473660.8 | 8473660.8 | 8473660.8 | County Government of Bungoma |  | 8473660.8 |  | 8473660.8 |  | 8473660.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
388 | Periodic Maintenance of Roads In Maeni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43484 | 43609 |  | 8473660.8 | 8473660.8 | 8473660.8 | County Government of Bungoma |  | 8473660.8 |  | 8473660.8 | 96.24% | 8473660.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
389 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
557 | Grading of Kundu-Sangura Road | Grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43962 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
598 | Routine Maintenance Of Roads In Tongaren And Kimilili Sub-Counties Through Framework Contracts | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43844 | 43971 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
836 | Periodic Maintenance of Kibisi - Musikiti - Khamulati Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44340 |  | 14696388 | 14696388 | 14696388 | County Government of Bungoma |  | 14696388 |  | 14696388 |  | 14696388 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
837 | Periodic Maintenance of Kibisi - Maeni Primary - Nameme Muslim - Yembe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44335 |  | 14696388 | 14696388 | 14696388 | County Government of Bungoma |  | 14696388 |  | 14696388 |  | 14696388 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
838 | Periodic Maintenance of Lumbasi Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44329 |  | 14696388 | 14696388 | 14696388 | County Government of Bungoma |  | 14696388 |  | 14696388 |  | 14696388 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
839 | Periodic Maintenance of Mutekesi - St. Jan Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44335 |  | 14696388 | 14696388 | 14696388 | County Government of Bungoma |  | 14696388 |  | 14696388 |  | 14696388 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
840 | Periodic Maintenance of Omonya - River Kamusinde Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44336 |  | 2275224 | 2275224 | 2275224 | County Government of Bungoma |  | 2275224 |  | 2275224 |  | 2275224 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
841 | Periodic Maintenance of Roads In Maeni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.9KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44334 |  | 14696388 | 14696388 | 14696388 | County Government of Bungoma |  | 14696388 |  | 14696388 | 100.01% | 14696388 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
842 | Periodic Maintenance of Roads In Maeni Ward - Negotiation 872544 | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44331 |  | 2275224 | 2275224 | 2275224 | County Government of Bungoma |  | 2275224 |  | 2275224 | 96.93% | 2275224 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
843 | Drainage Works In Kimilili And Tongaren | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44326 |  | 7838822 | 7838822 | 7838822 | County Government of Bungoma |  | 7838822 |  | 7838822 | 100.0% | 7838822 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1455 | Periodic Maintenance of Yembe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45058 |  | 2851864 | 2851864 | 2851864 | County Government of Bungoma |  | 2851864 |  | 2851864 |  | 2851864 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1456 | Periodic Maintenance of Nasusi Road And Yembe Road In Maeni Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kimilili | Maeni |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45067 |  | 2851864 | 2851864 | 2851864 | County Government of Bungoma |  | 2851864 |  | 2851864 | 99.96% | 2851864 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
122 | Purchase Of 1/2 An Acre For Maeni Youth Resource Center | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new resource centre | A half an acre of Land for Maeni Youth Resource Center Purchased | 3110599 | Ward based projects | Kimilili | Maeni |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 |  |  |  | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 1 | 0 | 0 |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
146 | Purchase of land for Kikwechi ECDE | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Kikwechi ECDE Purchased | 3110599 | Ward based projects | Kimilili | Maeni |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 20/07/2016 | 24/9/2016 | 24/8/2016 | 600000 | 600000 | 600000 | CGB | N/A | 600000 |  | 600000 |  | 600000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
168 | purchase of land for Kamasielo dispensary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for machakha dispensary Purchased | 3110599 | Ward based projects | Kimilili | Maeni |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/11/2015 | 21/02/2016 | 22/4/2016 | 600000 | 600000 | 600000 | CGB | N/A | 600000 |  | 600000 | 1 | 600000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
169 | purchase of land for Kamusinde Health Center | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new health centre | One acres of Land for Kamusinde Health Center Purchased | 3110599 | Ward based projects | Kimilili | Maeni |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | 21/11/2015 | 21/02/2016 | 22/4/2016 | 850000 | 850000 | 850000 | CGB | N/A | 850000 |  | 850000 | 1 | 850000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
170 | purchase of land for Kikwechi ECDE Classroom | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Kikwechi E.C.D.E Purchased | 3110599 | Ward based projects | Kimilili | Maeni |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 |  |  |  | 850000 | 850000 | 850000 | CGB | N/A | 850000 |  | 850000 | 1 | 0 |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
171 | Purchase of land parcel no. kimilili/sikhendu/2973 for cooperative society | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of a cooperative societty | One acres of Land for cooperative society Purchased | 3110599 | Ward based projects | Kimilili | Maeni |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2015/16 | [6 empty] | CGB | N/A |  |  |  | 1 |  |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
84 | proposed erection and completion works for 1 No. ECDE classroom at Nasioya, Kamusinde FYM and Kikwechi primary schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Maeni |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 5100000 | 4426876 | 5100000 | County Government of Bungoma | N/A | 5100000 | 0 | 4426876 | 1 | 4426876 | 0 | 0 | Complete and in use | 1
148 | Proposed Erection And Completion Of 1 No. Classroom At Buko Rc And Namboani Primary Schools In Maeni Ward. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Maeni |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 2400000 | 2500000 | 2400000 | County Government of Bungoma | N/A | 2400000 | 0 | 2500000 | 1 | 2142187.55 | 357812.45 | 0 | ongoing. At finishing | 0.9
201 | The Proposed Erection And Completion Of 1 N0 Classroom At Namboani Vtc, Maeni And Kamusinde Primary School In Maeni Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kimilili | Maeni |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4300000 | 4315340 | 4300000 | County Government of Bungoma | N/A | 4300000 |  | 4315340 | 1 | 4315340 | 0 |  | complete and in use | 100.0%
5 | Upgrading of Mkulima - Nasussi Road | Upgrading of road from Mkulima-Nasussi to butimenous standard | To enhance road accessbility | 0.6KM of Road Upgraded to Butiminous Standard | 2640503 | Other capital Grants and Transfer | Kimilili | Maeni |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilil Manicipality | 2020/2021 | 30/07/2022 | 30/12/2022 | 44951 | 33405394 | 33405394 | 33405394 | County Government[Equitable share] | Kenya urban support progamme-World Bank |  | 33405394.18 | 33405394.18 | 1 |  |  |  | Completed | 1 | [14 empty] | Complete and in use
6 | Installation of highmast lights at Nasusi Market | Installation of highmast lights at Nasusi market | To light the market and enhance security | 1 Highmast light installed | 2640505 | Other capital Grants and Transfer | Kimilili | Maeni |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 45149 | 45506 | 45278 | 3000000 | 2990400 | 2990400 | County Government[Equitable share] | Kenya urban support progamme-World Bank |  | 2990400 | 2990400 | 1 | 2990400 |  |  | Completed | 1 | [14 empty] | Complete and in use
11 | Periodic Maintenance of Nambaoni VTC-Topela Road | Periodic Maintenance of Namaoni VTC-Topela Road | To enhance road accessibility | 1.95KM of Road maintained | 3110599 | Other infrastructure and Civil Works | Kimilili | Maeni |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 2nd Feb,2024 | 2nd May,2024 | 8th May,2024 | 2000000 | 1850000 | 1850000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 1769812 | 0 | 1769812 | 1 |  |  |  | Completed | 1 | [14 empty] | Complete and in use
12 | Periodic Maintenance of Kibisi-Kamasielo Dispensary Road | Periodic Maintenance of Kibisi-Kamasielo Dispensary Road | To enhance road accessibility | 2KM of Road maintained | 3110599 | Other infrastructure and Civil Works | Kimilili | Maeni |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 11th April,2024 | 11th July,2024 | 13th June,2024 | 3000000 | 2893968 |  | County Government[Equitable share] | Kenya urban support progamme-World Bank | [7 empty] | completed | 1 | [14 empty] | Complete and in use
13 | Construction and Protection of 8 No.water Springs in Kimilili | Construction and Protection of 8 No.water Springs in Kimilili | To provide clean water | 8 Water springs protected | 3110599 | Other infrastructure and Civil Works | Kimilili | Maeni |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 11th April,2024 | 11th July,2024 | 13th June,2024 | 2000000 | 1900000 |  | County Government[Equitable share] | Kenya urban support progamme-World Bank | 1900000 | 0 | 1900000 | 1 | 1900000 |  |  | completed | 1 | [14 empty] | Complete and in use
22 | Periodic Maintenance of Namaraya-Antoni-Pius Kisiangani Road | Periodic Maintenance of Namaraya-Antoni-Pius Kisiangani Road | To enhance road accessibility | 1.9KM of Road maintained | 3110599 | Other infrastructure and Civil Works | Kimilili | Maeni |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 11th April,2024 | 11th July,2024 |  | 4750000 | 4750000 | 4750000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 4686295.6 | 0 | 0 | 0 | 0 | 4686295.6 |  | Completed | 1 | [14 empty] | Complete and in use
24 | Upgrading of Maeni Co-operative Borehole | Upgrading of Maeni Co-operative Borehole | To enhance access to clean water | 1 Borehole upgraded | 3110599 | Other infrastructure and Civil Works | Kimilili | Maeni |  | Agriculture,Urban and Rural Development | Lands,Urban/physical Planning, Housing and Manicipalities | Kimilili Municipality | 2023/2024 | 11th April,2024 | 11th July,2024 | 13 th June,2024 | 3000000 | 2850000 | 2850000 | County Government[Equitable share] | Kenya urban support progamme-World Bank | 2750000 | 0 | 0 | 0 | 0 | 2750000 | 2750000 | Completed | 1 | [14 empty] | Complete and in use
65 | Kamusinde Dispensary To Nasusi Water Project In Maeni Ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | Construction of 1 water project | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5000000 | 4960820.32 | 4960820.32 | CGB | N/A | 4960820.32 | 0 | 4960820.32 | 1 | 4960820.32 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
131 | Upgrading of Maeni dispensary borehole and protection of 10no. Water springs in Maeni ward. | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole upgraded and 10 water springs constructed and upgraded | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 5000000 | 4920000 | 4920000 |  | N/A | 4920000 | 0 | 4920000 | 1 | 4920000 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
152 | Drilling of water at buko primary school | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 2000000 | 1875024 | 1875024 |  | N/A | 1875024 | 0 | 1875024 | 1 | 1875024 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
199 | CONSTRUCTION AND PROTECTION OF 5NO. WATER SPRINGS IN MAENI WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 5 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1000000 | 960770 | 960770 |  | N/A | 960770 | 0 | 960770 | 1 | 960770 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
217 | KABERWA-KAPSOWONY-CHESAMISI-MAENI-KAMKUYWA WATER PROJECT PHASE I | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 35200000 | 35057364 | 35057364 |  | N/A | 35057364 | 0 | 35057364 | 1 | 11639962 | 23417402 | 0 | Complete and in use | 0.5 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
248 | DRILLING OF 3NO BOREHOLES IN MAENI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 3 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 5500000 | 5257236 | 5257236 |  | N/A | 5257236 | 0 | 5257236 | 1 | 5257236 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
272 | DRILLING OF SIKHENDU MARKET BOREHOLE IN MAENI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 1800000 | 1800000 | 1800000 |  | N/A | 1800000 | 0 | 1800000 | 1 | 1800000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
323 | DRILLING AND SINKING OF MAENI AND KAMASIELO BOREHOLES IN MAENI WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 3800000 | 3586680 | 3586680 |  | N/A | 3586680 | 0 | 3586680 | 1 | 3586680 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
353 | Protection of 8 water Springs and 2No roof catchments | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 springs constructed and 2 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 712455 | 712455 |  | N/A | 712455 | 0 | 712455 | 1 | 712455 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
373 | Protect 10No Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1500000 | 1429210 | 1429210 |  | N/A | 1429210 | 0 | 1429210 | 1 | 1429210 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
406 | Maeni Water Project laying extension and rehabilitation of existing line | Trenching; laying of water pipeline; construction of water points | To enhance access to clean and safe drinking water | KM of water pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 9000000 | 8921600 | 8921600 |  | N/A | 8921600 | 0 | 8921600 | 1 | 8921600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
423 | Upgrading of Maeni Community Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 3110599 | Other Infrastructure &Civil Works |  | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1300000 | 1241800 | 1241800 |  | N/A | 1241800 | 0 | 1241800 | 1 | 1241800 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
534 | Protect 10No Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1429210 | 1429210 |  | N/A | 1429210 | 0 | 1429210 | 1 | 1429210 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
535 | Construct 5No Roof catchment and 1No. 50m3 Storage tank | Construction of roof catchment; storage tank and water points | To enhance access to clean and safe drinking water | 5 roof catchments constructed and 1 water tank constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1346695 | 1346695 |  | N/A | 1346695 | 0 | 1346695 | 1 | 1346695 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
536 | Maeni Water Project laying extension and rehabilitation of existing line | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 9000000 | 8921600 | 8921600 |  | N/A | 8921600 | 0 | 8921600 | 1 | 8921600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
613 | Protection of 8 water Springs and 2No roof catchments | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 water springs constructed and 2 roof catchment constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1500000 | 1424910 | 1424910 |  | N/A | 1424910 | 0 | 1424910 | 1 | 1424910 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
614 | Upgrading of Maeni Community Water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kimilili | Maeni |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 2500000 | 2483300 | 2483300 |  | N/A | 2483300 | 0 | 2483300 | 1 | 2483300 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
6 | Construction of Maeni ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Maeni ward office constructed | 3111504 | Construction of non- residential buildings | Kimilili | Maeni | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2014/15 | 41981 | 45813 | 43544 | 9500000 | 10403554 | 9500000 | County Government of Bungoma | - | 10403554 | - | 10403554 | 1 | 10403554 | 0 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Construction Of Maeni Stores | Construction of Maeni Stores | To provide for storage for coffee produce | 1 store constructed | 3110504 | Other infrastructure and civil works | Kimilili | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 43253 | 43258 | 15/6/2018 | 3000000 | 1500000 | 1500000 | County Government of Bungoma |  | 1500000 | 0 | 1500000 | 1 | 1500000 | 0 | 0 | Completed
| Construction of stores for Maeni Cooperative Society | Construction of stores for Maeni Cooperative Society | To enhance income generation within the Community | 1 Store constructed | 3110504 | Other infrastructure and civil works | Kimilili | Maeni |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 42797 | 42802 | 23/6/2017 | 3500000 | 1500000 | 1500000 | County Government of Bungoma |  | 1500000 | 0 | 1500000 | 1 | 1500000 | 0 | 0 | Completed
| Construction of bean store for Maeni Cooperative Society | Construction of bean store for Maeni Cooperative Society | To enhance income generation among dairy farmers | Bean store constructed for Maeni Cooperative Society | 3110504 | Other infrastructure and civil works | Kimilili | Maeni |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 27/4/2019 | 27/10/2019 | 25/5/2019 | 5000000 | 3627328 | 3750000 | County Government of Bungoma |  | 3627328 | 0 | 3627328 | 1 | 3627328 | 0 | 0 | Completed
| Construction of Gate and Fencing for Maeni Warehouse | Construction of Gate and Fencing for Maeni Warehouse | To promote coffee production and enhance income generation among Coffee farmers | 1 gate fixed and fencind done | 3110504 | Other infrastructure and civil works | Kimilili | Maeni |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44898 | 44903 | 15/1/2025 | 6000000 | 3450000 | 3500000 | County Government of Bungoma |  | 3450000 | 0 | 2900840 | 0.84 | 2900840 | 549160 | 549160 | Completed
78 | Installation of 40 grid powered streetlights in Kimilili and webuye west sub-counties | of streetlights and Kimilili and webuye | [5 empty] | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | M/S Megawat Power and Telecommunication Company | 2021/22 |  | Complete and in use |  | 3028200 | 0 |  | CGB
97 | Construction of I no bodaboda sheds | Of bodaboda streetlights | [5 empty] | Maeni |  | Trade, Energy and Industrialization | Dept of Trade | Ms Denmo Enterprises Limited | 2021/22 |  | Complete and in use |  | 380712 |  |  | CGB
102 | Proposed insta+E51+A40:N42+A40:N43+A40:N45+E51+A40:N42+A40:N47+A40:N46+A40:M46+A40:L46+A40:J46+A40:I46+A40:H46+A40:I46 | insta N A A N A L A N I46+A | [5 empty] | Maeni |  |  |  | M/S Muweku General Contractors Limited | 2020/21 |  | Complete |  | 3230795 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | Maeni |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Maeni |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Maeni |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
29 | Purchase of medical equipment for Chepyuk and Kaimagul dispensaries | Equipping with drugs and medical equipment |  | medical equipments purchased |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 17/5/24 |  |  | 1000000 | 941150 | 941150 | CGB |  | 941150 | 0 | 0 | 0 | 0 | 941150 | 941150 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
46 | Construction of 4NO.Doors pit latrines at chepyuk market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 45327 |  |  | 1000000 | 996579 | 996579 | CGB |  | 996579 |  |  | 0 |  |  | 996579 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
61 | Construction of 11NO. Doors pit latrines with Urinal at Chepkurkur Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 11No.door pit latrine constructed |  |  | Mt. Elgon | CHEPYUK |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 |  |  |  | 800000 | 991718 | 991718 | CGB |  | 991718 | 0 | 0 | 0 | 0 |  | 991718 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
65 | Construction of 4NO.Doors pit latrines at chepyuk market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 4No.door pit latrine constructed |  |  | Mt. Elgon | CHEPYUK |  |  | Health & Sanitation | Health & Sanitation | 2023-2024 | 45327 |  |  | 1000000 | 996579 | 996579 | CGB |  | 996579 | 0 | 0 | 0 | 0 |  | 996579 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
73 | Erection And Completion Works For Maternity Ward At Chepyuk Dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wards erected and completed |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 3000000 | 2683750 | 2683750 | CGB |  | 2683750 | 0 | 2490691 | 0.92806 | 2490691 | 193059 | 193059 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
74 | Construction 0f 2no.Door Pit Latrines At Chepyuk And Kaimugul Dispensary | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 2No. Door pit latrines constructed |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 800000 | 747920 | 747920 | CGB |  | 747920 | 0 | 686560 | 0.91796 | 686560 | 61360 | 61360 | Complete and in use | [6 empty] | No | complete | Financial | Yes |  |  |  | No
100 | Construction Of 6 Door Pit Latrine At Chepkurkur Dispensary | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 6no. Door pit latrines constructed |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2021-2022 |  |  |  | 500000 | 498591 | 498591 | CGB |  | 498591 | 0 |  | 0 |  |  | 498591 | Yey to start | [6 empty] | No | complete | Financial | Yes |  |  |  | No
124 | Purchase Of Medical Beds For Kubura Dispensary |  |  | medical beds purchased |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 400000 | 441600 | 441600 | CGB |  | 441600 | 0 | 441600 | 1 | 441600 |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
157 | Construction Of Kubura Dispensary Maternity Wing | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1711975 | 1699420 | 1699420 | CGB |  | 1699420 | 0 | 0 | 0 | 0 |  | 1699420 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
158 | Construction Of Chepkurkur Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | dispensaries constructed |  |  | Mt. Elgon | CHEPYUK |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1985553 | 2174950 | 2174950 | CGB |  | 2174950 | 0 | 2054451 | 0.9446 | 2054451 |  | 120499 | Complete and in use | [6 empty] | No | complete | Financial | Yes
219 | Construction Of An Outpatient Unit At Chepyuk Dispensary And Kaimugul Dispensary-4 Door pit latrine | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Outpatient wings and 4No. Door pit latrines constructed |  |  | Mt. Elgon | CHEPYUK |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 10105885 | 9971945.76 | 9971945.76 | CGB |  | 9971945.76 | 0 | 7208720.8 | 0.7229 | 7208720.8 |  | 2763224.96 | Complete and in use | [6 empty] | No | complete | Financial | Yes
271 | Erection and completion of Chepkurkur Dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community. | dispensaries erected and completed |  |  | Mt. Elgon | CHEPYUK |  |  | CEF | Health & Sanitation | 2016/2017 | 42887 | 42826 | - |  | 6856000 | 6856000 | CGB |  | 6856000 | 0 | 0 | 0 | 0 |  | 6856000 | Contract terminated. | [6 empty] | No | complete | Financial | Yes |  |  |  | No
289 | Construction of public toilet at Kipsigon market | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To enhance access to sanitary facilities at the market | Public toilets constructed |  |  | Mt. Elgon | CHEPYUK |  |  | CEF | Health & Sanitation | 2016/17 | 42788 | 42877 |  |  | 42861 | 42861 | CGB |  | 42861 | 0 | 1200000 | 27.9975 | 1200000 |  | -1157139 | - | [6 empty] | No | complete | Financial | Yes
80 | Upgrading of Masaek-Kipsigon-Kapkesei | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2013/2014 | 41652 | 41781 |  | 5204250 | 5204250 | 5204250 | County Government of Bungoma |  | 5204250 |  | 5204250 | 100.0% | 5204250 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
307 | Upgrading of Kumurio Bridge | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43479 | 43606 |  | 8877132 | 8877132 | 8877132 | County Government of Bungoma |  | 8877132 |  | 8877132 |  | 8877132 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
308 | Construction of Kumurio Box Culvert In Chepyuk Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43484 | 43605 |  | 8877132 | 8877132 | 8877132 | County Government of Bungoma |  | 8877132 |  | 8877132 | 97.33% | 8877132 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
309 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
498 | Periodic Maintenance of Koring'Otuny - Kabchebuk Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43847 | 43970 |  | 6510152 | 6510152 | 6510152 | County Government of Bungoma |  | 6510152 |  | 6510152 |  | 6510152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
499 | Periodic Maintenance of Roads In Chepyuk Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43840 | 43975 |  | 6510152 | 6510152 | 6510152 | County Government of Bungoma |  | 6510152 |  | 6510152 | 99.8% | 6510152 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
724 | Periodic Maintenance of Chewangoi - Kabukwo - Kubra Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44326 |  | 4412408 | 4412408 | 4412408 | County Government of Bungoma |  | 4412408 |  | 4412408 |  | 4412408 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
725 | Upgrading of Roads In Chepyuk Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44334 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
726 | Periodic Maintenance of Roads In Chepyuk Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44334 |  | 4412408 | 4412408 | 4412408 | County Government of Bungoma |  | 4412408 |  | 4412408 | 99.77% | 4412408 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1054 | Upgrading of Kapkerwa - Terem - Sowos River Crossing | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44692 | 44723 | 12754896 | 12754896 | 12754896 | County Government of Bungoma |  | 12754896 |  | 12754896 |  | 12754896 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1055 | Periodic Maintenance of Land B - Chepyuk - Centre - Kibumet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44692 |  | 8010478.6 | 8010478.6 | 8010478.6 | County Government of Bungoma |  | 8010478.6 |  | 8010478.6 |  | 8010478.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1056 | Periodic Maintenance of Kipsigon - Kapsigei Junction - Koica Water Project | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44705 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1057 | Upgrading of Roads In Chepyuk Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44697 |  | 12754896 | 12754896 | 12754896 | County Government of Bungoma |  | 12754896 |  | 12754896 | 100.0% | 12754896 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1058 | Routine Maintenance Of Kipsigon - Kapsigei Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44697 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1059 | Routine Maintenance Of Land B - Chepyuk Centre - Kibumet Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 7.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44702 |  | 8010478.6 | 8010478.6 | 8010478.6 | County Government of Bungoma |  | 8010478.6 |  | 8010478.6 | 100.0% | 8010478.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1246 | Upgrading of Roads In Chepyuk Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44582 | 44697 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1371 | Construction of Sosap - Plel Box Culvert | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45065 |  | 7950988 | 7950988 | 7950988 | County Government of Bungoma |  | 7950988 |  | 7950988 |  | 7950988 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1372 | Periodic Maintenance of Kipsigon - Kubura Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 11.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45056 |  | 22996498.88 | 22996498.88 | 22996498.88 | County Government of Bungoma |  | 22996498.88 |  | 22996498.88 |  | 22996498.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1373 | Construction of Sosap - Plel Box Culvert In Chepyuk Ward | Construction of 1 No. box culvert | To improve drainage infrastructure and enhance accessibility | Box Culvert Constructed | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45066 |  | 7950988 | 7950988 | 7950988 | County Government of Bungoma |  | 7950988 |  | 7950988 | 100.0% | 7950988 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1374 | Periodic Maintenance of Kipsigon - Kubura Road In Mt. Elgon Sub County | Gravelling and grading works | To improve the road condition and enhance accessibility | 11.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45056 |  | 22996498.88 | 22996498.88 | 22996498.88 | County Government of Bungoma |  | 22996498.88 |  | 22996498.88 | 98.78% | 22996498.88 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1626 | Periodic Maintenance of St. John¦S Kumurio Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45427 |  | 4506295 | 4506295 | 4506295 | County Government of Bungoma |  | 4506295 |  | 4506295 |  | 4506295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1627 | Periodic Maintenance of Kakerua-Sosaplel Road In Chepyuk Warrd | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45432 |  | 4811854 | 4811854 | 4811854 | County Government of Bungoma |  | 4811854 |  | 4811854 | 99.9% | 4811854 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1628 | Periodic Maintenance of Miti Mbili Kewangoi Kabukwo Road In Chepyuk Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45433 |  | 6640341 | 6640341 | 6640341 | County Government of Bungoma |  | 6640341 |  | 6640341 | 99.98% | 6640341 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1629 | Periodic Maintenance of Kaimugul - Kipsikirok Road In Chepyuk Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45425 |  | 6823151 | 6823151 | 6823151 | County Government of Bungoma |  | 6823151 |  | 6823151 | 100.0% | 6823151 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1630 | Periodic Maintenance of St. John'S Kumurio Road In Chepyuk Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.1KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Mt. Elgon | CHEPYUK |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45311 | 45428 |  | 4506295 | 4506295 | 4506295 | County Government of Bungoma |  | 4506295 |  | 4506295 | 99.92% | 4506295 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
2 | Construction of 2 No. Workshop at Kipsigrok VTC in Chepyuk Ward | Construction of VTC workshop | To construct VTC workshop and provide conducive learning environment | VTC workshop constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Vocational Training | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 3000000 | 3000000 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 |  | 0 |  | 3000000 | 3000000 | ongoing | At ring beam (50%).
37 | Proposed Construction And Completion Works For 1no. Ecde Classroom At Kapchebuk and Kibumet Primary Schools In Chepyuk Ward | Completion for ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2195000 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 997642.3 | 0.45451 | 997642.3 | 1197357.7 | 1197357.7 | On-going at ring beam stage | 0.5
38 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Chepyuk And Kubura Primary Schools In Chepyuk Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2989560 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 0 | 0 | 0 | 2989560 | 2989560 | On-going at ring beam stage | 0.5
71 | Construction of 2 ECDE classrooms at kamachei, kamambus and kapkerwa | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 4500000 | 4833000 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 3281679.55 | 0.67902 | 3281679.55 | 1551320.45 | 1551320.45 | Complete and in use | 1
104 | Construction Of 1 No. Ecde Classroom And 2 No. Door Pit Latrine At Sosap-Plel, Kapkisei Cheptoror, Kewaningoi And Marichkut Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 7235000 | 4747505 | 7235000 | County Government of Bungoma | N/A | 7235000 | 0 | 0 | 0 | 0 | 4747505 | 4747505 | At roofing | 0.9
105 | Construction Of 1 No. Ecde Classroom And 2 No. Door Pit Latrine At Kaboroit, Chepkowo And Kimurio Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4365000 | 2433590 | 4365000 | County Government of Bungoma | N/A | 4365000 | 0 | 0 | 0 | 0 | 2433590 | 2433590 | complete and in use | 1
133 | Proposed Erection And Completion Of 1 No. Ecde At Soet And Kapkong Primary And 2 No. Door Pit Latrine At Kapkong Primary School | Construction of ECDE classroom |  | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3530040 | 3438302 | 3530040 | County Government of Bungoma | N/A | 3530040 | 0 | 1443063.54 | 0.4197 | 1443063.54 | 1995238.46 | 1995238.46 | complete and in use | 1
168 | Construction Of Ecde Classrooms At Kabukwo And Tuyabei And Pit latrines | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43801 | 43775 |  | 3000000 | 2867340 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2867340 | 1 | 2867340 | 0 |  | complete and in use | 1
187 | Proposed Erection And Completion Of 1no. Classroom At Somotwet, Saria And Serek Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Mt. Elgon | CHEPYUK |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4700000 | 1994058 | 4700000 | County Government of Bungoma | N/A | 4700000 |  | 0 | 0 | 0 | 1994058 |  | stalled. terminated. retendered. at awarding stage | 0.7
9 | Upgrading of Kopsiro Spring in Chepyuk Ward | Rehabilitation of spring, rehabilitation of sump, installation of solar pumping system, pipelaying; erction of a 30cubic metres, elevated pressed tank; construction of water points. | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change |  | 45544 | 45546 | 45546 | 6000000 | 5465920 | 5465920 | FLLOCA | N/A | 5465920 | 0 | 0 | 1 | 5465920 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
32 | Proposed Rehabilitation Of Kuywa, Lwakhakha Rivers And Matere Stream In Chepyuk, Cheptais And Chesikaki Wards Respectively. | Purchase and supply assorted tree seedlings (indigenous and bamboo) ▪ Deliver tree seedlings to different riparian areas in their respective regions ▪ Land preparation, including clearing planting sites and pitting holes of dimensions 1.5x1.5x1.5 ft) spaced at 1.5m to 2m apart. ▪ Plant the tree seedlings ▪ Work with the identified community-based organization (CBO) or Water Resource Users (WRUAs) to identify the right sites for planting and take the coordinates of the planting sites to inform the greening programme database. The cost of labour shall be incurred by the contractor. ▪ Post-planting maintenance for three months, including weeding, beating-up (gapping) and watering. | To promote climate change mitigation and adaptation | Rehabilitation of riverline riparian | 2640599 | Other Capital Grants and Transfers | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7888000 | 5909325 | 5909325 | FLLOCA | IDA | 0 | 5909325 | 0 | 1 | 0 | 0 |  | Re-tendered | 0 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
78 | Protection of 4 NO water springs in Chepyuk Ward | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 Water springs constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 1000000 | 938068 | 938068 | CGB | N/A | 938068 | 0 | 938068 | 1 | 938068 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
119 | Pipeline extension in Chepyuk ward | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1000000 | 897840 | 897840 |  | N/A | 897840 | 0 | 897840 | 1 | 0 | 897840 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
137 | Laying of Kapkerwa-Kubura distribution line in KOICA II water project | Trenching; pipeline extension; construction of water points | To enhance access to clean and safe drinking water | KM of Water pipeline constructed | 2640503 | Other Capital Grants and Transfers | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 6800000 | 6589032 | 6589032 |  | N/A | 6589032 | 0 | 6589032 | 1 | 6589032 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
142 | extension of kibumet piped water and kimurio | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 850000 | 630000 | 630000 |  | N/A | 630000 | 0 | 630000 | 1 | 630000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
356 | EMIA CHENGOYWO Springs construction | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 3 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 800000 | 618300 | 618300 |  | N/A | 618300 | 0 | 618300 | 1 | 618300 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
461 | EMIA CHENGOYWO Springs construction | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1800000 | 1545750 | 1545750 |  | N/A | 1545750 | 0 | 1545750 | 1 | 1545750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
546 | EMIA CHENGOYWO Springs construction | excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Water spring constructed and protected | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 8000000 | 7527750 | 7527750 |  | N/A | 7527750 | 0 | 7527750 | 1 | 7527750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
547 | Construction of Chepyuk Kapkateny water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 5500000 | 5481750 | 5481750 |  | N/A | 5481750 | 0 | 5481750 | 1 | 5481750 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
549 | Chepyuk kapkateny/ Water project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Mt. Elgon | CHEPYUK |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 2800000 | 2612550 | 2612550 |  | N/A | 2612550 | 0 | 2612550 | 1 | 2612550 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
13 | Construction of Chepyuk ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | Chepyuk ward office constructed | 3111504 | Construction of non- residential buildings | Mt. Elgon | CHEPYUK | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2023/24 | 45300 | 45415 | 45455 | 9500000 | 8953707 | 9500000 | County Government of Bungoma | - | 8953707 | - | 8953707 | 1 | 8602666 | 895370 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Construction of Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | Construction of 20 Coffee Drying Table At Kibingei Fcs, Misikhu Fcs, Sirandafu Fcs, Kapsacho Fcs , Tulkut Fcs | To support growth of coffee farmers and enhance income generation | 20 Coffee drying tables constructed | 3110504 | Other infrastructure and civil works | Mt. Elgon | CHEPYUK |  | Agriculture, Rural and Urban Development | Cooperative development | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44900 | 44838 | 10000000 | 3087863.88 | 3100000 | County Government of Bungoma |  | 3087863.88 | 0 | 3087863.88 | 1 | 3087863.88 | 0 | 0 | Completed
| Purchase and installation of pondliners, watertanks and solar pump kits for Kaptalelio SLM project | Purchase and installation of pondliners, watertanks and solar pump kits for Kaptalelio SLM project | To control loss of water through infiltration | Pondliners, water tanks and solar pump kits purchased and installed | 2640503 | Other Capital grants and transfer (NARGIP) | Mt. Elgon | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 |  |  |  |  | 3888000 | 4000000 | Development partner | IDA | 0 | 3888000 | 3888000 |  | 3888000 | 0 | 0 | Completed
11 | Proposed installation and Commissioning of 10M high powered streetlight in kapuisei,korugotuny,kipsis,chebkube,Bondeni,Sacharani,Chepsoigei, sibanga markets | Installation of streetlights | promotion of MSMEs and security | High powered streetlights installed | BGM/CNTY/TEI/08/OT/2024-2025 1667839-2024/2025 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | MANKOS AGENCIES LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New | 5500000 |  |  | CGB | [8 empty] | Works to commence
20 | Proposed contruction of Chain link and Fence at Kipsigon market | contruction link and Fence | Promotion of security | Chainlink and fence constructed | 1448892-2-2023-2024 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Trade | MURMO COMPANY | 2023/2024 |  | Completed | Complete and in use | 5000000 |  |  | CGB | [8 empty] | Complete | 100 | 1
39 | Proposed supply and installation of 6 NO. solar powered street lights | supply of NO solar | promotion of MSMEs and security | solar powered street lights installed | 1448834/2023-24 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | ENERGIA LIMITED | 2023/2024 |  | Completed | Complete and in use | 2000000 | 2075240 |  | CGB | [8 empty] | Complete | 100 | 6
45 | Proposed construction of auction ring at Chepyuk market | construction Chepyuk auction ring | promotion of MSMEs | Auction ring constructed | 1357647/2023-24 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Trade | MURMO COMPANY LIMITED | 2023/2024 |  | Award stage/Declined. Lack of land/Change project | Does not exist | 1000000 | 947650 |  | CGB | [8 empty] | Did not commence |  | 1
50 | Construction of Kipsigon market | Construction of market | Improved market infrastructure | Market Constructed | 1448892-2-2023-2024 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Trade | Murmo Company limited | 2023/24 |  | Complete | Complete and in use | 5000000 | 4802650 |  | CGB | [8 empty] | Complete | 100 | 1
77 | Installation of 42 grid powered streetlights in Sirisia and Mt Elgon sub-counties . | of streetlights and Sirisia and Mt | [5 empty] | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | M/S AQUASCOPE Services Limited | 2021/22 |  | Complete and in use |  | 3190200 |  |  | CGB
88 | Installation of Solar Street lighting | Of lighting streetlights | [5 empty] | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Chrislink Construction and General supplies | 2021/22 |  | Complete and in use |  | 448000 |  |  | CGB
106 | Proposed installation of 25 no. Grid powered street lights in Mt. Elgon Sub County | installation Grid lights street in Mt | [5 empty] | CHEPYUK |  |  |  | M/S FECAKO Investments Limited | 2020/21 |  | Complete |  | 2434212.5 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | CHEPYUK |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
87 | Installation of 2 No solar High mast flood lights | of flood solar High | [5 empty] | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Bishin Transpoters and Construction Company | 2021/22 |  | Complete and in use |  | 1988000 |  |  | CGB
106 | Proposed installation of 25 no. Grid powered street lights in Mt. Elgon Sub County | installation Grid lights street in Mt | [5 empty] | CHEPYUK |  |  |  | M/S FECAKO Investments Limited | 2020/21 |  | Complete |  | 2434212.5 |  |  | CGG
118 | Construction of 16 door Modern stalls | Of stalls streetlights | [5 empty] | CHEPYUK |  |  |  | Yonak (Ke) Limited | 2019/20 |  | Project not implemented. The BoQs were reviewed upward in terms of specifications without effecting the same on the budget which resulted to Contractor declining the contract. Additionally, there was no public land for construction of the market stalls. |  | 3096460 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | CHEPYUK |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | CHEPYUK |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | All Wards |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | All 9 Sub Counties |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | All 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | All wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | Across all 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | Across all 45 Wards |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | All wards |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | All wards |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | Across the county |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
255 | Construction Of Nalondo Health Centre | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | health centres constructed |  |  | Kabuchai | West Nalondo |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2377282 | 2588134 | 2588134 | CGB |  | 2588134 | 0 | 2377282 | 0.91853 | 2377282 |  | 210852 | Complete and in use | [6 empty] | No | complete | Financial | Yes
303 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 86.67% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
456 | Upgrading of West Nalondo Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43484 | 43596 |  | 9011634 | 9011634 | 9011634 | County Government of Bungoma |  | 9011634 |  | 9011634 | 99.96% | 9011634 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
457 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
458 | Periodic Maintenance of Rural Roads Through Nzoia Mou | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled |  |  | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43595 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
531 | Routine Maintenance Of Roads In Kabuchai, Sirisia And Mt. Elgon Sub-Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43846 | 43964 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
678 | Periodic Maintenance of Marobo - Nalondo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43963 |  | 8022819 | 8022819 | 8022819 | County Government of Bungoma |  | 8022819 |  | 8022819 |  | 8022819 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
679 | Periodic Maintenance of Nalondo - Namilama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43849 | 43962 |  | 9232135 | 9232135 | 9232135 | County Government of Bungoma |  | 9232135 |  | 9232135 |  | 9232135 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
680 | Periodic Maintenance of Sirare - Chebukwa (Mulaa) Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43965 |  | 3385173 | 3385173 | 3385173 | County Government of Bungoma |  | 3385173 |  | 3385173 |  | 3385173 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
681 | Periodic Maintenance of Marobo - Nalondo Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43974 |  | 8022819 | 8022819 | 8022819 | County Government of Bungoma |  | 8022819 |  | 8022819 | 95.81% | 8022819 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
682 | Periodic Maintenance of Nalondo - Namilama Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.1KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43975 |  | 9232135 | 9232135 | 9232135 | County Government of Bungoma |  | 9232135 |  | 9232135 | 97.98% | 9232135 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
683 | Routine Maintenance Of Roads In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43965 |  | 3385173 | 3385173 | 3385173 | County Government of Bungoma |  | 3385173 |  | 3385173 | 87.94% | 3385173 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1016 | Periodic Maintenance of Chemwa - Chebukwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44215 | 44336 |  | 3634024.8 | 3634024.8 | 3634024.8 | County Government of Bungoma |  | 3634024.8 |  | 3634024.8 |  | 3634024.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1017 | Periodic Maintenance of Salmond - Weta - Chemwa - Sikata Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44220 | 44332 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1018 | Periodic Maintenance of Salmond - Weta - Chemwa - Sikata Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 8.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44337 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1019 | Periodic Maintenance of Roads In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44338 |  | 3634024.8 | 3634024.8 | 3634024.8 | County Government of Bungoma |  | 3634024.8 |  | 3634024.8 | 97.3% | 3634024.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1251 | Upgrading of Roads In West Nalondo Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44691 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1333 | Periodic Maintenance of Kasosi - Sawali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44702 |  | 13921465.95 | 13921465.95 | 13921465.95 | County Government of Bungoma |  | 13921465.95 |  | 13921465.95 |  | 13921465.95 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1334 | Periodic Maintenance of Sirare - Khasule Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44701 |  | 13921465.95 | 13921465.95 | 13921465.95 | County Government of Bungoma |  | 13921465.95 |  | 13921465.95 |  | 13921465.95 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1335 | Periodic Maintenance of Nabende Market - Nalondo Girls High School Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44694 |  | 13921465.95 | 13921465.95 | 13921465.95 | County Government of Bungoma |  | 13921465.95 |  | 13921465.95 |  | 13921465.95 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1336 | Periodic Maintenance of Noco - Nangwe Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44705 |  | 13921465.95 | 13921465.95 | 13921465.95 | County Government of Bungoma |  | 13921465.95 |  | 13921465.95 |  | 13921465.95 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1337 | Periodic Maintenance of Mabanga Mkt - Ngalasia Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44584 | 44699 |  | 4804790.76 | 4804790.76 | 4804790.76 | County Government of Bungoma |  | 4804790.76 |  | 4804790.76 |  | 4804790.76 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1338 | Periodic Maintenance of Kasosi - Chebukwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44574 | 44700 | 44731 | 6711978 | 6711978 | 6711978 | County Government of Bungoma |  | 6711978 |  | 6711978 |  | 6711978 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1339 | Periodic Maintenance of Roads In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44700 |  | 13921465.95 | 13921465.95 | 13921465.95 | County Government of Bungoma |  | 13921465.95 |  | 13921465.95 | 21.55% | 13921465.95 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1340 | Routine Maintenance Of Mabanga Market - Ngalasia Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44696 |  | 4804790.76 | 4804790.76 | 4804790.76 | County Government of Bungoma |  | 4804790.76 |  | 4804790.76 | 100.0% | 4804790.76 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1341 | Routine Maintenance Of Kasosi - Chebukwa Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44571 | 44700 |  | 6711978 | 6711978 | 6711978 | County Government of Bungoma |  | 6711978 |  | 6711978 | 89.73% | 6711978 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1590 | Periodic Maintenance of Khalaba - Kabuchai Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45056 | 45087 | 5106177 | 5106177 | 5106177 | County Government of Bungoma |  | 5106177 |  | 5106177 |  | 5106177 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1591 | Periodic Maintenance of Busiraka - Bayumba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45056 | 45087 | 4370427 | 4370427 | 4370427 | County Government of Bungoma |  | 4370427 |  | 4370427 |  | 4370427 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1592 | Periodic Maintenance of Luucho - Chebukwa Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45059 | 45090 | 3783959 | 3783959 | 3783959 | County Government of Bungoma |  | 3783959 |  | 3783959 |  | 3783959 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1593 | Periodic Maintenance of Lusanjela - Lukaracha Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45062 |  | 2852440 | 2852440 | 2852440 | County Government of Bungoma |  | 2852440 |  | 2852440 |  | 2852440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1594 | Periodic Maintenance of Khalaba - Kabuchai Road In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45069 |  | 5106177 | 5106177 | 5106177 | County Government of Bungoma |  | 5106177 |  | 5106177 | 99.92% | 5106177 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1595 | Periodic Maintenance of Busiraka - Bayumba Road In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44937 | 45058 |  | 4370427 | 4370427 | 4370427 | County Government of Bungoma |  | 4370427 |  | 4370427 | 97.19% | 4370427 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1596 | Periodic Maintenance of Luucho - Chebukwa Road In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45059 |  | 3783959 | 3783959 | 3783959 | County Government of Bungoma |  | 3783959 |  | 3783959 | 99.76% | 3783959 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1597 | Framework Contracts For Maintenance Of Roads In Kabuchai And Sirisia Sub Counties | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45061 |  | 2852440 | 2852440 | 2852440 | County Government of Bungoma |  | 2852440 |  | 2852440 | 98.28% | 2852440 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1834 | Periodic Maintenance of Sitila - Bursar Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45315 | 45423 | 45454 | 3494442 | 3494442 | 3494442 | County Government of Bungoma |  | 3494442 |  | 3494442 |  | 3494442 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1835 | Periodic Maintenance of Pongola Cbm - Muyayi Dam Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45432 |  | 4370184 | 4370184 | 4370184 | County Government of Bungoma |  | 4370184 |  | 4370184 |  | 4370184 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1836 | Periodic Maintenance of Chemwa Tindi - Chemwa Dispensary - Salvation Army - Namachanja Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45430 |  | 8100918 | 8100918 | 8100918 | County Government of Bungoma |  | 8100918 |  | 8100918 |  | 8100918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1837 | Periodic Maintenance of Zion - Noco Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45431 |  | 3980424 | 3980424 | 3980424 | County Government of Bungoma |  | 3980424 |  | 3980424 |  | 3980424 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1838 | Periodic Maintenance of Chemwa Tindi - Chemwa Dispensary - Salvation Army - Namachanja Road In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 3.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45430 |  | 8100918 | 8100918 | 8100918 | County Government of Bungoma |  | 8100918 |  | 8100918 | 99.61% | 8100918 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1839 | Periodic Maintenance of Sitila - Bursar Road In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45423 |  | 3494442 | 3494442 | 3494442 | County Government of Bungoma |  | 3494442 |  | 3494442 | 96.7% | 3494442 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1840 | Periodic Maintenance of Pongola Cbm - Muyayi Dam Road In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45310 | 45432 |  | 4370184 | 4370184 | 4370184 | County Government of Bungoma |  | 4370184 |  | 4370184 | 27.47% | 4370184 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1841 | Periodic Maintenance of Zion - Nocco Road In West Nalondo Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45429 |  | 3980424 | 3980424 | 3980424 | County Government of Bungoma |  | 3980424 |  | 3980424 | 99.61% | 3980424 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1842 | Periodic Maintenance of Luucho-Temoi Road In West Nalondo Ward (1450755-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Kabuchai | West Nalondo |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45429 |  | 4938990 | 4938990 | 4938990 | County Government of Bungoma |  | 4938990 |  | 4938990 | 100.0% | 4938990 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
98 | Purchase Of 2 Acres For Nabende Ecde | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new ECDE centre | Two acres of Land For Nabende Ecde Purchased | 3110599 | Ward based projects | Kabuchai | West Nalondo |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2018/19 |  |  |  | 30000000 | 2900000 | 2900000 | CGB |  | 2900000 |  | 2900000 |  |  |  |  | Stalled | 0 | [14 empty] | The project is staled due Lack of documentations(Title deed)
20 | Construction of 1 No. ECDE Classroom at Luucho primary school and construction of 2NO. Door pit latrines at Sawali and Khalaba primary schools in West Nalondo Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | West Nalondo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 2400000 | 2334640 | 2400000 | County Government of Bungoma | N/A | 2400000 | 0 |  | 0 |  | 2334640 | 2334640 | ongoing | Walling.(65%)
66 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Chemwa And Kabuchai Primary Schools In West Nalondo Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | West Nalondo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3200000 | 2985304 | 3200000 | County Government of Bungoma | N/A | 3200000 | 0 | 1339243.05 | 0.44861 | 1339243.05 | 1646060.95 | 1646060.95 | complete and in use | 1
97 | construction of 1 no. ECDE classroom at kasosi and chebukwa primary school | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | West Nalondo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 3000000 | 2997000 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2997000 | 1 | 2997000 | 0 | 0 | ongoing and not in use | 0.2
129 | Construction Of 1 No. Ecde Classroom At Sikata, Sawali, Nabende, Pongola And Kisiwa Primary Schools | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | West Nalondo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 6000000 | 5818200 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 | 5818200 | 1 | 5818200 | 0 | 0 | At roofing | 0.9
164 | Proposed Erection And Completion Of 1 No. Ecde At Khalaba Primary School In West Nalondo Ward. | Construction of ECDE classroom and pit latrine | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Kabuchai | West Nalondo |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 1245732.99 | 1468280 | 1245732.99 | County Government of Bungoma | N/A | 1245732.99 | 0 | 1468280 | 1 | 1468280 | 0 | 0 | complete and in use | 1
38 | Proposed Tree Growing Within Institutions In Khasoko, Kabula, Musikoma, Bukembe East, West Nalondo And Chesikaki Wards. | Installation of a standard modern nursery shade net structure. An irrigation system with a water pump(7-10HP) and a 5000 litre water tank. Production of fruit tree seedlings . Training of nursery operators on grafting and nuursery managemnt. Supply of 2(100kgs bags) of root stock and 1,000 scions | To promote climate change mitigation and adaptation | Trees planted within institutions | 2640599 | Other Capital Grants and Transfers | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45452 | 45455 | 45455 | 7101000 | 6960000 | 6960000 | FLLOCA | IDA | 0 | 6960000 | 0 | 1 | 0 | 0 |  | On going and not in use | 0.2 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
77 | Drilling and upgrading of Chemwa Primary school borehole | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 5600000 | 5450190 | 5450190 | CGB | N/A | 5450190 | 0 | 5450190 | 1 | 5450190 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
162 | REHABILITATION OF SIRARE WATER PROJECT | Trenching and laying of water pipeline | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 3800000 | 3763040 | 3763040 |  | N/A | 3763040 | 0 | 3763040 | 1 | 3763040 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
164 | MUYAYI COMMUNITY WATER PROJECT-NALONDO GIRLS WEST NALONDO WARD | Trenching and laying of water pipeline | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 5000000 | 4872000 | 4872000 |  | N/A | 4872000 | 0 | 4872000 | 1 | 4872000 | 0 | 0 | Complete and in use | 0.5 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
215 | INSTALLATION OF HYBRID PUMPING SYSTEM AT NANGWE PRIMARY SCHOOL AND NGALASIA DISPENSARY | Solarization and rehabilitation of spillway | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 2100000 | 2006400 | 2006400 |  | N/A | 2006400 | 0 | 2006400 | 1 | 2006400 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
216 | TOILI WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 3900000 | 3798500 | 3798500 |  | N/A | 3798500 | 0 | 3798500 | 1 | 3798500 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
220 | MUYAYI DAM WATER PROJECT | Solarization, pipeline extension and rehabilitation of spillway | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1200000 | 1190160 | 1190160 |  | N/A | 1190160 | 0 | 1190160 | 1 | 1190160 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
227 | CHEBUKWA WATER PROJECT IN WEST NALONDO WARD | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 4800000 | 4513545.5 | 4513545.5 |  | N/A | 4513545.5 | 0 | 4513545.5 | 1 | 4513545.5 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
229 | PROTECTION OF 10NO WATER SPRINGS IN WEST NALONDO WARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2500000 | 2302600 | 2302600 |  | N/A | 2302600 | 0 | 2302600 | 1 | 2302600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
269 | REBABILITATION OF NANGWE WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 2800000 | 2066588 | 2066588 |  | N/A | 2066588 | 0 | 2066588 | 1 | 2066588 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
270 | CONSTRUCTION OF MUSOKHO WATER PROJECT | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of Water pipeline extended | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2018/2019 |  |  |  | 2400000 | 2096166.4 | 2096166.4 |  | N/A | 2096166.4 | 0 | 2096166.4 | 1 | 2096166.4 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
327 | KIBABII-SASURI WATER PROJECT PHASE 11 | Trenching and laying of water pipeline; water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 34000000 | 32430400 | 32430400 |  | N/A | 32430400 | 1 | 32430400 |  | 26917232 | 5513168 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
361 | Fixing of pump Kalamu b/h of and construction of 8 spring | Improvement of a standard apron with drainage tunnel and replacement of 1 Afrdev hand pump;Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 springs constructed and 1 borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 300000 | 220000 | 220000 |  | N/A | 220000 | 0 | 220000 | 1 | 220000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
387 | Fixing of pump Kalamu b/h of and construction of 8 spring | Installation of solar pannels and solar pumps; installation of steel stand and plastic tank; pipeline extension and construction of water points; excavation, construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 1 Borehole rehabilitated and 8 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 1800000 | 1556671 | 1556671 |  | N/A | 1556671 | 0 | 1556671 | 1 | 1556671 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
417 | Construction of 5Roof catchment and 1 Storage tank 50m3 at Sitila primary School. | Construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed and 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1377543 | 1377543 |  | N/A | 1377543 | 0 | 1377543 | 1 | 1377543 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
449 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs. constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1500000 | 1443690 | 1443690 |  | N/A | 1443690 | 0 | 1443690 | 1 | 1443690 | 0 | 0 | Complete and in use | 0.3 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
496 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1443690 | 1443690 |  | N/A | 1443690 | 0 | 1443690 | 1 | 1443690 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
497 | Construction of 5Roof catchment and 1 Storage tank 50m3 at Sitila primary School. | construction of roof catchment; erection of storage tank and provision of water points | To enhance access to clean and safe drinking water | 5 roof catchment constructed; 1 storage tank constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 1500000 | 1377543.6 | 1377543.6 |  | N/A | 1377543.6 | 0 | 1377543.6 | 1 | 1377543.6 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
568 | Fixing of pump Kalamu b/h and construction of 8 spring and drilling of sirale borehole | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points; Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Improvement of a standard apron with drainage tunnel and replacement of Afrdev pump | To enhance access to clean and safe drinking water | 1 borehole drilled, 1 borehole rehabilitated and 8 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Kabuchai | West Nalondo |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 3800000 | 3756671 | 3756671 |  | N/A | 3756671 | 0 | 3756671 | 1 | 3756671 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
| Purchase of Dairy cows for Registered Groups | Purchase and delivery of 26 Dairy cows for Registered Groups | To increase dairy production, value addition and income generation | 26 Dairy animals purchased and delivered | 3110599 | Ward Based projects | Kabuchai | West Nalondo |  | Agriculture, Rural and Urban Development | livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 15/12/2021 | 15/3/2022 | 17/2/2022 | 2670000 | 2670000 | 2670000 | County Government of Bungoma |  | 2670000 | 0 | 2670000 | 1 | 2670000 | 0 | 0 | Completed
| Purchase of Dairy cows for Registered Groups | Purchase and delivery of 30 Dairy cows for Registered Groups | To increase dairy production, value addition and income generation | 30 dairy animals purchased and delivered to farmer groups | 3110599 | Ward Based projects | Kabuchai | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 44846 | 45202 | 15/2/2023 | 2000000 | 1998000 | 2000000 | County Government of Bungoma |  | 1998000 | 0 | 1998000 | 1 | 1998000 | 0 | 0 | Completed
28 | Proposed supply and Installation of 6no. solar powered streetlights | supply of solar of 6no | promotion of MSMEs and security | solar powered street lights installed | 1363123-2023-24 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | YAZEEM LIMITED | 2023/2024 |  | Completed | Complete and in use | 2000000 |  |  | CGB | [8 empty] | Complete | 100 | 6
74 | Installation of 54 grid powered streetlights in Kanduyi and Kabuchai sub-counties | of streetlights Kanduyi Kanduyi and | [5 empty] | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | M/S Bishin Transporters | 2021/22 |  | Complete and in use |  | 4154100 |  |  | CGB
103 | Proposed installation of 50 no. Grid powered street lights in Tongaren, Kabuchai and Mt. Elgon Sub Counties | installation Grid lights Kabuchai street and Mt |  |  | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Nalondo |  |  |  | M/S House of Brands Limited | 2020/21 |  | Complete |  | 4375507.5 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Nalondo |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | West Nalondo |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
17 | Erection and completion works of outpatient wing at Mateka dispensary | Excavation of trenches for foundation,construction of 150mm think floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Outpatient wings erected and completed |  |  | Bumula | South Bukusu |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21-2-2024 |  |  | 3000000 | 2797108 | 2797108 | CGB |  | 2797108 | 0 | 0 | 0 | 0 | 0 | 2797108 | [7 empty] | No | complete | Financial | Yes |  |  |  | No
26 | Completion of maternity wing at Lunakwe dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Maternity wings completed |  |  | Bumula | South Bukusu |  |  | WBPSPCU | Health & Sanitation | 2023-2024 | 21-2-2024 |  |  | 1000000 | 985610 | 985610 | CGB |  | 985610 | 0 | 0 | 0 | 0 | 985610 | 985610 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
251 | Construction Of Maternity Wing And Fencing Of Lunakwe Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible and affordable health services within the community | Maternity wings constructed |  |  | Bumula | South Bukusu |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 2000000 | 2088310 | 2088310 | CGB |  | 2088310 | 0 | 2086028 | 0.99891 | 2086028 |  | 2282 | Stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
250 | Periodic Maintenance of Muanda Primary - Tulumba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43123 | 43236 |  | 4406967.6 | 4406967.6 | 4406967.6 | County Government of Bungoma |  | 4406967.6 |  | 4406967.6 |  | 4406967.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
251 | Periodic Maintenance of Periodic Maintenance Of Roads In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2017/2018 | 43117 | 43241 |  | 4406967.6 | 4406967.6 | 4406967.6 | County Government of Bungoma |  | 4406967.6 |  | 4406967.6 | 85.76% | 4406967.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
430 | Periodic Maintenance of Periodic Maintenane Of Roads In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43485 | 43603 |  | 9792476.4 | 9792476.4 | 9792476.4 | County Government of Bungoma |  | 9792476.4 |  | 9792476.4 | 100.01% | 9792476.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
431 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
560 | Mechanical Transport Fund Phase 3 | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43843 | 43965 |  | 60000000 | 60000000 | 60000000 | County Government of Bungoma |  | 60000000 |  | 60000000 | 100.0% | 60000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
611 | Expression Of Intrest For Lease Of Gravel Excavation Land | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43961 |  | 10060000 | 10060000 | 10060000 | County Government of Bungoma |  | 10060000 |  | 10060000 | 44.73% | 10060000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
647 | Periodic Maintenance of Mateka - R. Sio Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43963 |  | 11914780 | 11914780 | 11914780 | County Government of Bungoma |  | 11914780 |  | 11914780 |  | 11914780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
648 | Periodic Maintenance of Justus - Nabwela - Chiliba Inn Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43854 | 43961 |  | 5463832 | 5463832 | 5463832 | County Government of Bungoma |  | 5463832 |  | 5463832 |  | 5463832 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
649 | Upgrading of Kandawala - Biliso - Tulumba - Lukhuna Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43853 | 43967 |  | 3198120 | 3198120 | 3198120 | County Government of Bungoma |  | 3198120 |  | 3198120 |  | 3198120 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
650 | Upgrading of Spot Improvement Of Kandawala - Biliso - Tulumba - Lukhuna Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43850 | 43970 |  | 3198120 | 3198120 | 3198120 | County Government of Bungoma |  | 3198120 |  | 3198120 | 58.76% | 3198120 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
651 | Periodic Maintenance of Roads In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.7KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43961 |  | 5463832 | 5463832 | 5463832 | County Government of Bungoma |  | 5463832 |  | 5463832 | 99.79% | 5463832 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
652 | Periodic Maintenance of Mateka-River Sio Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.5KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43961 |  | 11914780 | 11914780 | 11914780 | County Government of Bungoma |  | 11914780 |  | 11914780 | 98.67% | 11914780 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
946 | Periodic Maintenance of Mayanja - Tabuti -Mareba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44211 | 44340 |  | 7525645 | 7525645 | 7525645 | County Government of Bungoma |  | 7525645 |  | 7525645 |  | 7525645 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
947 | Periodic Maintenance of Mayanja - Tabuti -Mareba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44208 | 44336 |  | 7525645 | 7525645 | 7525645 | County Government of Bungoma |  | 7525645 |  | 7525645 |  | 7525645 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
948 | Periodic Maintenance of Biliso Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44327 |  | 10783986.4 | 10783986.4 | 10783986.4 | County Government of Bungoma |  | 10783986.4 |  | 10783986.4 |  | 10783986.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
949 | Periodic Maintenance of Muanda - Tulumba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44209 | 44333 |  | 10783986.4 | 10783986.4 | 10783986.4 | County Government of Bungoma |  | 10783986.4 |  | 10783986.4 |  | 10783986.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
950 | Periodic Maintenance of Lurare - Lukhuna Primary Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44328 |  | 10783986.4 | 10783986.4 | 10783986.4 | County Government of Bungoma |  | 10783986.4 |  | 10783986.4 |  | 10783986.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
951 | Periodic Maintenance of Roads In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44338 |  | 10783986.4 | 10783986.4 | 10783986.4 | County Government of Bungoma |  | 10783986.4 |  | 10783986.4 | 99.99% | 10783986.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
952 | Spot Improvement Of Mayanja - Tabuti - Mareba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.0KM GRAVELLED | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44213 | 44334 |  | 7525645 | 7525645 | 7525645 | County Government of Bungoma |  | 7525645 |  | 7525645 | 98.06% | 7525645 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1278 | Periodic Maintenance of Lurare - Tulumba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44705 | 44736 | 4252768.8 | 4252768.8 | 4252768.8 | County Government of Bungoma |  | 4252768.8 |  | 4252768.8 |  | 4252768.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1279 | Upgrading of Mareba - Mwomo - Lwanja - Kimwanga Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44575 | 44702 | 44733 | 7066749 | 7066749 | 7066749 | County Government of Bungoma |  | 7066749 |  | 7066749 |  | 7066749 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1280 | Upgrading of Drainage Works On Kandawala Biliso Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44705 | 44736 | 1284120 | 1284120 | 1284120 | County Government of Bungoma |  | 1284120 |  | 1284120 |  | 1284120 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1281 | Periodic Maintenance of Tarmac - Sichekereni Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44697 |  | 2379363 | 2379363 | 2379363 | County Government of Bungoma |  | 2379363 |  | 2379363 |  | 2379363 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1282 | Periodic Maintenance of Roads In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44700 |  | 4252768.8 | 4252768.8 | 4252768.8 | County Government of Bungoma |  | 4252768.8 |  | 4252768.8 | 100.0% | 4252768.8 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1283 | Periodic Maintenance of Roads In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.6KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44572 | 44693 |  | 2379363 | 2379363 | 2379363 | County Government of Bungoma |  | 2379363 |  | 2379363 | 99.8% | 2379363 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1284 | Spot Improvement Of Mareba - Mwomo - Lwanja - Kimwanga Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44701 |  | 7066749 | 7066749 | 7066749 | County Government of Bungoma |  | 7066749 |  | 7066749 | 98.36% | 7066749 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1285 | Completion Of Kandawala - Biliso Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44579 | 44702 |  | 1284120 | 1284120 | 1284120 | County Government of Bungoma |  | 1284120 |  | 1284120 | 99.97% | 1284120 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1536 | Periodic Maintenance of Kandawala - Biliso - Muanda - Tulumba Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44943 | 45061 |  | 5378249 | 5378249 | 5378249 | County Government of Bungoma |  | 5378249 |  | 5378249 |  | 5378249 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1537 | Periodic Maintenance of Makhanu - Sindani - Walulu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44941 | 45058 |  | 8770218.4 | 8770218.4 | 8770218.4 | County Government of Bungoma |  | 8770218.4 |  | 8770218.4 |  | 8770218.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1538 | Periodic Maintenance of Murutu - Sango - Kibachenje Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44940 | 45057 |  | 8770218.4 | 8770218.4 | 8770218.4 | County Government of Bungoma |  | 8770218.4 |  | 8770218.4 |  | 8770218.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1539 | Periodic Maintenance of Muanda Primary - Tulumba Ack Church | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44946 | 45061 |  | 8770218.4 | 8770218.4 | 8770218.4 | County Government of Bungoma |  | 8770218.4 |  | 8770218.4 |  | 8770218.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1540 | Periodic Maintenance of Namatelema Ecde Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44939 | 45065 |  | 8770218.4 | 8770218.4 | 8770218.4 | County Government of Bungoma |  | 8770218.4 |  | 8770218.4 |  | 8770218.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1541 | Periodic Maintenance of Quarry - Kibachenje Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45068 |  | 2992400.38 | 2992400.38 | 2992400.38 | County Government of Bungoma |  | 2992400.38 |  | 2992400.38 |  | 2992400.38 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1542 | Periodic Maintenance of Kandawala - Biliso - Tulumba In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 5.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44938 | 45070 |  | 5378249 | 5378249 | 5378249 | County Government of Bungoma |  | 5378249 |  | 5378249 | 97.37% | 5378249 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1543 | Periodic Maintenance of Makhanu Sindani - Walulu, Muruta - Sango - Kibachenje, Muanda Pri - Tulumba Ack Church, Namatelema Ecde Road In S. Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45063 |  | 8770218.4 | 8770218.4 | 8770218.4 | County Government of Bungoma |  | 8770218.4 |  | 8770218.4 | 99.83% | 8770218.4 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1544 | Framework Contracts For Maintenance Of Roads In Kanduyi And Bumula Sub Counties | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44945 | 45061 |  | 2992400.38 | 2992400.38 | 2992400.38 | County Government of Bungoma |  | 2992400.38 |  | 2992400.38 | 100.0% | 2992400.38 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1786 | Upgrading of Patrick Wabuke - Kibachenje - Karoneri - Lumboka Market Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45314 | 45424 |  | 5494641 | 5494641 | 5494641 | County Government of Bungoma |  | 5494641 |  | 5494641 |  | 5494641 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1787 | Periodic Maintenance of Bishop Justice - Engineer Malaba - Chiliba Inn Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45423 |  | 3243534 | 3243534 | 3243534 | County Government of Bungoma |  | 3243534 |  | 3243534 |  | 3243534 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1788 | Upgrading of Patrick Wabuke - Kibachenje - Karoneri - Lumboka Road In South Bukusu Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 3110599 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45436 |  | 5494641 | 5494641 | 5494641 | County Government of Bungoma |  | 5494641 |  | 5494641 | 99.91% | 5494641 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1789 | Periodic Maintenance of Bishop Justus - Engineer Malaba - Chiliba Inn Junction Road In South Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.6KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45422 |  | 3243534 | 3243534 | 3243534 | County Government of Bungoma |  | 3243534 |  | 3243534 | 99.91% | 3243534 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1790 | Periodic Maintenance of Biliso Road In South Bukusu Ward (1450745-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45427 |  | 3841572 | 3841572 | 3841572 | County Government of Bungoma |  | 3841572 |  | 3841572 | 99.77% | 3841572 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1791 | Periodic Maintenance of Muanda Primary Road In South Bukusu Ward (1450754-2023/2024) | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | South Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45301 | 45425 |  | 4019034.6 | 4019034.6 | 4019034.6 | County Government of Bungoma |  | 4019034.6 |  | 4019034.6 | 99.98% | 4019034.6 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
16 | Purchase of 1 Acre for Burangasi V.T.C. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new VTC | One acre of Land Purchased for Burangasi VTC | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45078 | 45809 | 45658 | 900000 | 1200000 | 900000 | CGB | N/A | 900000 | 0 | 900000 | 1 | 1200000 |  |  | Completed | 1 |  |  |  |  | 0 | No | [8 empty] | The project is 100% complete and not in use
17 | Purchase of 1/2 an Acre for St. Joseph Mwanda V.T.C. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of VTC | Half an acre of Land Purchased for St.Joseph Mwanda VTC | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45078 | 45809 | 45682 | 900000 | 1200000 | 900000 | CGB | N/A | 900000 | 0 | 900000 | 1 | 1200000 |  |  | Completed | 1 |  |  |  |  | 0 | No | [8 empty] | The project is 100% complete and not in use
51 | Purchase of land for Muanda dispensary Buildings | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new dispensary | One acre of Land for Muanda dispensary Purchased | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2021/22 | 45078 | 45413 | 45597 | 900000 | 600000 | 600000 | CGB |  | 600000 |  | 600000 | 1 | 650000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
59 | Purchase of Land for Tulumba VTC. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new VTC | One acre of Land For Tulumba VTC Purchased | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2021/22 | 20/2/2022 | 31/6/2022 | 31/12/2022 | 6000000 | 6000000 | 6000000 | CGB |  | 6000000 |  | 6000000 | 1 | 6000000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
81 | Purchase Of 2 Acre Of Land For Lukhuna Primary | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for expansion of ECDE centre | Two acres of Land For Lukhuna Primary Purchased | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2019/20 | 21/2/2020 | 22/4/2020 | 30/6/2020 | 1500000 | 1379648.69 | 1379648.69 | CGB |  | 1379648.69 |  | 1379648.69 | 1 | 600000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
127 | Purchase Of Land For Muanda Dispensary Buildings | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new dispensary | One acres of Land for Muanda Dispensary Purchased | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 20/7/2017 | 20/9/2017 | 15/12/2017 | 900000 | 900000 | 900000 | CGB | N/A | 900000 |  | 900000 | 1 | 900000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
143 | Purchase of 4.2 acre of land for kibabii university | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new university | One acres of Land for kibabii university Purchased | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 42768 | 42770 | 20/6/2017 | 3100000 | 3100000 | 3100000 | CGB | N/A | 3100000 |  | 3100000 | 1 | 3100000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
144 | Purchase of 1 acre for Sereti junction E.C.D.E | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new ECDE centre | One acres of Land for Sereti junction ECDE Purchased | 3110599 | Ward based projects | Bumula | South Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2016/17 | 42497 | 42499 | 20/10/2016 | 650000 | 650000 | 650000 | CGB | N/A | 650000 |  | 650000 | 1 | 650000 |  |  | Completed | 1 | [14 empty] | The project is 100% complete and not in use
17 | Construction of 1 NO. ECDE classroom at Nandingwa, Tabuuti and St. John Nakholo primary Schools in South Bukusu Ward | Construction of ECDE classroom | To construct ECDE classroom and Provide a conducive learning environment for learners | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | South Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 4200000 | 4352060 | 4200000 | County Government of Bungoma | N/A | 4200000 | 0 |  | 0 |  | 4352060 | 4352060 | ongoing | At substructure (15%)
23 | Construction of 1 NO. Classroom at St Josephs Sudi VTC in South Bukusu Ward | Construction of VTC classroom | To construct VTC classroom and provide conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | South Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 6000000 | 5993950 | 6000000 | County Government of Bungoma | N/A | 6000000 | 0 |  | 0 |  | 5993950 | 5993950 | ongoing | At substructure (15%)
62 | Proposed Constructruction And Completion Works For 1no. Ecde Classroom At Mulukoba And Lukhuna Primary Schools In South Bukusu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | South Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 3000000 | 2900420 | 3000000 | County Government of Bungoma | N/A | 3000000 | 0 | 2371027.15 | 0.81748 | 2371027.15 | 529392.85 | 529392.85 | complete and in use | 1
93 | proposed erection and completion works for 1No. ECDE classrooms at Sikata, Biliso, Namaterema, Kimatuni and Lumboka primary schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | South Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44564 | 30/6/2022 |  | 7600000 | 7544675 | 7600000 | County Government of Bungoma | N/A | 7600000 | 0 | 2089109.95 | 0.2769 | 2089109.95 | 5455565.05 | 5455565.05 | Complete and not in use | 1
127 | Construction Of 1 No. Ecde Classroom At Mateka, Kibachenje And Burangasi Primary Schools. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | South Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 3900000 | 3991370 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 3991370 | 1 | 3991370 | 0 | 0 | complete and in use | 1
160 | Prposed Erection And Completion Of 1 No. Ecde At Muanda, Bulosi And Elmolo Primary Schools In South Bukusu Ward. | Construction of ECDE classroom and VTC workshop |  | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | South Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 3900000 | 3616085.2 | 3900000 | County Government of Bungoma | N/A | 3900000 | 0 | 3616085.2 | 1 | 2003333.8 | 1612751.4 | 0 | at finishes | 0.9
214 | Construction Of 1 Ecde 1 Classroom And Gtoilets At Nakholo/Nandingwa/Tabuti And Tulumba Primary School | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | South Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 4700000 | 4664400 | 4700000 | County Government of Bungoma | N/A | 4700000 |  | 4664400 | 1 | 4664400 | 0 |  | complete and in use | 100.0%
74 | Borehole Rehabilitation in South Bukusu Ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | South Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 500000 | 487780 | 487780 | CGB | N/A | 487780 | 0 | 487780 | 1 | 487780 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
98 | Construction of perimeter fence and office at Bungoma dumpsite phase II | Construction and completion of perimeter fence(660m); construction of offices; erection of steel gates; installation of weigh bridge; undertake electrical works; fabrication and installation of 30 - 3 in 1 litter bins; construction of an incinerator; fire management system; undertaking an Environmental and social Impact Assessment Study; drilling and equiping of a borehole | To enhance environmental protection and conservation | Perimeter wall constructed on 1 dumpsite | 3110599 | Other Infrastructure &Civil Works | Bumula | South Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 31016521 | 11217950 | 11217950 | CGB | N/A | 11217950 | 0 | 11217950 | 1 | 11217950 | 19798571 | 0 | stalled | 80% complete | 80% complete | Contractor abandoned site | 2023/2024 |  | 19798571 | No | Terminate | Financial and Environmental | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | Termination procxess ongoing
112 | Drilling and equipping of Lukhuna primary borehole in South Bukusu ward | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1Borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | South Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 2000000 | 1793384 | 1793384 |  | N/A | 1793384 | 0 | 1793384 | 1 | 1793384 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
239 | PROTECTION OF 4NO WATER SPRINGS IN SOUTH BUKUSUWARD | excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 4 springs constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | South Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 600000 | 580000 | 580000 |  | N/A | 580000 | 0 | 580000 | 1 | 580000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
369 | Protection of 8 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 8 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | South Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2016/2017 |  |  |  | 3300000 | 3207893 | 3207893 |  | N/A | 3207893 | 0 | 3207893 | 1 | 3207893 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
526 | Upgrading of mateka borehole to electrical pumping system | Improvement of standard apron with drainage tunnel and replacement of 1 Afridev handpump | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | South Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 6500000 | 6415786 | 6415786 |  | N/A | 6415786 | 0 | 6415786 | 1 | 6415786 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
599 | Protection of 5 water Springs And 4 Shallow wells | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection; Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 5 water springs constructed and 4 of shallow wells constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | South Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1900000 | 1799168 | 1799168 |  | N/A | 1799168 | 0 | 1799168 | 1 | 1799168 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
14 | Construction of South Bukusu ward office | Erection and completion of Physical structure with offices, meeting rooms, reception area and sanitation facilities. | Improve access to County Government services | South Bukusu ward office constructed | 3111504 | Construction of non- residential buildings | Bumula | South Bukusu | - | Public Service Management and Administration | Public Service Management and Administration | Public Administration | 2023/24 | 45300 | 45415 | 45461 | 9500000 | 9491500 | 9500000 | County Government of Bungoma | - | 9491500 | - | 9491500 | 1 | 4838240 | 949150 | 0 | Completed | - | - | - | - | - | - | - |  | - | No | - | No | - | No | - | -
| Rehabilitation of cattle dips | Rehabilitation of cattle dips in Luuya, Kibisi, Bukembe, Lutaso, Tulumba, and Myanga Cattle Dips | To improve animal health and productivity | 6 Cattle dips rehabiliatated | 3110504 | Other infrastructure and civil works | Bumula | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 44136 | 44139 | 14/3/2020 | 5000000 | 3486950 | 3548016 | County Government of Bungoma |  | 3486950 | 0 | 3486950 | 1 | 3486950 | 0 | 0 | Completed
| Supply and delivery of two months old improved vaccinated indigeneous chicks and chick mash (feeds) | Supply and delivery of two months old improved vaccinated indigeneous chicks and chick mash (feeds) | To enhance poultry production and increase household incomes | 9,000 2-months old improved vaccinated chicks supplied and delivered to farmer groups | 3110599 | Ward Based projects | Bumula | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 23/11/2023 | 23/2/2024 | 23/1/2024 | 7000000 | 6998975 | 7000000 | County Government of Bungoma |  | 6998975 | 0 | 6998975 | 1 | 6998975 | 0 | 0 | Completed
| Supply and delivery of two months old improved vaccinated indigenous chicks and chick mash (feeds) | Supply and delivery of two months old improved vaccinated indigenous chicks and chick mash (feeds) | To enhance poultry production and increase household incomes | 576 Chicks and 571kgs of feeds supplied and delivered | 3110599 | Ward Based projects | Bumula | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/2024 | 22/4/2024 | 22/6/2024 | 45631 | 500000 | 500000 | 500000 | County Government of Bungoma |  | 500000 | 0 | 500000 |  | 500000 | 0 | 0 | Completed
30 | Proposed supply and installation of 3No. solar powered streetlights | supply of solar of 3No | promotion of MSMEs and security | solar powered street lights installed | 1358177-2023-24 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | YAZEEM LIMITED | 2023/2024 |  | Completed | Complete and in use | 1000000 |  |  | CGB | [8 empty] | Complete | 100 | 3
75 | Installation of 50 grid powered streetlights in Bumula sub-counties . | of streetlights Bumula streetlights in | [5 empty] | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | M/S Emricon Limited | 2021/22 |  | Complete and in use |  | 3565000 |  |  | CGB
104 | Proposed installation of 35 no. Grid powered street lights in Webuye East, Webuye West, Kimilili and Bumula Sub Counties | installation Grid lights East Kimilili street Kimilili and | [5 empty] | South Bukusu |  |  |  | M/S Rygeo Tech Solution | 2020/21 |  | Complete |  | 3232265 |  |  | CGG
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | South Bukusu |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | South Bukusu |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | South Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | South Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB
27 | Renovation of Ng'oli dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Dispensaries renovated |  |  | Bumula | West Bukusu |  |  | WBPSPCU | Health & Sanitation | 2023-2024 |  |  |  | 850000 | 849829 | 849829 | CGB |  | 849829 | 0 | 0 | 0 | 0 | 849829 | 849829 | Complete | [6 empty] | No | complete | Financial | Yes |  |  |  | No
89 | Renovation Of Ng'oli Dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | Dispensaries renovated |  |  | Bumula | West Bukusu |  |  | WBPSPCU | Health & Sanitation | 2022-2023 |  |  |  | 800000 | 777620 | 777620 | CGB |  | 777620 | 0 | 757250 | 0.9738 | 757250 |  | 20370 | Done against the BoQ | [6 empty] | No | complete | Financial | Yes |  |  |  | No
147 | Renovation And Roofing Of Mwomo Dispensary | Walling,roofing,painting,fixing of doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries renovated |  |  | Bumula | West Bukusu |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 1000000 | 966150 | 966150 | CGB |  | 966150 | 0 | 966150 | 1 | 966150 |  | 0 | complete and in use | [6 empty] | No | complete | Financial | Yes
148 | Construction Of 2no. Door Pit Latrine At Nang'eni Market | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 2No. Door pit latrines constructed |  |  | Bumula | West Bukusu |  |  | WBPSPCU | Health & Sanitation | 2020-2021 |  |  |  | 500000 |  |  | CGB |  |  | 0 | 0 | #DIV/0! | 0 |  | 0 | Project does not exist | [6 empty] | No | complete | Financial | Yes
181 | Construction of Kimwanga Market Pit Latrine | Digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | market pit latrines constructed |  |  | Bumula | West Bukusu |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 500000 | 475150 | 475150 | CGB |  | 475150 | 0 |  | 0 |  |  | 475150 | Project does not exist | [6 empty] | No | complete | Financial | Yes
182 | Completion Of Tunya Dispensary | Walling,roofing,painting,fixing doors and windows | To develop and maintain infrastructure for enhanced access to quality health care services. | dispensaries completed |  |  | Bumula | West Bukusu |  |  | WBPSPCU | Health & Sanitation | 2019-2020 |  |  |  | 1650000 | 1422995 | 1422995 | CGB |  | 1422995 | 0 | 1029910 | 0.72376 | 1029910 |  | 393085 | complete and in use | [6 empty] | No | complete | Financial | Yes
254 | Constuction Of 2door Pit Latrine At Mayanja Market | digging of 20ft deep pit,flooring,walling,roofing,painting and fitting doors | To develop and maintain infrastructure for enhanced access to quality health care services. | 2 No.door pit latrines constructed |  |  | Bumula | West Bukusu |  |  | CEF | Health & Sanitation | 2017-2018 |  |  |  | 200000 | 399400 | 399400 | CGB |  | 399400 | 0 | 399400 | 1 | 399400 |  | 0 | stalled | [6 empty] | No | complete | Financial | Yes |  |  |  | No
266 | Construction of Mwomo Dispensary | Excavation of trenches for foundation,construction thick floor slab,walling,roofing,painting,fixing of doors and windows | To provide accessible,affordable health services within the community | dispensaries constructed |  |  | Bumula | West Bukusu |  |  | Ward Fund | Health & Sanitation | 2014/15 | 2nd Aug 2015 | 42339 | 1st Dec 2015 |  | 969600 | 969600 | CGB |  | 969600 | 0 | 893269 | 0.92128 | 893269 |  | 76331 | Complete and in use | [6 empty] | No | complete | Financial | Yes
270 | Construction of 3-door pit latrine. | Digging of 20ft deep pit,Flooring, walling,painting,roofing and fitting doors | To enhance access to sanitary facilities at the dispensary. | 3No. Door pit latrines constructed |  |  | Bumula | West Bukusu |  |  | Ward Fund | Health & Sanitation | 2014/15 | [6 empty] | CGB |  |  | 0 |  | #DIV/0! |  |  | 0 | Complete and in use | [6 empty] | No | complete | Financial | Yes
432 | Lease Of Gravel Pits | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110504 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43476 | 43600 |  | 6000000 | 6000000 | 6000000 | County Government of Bungoma |  | 6000000 |  | 6000000 | 86.67% | 6000000 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
454 | Periodic Maintenance of In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 3110399 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43475 | 43595 |  | 10142924 | 10142924 | 10142924 | County Government of Bungoma |  | 10142924 |  | 10142924 | 98.82% | 10142924 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
455 | Periodic Maintenance of Rural Roads Through MTF Program | Gravelling and grading works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2018/2019 | 43488 | 43608 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 100.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
539 | Routine Maintenance Of Roads In Kanduyi And Bumula Sub Counties Through Framework Contracting | Gravelling and grading works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43852 | 43965 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 | 0.0% | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
663 | Drainage Works In Kanduyi And Bumula Sub-Counties(Lot 2) | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43974 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 | 96.54% | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
673 | Upgrading of Mwomo - Nang'Eni - Tabuti Road | Road improvement works | To improve the road condition and enhance accessibility | Box Culvert Constructed | 2640503 | Other Capital Grants and Transfers | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43968 |  | 6293406 | 6293406 | 6293406 | County Government of Bungoma |  | 6293406 |  | 6293406 |  | 6293406 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
674 | Periodic Maintenance of Makwara - Kingi - Lawrence Wepukhulu Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43841 | 43965 |  | 3479014 | 3479014 | 3479014 | County Government of Bungoma |  | 3479014 |  | 3479014 |  | 3479014 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
675 | Upgrading of Tabuti - Mwomo - Nang'Eni Ward | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43848 | 43972 |  | 2462680 | 2462680 | 2462680 | County Government of Bungoma |  | 2462680 |  | 2462680 |  | 2462680 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
676 | Upgrading of Spot Improvement Of Tabuti - Mwomo - Nang'Eni Road | Road improvement works | To improve the road condition and enhance accessibility | Road Graveled | 2640503 | Other Capital Grants and Transfers | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43851 | 43967 |  | 2462680 | 2462680 | 2462680 | County Government of Bungoma |  | 2462680 |  | 2462680 | 93.83% | 2462680 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
677 | Periodic Maintenance of Roads In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM GRAVELLED | 3110399 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2019/2020 | 43842 | 43971 |  | 3479014 | 3479014 | 3479014 | County Government of Bungoma |  | 3479014 |  | 3479014 | 98.26% | 3479014 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1010 | Periodic Maintenance of Taata - Wepukhulu - Muchele Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44337 |  | 10194051 | 10194051 | 10194051 | County Government of Bungoma |  | 10194051 |  | 10194051 |  | 10194051 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1011 | Periodic Maintenance of Javan - Wacholi - Nyangali Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44210 | 44335 |  | 10194051 | 10194051 | 10194051 | County Government of Bungoma |  | 10194051 |  | 10194051 |  | 10194051 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1012 | Periodic Maintenance of Tarmac (A104) - Sda Church - Wabuna Spring - Mupeli Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44216 | 44340 |  | 10194051 | 10194051 | 10194051 | County Government of Bungoma |  | 10194051 |  | 10194051 |  | 10194051 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1013 | Upgrading of Nang'Eni - Nangata Road | Road improvement works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44214 | 44335 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1014 | Upgrading of Mzee Busolo - Tunya - Kisioyi / Tunya Nyangali Road | Road improvement works | To improve the road condition and enhance accessibility | 6.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44206 | 44340 |  | 0 | 0 | 0 | County Government of Bungoma |  | 0 |  | 0 |  | 0 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1015 | Periodic Maintenance of Roads In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2020/2021 | 44207 | 44339 |  | 10194051 | 10194051 | 10194051 | County Government of Bungoma |  | 10194051 |  | 10194051 | 99.99% | 10194051 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1327 | Periodic Maintenance of Busolo - Kizito - Kibiriti Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44581 | 44697 |  | 15689362.5 | 15689362.5 | 15689362.5 | County Government of Bungoma |  | 15689362.5 |  | 15689362.5 |  | 15689362.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1328 | Periodic Maintenance of Lukhanyu - Lwanja - Pamba - Lwanja Stage Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44577 | 44703 |  | 15689362.5 | 15689362.5 | 15689362.5 | County Government of Bungoma |  | 15689362.5 |  | 15689362.5 |  | 15689362.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1329 | Periodic Maintenance of Ap - Machwele Pri. Kimwanga Market Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44580 | 44692 |  | 15689362.5 | 15689362.5 | 15689362.5 | County Government of Bungoma |  | 15689362.5 |  | 15689362.5 |  | 15689362.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1330 | Periodic Maintenance of Kibuke Dispensary - Kibuke Primary - Weita Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44583 | 44700 |  | 15689362.5 | 15689362.5 | 15689362.5 | County Government of Bungoma |  | 15689362.5 |  | 15689362.5 |  | 15689362.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1331 | Upgrading of Javan - Tenge - Mwomo Road | Road improvement works | To improve the road condition and enhance accessibility | 0.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44585 | 44698 |  | 15689362.5 | 15689362.5 | 15689362.5 | County Government of Bungoma |  | 15689362.5 |  | 15689362.5 |  | 15689362.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1332 | Periodic Maintenance of Roads In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 0.4KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2021/2022 | 44576 | 44691 |  | 15689362.5 | 15689362.5 | 15689362.5 | County Government of Bungoma |  | 15689362.5 |  | 15689362.5 | 100.0% | 15689362.5 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1586 | Periodic Maintenance of Mzee Samson - Machwele - Nangata River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44944 | 45057 |  | 1884855 | 1884855 | 1884855 | County Government of Bungoma |  | 1884855 |  | 1884855 |  | 1884855 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1587 | Periodic Maintenance of Tarmac - Sda Church - Wapuma - Mupeli Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44947 | 45061 |  | 6287296 | 6287296 | 6287296 | County Government of Bungoma |  | 6287296 |  | 6287296 |  | 6287296 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1588 | Periodic Maintenance of Tarmac - Sda Church - Wabuma - Mupeli Road In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.5KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44950 | 45065 |  | 6287296 | 6287296 | 6287296 | County Government of Bungoma |  | 6287296 |  | 6287296 | 98.95% | 6287296 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1589 | Periodic Maintenance of Mzee Samson - Machwele - Nangata River Road In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2022/2023 | 44949 | 45063 |  | 1884855 | 1884855 | 1884855 | County Government of Bungoma |  | 1884855 |  | 1884855 | 99.88% | 1884855 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1826 | Periodic Maintenance of Mulati Junction - Maritini - Rasto Wanjala Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45302 | 45433 | 45464 | 5087391 | 5087391 | 5087391 | County Government of Bungoma |  | 5087391 |  | 5087391 |  | 5087391 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1827 | Periodic Maintenance of A104 Douglas Juma - Joseph Nakisanderi - Mayanja River Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45306 | 45435 |  | 5407627 | 5407627 | 5407627 | County Government of Bungoma |  | 5407627 |  | 5407627 |  | 5407627 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1828 | Periodic Maintenance of Machwele Ap Camp - Tarmac - Matayo Khisa - Enoka Japheth Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45313 | 45424 |  | 2716140 | 2716140 | 2716140 | County Government of Bungoma |  | 2716140 |  | 2716140 |  | 2716140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1829 | Periodic Maintenance of Kibuke Dispensary - Kibuke Primary - Weyeta Junction Road | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45307 | 45426 |  | 2070368 | 2070368 | 2070368 | County Government of Bungoma |  | 2070368 |  | 2070368 |  | 2070368 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1830 | Periodic Maintenance of A104 Douglas Juma - Joseph Nakisanderi - Mayanja River Road In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.0KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45427 |  | 5407627 | 5407627 | 5407627 | County Government of Bungoma |  | 5407627 |  | 5407627 | 99.96% | 5407627 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1831 | Periodic Maintenance of Machwele Ap Camp - Tarmac - Matayo Khisa - Enoka - Japheth Road In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 1.5KM TARMACKED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45304 | 45425 |  | 2716140 | 2716140 | 2716140 | County Government of Bungoma |  | 2716140 |  | 2716140 | 99.51% | 2716140 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1832 | Periodic Maintenance of Mulati Junction - Rasto Wanjala Road In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 4.2KM GRAVELLED | 3110599 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45303 | 45431 |  | 5087391 | 5087391 | 5087391 | County Government of Bungoma |  | 5087391 |  | 5087391 | 90.14% | 5087391 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
1833 | Periodic Maintenance of Kibuke Dispensary - Kibuke Primary - Weyeta Junction In West Bukusu Ward | Gravelling and grading works | To improve the road condition and enhance accessibility | 2.0KM GRAVELLED | 3110504 | Other Infrastructure and Civil Works | Bumula | West Bukusu |  | Energy, Infrastructure and ICT | Roads, Infrastructute and Public Works | Roads, Infrastructute and Public Works | 2023/2024 | 45305 | 45425 |  | 2070368 | 2070368 | 2070368 | County Government of Bungoma |  | 2070368 |  | 2070368 | 98.52% | 2070368 | 0 | 0 | Completed | 1 | [5 empty] | No |  | Financial, Operational, Environmental | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | No | Inadequate Framework and Capacity. To be incorporated in subsequent projects subject to available Framework and Capacity | The project is in use
18 | Purchase of 1/2 an Acre for Kibuke dispensary. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of a new dispensary | Half an acre of Land Purchased for Kibuke dispensary | 3110599 | Ward based projects | Bumula | West Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45231 | 45444 |  | 900000 | - | 900000 | CGB | N/A | 900000 | 0 | 900000 | 1 | 0 |  |  | Stalled | 0 | 0 | Lack of documentations(Title deed) | 2023/24 |  | 0 | No | [8 empty] | The project is stalled due Lack of documentations(Title deed)
19 | Purchase of 1/2 an Acre for Wamaliacha E.C.D.E. | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide physical space for construction of new ECDE centre | Half an acre of Land Purchased for Wamaliacha ECDE | 3110599 | Ward based projects | Bumula | West Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2023/24 | 45231 | 45444 |  | 900000 | - | 900000 | CGB | N/A | 900000 | 0 | 900000 | 1 | 0 |  |  | Ongoing | 0.5 |  |  |  |  | 0 | No | [8 empty] | The project is 50% complete
129 | Purchase Of Land For Ngoli Polytchenic | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of new polytechnic | One acre of land for Ngoli Polytchenic Purchased | 3110599 | Ward based projects | Bumula | West Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 |  |  |  | 1000000 | 1000000 | 1000000 | CGB | N/A | 1000000 |  | 1000000 | 1 | 0 | 0 | [17 empty] | The project is stalled due Lack of documentations(Title deed)
130 | Purchase Of Land For Kimwanga Market Stalls | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for constrcution of market stalls | One acres of Land for Kimwanga Market Stalls Purchased | 3110599 | Ward based projects | Bumula | West Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2017/18 | 42959 | 43376 | 13/5/2018 | 800000 | 800000 | 800000 | CGB | N/A | 800000 |  | 800000 | 1 | 950000 | 0 |  | Completed | 1 | [14 empty] | The project is 100% complete and in use
196 | Purchase of 1 acre for Kimwanga market | Requistion,advertisement,survey,valuation,agreement signing and payment | To provide space for construction of expansion market | One acres of Land for Kimwanga market Purchased | 3110599 | Ward based projects | Bumula | West Bukusu |  | Lands,Urban/Physical Planning,Housing and Municipalities | Lands and Physical Planning | Lands and Physical Planning | 2014/15 |  |  |  | 1500000 | 1500000 | 1500000 | CGB | N/A | 1500000 |  | 1500000 | 1 |  |  |  | Stalled | 0 | [14 empty] | The project is stalled due Lack of documentations(Title deed)
19 | Construction of a 1 NO. Workshop at Lwanja VTC in West Bukusu Ward | Construction of VTC workshop | To construct VTC workshop and provide conducive learning environment | VTC workshop constructed | 3110599 | Construction and Civil works | Bumula | West Bukusu |  | Education and Vocational Training | Vocational Training | Education and Vocational Training |  | 45293 | 30/06/2024 |  | 2000000 | 1567120 | 2000000 | County Government of Bungoma | N/A | 2000000 | 0 |  | 0 |  | 1567120 | 1567120 | ongoing | Walling.(65%)
65 | Proposed Erection And Completion Works Of 1no. Ecde Classroom At Mwomo, Ng’oli, Wacholi And Kisyoyi Primary School In West Bukusu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | West Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44928 | 30/06/2023 |  | 6350000 | 5649640 | 6350000 | County Government of Bungoma | N/A | 6350000 | 0 | 4774213.5 | 0.84505 | 4774213.5 | 875426.5 | 875426.5 | complete and in use | 1
128 | Construction Of 1 No. Ecde Classroom At Mayanja And Namuningie Primary School. | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | West Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 44230 | 44414 |  | 4500000 | 2893900 | 4500000 | County Government of Bungoma | N/A | 4500000 | 0 | 2893900 | 1 | 2893900 | 0 | 0 | complete and in use | 1
163 | Proposed Erection And Completion Of 1 No. Ecde At Tunya And Machwele Primary School In West Bukusu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | West Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43864 | 44049 |  | 2400000 | 2398820 | 2400000 | County Government of Bungoma | N/A | 2400000 | 0 | 2398820 | 1 | 2398820 | 0 | 0 | complete and in use | 1
218 | Construction Of 1no. Classroom And 2 Door Pit Latrine At Lwanja Polytechnic And Fencing Of Ngoli And Namuningie Vtc School In Westbukusu Ward | Construction of ECDE classroom | To construct ECDE classroom providing a conducive learning environment | ECDE classroom constructed | 3110599 | Construction and Civil works | Bumula | West Bukusu |  | Education and Vocational Training | Early Childhood Development Education | Education and Vocational Training |  | 43436 | 43410 |  | 1900000 | 1995446 | 1900000 | County Government of Bungoma | N/A | 1900000 |  | 1422305.7 | 0.71278 | 1422305.7 | 573140.3 |  | complete and in use | 100.0%
18 | Solarisattion and Extension of Namuninge Dam water Project | Solarization; pipeline extension and rehabilitation of spillway | To enhance access to clean and safe drinking water | Solarisation and extension of 1 dam | 2640599 | Other Capital Grants and Transfers | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Tourism, Environment and Climate Change | 2023/2024 | 45544 | 45546 | 45546 | 5000000 | 4824707 | 4824707 | FLLOCA | IDA | 0 | 4824707 | 0 | 1 | 0 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
76 | Drilling and Upgrading of Machwele Primary Borehole in West Bukusu Ward | Site identification; geological survey; drilling development(entails casing and gravel use); construction of borehole chamber identificationImprovement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 borehole drilled and upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2023/2024 |  |  |  | 3350000 | 3269228 | 3269228 | CGB | N/A | 3269228 | 0 | 3269228 | 1 | 3269228 | 0 | 0 | Complete and in use | 100% Completed | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
115 | Upgrading of Mayanja market borehole in west bukusu ward | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points | To enhance access to clean and safe drinking water | 1 Borehole upgraded | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2022/2023 |  |  |  | 1600000 | 1589896 | 1589896 |  | N/A | 1589896 | 0 | 1589896 | 1 | 1589896 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test | WORKS COMPLETED AND PROJECT IS OPERATIONAL
161 | rehabilitation of shallow wells in west bukusu ward | Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of a hand pump | To enhance access to clean and safe drinking water | 1 Shallow well rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2021/2022 |  |  |  | 500000 | 475600 | 475600 |  | N/A | 475600 | 0 | 475600 | 1 | 475600 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
214 | CONSTRUCTION OF 3 NO. SHALLOW WELLS AND REHABILITATION OF BOREHOLES IN WEST BUKUSU WARD | Improvement of a standard apron with drainage tunnel ;solarization;installation of a steel stand, plastic tank; pipeline extension and construction of water points; Digging of a 15ft shallow well, walling using bricks, installation of pipes and fixing of | To enhance access to clean and safe drinking water | 1 borehole upgraded, 3 shallow well rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2020/2021 |  |  |  | 1500000 | 1256860 | 1256860 |  | N/A | 1256860 | 0 | 1256860 | 1 | 1256860 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
243 | DRILLING OF LWANJA VTC BOREHOLE IN WEST BUKUSU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 1 Borehole drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2019/2020 |  |  |  | 2200000 | 2074080 | 2074080 |  | N/A | 2074080 | 0 | 2074080 | 1 | 2074080 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
302 | DRILLING OF NABUYEFWE AND NG’OLI BOREHOLES IN WEST BUKUSU WARD | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3795750 | 3795750 |  | N/A | 3795750 | 0 | 3795750 | 1 | 3795750 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
303 | DRILLING OF TUNYA AND KISYOYI BOHEHOLE IN WEST BUKUSU | site identification; geological survey; drilling development (entails casing and gravel use); construction of borehole chamber; construction of water points | To enhance access to clean and safe drinking water | 2 Boreholes drilled | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2017/2018 |  |  |  | 4000000 | 3730100 | 3730100 |  | N/A | 3730100 | 0 | 3730100 | 1 | 3730100 | 0 | 0 | complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
410 | Protection of 10 water Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works |  | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 1900000 | 1554900 | 1554900 |  | N/A | 1554900 | 0 | 1554900 | 1 | 1554900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
437 | Rehabilitation of Machwele water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | 1 Borehole rehabilitated | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2015/2016 |  |  |  | 2200000 | 2107200 | 2107200 |  | N/A | 2107200 | 0 | 2107200 | 1 | 2107200 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
530 | Rehabilitation of Machwele water Project | Trenching; laying of water pipeline and water points | To enhance access to clean and safe drinking water | KM of pipeline constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2014/2015 |  |  |  | 3600000 | 3512000 | 3512000 |  | N/A | 3512000 | 0 | 3512000 | 1 | 3512000 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
607 | Protection of 10 Springs | Excavation,construction of wing walls, fixing of draw pipes and trenching of cut off drain and protection | To enhance access to clean and safe drinking water | 10 water springs constructed | 3110599 | Other Infrastructure &Civil Works | Bumula | West Bukusu |  | Environment, Water and Natural Resources | Tourism, Environment,Natural Resources, Water and Climate Change | Water and Natural Resources | 2013/2014 |  |  |  | 1700000 | 1554900 | 1554900 |  | N/A | 1554900 | 0 | 1554900 | 1 | 1554900 | 0 | 0 | Complete and in use | 1 | [8 empty] | Yes | Development and monitoring of Climate & Risk Management Plans | Yes | Ensuring compliance by contractors of Environmental & Social Management Plans and the general NEMA conditions | Yes | Project compliant with the Techno - Economic viabilty screening test
26 | Proposed Installation and commissioning of 3No. Solar powered Floodlight | Installation of Solar of 3No | promotion of MSMEs and security | Solar powered floodligts installed | 1472960-2023-24 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INTERNATIONAL LIMITED | 2023/2024 |  | Completed | Complete and in use | 5620000 |  |  | CGB | [8 empty] | Complete | 100 | 3
75 | Installation of 50 grid powered streetlights in Bumula sub-counties . | of streetlights Bumula streetlights in | [5 empty] | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | M/S Emricon Limited | 2021/22 |  | Complete and in use |  | 3565000 |  |  | CGB
105 | Proposed installation of 50 no. Grid powered street lights in Bumula and Sirisia Sub Counties | installation Grid lights street Bumula and | [5 empty] | West Bukusu |  |  |  | M/S Sinawa Enterprises | 2020/21 |  | Complete |  | 4431050 |  |  | CGG
109 | Construction of 4 no. Boda boda sheds at Ng’oli, Mayanja, Nang’eni and Kimwanga | of boda Ng at Mayanja, Nang | [5 empty] | West Bukusu |  |  |  | Vertall General Contractors | 2019/20 |  | Complete |  | 974000 |  |  | CGG
132 | Installation of 493 streetlight ,KPLC –Phase 1 | 1 Installation of | [5 empty] | West Bukusu |  |  |  | KPLC | 2017/18 |  | Complete. The County Government through the ministry of Trade, Energy and Industrialization entered into an agreement with KPLC to install 823 street lights across all wards. 493 streetlights to have installed in phase 1 and 330 streetlights to be installed in phase 2. |  | 46000000 |  |  | CGG
| Purchase of fertilizer | Purchase and distribution of 900,000kgs fertilizer to 9,000 vulnerable farmers across the County+3344:3415 | To enhance crop production and productivity for food security | 900,000kgs of fertilizer purchased and supplied to 9,000 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 14/11/2013 | 14/1/2014 | 41640 | 120000000 | 97000000 | 97000000 | County Government of Bungoma |  | 97000000 |  | 97000000 | 1 | 97000000 |  | 0 | Completed
| Purchase and installation of green houses | Purchase and installation of 139 green houses | To enhance crop production for high value crop, productivity, value addition and incomes among the youth and women | 139 Green houses purchased and installed | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/4/2014 | 41708 |  | 29172000 | 29172000 | County Government of Bungoma |  | 29172000 |  | 29172000 | 1 | 29172000 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 14 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 14 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41709 | 13500000 | 4310741 | 4500000 | County Government of Bungoma |  | 4310741 |  | 4310741 | 1 | 4310741 | 0 | 0 | Completed
| Supply and delivery of Motorcycle | Supply and delivery of 11 Motorcycles across the Sub Counties | To improve mobility of extension officers in reaching farmers | 11 Motorcylces supplied and delivered | 3111103 | Purchase of Agricultural Machinery and Equipment | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2013/2014 | 17/1/2014 | 17/3/2014 | 41710 | 3500000 | 3350253 | 3500000 | County Government of Bungoma |  | 3350253 |  | 3350253 | 1 | 3350253 | 0 | 0 | Completed
| Purchase of Mavuno Fertilizer | Purchase of 1,736,000kgs Mavuno Fertilizer to 17,360 vulnerable farmers | To enhance crop production and productivity for food security | 1,736,000kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 27/11/2014 | 27/1/2015 | 15/2/2015 | 50000000 | 49683000 | 50000000 | County Government of Bungoma |  | 49683000 |  | 49683000 | 1 | 49683000 | 0 | 0 | Completed
| Tissue Banana Seedlings | Supply and delivery of 10,000 tissue Banana Seedlings | To increase crop production and productivity for food security | 10,000 tissue banana seedlings supplied and delivered | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 42309 | 42312 | 17/3/2015 | 5000000 | 2000000 | 2000000 | County Government of Bungoma |  | 2000000 |  | 2000000 | 1 | 2000000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 64 dairy cows to farmers across the County | To enhance dairy production, value addition and income generation | 64 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 17/3/2015 | 15000000 | 7040000 | 7040000 | County Government of Bungoma |  | 7040000 |  | 7040000 | 1 | 7040000 | 0 | 0 | Completed
| Purchase and delivery of dairy cows | Purchase and delivery of 153 dairy cows to farmers across the County | To increase dairy production, value addition and income generation | 153 Dairy cows purchased and delivered | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 |  | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Supply and Delivery of Dairy Cattle | Supply and Delivery of 124 Dairy Cattle to farmers across the County | To increase fish production and improve on food and nutrition security | 124 dairy cows purchased and delivered to farmers | 3110504 | Other infrastructure and civil works | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 42342 | 20000000 | 12450000 | 12450000 | County Government of Bungoma |  | 12450000 |  | 12450000 | 1 | 12450000 | 0 | 0 | Completed
| Supply of Breeding Stock | Supply of 45,000 Fish Breeding Stock | To increase dairy production, value addition and income generation | 45,000 breeding stock supplied | 2211023 | Supplies for production | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 18/3/2015 | 10000000 | 4270000 | 4270000 | County Government of Bungoma |  | 4270000 |  | 4270000 | 1 | 4270000 | 0 | 0 | Completed
| Supply and delivery of AI Kits | Supply and delivery of AI Kits | To increase dairy production, value addition and income generation | 2,000 AI kits supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 22/3/2015 | 20000000 | 18439700 | 20000000 | County Government of Bungoma |  | 18439700 |  | 18439700 | 1 | 18439700 | 0 | 0 | Completed
| Supply and delivery Disease Control items in Bungoma County | Supply and delivery Disease Control items in Bungoma County | To enhance dairy production, value addition and income generation | Assorted disease control items supplied and delivered | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 23/3/2015 | 8000000 | 7658845 | 8000000 | County Government of Bungoma |  | 7658845 |  | 7658845 | 1 | 7658845 | 0 | 0 | Completed
| Purchase of Refrigerators and 45 Cool Boxes | Purchase of Refrigerators and 45 Cool Boxes | To increase production and productivity | 45 refrigerators and cool boxes purchased | 2211003 | Veterinarian supplies and materials | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2014/2015 | 15/2/2015 | 15/4/2015 | 20/3/2015 | 6500000 | 2580900 | 3000000 | County Government of Bungoma |  | 2580900 |  | 2580900 | 1 | 2580900 | 0 | 0 | Completed
| Supply and delivery of Fertilizer | Supply and delivery of 1,736,000 kgs of Fertilizer to 17,360 vulnerable farmers | To enhance production, productivity and income generation | 1,7360,000 kgs of fertilizer purchased and supplied to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 150000000 | 35265090 | 36000000 | County Government of Bungoma |  | 35265090 |  | 35265090 | 1 | 35265090 | 0 | 0 | Completed
| Supply and delivery of Seeds | Supply and delivery of 173,600 Bags of 10kgs of maize Seeds | To enhance production, productivity and income generation | 17,360 Bags of 10kgs of maize seed supplied and delivered to 17,360 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42228 | 42585 | 20/2/2016 | 70000000 | 3996000 | 4000000 | County Government of Bungoma |  | 3996000 |  | 3996000 | 1 | 3996000 | 0 | 0 | Completed
| Supply and delivery of Dairy Cattle | Supply and delivery of 9 Dairy Cattle to farmer groups | To enhance dairy production and increase household incomes | 8 dairy cattle supplied and delivered to farmer groups | 2211023 | Supplies for production | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 846600 | 1000000 | County Government of Bungoma |  | 846600 |  | 846600 | 1 | 846600 | 0 | 0 | Completed
| Supply and delivery of Dairy Goats | Supply and delivery of 150 Dairy Goats to farmer groups within the County | To enhance dairy production and increase household incomes | 150 dairy goats supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2015/2016 | 42491 | 42494 | 28/3/2016 | 10000000 | 3750000 | 4000000 | County Government of Bungoma |  | 3750000 |  | 3750000 | 1 | 3750000 | 0 | 0 | Completed
| Supply Of Mavuno Top Dressing Fertilizer | Supply and delivery of 1,736,000 kgs Mavuno Top Dressing Fertilizer to 17,360 vulnerable farmers | To enhance crop production, productivity and income generation | 1,736,000 kgs of fertilizer supplied and delivered to 17,360 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 150000000 | 120399200 | 120399200 | County Government of Bungoma |  | 120399200 | 0 | 120399200 | 1 | 120399200 | 0 | 0 | Completed
| Supply Of Certified Maize Seed | Supply and delivery of 17,360 bags(10kgs) of Certified Maize Seed | To enhance crop production, productivity and income generation | 173,600kgs of maize seeds supplied and delivered to 17,360 farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/3/2017 | 28/2/2017 | 60000000 | 57430600 | 57430600 | County Government of Bungoma |  | 57430600 | 0 | 57430600 | 1 | 6600000 | 0 | 0 | Completed
| Supply Of Fertilizer | Supply Of Fertilizer | To enhance crop production, productivity and income generation | 1,504,512kgs of fertilizer supplied to 150,451 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 15/12/2016 | 15/5/2017 | 42952 | 60000000 | 55899200 | 55899200 | County Government of Bungoma |  | 55899200 | 0 | 55899200 | 1 | 55899200 | 0 | 0 | Completed
| Supply of incalf Dairy Cows | Supply Of 170 Incalf Dairy Cows (Ayrshires, Friesians, Guanseys & Jerseys) | To enhance dairy production and increase household incomes | 170 dairy cows supplied and delivered to farmer groups across the County | 2211023 | Supplies for production | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2016/2017 | 43010 | 15/6/2017 | 25/5/2017 | 45000000 | 15300000 | 15300000 | County Government of Bungoma |  | 15300000 | 0 | 15300000 | 1 | 15300000 | 0 | 0 | Completed
| Purchase and delivery of Certified Maize Seed | Purchase and delivery of 32,610 bgs of 1okgs of Certified Maize Seed to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 32,610 bags of 10kgs of certified maize seed supplied to 32,610 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/3/2018 | 20/2/2018 | 70000000 | 67016200 | 68000000 | County Government of Bungoma |  | 67016200 | 0 | 67016200 | 1 | 67016200 | 0 | 0 | Completed
| Purchase and delivery of Certified Fertilizer (750 beneficiaries per Ward (50KG PKTS planting and top dressing)) | Purchase and delivery of 3,261,000 kgs of Certified Fertilizer (planting and top dressing) to 32,610 vulnerable farmers (750 beneficiaries per Ward for 43 Wards and 180 for two wards; Township &Khalaba) | To enhance crop production and productivity for food security | 3,261,000 kgs of Certified Fertilizer supplied and delivered to 32,610 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 17/12/2017 | 17/2/2018 | 20/2/2018 | 200000000 | 183941341 | 185500000 | County Government of Bungoma |  | 183941341 | 0 | 183941341 | 1 | 183941341 | 0 | 0 | Completed
| Purchase and Delivery of tilapia and catfish fingerlings | Purchase and Delivery of tilapia and catfish fingerlings | To enhance fish production and income generation | 260,000 Tilapia and catfish fingerlings purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 26/3/2018 | 5000000 | 2600000 | 3000000 | County Government of Bungoma |  | 2600000 | 0 | 2600000 | 1 | 2600000 | 0 | 0 | Completed
| Purchase and delivery fish feeds | Purchase and delivery fish feeds | To enhance fish production and income generation | 48 tonnes of fish feeds purchased and delivered | 2211023 | Supplies for production | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2017/2018 | 15/1/2018 | 15/04/2018 | 17/3/2018 | 8000000 | 4080000 | 4100000 | County Government of Bungoma |  | 4080000 | 0 | 4080000 | 1 | 4080000 | 0 | 0 | Completed
| Procurement of certified maize seed for vulnerable farmers | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 65500000 | 33462500 | 33462500 | County Government of Bungoma |  | 33462500 | 0 | 33462500 | 1 | 33462500 | 0 | 0 | Completed
| Procurement of fertilizer for vulnerable farmers | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2018/2019 | 43385 | 43740 | 43501 | 120500000 | 94686973.74 | 94686973.74 | County Government of Bungoma |  | 94686973.74 | 0 | 94686973.74 | 1 | 94686973.74 | 0 | 0 | Completed
| Supply and delivery of certified fertilizer across the County | Supply and delivery of 1,809,000kgs non-acidic planting and top dressing fertilizer to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 1,809,000kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 93823520 | 94000000 | County Government of Bungoma |  | 93823520 | 0 | 93823520 | 1 | 93823520 | 0 | 0 | Completed
| Supply and delivery of certified maize seed for 45 Wards (402 farmer beneficiaries per ward) | Supply and delivery of 18,090 bags of 10kgs of certified maize seed to 18,090 vulnerable farmers across the County (402 farmer beneficiaries per ward for 45 Wards) | To enhance crop production, productivity and income generation | 18,090 bags of 10kgs of certified fertilizer supplied and delivered to 18,090 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2019/2020 | 23/12/2019 | 23/3/2020 | 44167 |  | 38390900 | 38390900 | County Government of Bungoma |  | 38390900 | 0 | 38390900 | 1 | 38390900 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer | Procurement of fertilizer for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 1,764,600kgs of Fertilizer procured and delivered to 17,646 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 120000000 | 79184782 | 68099441 | County Government of Bungoma |  | 79184782 | 0 | 79184782 | 1 | 79184782 | 0 | 0 | Completed
| Purchase and delivery of certified Maize seed | Procurement of certified maize seed for 17,646 vulnerable farmers (402 farmers per Wards for 43 Wards and 180 farmers for 2 Wards;Township and Khalaba) | To enhance crop production, productivity and income generation | 176,460 bags of 10kgs of certified seed procured and delivered to 17,646 vulnerable farmers across the County | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2020/2021 | 20/12/2020 | 20/2/2021 | 20/2/2021 | 65600000 | 20537350 | 20537350 | County Government of Bungoma |  | 20537350 | 0 | 20537350 | 1 | 20537350 | 0 | 0 | Completed
| Supply and delivery of Rain Gun Drip Irrigation | Supply and delivery of Rain Gun Drip Irrigation | To enhance production, productivity and income generation | 20 rain gun drip irrigation supplied and delivered | 2211007 | Agricultural materials, supplies and small equipment | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44896 | 44898 | 15/2/2022 | 5000000 | 1058900 | 1058900 | County Government of Bungoma |  | 1058900 | 0 | 1058900 | 1 | 1058900 | 0 | 0 | Completed
| Supply and delivery of Basal/Planting and Top Dressing Fertilizers | Supply and delivery of 1,363,000 kgs of Basal/Planting and Top Dressing Fertilizers to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 1,363,000 kgs of fertilizer supplied and delivered to 13,630 vulnerable farmers | 31201199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 60000000 | 58348000 | 60000000 | County Government of Bungoma |  | 58348000 | 0 | 58348000 | 1 | 58348000 | 0 | 0 | Completed
| Supply and delivery of Certified Hybrid Maize Seeds | Supply and delivery of 13,630 bags of 10kgs of Certified Hybrid Maize Seeds to 13,630 vulnerable farmers | To enhance crop production, productivity and income generation | 13,630 bags of 10kgs of certified maize seed supplied and delivered to 13,630 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44542 | 44898 | 44836 | 30000000 | 27260000 | 27500000 | County Government of Bungoma |  | 27260000 | 0 | 27260000 | 1 | 27260000 | 0 | 0 | Completed
| Purchase of steel cabinets for CDDCs | Purchase of 20 steel cabinets for CDDCs | To enhance service delivery | 20 steel cabinets purchased and delivered | 2640503 | Other Capital grants and transfer (NARGIP) | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and irrigation -NARGIP | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44415 | 44417 | 44418 |  | 619000 | 700000 | Development partner | IDA | 0 | 619000 | 619000 |  | 619000 | 0 | 0 | Completed
| Supply and delivery of Aquaculture Equipment for sub county fisheries | Supply and delivery of Aquaculture Equipment for sub county fisheries | To increase fish production and improve on food and nutrition security | Equipment for andd and delivered to Equipment All 9 Sub Counties | 2211023 | Supplies for production | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Livestock, Fisheries and Veterinary Services | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2021/2022 | 44866 | 44868 | 15/2/2022 | 5000000 | 2393100 | 2500000 | County Government of Bungoma |  | 2393100 | 0 | 2393100 | 1 | 2393100 | 0 | 0 | Completed
| Purchase and delivery of certified fertilizer for Farm Input Support (500 beneficiaries per ward) | Purchase and delivery of 2,250,000kgs certified fertilizer (top dressing and planting) to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 2,250,000kgs of certified fertilizers purchased and delivered to 22,500 vulnerable farmers | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 270000000 | 253779390 | 270000000 | County Government of Bungoma |  | 253779390 | 0 | 253779390 | 1 | 253779390 | 0 | 0 | Completed
| Purchase and delivery of certified maize seed for Farm Input Support (500 beneficiaries per Ward) | Purchase and delivery of 22,500 bags of 10kgs of certified maize seed to 22,500 vulnerable farmers (500 beneficiaries per ward) | To enhance crop production and productivity for food security | 22,500 bags of 10kgs of certified maize seeds supplied to 22,500 vulnerable farmers | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 45261 | 45263 | 22/2/2023 | 56000000 | 65200500 | 56000000 | County Government of Bungoma |  | 65200500 | 0 | 65200500 | 1 | 65200500 | 0 | 0 | Completed
| Crop Insurance | Crop Insurance for 45,000 farmers (1,000 farmers per Ward for 45 Wards) | To reduce on financial risks caused by unforseen crop damage to farmers | 45000 farmers covered | 2210904 | Crop insurance | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2022/2023 | 17/1/2023 | 17/3/2023 | 27/2/2023 |  | 32620088 | 32625000 | County Government of Bungoma | 0 | 32620088 | 0 | 32620088 | 1 | 32620088 | 0 | 0 | Completed
| Supply and delivery of certified maize seeds varieties for highland areas | Supply and delivery of certified maize seeds varieties for highland areas | To enhance crop production, productivity and income generation | 138,500Kgs of Maize seed suppiled for highland areas | 3111301 | Purchase of Certified Crop seed | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 26250000 | 71800000 | 71800000 | County Government of Bungoma |  | 71800000 | 0 | 71800000 |  | 71800000 | 0 | 0 | Completed
| Supply and delivery of fertilizer | Supply and delivery of fertilizer | To enhance crop production, productivity and income generation | 225,000Kgs of fertilizer suppiled | 3120199 | Purchase of fertilizer | All 9 Sub Counties | West Bukusu |  | Agriculture, Rural and Urban Development | Agriculture and Irrigation | Agriculture, Livestock, Fisheries, Irrigation and Cooperatives | 2023/24 | 45385 | 45387 | 29/4/2024 | 128000000 | 247422915 | 128000000 | County Government of Bungoma |  | 247422915 | 0 | 181822915 | 0.73 | 181822915 | 65600000 | 65600 | Completed
18 | Proposed installation and Commissioning of 8M solar powered streetlights in sipala Market,,Sango,Mukhuyu,Makaura market/police post,Lwanda and Nasaka Markets,Mukuyuni market,Mombasa ndogo and Namboko primary,Nasyanda and Mutembi Markets. | installation of powered sipala Mukhuyu police and Mukuyuni ndogo primary solar primary,Nasyanda | promotion of MSMEs and security | solar powered street lights installed | BGM/CNTY/TEI/01/OT/2024-2025 Neg. 1667805/2024-2025 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | PISONAZ INT'L LTD | 2024/2025 |  | Awarded in Dec 2024 | Yet to Start/New |  |  |  | CGB | [8 empty] | Works to commence |  | 8
22 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1448863-2-2023/2024 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | WESTLINK ELECTRICAL AND HARDWARE | 2023/2024 |  | Supplied | Supplied and used | 3875000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
23 | Supply of Electrical Materials for Grid | rid of Electrical | Maintenance of electrical infrustructure | Electrical materials supplied | 14777172-2023/2024 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | KAMILI ENTERPRISES | 2023/2024 |  | Supplied | Supplied and used | 2125000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
24 | Supply and delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | M/S NEOSTARGATE LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
25 | Supply delivery of electrical materials | materials and delivery | Maintenance of electrical infrustructure | Electrical materials supplied | 1355362-2023-24 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | M/S MILCON CONTRACTORS LIMITED | 2023/2024 |  | Supplied | Supplied and used | 2500000 |  |  | CGB | [8 empty] | Complete | 100 | Bulk
47 | Purchase and installation of transformers | Installation of transformers | Increased connectivity to grid electricity | Transformers Installed |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | REREC/CGB | 2023/2024 |  | This was a matching fund where the County provided Kshs. 45,000,000 and the same was added by REREC. Survey of proposed sites carried out and coordinates collected. Awaiting installation of transformers. | Ongoing and in use | 45000000 | 90000000 |  | CGB/REREC | [8 empty] | Works on shedule |  | 21
48 | Disbursement of County Trade Loan across all 45 wards | of all Trade Loan | Empowerment of MSMEs | Loans disbursed |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Trade | N/A | 2023/2024 |  | Regulations were gazetted, MSMEs sensitized and Ward and County Trade Loan Committee members appointed and inducted. Funds transferred to special purpose account, awaiting for disbursement to qualified MSMEs | Ongoing and in use |  | 10000000 |  | CGB | [8 empty] | Revolving |  | All wards
53 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Streetlights installed, repaired and maintained |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 19995600 |  |  | CGB
54 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar powered highmast flood lights installed | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 39959400 |  |  | CGB
55 | Proposed supply, installation and commissioning of 10M solar street lights across the county. | supply commissioning solar M street lights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Capstone Construction Limited | 2022/23 |  | Complete and in use |  | 19060076 |  |  | CGB
59 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 14849088 |  |  | CGB
62 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 7563363 |  |  | CGB
64 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | 2706213 |  |  | CGB
66 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed, repaired and mantained |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -2150937 |  |  | CGB
67 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -4579512 |  |  | CGB
69 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | promotion of MSMEs and security | Solar streetlights installed and commisioned |  |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -9436662 |  |  | CGB
70 | Proposed supply, installation and commissioning of 15M solar powered high flood mast lights across the county. | supply commissioning solar flood M mast lights | promotion of MSMEs and security | Solar streetlights installed and commisioned | BGM/CNTY/TEI/05/OT/2024-2025 1667821-2024/2025 |  |  | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -11865237 |  |  | CGB
72 | Proposed installation, repair and mantainance of 7M solar poered streetlights in Bungoma county | installation mantainance solar M poered streetlights | [5 empty] | West Bukusu |  | Trade, Energy and Industrialization | Dept of Energy | Westlink Electrical Hardware | 2022/23 |  | Complete and in use |  | -16722387 |  |  | CGB

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled