## Sheet2
| WARD | LOCATION | NAME OF PROJECT | SECTOR | PROJECT STATUS
1 | Bokoli | Baptist church | Drilling of Monyofwe Baptist church borehole | Water & Natural Resources | Complete and in use
2 | Bokoli | Mahanga Market | Openning ,Grading and Gravelling of Mahanga market- Sichei river road | Roads & Infrastructure | Complete
3 | Bokoli | Kasembeli Watila Road | Periodic maintenance of Wafula Mukhebo- Kasembeli Watila road | Roads & Infrastructure | Complete
4 | Bokoli | Bruno road | Periodic maintenance of Kuywa-Lukuku-Bruno road | Roads & Infrastructure | Complete
5 | Bokoli | Bokoli Rc | Grading and gravelling of Wanyonyi- Mukhale- Kanuti- Moyokwe- Ben Kapten- Bokoli RC school | Roads & Infrastructure | Complete
6 | Bukembe East | Bunana | Periodic Maintenance of Martin Sindani Road | Roads & Infrastructure | Complete
7 | Bukembe East | Misanga | Opening,grading and gravelling of Nyaranga Road | Roads & Infrastructure | Complete
8 | Bukembe East | Tembelela | Opening grading and gravelling of Makunjo Road | Roads & Infrastructure | Complete
9 | Bukembe East | Bunana | Drilling of borehole and solarization at Bunana Village | Water & Natural Resources | Complete and in use
10 | Bukembe East | Sudi/Sipala | Drilling of borehole and solarization at Sipala Market | Water & Natural Resources | Complete and in use
11 | Bukembe East | Kongoli | Proposed supply and installation of streetlights | Trade & Industrialization | Complete
12 | Bukembe East | misanga | Proposed supply and installation of streetlights | Trade & Industrialization | Complete
13 | Bukembe East | across the ward | Purchase and supply of dairy cows to farmers across the Ward | Agriculture, Livestock & Fisheries | Supplied
14 | Bukembe west | Kisuluni | Periodic maintenance of Maina Chengasia road | Roads & Infrastructure | Complete
15 | Bukembe west | Ekitale/kisuluni | Periodic maintenance of Wakhisi road | Roads & Infrastructure | Complete
16 | Bukembe west | Sichekereni/Ekitale | Periodic maintenance of Toko- Sichekereni- Mufuti road | Roads & Infrastructure | Complete
17 | Bukembe west | Khaoya/Mutayi | Periodic maintenanceof Kanisa mbili- Chefunea- Makokha- MCA road | Roads & Infrastructure | Complete
18 | Bukembe west | Chemche/Ekitale | Periodic maintenance of Chemche primary- Rodesha road | Roads & Infrastructure | Complete
19 | Bukembe west | Ekitale | Periodic maintenance of Nachango- Mufuti road | Roads & Infrastructure | Complete
20 | Bukembe west | Muyai/Khaoya | Periodic maintenance of SDA Church- Sibi- Misiko road | Roads & Infrastructure | Complete
21 | Bukembe west | Nalutiri/Ndengelwa | Periodic maintenance of Ndengelwa primary - Misiko road | Roads & Infrastructure | Complete
22 | Bukembe west | Nalutiri/Ndengelwa | Equipping of Bukembe west dairy cooperative sacco water project to include Installation of Hybrid pump, Solar system, Elevation of 12M high pressed steel tank, Extension of water pipeline up to 3kms, Construction of 3 water points and construction of 1 water kiosk | Water & Natural Resources | Complete and in use
23 | Bukembe west | Namirembe | Construction of maternity wing at Namirembe dispensary | Health & Sanitation | Site handed over
24 | Bukembe west | Kisuluni/Ekitale/Muyai/Khaoya/Nalutiri | Supply and delivery of 10,000 grafted avocado seedling to farmers | Agriculture, Livestock & Fisheries | Awarded
25 | Bukembe West | Kisuluni/Ekitale/Muyai/Khaoya/Nalutiri | Purchase of assorted sporting items | Youth & Sports | complete
26 | Bumula | watamba kasi, Lutaso, Yakobo, Mukinga Kachala and wekesa mlima | Protection of 5no water springs watamba kasi, Lutaso, Yakobo, Mukinga Kachala and wekesa mlima | Water & Natural Resources | Complete and in use
27 | Bumula | Mukuyuni primary and Musia boreholes | Drilling and equipping of Mukuyuni primary and Musia boreholes | Water & Natural Resources | Complete and in use
28 | Bumula | Lutaso/siyekumulo | Periodic maintananace of Baridi- Lutaso-Sabwami-Makokha-Kele- Kituyi road | Roads & Infrastructure | Complete
29 | Bumula | Lurare/Bumula | Periodic maintananace of Lurare primary- Kmtc Remo- Matokho mkt- Masinde wekora- Lunao fym primary - Lunao vtc road road | Roads & Infrastructure | Complete
30 | Bumula | Lunao | Periodic maintenance of church of Loise wafula- Namosi railway crossing- Lunao dispensary - Billy wanjala - Nandingwa,Tukai lutuli- Mikokwe primary road, Wafukho scola- Nandingwa road | Roads & Infrastructure | Complete
31 | Bumula | Siyekumulo | Syekumulo- Raphael- Mbaisi Road | Roads & Infrastructure | At award stage
32 | Bumula | Namusasi | proposed construction of Sango Junction- Bwaliro-2*4 box culvert on river Namusasi | Roads & Infrastructure | At award stage
33 | Bumula | across the ward | Supply of poultry to registered groups | Agriculture, Livestock & Fisheries | Complete
34 | Bumula | Bumula playground | Construction of Ablution block at Bumula playground | Health & Sanitation
35 | Bumula | Kimatuni/Mabusi | Musiya Primary- Wamuteke Road/ nasianda dispensary culvert | Roads & Infrastructure | Complete
36 | Cheptais | Cheptais/Ngachi | Periodic maintenance of Hill school- Kapchebus-Marama-Kanga'ng'a- Chemuses-Kapmuchonje road | Roads & Infrastructure | Complete
37 | Cheptais | Chebkube/Chebweek | Periodic maintenance of Cheptoror -Chepngwaen road | Roads & Infrastructure | Complete
38 | Cheptais | Chebkube/Walanga | Periodic maintenance of Kapchemwoikut-Kapmwanje-Police-Josphat -County Council land roadand installation of gabions at Kikar bridge | Roads & Infrastructure | Complete
39 | Cheptais | Chebkube | Periodic maintenance of Walanga Boarder -Chebusienya-Miruni road | Roads & Infrastructure | Complete
40 | Cheptais | Ngachi | Construction of modern flash toilets with elavated tanks at Cheptais market | Water & Natural Resources | Complete and in use
41 | Bumula | Bunambobi Primary School | Proposed Construction works for 1 no ECDE Classroom and 3 no door pit Latrine at Bunambobi Primary School in Bumula ward | Education & Vocational Training | Complete
42 | Chepyuk | Kubura | Grading and gravelling of Kabukwo Junc -Kubura Road | Roads & Infrastructure | Complete
43 | Chepyuk | Chepyuk | Grading and gravelling of St Johns Chepyuk -Sosaplel road | Roads & Infrastructure | Complete
44 | Chepyuk | Kapkisei/Kubura | Opening ,grading,and gravelling of Chepkurkur-Kamabus rd | Roads & Infrastructure | Complete
45 | Chepyuk | Kamabus/Chepkurkur | Opening ,grading and gravelling of Kapkisei- Kabukwo Juncrd | Roads & Infrastructure | Complete
46 | Chepyuk | Kubura | Grading and gravellingof Kubura -Chepkowo Rd | Roads & Infrastructure | Complete
47 | Chepyuk | Berurr/Chepkurkur | Opening ,grading and gravelling of Berur -Marichkut Rd | Roads & Infrastructure | Complete
48 | Chepyuk | Kaimugul | Grading and gravelling of Kipsikirok- Chepokos road | Roads & Infrastructure | Complete
49 | Chepyuk | Emia | Opening,grading and gravelling of Cheptaburbur road | Roads & Infrastructure | Complete
50 | Chepyuk | Chepyuuk | construction of foot bridge at Kimurio River | Roads & Infrastructure | Complete
51 | Chepyuk | Kimurio | Pipelaying of Kimurio intake - Kimurio water tank | Water & Natural Resources | Complete and in use
52 | Chepyuk | Cheptoror/Chewangoi | The proposed Completion of 1NO. ECDE CLASSROOM AT CHEPTOROR PRIMARY SCHOOL AND RENOVATION OF 1NO. CLASSROOM AT CHEWANGOI PRIMARY IN CHEPYUK WARD | Education & Vocational Training | Complete and in use
53 | Chepyuk | Chepkurkur/Kaimugul | Construction of Chepkurkur and Kaimugul Dispensaries and construction of maternity wards phase 1 | Health & Sanitation | site handed over
54 | Chepyuk | Chepyuk & Kipsigon | Installation of grid street lighting at Chepyuk and Kipsigon Market | Trade & Industrialization | Retendered
55 | Chesikaki | Kiptii/Sasur | periodic maintenance Kiptii-Chebukoke road | Roads & Infrastructure | Yet to start
56 | Chesikaki | Chesikaki/Chebinyiny | Chebinyinyi-Runik road | Roads & Infrastructure | Yet to start
57 | Chesikaki | Kamarang | River Emanang'-Kamarang road | Roads & Infrastructure | Yet to start
58 | Chesikaki | Kamarang | Periodic maintenance Kisiero- Kamarang Road | Roads & Infrastructure | Yet to start
59 | Chesikaki | Chesikaki | Periodic maintenance of Kingo Junction- Border Road | Roads & Infrastructure | Complete
60 | Chepyuk | Sosaplel primary | Proposed construction works for 1 no ECDE classroom at Sosaple primary school in Chepyuk ward | Education & Vocational Training | Ongoing
61 | Chesikaki | Kaptoboi and Kapkurongo | Installation of 2No solar interg lights | Trade & Industrialization | Complete
62 | Chesikaki | Kimabole | Installation of solar powered lights at Kimabole Market | Trade & Industrialization
63 | Chesikaki | Mulatiwa | construction of boda boda sheds at Mulatiwa market | Trade & Industrialization | Complete and in use
64 | Chesikaki | Embakasi | construction of boda boda sheds at Embakasi market | Trade & Industrialization | Complete and in use
65 | Chesikaki | Sasur market | construction of boda boda sheds at sasur market | Trade & Industrialization | Complete and in use
66 | Chesikaki | kaberoo/Bukonoi | Extension of Kabero-Bukonoi water supply | Water & Natural Resources | Complete and in use
67 | Chesikaki | Tuikut | Construction ofTuikut Health Centre | Health & Sanitation
68 | Chesikaki | Chemondi | Purchase of one acre of land for Chemondi farmers cooperative society | Lands, Urban & Physical Planning | Contract signing
69 | Chesikaki | across the ward | Purchase and supply of dairy goats,cows ,and poultry | Agriculture, Livestock & Fisheries | Complete
70 | Chesikaki | across the ward | Purchase and supply of poultry | Agriculture, Livestock & Fisheries | Complete
71 | Chwele/ Kabuchai | Sanandiki | Periodic maintenance of Londo-Sanandiki- Saisi- Yoram road | Roads & Infrastructure | Complete
72 | Chwele/ Kabuchai | Sikhana-Loboni Road (Namilama) | Opening, Grading and Gravelling of Sikhana-Loboni road | Roads & Infrastructure | Complete
73 | Chwele/ Kabuchai | Chwele | Periodic maintenance of Chwele S.A- Sirisia road | Roads & Infrastructure | Complete
74 | Chwele/ Kabuchai | Mukhweya Cathoilc Church | Installation of 1No 30M solar lights | Trade & Industrialization | Ongoing
75 | Chwele/ Kabuchai | Chwele/Mukhweya/Makhonge/Namilama | purchase and supply of chicken to registered groups | Livestock, Fisheries and Veterinary services | Complete
76 | East Sang'alo | Kimugui | Grading and gravelling of Nabutola -Fuchani rd | Roads & Infrastructure | Complete
77 | East Sang'alo | Dorofu | Grading and gravelling of Dorofu Siche-River Chwele rd | Roads & Infrastructure | Complete
78 | East Sang'alo | Lutungu | Grading and gravelling of Sunrise-Nyange Rd | Roads & Infrastructure | Complete
79 | East Sang'alo | Mwibale/Kimugui | Opening and grading Silunda- Mukonyi road and ring culvert across Namasela stream | Roads & Infrastructure | Complete
80 | East Sang'alo | Mechimeru | Grading and gravelling Mechimeru-Sango-Sikalame Rd | Roads & Infrastructure | Complete
81 | East Sang'alo | Mechimeru | Rehabilitation and Extension of Mechimeru and Mabusi water projects in East Sangalo ward | Water & Natural Resources | Complete and in use
82 | Chwele/ Kabuchai | Namakhele primary | Proposed Renovation works for 1 no ECDE Classrooms at Namakhele Primary School in Chwele Kabuchai ward | Education & Vocational Training | Yet to start
83 | East Sang'alo | Wacheka | Construction of an automotive/Mechanical 1No and 1No sizeable staffroom workshop at Wacheka VTC with 2No modern pit latrines for leaners and staff | Education & Vocational Training | Complete
84 | East Sang'alo | Mwibale | Zakayo- Malyongobi- Nasoko Road | Roads & Infrastructure | Complete
85 | East Sang'alo | Mechimeru | 4 No. door latrine at Mechimeru Health Center | Health & Sanitation | Site handed over
86 | Elgon | Richard-Murunga | Extension of pipeline and protection of Richard Jacktons spring in Elgon ward | Water & Natural Resources | Complete and in use
87 | Elgon | Kaberwa | construction of ECDE classroom at Kaberwa primary | Education & Vocational Training | Ongoing
88 | Elgon | Kapsokwon | construction of ECDE classroom at Kibuk primary | Education & Vocational Training | Ongoing
89 | Elgon | Namorio/Kamkata | Periodic maintanance of Mzee Tindis' Road -Kimobo -Kipyeto market road | Roads & Infrastructure | Ongoing
90 | Kabula | Wamunyiri | Periodic maintenance of Wamunyiri road | Roads & Infrastructure | Complete
91 | Kabula | Wamumali | Periodic maintenance of Wamumali road | Roads & Infrastructure | Complete
92 | Kabula | Samichi | Periodic maintenance of Samichi cattlle dip road | Roads & Infrastructure | Complete
93 | Kabula | Remwa | Periodic maintenance of Remwa road | Roads & Infrastructure | Complete
94 | Kabula | Kabula | Periodic maintenance of Kabula Machinjoni road | Roads & Infrastructure | Complete
95 | Kabula | Malinda | Periodic maintenance of Otunga-Nuah road | Roads & Infrastructure | Complete
96 | Kabula | across the ward | Purchase of Dairy animals and Pig lets for registered groups (Dairy animals 4m and piglets 1m ) | Agriculture, Livestock & Fisheries | Complete
97 | Kabula | across the ward | supply and delivery piglets’ large white landrace/duroc/hampshire/ pietrain 3-4 months in Kabula Ward | Agriculture, Livestock & Fisheries | complete
98 | Kabula | Yacobo/Macho | Yacobo- Macho Road(1.2KM) | Roads & Infrastructure | Complete
99 | Kabula | Namasanda market plus installation of solar pump | Drilling of borehole at Namasanda market plus installation of solar pump | Water & Natural Resources | Complete and in use
100 | Kamukuywa | Mbongi | Periodic maintenance of Chesamisi mkt - Sosio river road | Roads & Infrastructure | Complete
101 | Kamukuywa | Nabikoto | Periodic maintenance of Karoli- Kitale high ways river road | Roads & Infrastructure | Complete
102 | Kamukuywa | Kimakwa | Periodic maintenance of Katinga - Chief Mukire road(3.1KM) | Roads & Infrastructure | Complete
103 | Kamukuywa | Musembe | Periodic maintenance of Sipakala road | Roads & Infrastructure | Complete
104 | Kamukuywa | Musembe | Periodic maintenance of Mzee Alex Road in Musembe village | Roads & Infrastructure | Yet to start
105 | Kamukuywa | Mbongi/Nabikoto/Musembe/Kimakwa/Mapera | Purchase of dairy animals for registered groups | Agriculture, Livestock & Fisheries | Complete
106 | Kamukuywa | Nabikoto | Purchase of 2acres of land for sports purposes at Nabikoto | Lands, Urban & Physical Planning | At contract signing
107 | Kamukuywa | Chesamisi mkt, Chesamisi junct, Mukhuyu mkt and Makhonge mkt | Installation of Solar powered street lights at Chesamisi mkt, Chesamisi junct, Mukhuyu mkt and Makhonge mkt | Trade & Industrialization
108 | Kamukuywa | Sulwe dispensary | The Proposed Erection And Completion Works For Maternity Wing (Phase 1) At Sulwe Dispensary In Kamukuywa Ward Bungoma County | Health & Sanitation
109 | Kapkateny | Chepchabai | Periodic maintenance of Jipcho -Chepchabai | Roads & Infrastructure | Yet to start
110 | Kapkateny | kamuneru | Kamuneru main road- Boundary tea plantation Road | Roads & Infrastructure | Yet to start
111 | Kabula | Wamunyiri, Mukhuma, Syoya and Lukusi Primary Schools | Proposed renovation works for 1 no ECDE Classroom at Wamunyiri, Mukhuma, Syoya and Lukusi Primary School in Kabula ward | Education & Vocational Training | Complete
112 | Kapkateny | Kapsambu ECDE | The proposed construction of 1no ECDE classroom and 2no door pit latrine at Kapsambu ECDE centre in Kapkateny ward | Education & Vocational Training | Yet to start
113 | Kapkateny | Land B | Extension of Land B water pipeline | Water & Natural Resources | Complete and in use
114 | Kapkateny | kapkeke | Construction of Maternity wing at Kapkeke Dispensary | Health & Sanitation | To pay pending bills
115 | Kapkateny | kapkurongo | PROPOSED SUPPLY AND INSTALLATION OF 4 DISC COFFEE PULPING MACHINE | Agriculture, Livestock & Fisheries | Yet to be supplied
116 | Kapkateny | Masaeek | Periodic maintenance of Masaek-Kiptungururwo Road(2.0) | Roads & Infrastructure | Complete
117 | Kaptama | kongiit | Periodic maintenance of Sultan -Kaptegandet road(4.5KM) | Roads & Infrastructure | Complete
118 | Kaptama | kaboywo | Periodic maintenance of Kaboywo dip-Kap Dik-Kaboywo canteen road- Kapmoim-Chikondi road | Roads & Infrastructure | Complete
119 | Kaptama | kaborom | The Proposed Construction Of Maternity Wing At Kaborom Dispensary In Kaptama Ward | Health & Sanitation | site handed
120 | Kaptama | kongiit | Construction of Kongit maternity wing | Health & Sanitation | site handed over
121 | Kaptama | Kiptichor dispensary | The Proposed Erection And Completion Works For Outpatient Wing And 2No Door Pit Latrine At Kiptichor Dispensary In Kaptama Ward Bungoma County | Health & Sanitation | site handed over
122 | Kaptama | kaptamaa market | The Proposed Construction Works For Modern Latrines At Kaptama Market In Kaptama Ward Bungoma County | Health & Sanitation | site handed over
123 | Kaptama | kaptamaa market | Purchase of Coffee seedlings | Agriculture, Livestock & Fisheries | not supplied
124 | Kaptama | kaptelelio and Kiptiroko | Installation of 2No solar powered Flood Lights at kaptelelio and kiptiroko markets | Trade & Industrialization | To be retendered
125 | Kapkateny | Sacho Primary School | Proposed Construction works for 1 no ECDE Classroom and 3no. door pit Latrine at Sacho Primary School in Kapkateny ward | Education & Vocational Training | Yet to start
126 | Kaptama | Kapchebon VTC | The proposed construction works for 1NO WORKSHOP and 2NO. DOOR PIT LATRINE AT KAPCHEBON VTC IN KAPTAMA WARD | Education & Vocational Training | Ongoing
127 | Khalaba | Namuyembe | Opening of Khakila- Matanda road,Opening of Namachanja-Total road,Opening of Bishop Adrian-Kolikho road and periodic maintenance of Nabangi-Atiema road | Roads & Infrastructure | Yet to start
128 | Khalaba | Khalaba | Periodic maintanance of saferio-Khalaba river road,pamus-daudi mechumo road,deliverance church road,Micha guest house road | Roads & Infrastructure | Complete
129 | Khalaba | Khalaba/Bondeni/Namuyemba | Purchase of 20 pieces of 528 capacity incubators, 2No for poultry feed pellets machines and 5,000 eggs | Agriculture, Livestock & Fisheries | Complete
130 | Khalaba | Khalaba/Bondeni/Namuyemba | Reapairs and Maintenance of streetligfhts | Trade & Industrialization | 0ngoing
131 | Khalaba | Khalaba/Bondeni/Namuyemba | Supply and Delievry of car wash machines | Trade & Industrialization | Ongoing
132 | Kaptama | Chemeker Primary | Proposed construction works for 1 No ECDE classroom and 3 no door pit latrine at Chemeker primary school in Kaptama ward | Education & Vocational Training | Ongoing
133 | Khalaba | Khalaba/Bondeni/Namuyemba | Fencing of Namuyemba dispensary | Health & Sanitation | At Evaluation stage
134 | Khalaba | namoya/Sitabicha/Saferio/banda | Rehabilitation of 5No water springs(Namoya spring,sitabicha spring, Daudi Mechumo spring,Banda spring) | Water & Natural Resources | Complete and in use
135 | Khasoko | Namatotoa/Namusasi | Proposed Construction of Sango Junction - Bwaliro 2*4 Box Culvert on R.Namusasi in bumula ward | Roads & Infrastructure | Complete
136 | Khasoko | Khasoko/Mungore | Grading and gravelling of Namatotoa- Maraba-Mungore Parani rd road | Roads & Infrastructure | Complete
137 | Khasoko | Khasoko | Periodic maintenance of Absalom Barasa -Khasoko high school -Parani-Mundaa road | Roads & Infrastructure | Complete
138 | Khasoko | Khasoko | Periodic maintenance of Namanze Junction-Namanze prischool junc-Namanze Sec-maning road | Roads & Infrastructure | Complete
139 | Khasoko | Namusasi | Periodic maintenance of Juma -Sambui-Elias Wanupi-Namusasi-dispensary road(1km) | Roads & Infrastructure | Complete
140 | Khasoko | Lubunda | construction of 3 no market stalls at Lubunda market | Trade & Industrialization | Retendered
141 | Khasoko | maraba | Drilling and Upgrading of Maraba Primary and Namanze Primary boreholes in Khasoko ward | Water & Natural Resources | Complete and in use
142 | Khasoko | Nasianda Bahai | Piping of Nasianda Bahai water | Water & Natural Resources | Complete and in use
143 | Khasoko | Mungore | Construction of 10 door pit latrine at Mungore primary school | Education & Vocational Training | Complete and in use
144 | Khasoko | Mungore primary | Construction of 10 door pit latrine at Khasoko primary school | Health & Sanitation
145 | Khasoko | Sango | Installation of 4No solar streetlights | Trade & Industrialization | Complete
146 | Khasoko | Mungore health centre | Construction and erection of gate and fencing of Mungore Health Center | Health & Sanitation | site handed over
147 | Khasoko | Namanze dispensary | Erection of gate and fencing of Namanze Dispensary | Health & Sanitation
148 | Khasoko | Namusasi | Erection of gate and fencing of Namusasi Dispensary | Health & Sanitation
149 | Kibingei | Khwiroro | Periodic maintanace of Moi girls Kamusinga-Allan Bradly Primary(1.4km) | Roads & Infrastructure | Ongoing
150 | Kibingei | Khwiroro | Periodic maintenance of mzee sokoni-onyamase rd | Roads & Infrastructure | Ongoing
151 | Kibingei | Khwiroro | periodic maintanace of kibisi friends church-kinda silas nyaranga-peter machengo road | Roads & Infrastructure | Ongoing
152 | Kibingei | Siuna | Periodic maintenance of Mzee marumbu-buteyo-hamisi road | Roads & Infrastructure | Ongoing
153 | Kibingei | kibunde/Khwiroro/Siuna/daraja mungu | Extension Kimilili FYM water project in Kibingei ward | Water & Natural Resources | Complete and in use
154 | Kibingei | Khwiroro/Kibunde/daraja Mungu/Siuna | Purchase and supply of poultry and feeds for registred farmers | Agriculture, Livestock & Fisheries | complete
155 | Kibingei | across the ward | Purchase of Dairy animals | Agriculture, Livestock & Fisheries | Complete
156 | Kimaeti | Myanga primary | Periodic maintenance of Railway crossing-Myanga primary -Libolina- Wambu- Maseno road | Roads & Infrastructure | Complete
157 | Kimaeti | Carmel view | Periodic maintenance of Myanga - Bukirimo- Carmel view - Sparki road | Roads & Infrastructure | Complete
158 | Kimaeti | Radi school | Periodic maintenance of Kitabisi- Radi school | Roads & Infrastructure | Complete
159 | Kimaeti | Bitobo | Periodic maintenance of Bitobo- Impreza road | Roads & Infrastructure | complete
160 | Kimaeti | Nakalira | Upgrading of Kitingya,Bukirimo, tulukui, Masielo and Nakalila primary school boreholes | Water & Natural Resources | Complete and in use
161 | Kimaeti | Kimaeti/Nakhwana/Bitobo/Kamurumba | Purchase of dairy animals | Agriculture, Livestock & Fisheries | Complete
162 | Kimaeti | Kimaeti/Nakhwana/Bitobo/Kamurumba | SUPPLY AND DISTRIBUTION OF CERTIFIED GRAFTED HASS AVOCADO SEEDLINGS TO SUPPORT YOUTH GROUPS | Agriculture, Livestock & Fisheries | Supplied
163 | Kimaeti | Nakalira | Nakalila- Masielo Road(1.7km) | Roads & Infrastructure | complete
164 | Kimaeti | Sihilila | Rehabilitation of Syombe and Siilila water projects in Kimaeti ward | Water & Natural Resources | Complete and in use
165 | Kimilili | Khamulati/Matili | Periodic maintanance of Matili RC- Catholic church - Bahai primary Apprx 2.7km | Roads & Infrastructure | complete
166 | Kimilili | Matili | Periodic maintenance of Matili marrum- Lwanda- Bituyu appostalic road | Roads & Infrastructure | complete
167 | Kimilili | Matili | Periodic maintenance of Makaburini- Khamulati factory road | Roads & Infrastructure | complete
168 | Kimilili | Township | Periodic maintenance of Lanchester cabros- Kibisi spring road | Roads & Infrastructure | complete
169 | Kimilili | Matili | Periodic maintenance of Bituyu- Nandika - Mukanda Area road | Roads & Infrastructure | complete
170 | Kimilili | Township | Periodic maintenance of Posta Booster- Soweto estate- Donly school road | Roads & Infrastructure | complete
171 | Kimilili | Township | Periodic maintenance of Munanda phim school- Matili mkt road | Roads & Infrastructure | complete
172 | Luuya Bwake | Chekulo | Periodic maintenance of Chekulo -Chebeni road | Roads & Infrastructure | complete
173 | Luuya Bwake | Khachonge/Khalitaba | Periodic maintenance of Khachonge-Khalitaba road | Roads & Infrastructure | complete
174 | Luuya Bwake | Nangili | Periodic maintenance of Nangili-Coffee factory road | Roads & Infrastructure | complete
175 | Luuya Bwake | Nangubo | Periodic maintenance of Nangubo Pri -Chwele River Road | Roads & Infrastructure | complete
176 | Luuya Bwake | Nanjofu | Periodic maintenance of Mabanga Catholic -Nanjofu Road | Roads & Infrastructure | complete
177 | Luuya Bwake | Matunda | Periodic maintenance of Nasaka Markett -Misanga road | Roads & Infrastructure | complete
178 | Luuya Bwake | Sango/nalondo | Periodic Maintenance of Nalondo-Changalwa Roa | Roads & Infrastructure | complete
179 | Luuya Bwake | Sitila | Periodic of Sitila- Chwele river road | Roads & Infrastructure | complete
180 | Luuya Bwake | Sichei | Periodic maintananace of Mukombozi- Khachonge road | Roads & Infrastructure | complete
181 | Luuya Bwake | Misri/Sichei | Periodic maintenance of Misri Corner-Sichei road | Roads & Infrastructure | complete
182 | Luuya Bwake | (Marobo Musungu,Nangubo,Muganda and Nabaala )Water Spring | Protection of 3 no water springs(Marobo Musungu,Nangubo,Muganda and Nabaala )Water Spring | Water & Natural Resources | Complete and in use
183 | Luuya Bwake | Sikenga&Marobo mkt | Installation&Commissioning of 3No 12M Solar floodlights | Trade & Industrialization
184 | Luuya Bwake | Chekulo/Khalitaba/Nasaka/Sango/Nalondo/Nangili/Sichei/Matunda/Sitila/nanjofu/Misri | supply and delivery of cows for women and youth groups | Agriculture, Livestock & Fisheries | Complete
185 | Luuya Bwake | Chekulo/Khalitaba/Nasaka/Sango/Nalondo/Nangili/Sichei/Matunda/Sitila/nanjofu/Misri | Supply and delivery of chicken, for women and youth groups | Agriculture, Livestock & Fisheries | Complete
186 | Luuya Bwake | Nasaka | Opening of the Nasaka Market- Chebosi Road | Roads & Infrastructure | complete
187 | Luuya Bwake | Namukongo | Opening of the Sitila Macho- Chwele River Road | Roads & Infrastructure | complete
188 | Luuya Bwake | Khatete water project | Upgrading of Misri pri School Borehole and Extension of Khatete water project in Luuya Bwake ward | Water & Natural Resources | Complete and in use
189 | Lwandanyi | Tamulega/Namwesi | Periodic maintenance of Lurare -Ack Malakisi-Luyekhe-Matumbai- Tamlega road | Roads & Infrastructure | Complete
190 | Lwandanyi | Machakha/Sitabicha | Periodic maintenance of Londo- Stabicha- Mukhuyu road(2.5km) | Roads & Infrastructure | Complete
191 | Lwandanyi | Machakha Dispensary | Construction of Machakha Dispensary Phase 2 | Health & Sanitation | At Opinion Stage
192 | Maeni | Kamasielo | Periodic maintenance of Wanyibe-Wenani-Wetoto Road | Roads & Infrastructure | Complete
193 | Maeni | Kikwechi/Nasusi | Periodic maintence of Kikwechi centre-Kasenge Patroba Road | Roads & Infrastructure | Complete
194 | Maeni | Nasusi/Maeni | Periodic maintance of Ndumba -Wesisisi Road | Roads & Infrastructure | Complete
195 | Maeni | Wekunda/Kundu/Sangura/Kamasielo | Periodic maintenance of Khwiroro -Eman Road | Roads & Infrastructure | Complete
196 | Maeni | kamusinde | Periodic maintenance of Kamusinde SDA-Yona -Sitabicha Road | Roads & Infrastructure | Complete
197 | Maeni | Sikhendu | Periodic maintenance of Ndobo -Richard Khaemba-Masafu Road | Roads & Infrastructure | Complete
198 | Maeni | Lukhuna | The Proposed Construction Of Lukhuna Dispensary In Maeni Ward | Health & Sanitation | Retendered
199 | Maeni | Nameme | Construction of maternity wing at Namemedispensary | Health & Sanitation | At Evaluation stage
200 | Maeni | Kamusinde FYM | Drilling and upgrading of Nambaoni Secondary Borehole | Water & Natural Resources | Complete and in use
201 | Maeni | maeni Market | Construction of a public toilet at Maeni market | Health & Sanitation | At Evaluation stage
202 | Malakisi Kulisiru | Bukokholo/butonge | Periodic maintenance of Kibeu junction- Singicha rds 3.5km | Roads & Infrastructure | Ongoing
203 | Malakisi Kulisiru | Wekelekha | Periodic maintenance from St Antony Sec-Malinda-Ex chief road | Roads & Infrastructure | Ongoing
204 | Malakisi Kulisiru | lutaso | Periodic maintanance of Russia-Chongoi Rd 2.5km | Roads & Infrastructure | Ongoing
205 | Malakisi Kulisiru | lutaso | Periodic maintenance of Butere -Chongoi Road and installation of culverts | Roads & Infrastructure | Ongoing
206 | Malakisi Kulisiru | lutaso | Installation of cross culverts at Reformed church | Roads & Infrastructure | Ongoing
207 | Malakisi Kulisiru | lutaso | Periodic maintenance of Namawanga Junc -Chongoi-Bitunde rds (2.5KM) | Roads & Infrastructure | complete
208 | Malakisi Kulisiru | lutaso | Drilling of Sango SA church (Lutaso) borehole and installation of handpump | Water & Natural Resources | Complete and in use
209 | Malakisi Kulisiru | ndakaru | Drilling of borehole at Namunyu primary school and installation of handpump | Water & Natural Resources | Complete and in use
210 | Malakisi Kulisiru | lutaso | Drilling and capping of Boreholes at Henry Nato and Namawanga Primary in Malakisi Kulisiru ward | Water & Natural Resources | Ongoing
211 | Maeni |  | Supply and delivery of medical equipments for maeni and kamasielo dispensary | Health & Sanitation
212 | Malakisi Kulisiru | Wekelekha | Construction of a maternity wing at Namango'fulo Dispensary | Health & Sanitation | At Evaluation stage
213 | Malakisi Kulisiru | chebukutumi | Construction of 2 door pit latrines at Bisunu market | Health & Sanitation | site handed over
214 | Maraka | Lufwindri/Khamoto | Opening of SA-Amos-Mwanja-Kakimanyi rd | Roads & Infrastructure | Complete
215 | Maraka | Lurare/maraka | Opening and murraming of Maraka Stadium- Nzoia Market- Mukisu Stream Road | Roads & Infrastructure | Complete
216 | Maraka | Lukhova | maintenance of main road-lukhova-mutali rd | Roads & Infrastructure | Complete
217 | Maraka | Lukhova | opening of road block-kasaya-nzoia river road | Roads & Infrastructure | Complete
218 | Maraka | Lukhova'/township | Murramming,compacting,opening of drainage in estates,sites and service | Roads & Infrastructure | Complete
219 | Maraka | Nangeni | Murramming,compacting,opening of drainage in national estates(3 streets) | Roads & Infrastructure | Complete
220 | Maraka | Township | Murramming,compacting,opening of drainage in estates,half london and st stephen | Roads & Infrastructure | Complete
221 | Maraka | Nangeni | Gravelling,murramming and compacting wananchi-st marys-national | Roads & Infrastructure | Complete
222 | Maraka | japhezer,muhhammed,Nalua,Maruti,Kapchanga, and flashing of Muji poly borehole) | Gravelling,murramming and compacting CPB -public works | Roads & Infrastructure | Complete
223 | Maraka | Lurare | Partitioning,ceiling board and water connection in a maternity wing at Lurare dispensary | Health & Sanitation | site handed over
224 | Maraka | Lurare | Mounting and roofing with a verandah at catholic mobile clinic | Health & Sanitation | To be retendered
225 | Maraka | Nangéni ECDE Centre | The proposed construction works for barbed wire fence and gate at Nang’eni ECDE centre in Maraka ward | Education & Vocational Training | Yet to start
226 | Maraka | Lurare | Fencing of maraka stadium with chain link wire with steel main gate with a watchman room | youth & sports | At Evaluation stage
227 | Maraka | Lufwindri/Khamoto | Flashing of borehole at Lukhova dispensary ,installation of 10 thousand litres ,water tank,solar submersive pump | Water & Natural Resources | Complete and in use
228 | Maraka | japhezer,muhhammed,Nalua,Maruti,Kapchanga, and flashing of Muji poly borehole) | Repair and rehabilitation of water springs(japhezer,muhhammed,Nalua,Maruti,Kapchanga, and flashing of Muji poly borehole) | Water & Natural Resources | Complete and in use
229 | Maraka | Muji | Maintenance of Sahenyi Road- Webuye Stream | Roads & Infrastructure | Complete
230 | Matulo | Matulo | Matulo Market-Mawang’i Spring –Kinisu-Dina-SA primary road | Roads & Infrastructure | Ongoing
231 | Matulo | Malaha | Malaha Market -Ex Chief Mukhongo- Kingdom hospital-murram PAG mwamba road | Roads & Infrastructure | Ongoing
232 | Matulo | Township | Dina-radio mambo-musikari kombo | Roads & Infrastructure | Ongoing
233 | Matulo | Makhele | Cleophas-Chief-Kurarwa-Railway-Wanyonyi Foti- Wechuli –Nalika-Makhele Market- Woodhill Bridge | Roads & Infrastructure | Ongoing
234 | Matulo | Wenyinyila | Kingdom-Daraja Mbili-Wenyila Road | Roads & Infrastructure | Ongoing
235 | Matulo | Mulati road | Jovenah- Mulati SA Road | Roads & Infrastructure | Ongoing
236 | Matulo | kona Mbaya | Pajero-Namachi-Kona Mbaya Road | Roads & Infrastructure | Ongoing
237 | Matulo | Township | weigh bridge-musikari kombo-soko mjinga road | Roads & Infrastructure | Ongoing
238 | Matulo | Malaha Polytechnic | Munyende-Malaha Poly-Malaha Market Road | Roads & Infrastructure | Ongoing
239 | Matulo | Matulo RC Primary | Drilled Borehole and piping Solar-Matulo RC Primary/st andrews | Water & Natural Resources | Complete and in use
240 | Matulo | across the ward | Purchase and supply of poultry | Agriculture, Livestock & Fisheries | Complete
241 | Matulo | across the ward | Purchase of goats for farmers | Agriculture, Livestock & Fisheries | Complete
242 | Mbakalo | Karima | Periodic maintenance of Mukhisa Kobilo-Justus-Nandorobo Pri-Bidii Road | Roads & Infrastructure | Ongoing
243 | Mbakalo | Makunga | Periodic mainatanance of Nakitare -Juma Boy-Simatwa-Mulongo-Makhanu Road | Roads & Infrastructure | Ongoing
244 | Mbakalo | Mbakalo | Periodic maintenance of Mbakalo ACK-Musa Mbaki-Mbakalo Friends Church-Police- Soteni road | Roads & Infrastructure | Ongoing
245 | Mbakalo | Musembe | Periodic maintenance of Walucho -Murenga-Musembe-Gaburiel-Mapambano-Kulecho rd | Roads & Infrastructure | Ongoing
246 | Mbakalo | Kibisi/Nabiswa/Karima/Mbalo/Makunga | Supply and delivery of Poultry to registered groups | Agriculture, Livestock & Fisheries | Complete
247 | Mbakalo | Kibisi/Nabiswa/Karima/Mbalo/Makunga | Supply and delivery of goats to registered groups | Agriculture, Livestock & Fisheries | Complete
248 | Mbakalo | Kibisi/Nabiswa/Karima/Mbalo/Makunga | purchase of sports equipment for youth groups | youth & sports | complete
249 | Mbakalo | Kikechi | Upgrading and solarization of Kikechi water spring | Water & Natural Resources | Complete and in use
250 | Mbakalo | Makhakara- Testerio-Onyaiti Road | Makhakara- Testerio-Onyaiti Road | Roads & Infrastructure | Ongoing
251 | Mbakalo | Testerio- Onyaiti- Karima Bridge | Testerio- Onyaiti- Karima Bridge | Roads & Infrastructure | Ongoing
252 | Mihuu | Misimo secondary Schools | Drilling and upgrading of Misimo Sec School borehole and Rehabilitation of Savanna Dispensary borehole in Mihuu ward | Water & Natural Resources | Complete and in use
253 | Mihuu | Misimo | The proposed construction works for 1NO. ECDE CLASSROOM AT NABUYOLE PRIMARY SCHOOL IN MIHUU WARD | Education & Vocational Training | Ongoing
254 | Mihuu | Misimo/Froi | Periodic maintenance of Kivorani road 2km | Roads & Infrastructure
255 | Mihuu | Misimo | Periodic maintenance of Mihuu- Masindu road | Roads & Infrastructure
256 | Mihuu | Nabuyole | Periodic maintenance of Nabuyole- abigail road | Roads & Infrastructure
257 | Mihuu | Sipala | Periodic maiantanance of Sipala sec - Kafs road 11/2km | Roads & Infrastructure
258 | Mihuu | Chetambe | Periodic maintananace of Ndumbu road 1/2 km | Roads & Infrastructure
259 | Mihuu | Magemo | Periodic maintenance of St John Savanna-Savanna dispensary road 1km | Roads & Infrastructure
260 | Mihuu | across the ward | Purchase and supply of dairy animals to farmers | Agriculture, Livestock & Fisheries | Complete
261 | Mihuu | Mikuva | Barasa Sibuchi- Kutukhulu Road (2km) | Roads & Infrastructure
262 | Mihuu | across the ward | Purchase and supply of chicken to farmers | Agriculture, Livestock & Fisheries | Complete
263 | Milima | across the ward | Purchase of dairy animals | Agriculture, Livestock & Fisheries | Complete
264 | Milima | across the ward | Purchase of poultry birds | Agriculture, Livestock & Fisheries | Complete
265 | Milima | across the ward | Supply and delivery of Post Fingerlings in Milima Ward | Agriculture, Livestock & Fisheries | supplied
266 | Milima | milima market | Renovation of NADAFA | Agriculture, Livestock & Fisheries | ongoing
267 | Milima | Lukhokhwe Dispensary | Equiping of Lukhokhwe dispensary with modern health equipments | Health & Sanitation | To be retendered
268 | Milima | Lukhokhwe Dispensary | Construction of Bodaboda sheds across the ward | Trade & Industrialization | Retendered
269 | Milima | Mukuyuni | Grading and gravelling of Shandumba-Shivachi road | Roads & Infrastructure | Complete
270 | Milima | Binyenya/mwambi | Grading and gravelling of Binyenya - Dr Eseli road | Roads & Infrastructure | Complete
271 | Milima | Mpakani | Purchase of one acre land for construction of ECDE Center at Mpakani | Lands, Urban & Physical Planning | retendered
272 | Milima | Mukuyuni | Extension of Mukuyuni Water Project in Milima Ward. | Water & Natural Resources | Complete and in use
273 | Milima | Across the ward | Construction and renovation of 7 no. water springs across the Ward (Namboko/Manyonge/Wainanga/Mteve/Welime/Aswan/Ayuku/bateta/Maliki/Chachi/Samita/Sunguri/Cheloti/Adebe/maindi/Kwa glasi/Richard Waswa/Wakweika/Sirengo/Rodesha | Water & Natural Resources | Complete and in use
274 | Misikhu | Bunjosi | Periodic maintanace of Sirisia Coffee factory road | Roads & Infrastructure | Complete
275 | Misikhu | Sibembe | Periodic maintanace of Daraja Mbili-Sichuru-Misoki road | Roads & Infrastructure | Complete
276 | Misikhu | Bunjosi | Periodic maintanance of Namusiule- Bunjosi dispensary road | Roads & Infrastructure | Complete
277 | Misikhu | Bunangéni | Periodic maintanance of Bunange'ni-Leo-Lutuli road | Roads & Infrastructure | Complete
278 | Misikhu | Sirende | Periodic maintanance of Awinji-Nato-Friends Church Road | Roads & Infrastructure | Complete
279 | Misikhu | Sibembe | Periodic maintanace of Blue Canteen -Mzee Mombasa Road | Roads & Infrastructure | Complete
280 | Misikhu | Misikhu | Opening of Ainea Chengwa'li road | Roads & Infrastructure
281 | Misikhu |  | Opening of Lugulu Day- Wekesa Situma Road | Roads & Infrastructure
282 | Misikhu | Mungakha primary, Lugulu PEFA church, makhonge primary and Sirende Primary | Drilling and equiping of boreholes at Makhonge Pri and Sirende Pri Sch | Water & Natural Resources | Complete and in use
283 | Misikhu | Misikhu dispensary | Construction of maternity wing at Mukhe dispensary and completion of maternity wing at Misikhu dispensary | Health & Sanitation | site handed over
284 | Misikhu | Misikhu Ward | Supply and delivery of grafted Avocado and coffee seedlings to farmers | Agriculture, Livestock & Fisheries | Supplied
285 | Mukuyuni | Sikhana | Periodic maintanace of Sikhana-Mbako-Makhonge 2.6km | Roads & Infrastructure
286 | Mukuyuni | lukhome | Periodic maintenance of Kitai- Chemwile-Chief Musakali road 3km | Roads & Infrastructure
287 | Mukuyuni | Matisi | Periodic maintenance of Sikhana- Mbako-Makhonge and Pathway-Nicola-Matisi road in Mukuyuni Ward | Roads & Infrastructure
288 | Mukuyuni | Sichei | Kuywa Junction- Sikulu Primary- Lukhuna Road | Roads & Infrastructure
289 | Mukuyuni | across the ward | Purchase and supply of poultry chicken across the ward | Agriculture, Livestock & Fisheries | Completed
290 | Musikoma | across the ward | Purchase of dairy animals | Agriculture, Livestock & Fisheries | Complete
291 | Musikoma | Sio | Periodic maintenance of pumzika junction-munyali bridge-maina railway road | Roads & Infrastructure | Complete
292 | Musikoma | Namasanda | Periodic maiantanance of Jordan Road ( Wamwana junction- Mzee Cheloti) | Roads & Infrastructure | Complete
293 | Musikoma | Wabukhe | Periodic maintenance of Makhanu-MusamaliMusungu- Rich minister road | Roads & Infrastructure | Complete
294 | Musikoma | Walala | Periodic maintenance of Omondi- Barkery- Wanalisi- Walala road | Roads & Infrastructure | Complete
295 | Musikoma | Walala | Intallation of Solar system at Namammuka water project | Trade & Industrialization | Retendered
296 | Musikoma | Sio ECDE | Construction of 4no door Toilet at Sio ECDE primary | Education & Vocational Training | New
297 | Musikoma | Sio | Periodic of Mwalimu Waka- Nyorita road | Roads & Infrastructure | Complete
298 | Musikoma | Musikoma muslim chiefs office | Movement and refurbishment of medical container from Mjini slums to Chief’s office in Muslim | Health & Sanitation | to be handed over
299 | Musikoma | Sirtanyi | Kapuru- ACK Sacred Road | Roads & Infrastructure | Ongoing
300 | Musikoma | Sio ECDE | Fencing and construction of coffee driers at Makhanga coffee factory | Education & Vocational Training | Yet to start
301 | Naitiri/ Kabuyefwe | Nzoia RC | Construction and equiping of ECDE Classroom at Nzoia rc primary | Education & Vocational Training | ongoing
302 | Naitiri/ Kabuyefwe | Shihilila KAG | Elevation of water tank and extension of Shihilila KAG church borehole to the community | Water & Natural Resources | Complete
303 | Naitiri/ Kabuyefwe | Sirakaru | Upgrading to solar piping system, construction of water kiosk and extension of pipeline from stock farm / Sirakaru colonial borehole to Sirakaru primary, Sirakaru secondary,Sirakaru dispensary and Sirakaru market | Water & Natural Resources | Complete and in use
304 | Naitiri/ Kabuyefwe | Pwani Market Road | Periodic maintenance of Mukweyi- Musila- PAG church - Makumu- Pwani mkt road | Roads & Infrastructure | Complete
305 | Naitiri/ Kabuyefwe | across the ward | supply of dairy animals across the ward | Agriculture, Livestock & Fisheries | Complete
306 | Naitiri/ Kabuyefwe | across the ward | Supply of chicks to Bungoma North Poultry fcs and Naitiri division women sacco and self help groups | Agriculture, Livestock & Fisheries | Completed
307 | Naitiri/ Kabuyefwe | Makhanga market | Fencing and construction of coffee driers at Makhanga coffee factory | Agriculture, Livestock & Fisheries | ongoing
308 | Naitiri/ Kabuyefwe | kabuyefwe | Construction of Mepu box culvert on the Sokomoko- Mepu- Kakai Road | Roads & Infrastructure | Complete
309 | Namwela | Kikai/nabeki | Periodic maintanance of Kikai-Nabeki Road | Roads & Infrastructure | Complete
310 | Namwela | Mutonyi | Periodic maintenance of Chwele Girls -Butunde Road | Roads & Infrastructure | Complete
311 | Namwela | Toloso | Periodic maintenance of Chwele -Sibumba-Kwafu road | Roads & Infrastructure | Complete
312 | Namwela | Nabeki/Mutonyi/Toloso/Kolani | supply and delivery of dairy goats to registered groups | Agriculture, Livestock & Fisheries | Completed
313 | Namwela | Nanjikobe | Upgrading of Namwela Market borehole ,and drilliing of Nanjikobe coffee factory borehole ,piping of Menu factory water to menu Primary and construction of a water kiosk,and extension of lukhuna water project to lukhuna center | Water & Natural Resources | Complete and in use
314 | Namwela | Kolani | Construction of a maternity wing at Kolani Dispensary | Health & Sanitation | SOME MONEY WAS USED TO PAY PENDING BILL
315 | Namwela | Sibumba dispensary | Purchase of land for Sibumba Dispensary | Lands, Urban & Physical Planning | At Professional opinion
316 | Ndalu/Tabani | Ndalu | Periodic mainantananace of Faith Academy-Bunyasi road ,Muliro market-Musembe-Muhanji road | Roads & Infrastructure | Complete
317 | Ndalu/Tabani | Muliro | Periodic mainantananace of Proffessor Odhiamb o-John Bengi-Julius Opanga'na rd | Roads & Infrastructure | Complete
318 | Ndalu/Tabani | Ndalu/Muliro | Installation of 8 no Flood lights across the ward | Trade & Industrialization | Yet to start
319 | Ndalu/Tabani | Ndalu/Muliro | Supply of Poultry to widows and vulnerable groups | Agriculture, Livestock & Fisheries | Complete
320 | Ndalu/Tabani | Lower/Upper/Central Township | Purchase of 10N0 egg incubators for farmers across the ward | Agriculture, Livestock & Fisheries | Complete
321 | Ndalu/Tabani | Tabani market | Construction of of 1No milk coolere structure at Tabani Market | Agriculture, Livestock & Fisheries | ongoing
322 | Ndalu/Tabani | Ndalu market | Purchase and installation of 4No of 40ft*80 ft fabricated containers to be partitioned into kiosks for small scale traders In Ndalu Market | Trade & Industrialization | Ongoing
323 | Ndivisi | Magemo | Periodic maintenance of makuselwa-khaoya 3.8km | Roads & Infrastructure | Complete
324 | Ndivisi | Chebukora | Periodic maintenance of Misikhu -Makemo-Namarambi-chebukora road 4km | Roads & Infrastructure | Complete
325 | Ndivisi | across the ward | Purchase of dairy cows for 21 groups | Agriculture, Livestock & Fisheries | Complete
326 | Ndivisi | Sinoko/sambu primary schools | construction of 2 no Ecde classrooms at Sambu primary | Education & Vocational Training | Ongoing
327 | Ndivisi | namarambi | Drilling and upgrading of Namarambi borehole | Water & Natural Resources | Complete and in use
328 | Ndivisi | Namarambi | Installation of street lights at Namarambi Juncion | Trade & Industrialization | Awarded
329 | Namwela |  | Supply and delivery of medical equipments at kolani and kaptanai dispensary | Health & Sanitation
330 | Ndivisi | wabukhonyi | Construction of maternity wing at Wabukhonyi health centre | Health & Sanitation | used to pay pending bill
331 | Siboti | Kisawayi/Mukwa | Periodic maintenance of Netima-Mukwa Market road | Roads & Infrastructure | Complete
332 | Siboti | Kisawayi | periodic maintenance of Miluki-Namanje road | Roads & Infrastructure | Complete
333 | Siboti | Kisawayi | Opening and grading of Martin Sikuku Junc -Nyongesa Mwanja junc Rd | Roads & Infrastructure | Complete
334 | Siboti | Siboti | Opening and grading of Nandika Pstation -Nandika Catholic Church -Khabusi Bridge Rd | Roads & Infrastructure | Complete
335 | Siboti | Musakasa | Opening and grading of Mukwa sec - Kikwech rd | Roads & Infrastructure | Complete
336 | Siboti | east Siboti | Opening and grading of Netima pri-Peter sumbi Junc Rd | Roads & Infrastructure | Complete
337 | Siboti | mukwa\ | Opening and grading of Wekesa Anthony-Martin Wasike-Nandika Bridge Rd | Roads & Infrastructure | Complete
338 | Siboti | Masielo | Opening of Musakasa Market -Charle sArnest rd | Roads & Infrastructure | Complete
339 | Siboti | Musakasa | Opening of Waswa Maruti-Mwasame rd | Roads & Infrastructure | Complete
340 | Siboti | Musakasa | Opening of ,Miluki Sec -Timina rd | Roads & Infrastructure | Complete
341 | Siboti | Musakasa | Opening of Siboti Junc ACK church-Health centre- Thomas Matasi junc rd | Roads & Infrastructure | Complete
342 | Siboti | East Siboti | Opening of Bosio Pr-Namuningie dam-Simiyu Temteo rd | Roads & Infrastructure | Complete
343 | Siboti | Kisawayi | Opening of Kisawai Alex Junc Rd -Toloso River | Roads & Infrastructure | Complete
344 | Siboti | Kisawayi | Opening and grading of Wepukhulu-Chananga-Sango rd | Roads & Infrastructure | Complete
345 | Siboti | Masielo | Opening and grading of Wanyonyi Tumen Junc -Nandika Bridge rd | Roads & Infrastructure | Complete
346 | Siboti | Kisawayi | periodic maintenance of Netima-Bisuche junc-kisawai-Makari junc road | Roads & Infrastructure | Complete
347 | Siboti | East Siboti | Periodic maintanace of Masielo mkt -St Peters Siboti mkt rd | Roads & Infrastructure | Complete
348 | Siboti | Kisawayi | Opening of Sinne -Bosio dam rd | Roads & Infrastructure | Complete
349 | Siboti | Masielo | Opening of Napara ACK Pri -Toloso-Sango bridge | Roads & Infrastructure | Complete
350 | Siboti | East Siboti | Periodic maintenance of Nandika Junc - Nandika River rd | Roads & Infrastructure | Complete
351 | Siboti | Siboti primary | construction of 1 no ECDE classroom at Siboti Primary school | Education & Vocational Training | Ongoing
352 | Siboti | Khabusi Primary | construction of 1 no ECDE classroom at Khabusi Primary school | Education & Vocational Training | Ongoing
353 | Siboti | Namanje Primary | construction of 1 no ECDE classroom at Namanje Primary school | Education & Vocational Training | Ongoing
354 | Siboti | Nasimbo Primary | construction of 1 no ECDE classroom at Nasimbo Primary school | Education & Vocational Training | Ongoing
355 | Siboti | Nang'ata primary | construction of 1 no ECDE classroom at Nangata Primary school | Education & Vocational Training | Ongoing
356 | Siboti | Murumba ECDE | purchase of land for construction of Murumba ecde centre | Lands, Urban & Physical Planning | At contract signing
357 | Siboti | Sango ECDE | purchase of land for construction of Sango ecde centre | Lands, Urban & Physical Planning | At contract signing
358 | Siboti | Kisawayi | purchase of land for construction of Kisawai ecde centre | Lands, Urban & Physical Planning | At contract signing
359 | Siboti | Kisawayi Dispensary | Construction Of 6 Door Ablution Block At Kisawai Dispensary | Health & Sanitation | complete
360 | Siboti | Sango Market | Contruction Of 6 Door No. Ablution Block At Sango Market | Health & Sanitation | site handed over
361 | Sitikho | Nambalayi | Periodic maintenance of Namisi road | Roads & Infrastructure | Complete
362 | Sitikho | Sitikho | Periodic maintenance of Sitikho road | Roads & Infrastructure | Complete
363 | Sitikho | Kuywa | Periodic maintenance of Milele road | Roads & Infrastructure | Complete
364 | Sitikho | Ngwelo | Periodic maintenance of Box 1 road | Roads & Infrastructure | Complete
365 | Sitikho | Ngachi | Periodic maintanance of Ngachi Road and Bridge | Roads & Infrastructure | Complete
366 | Sitikho | Khalumuli | Periodic maintenance of Mwangala Road | Roads & Infrastructure | Complete
367 | Sitikho | Mahele | Periodic maintenance of mahele market-catholic Church | Roads & Infrastructure | Complete
368 | Sitikho | Mangana | Periodic maintenance of Kasisi Road | Roads & Infrastructure | Complete
369 | Sitikho | Milo/Mangana | periodic maintenance of Kukwangali SDA Road | Roads & Infrastructure | Complete
370 | Siboti | Maliki Primary | Proposed construction works for 1No ECDE Classroom and 3no door pit Latrine at Miluki Primary School in Siboti Ward | Education & Vocational Training | Complete
371 | Sitikho | Milo/Mangana | Construction of Manga'na ECDEclassroom | Education & Vocational Training | ongoing
372 | Sitikho | Mangána | Installation of 8No solar interg lights | Trade & Industrialization | Complete
373 | Sitikho | maina |  | Trade & Industrialization
374 | Sitikho | Mahele |  | Trade & Industrialization
375 | Sitikho | ngwelo | Fencing of Ngwelo Dispensary | Health & Sanitation | site handed ovber
376 | Sitikho | Ngwelo dispensary | Drilling of 1 no borehole at Ngwelo Dispensary | Water & Natural Resources | Complete and in use
377 | South Bukusu | Muanda | Grading and gravelling of Muanda health center- Silingi rd, Nasongo- Mukanda- Makhanu anaseth rd and Ngutuku-Isabelah-Sio river- Wesonga kinabati-motima makhanu chapili tulumba TTI rd,kayobia-muanda primary rd | Roads & Infrastructure | Complete
378 | South Bukusu | Mateka | Grading and gravelling of Nelima- Khayota- Bilenge- Nganga rd, Namachanja- Mukoro- George wasolo rd,sifuniame-chief mildred rd,mutuunyi-wasolo rd | Roads & Infrastructure | Complete
379 | South Bukusu | Lumboka | Namasake cattle dip- Wesamba- Chief Nyongesa rd, Wangila lupao- sio river rd,musumba rd, Burangasi- VTC- Mambo rd, Mark makokha rd , Kakumeka- vincent rd, Musumba rd | Roads & Infrastructure | Complete
380 | South Bukusu | Biliso | Opening of Protus Mukusi-road, | Roads & Infrastructure | Complete
381 | South Bukusu | Muanda/Mateka/lumboka/Kimatuni | Supply and delivery of Poultry chicken(2 months old) to registered groups | Livestock, Fisheries and Veterinary services | Completed
382 | South Bukusu | Tulumba | Construction of Tulumba Primary ECDE | Education & Vocational Training | New
383 | South Bukusu | Naika village | maintenance of Khaoya Sindani, Burangasi, Kibachenje water pumps and Protection of 4no water springs(Kalasinga water spring,Sali/sio/Elmoro water spring,Nikola/sio/mateka water spring,Namachanja mukoro water spring) | Water & Natural Resources | Complete and in use
384 | South Bukusu | Lunakwe | Construction of placenta pit at Lunakwe Dispensary | Health & Sanitation | awaiting site handover
385 | South Bukusu | Biliso | Purchase of half an acre land for Biliso primary ECDE | Lands, Urban & Physical Planning | At contract signing
386 | South Bukusu | Mulukoba | Purchase of half an acre land for Mulukoba village dispensary | Lands, Urban & Physical Planning | At contract signing
387 | South Bukusu | Muanda/Mateka/lumboka/Kimatuni | Supply of dairy goats | Livestock, Fisheries and Veterinary services | Awarded
388 | Soysambu/ Mitua | Mitua VTC | The proposed constuction works for model vtc at Mitua vocational training centre in Soysambu/Mitua ward | Education & Vocational Training | Ongoing
389 | Tongaren | Mabusi | Periodic maintenance of Bishop Atundo Secondary- Jusper Kiveu -Sango markt- Mitoto- Mfunje- namungubo road-njiwa chananga-machakha road junction(grading and gravelling and installation of culverts) 6.8km | Roads & Infrastructure | Complete
390 | Tongaren | Binyenya | Periodic maintenance of R Harrows bridge Savania- Nyamweso Binyenya mrkt- Friends church Binyenya dam- Nabongolo sikulu- Matisi primary Ngome road- Sokomoko, Sawa kiminini river- Manyasa Lungai junction road | Roads & Infrastructure | Complete
391 | Tongaren | Matisi, Machakha, Mitoto, Birunda and Milimani primary schools | Construction of ECDE classrooms at Lukhuna pri, Matisi Pri, Mitoto Pri, Birunda Pri, Milimani Pri and Machakha primary schools | Education & Vocational Training | New
392 | Tongaren | Msalaba | Drilling and Capping of Msala borehole in Tongaren ward | Water & Natural Resources | ongoing
393 | Tongaren | Binyenya/Mabusi | Purchase of 26 No. combined option (electrical and diesel) 10 horsepower grade two posho mills for registered women, widows and youth groups- | Trade & Industrialization | Retendered
394 | Township | Lower/Upper/Central Township | Construction of 10 no Bodaboda sheds across the ward | Trade & Industrialization | ongoing
395 | Township | Lower/Upper/Central Township | Installation&Maintanance of 8M Grid streetlights | Trade & Industrialization | Completed
396 | Township | Moi DEB/Central primary | Construction of 20 No toilets at Moi DEB primary and Central primary | Health & Sanitation | site handed over
397 | Township | across the ward | Purchase of 10 no incubators and food formulators and 10,000 fertilized eggs | Livestock, Fisheries and Veterinary services | Supplied
398 | Township | CBD | Fencing of Ngwelo Dispensary | Trade & Industrialization | Supplied
399 | Tuuti-Marakaru | kimukungi | Opening,grading and gravelling and installation of culverts on Kimukungi-Dismas Nakokonya-Khalaba road | Roads & Infrastructure | Complete
400 | Tuuti-Marakaru | Mayanja | Opening of Makutano-legio maria church | Roads & Infrastructure | Complete
401 | Tuuti-Marakaru |  | Opening of Manoa-Kangabasi road | Roads & Infrastructure | Complete
402 | Tuuti-Marakaru | Marakaru | opening,grading and gravelling and installation of culvers on Nabongo-Khalaba road | Roads & Infrastructure | Complete
403 | Tuuti-Marakaru | Nabukhisa | Periodic maintenance of Shibale-Kikwechi Police post | Roads & Infrastructure | Complete
404 | Tuuti-Marakaru | Makutano | Gravelling of Makutano Corner shop-Mwalimu Henry road | Roads & Infrastructure | Complete
405 | Tuuti-Marakaru | Kibabii | Gravelling of Cardinal Otunga-Kamukunda-Fr Osyanju road | Roads & Infrastructure | Complete
406 | Tuuti-Marakaru | Mayanja | Periodic maintenance of Mwalimu Nandemu-Wetungu-Wasike road | Roads & Infrastructure | Complete
407 | Tuuti-Marakaru | Bukananchi | Periodic maintanace of Bukananachi -Lumasa road | Roads & Infrastructure | Complete
408 | Tuuti-Marakaru | Bukananchi | Gravelling of Bukananchi -Namawanga road | Roads & Infrastructure | Complete
409 | Tuuti-Marakaru | Namikelo/Namawanga | Opening,grading and gravelling and installation of culverts on Lusweti-John Namela-Round-Matayo Bilasio-Rogino Road road | Roads & Infrastructure | Complete
410 | Tuuti-Marakaru | Kibabii VTC | The proposed construction of SENTRY,MODERN GATE AND EXHIBITION STALLS AT KIBABII VOCATIONAL TRAINING CENTRE IN TUUTI/MARAKARU WARD | Education & Vocational Training | Ongoing
411 | West Bukusu | lwanja | Periodic maintenance of Muchoe junction - Nabikubo road | Roads & Infrastructure | Complete
412 | West Bukusu | lwanja | Periodic maintenance of Makhanu- Wenani road | Roads & Infrastructure | Complete
413 | West Bukusu | lwanja | Periodic mainatanace of Masinde- Glory- Lwanja primary junction road | Roads & Infrastructure | Complete
414 | West Bukusu | Kibuke | Periodic mainatanace of Catholi churchc- Machwele river- Wacholi road | Roads & Infrastructure | Complete
415 | West Bukusu | mayanja | Periodic mainatanance ofv Namuningie- Chief masolo road | Roads & Infrastructure | Complete
416 | West Bukusu | Ngoli | Periodic maintenance of Cheupe- Kauka road | Roads & Infrastructure | Complete
417 | West Bukusu | Nyangali market | Periodic maintenance of Juma Rose- Machwele primary road | Roads & Infrastructure | Complete
418 | West Bukusu | across the ward | Purchase of Dairy animals and Chiken | Agriculture, Livestock & Fisheries | Complete
419 | West Bukusu | Luwanja/Kibuke/Ngóli/mayanja | Construction of 3No Door Pit Latrine&Urinal | Trade & Industrialization | Complete
420 | West Bukusu | Kimwanga | Installation&Commissioning of 1No 12M Solar floodlights | Trade & Industrialization | Retendered
421 | West Bukusu | Mayanja | Periodic maintenance of Nyangali Market- Machwele River Road | Roads & Infrastructure | Complete
422 | West Bukusu | Luwanja/Kibuke/Ngóli/mayanja | Repair and installation of culverts across the Ward | Roads & Infrastructure | Complete
423 | West Nalondo | Kisiwa | Periodic maintenance of Pongola- Muyai dam | Roads & Infrastructure
424 | West Nalondo | Nangwe/Sirare | Periodic maintenance of Noco- Busiraka road | Roads & Infrastructure | Complete
425 | West Nalondo | Kisiwa | Periodic maintenance of Chebukwa- Muyekhe road | Roads & Infrastructure | Complete
426 | West Nalondo |  | Periodic maintenance of Mulaa road | Roads & Infrastructure | Complete
427 | West Nalondo | Sirare | Opening and murraming of Sawali- Ndengelwa Bridge Road | Roads & Infrastructure | Complete
428 | West Sang'alo | Bulondo | Periodic maintenance of Bulondo Catholic Church -Butunde-Khalaba River apprx 3.7Km | Roads & Infrastructure | Complete
429 | West Sang'alo | Ranje | Periodic maintenance of Masibo Junc-Makindi market-Makitola junc-Ranje 2km | Roads & Infrastructure | Complete
430 | West Sang'alo | Ranje Dispensary/Kachomba market/Airport Market | Proposed supply and installation of 12 No. solar powered split streetlights | Trade & Industrialization | Complete
431 | Tuuti-Marakaru | Kibabii VTC | The proposed construction of administration block at Kibabii VTC in Tuuti Marakaru ward. | Education & Vocational Training | Complete
432 | West Sang'alo | Namisi | Construction of 1 no modern ECDEclassroom at Namisi Primary | Education & Vocational Training | New
433 | West Sang'alo | Roads | Lwanda Junction- Ekitale Market Road | Roads & Infrastructure | Complete
434 | West Sang'alo | Health | The Proposed Construction Of 4 No Doors Pit Latrine At Ekitale Market In West Wang’Alo Ward | Health & Sanitation | Retendered
435 | H/Q |  | Renovation and refurbishment of 12 county residential houses | Housing | NEW
436 | Kanduyi Sub-County | Mabanga | Construction of Governors residential houses | Housing | Ongoing
437 | Kanduyi Sub-County | Musikoma | Construction of Deputy Governors residential houses | Housing | Ongoing
438 | Bokoli,Bukembe,Kanduyi,Kimaeti | Milimani | Construction of county residential houses | Housing | ongoing
439 | Webuye,Chwele and Kimilili |  | KISIP 2 Infrastructure Grant for slum upgrading | Housing | ongoing
440 | H/Q |  | Construction of County Executive office block | Housing | ongoing
441 | Township |  | Augmentation of existing water supply pipeline at uwanja wa ndege catchment. | Climate Change | At Evaluation stage
442 | Countywide |  | ESTABLISHMENT AND MANAGEMENT OF JUNCAO FODDER BULKING SITES UNDER THE FLLoCA PROGRAMME IN BUNGOMA COUNTY | Climate Change | Awarded
443 | West Sang'alo |  | Integrated Community Resilience Project in water, agriculture and Environment at Luanda Water Spring Catchment | Climate Change | Awarded
444 | Kaptama |  | Integrated Community Resilience Project in water, agriculture and Environment at Kaptelelio/Chepkoya Spring Catchment | Climate Change | Awarded
445 | Maeni |  | Integrated Community Resilience Project in water, agriculture and Environment at Balayo Spring Catchment | Climate Change | Awarded
446 | Chesikaki |  | Integrated Community Resilience Project in water, agriculture and Environment at Cheseker Catchment (REHABILITATION AUGMENTATION OF CHESEKER WATER PROJECT IN CHESIKAKI WARD) | Climate Change | awarded
447 | South Bukusu |  | Integrated Community Resilince Project through upgrading of water supply at Biliso borehole(UPGRADING OF NANDINGWA BOREHOLE IN SOUTH BUKUSU WARD ) | Climate Change | Awarded
448 | Khasoko |  | Integrated Community Resilince Project through upgrading water supply at Bwaliro borehole | Climate Change | Awarded
449 | West Nalondo |  | Integrated Community Resilience Project through Promotion of Climate Smart Agriculture at Muyayi Water Pan Catchment | Climate Change | Awarded
450 | Ndivisi |  | Integrated Community Resilience Project through Promotion of Climate Smart Agriculture at Magemo Water Pan Catchment | Climate Change | Awarded
451 | Milima |  | Integrated Community Resilience Project through Promotion of Climate Smart Agriculture at Nabingèngè Water Pan Catchment | Climate Change | Awarded
452 | Kibingei |  | Integrated Community Resilience Project through Promotion of Climate Smart Agriculture at Chebukwabi Water Pan Catchment | Climate Change | Awarded
453 | Musikoma |  | Integrated Community Resilience Project in water, agriculture and Environment at Namasanda Water Pan Catchment | Climate Change | Awarded
454 | Bukembe west |  | UPGRADING OF NAMIREMBE DISPENSARY BOREHOLE AND PROMOTION OF FRUIT TREE FARMING WITHIN THE CATCHMENT IN BUKEMBE WEST WARD | Climate Change | Awarded
455 | Tuuti-Marakaru |  | Integrated Community Resilience Project in water, agriculture and Environment at Munala Borehole Catchment | Climate Change | Awarded
456 | Bukembe East |  | Integrated Community Resilience Project in water, agriculture and Environment at Misanga Borehole Catchment | Climate Change | Awarded
457 | Khalaba |  | Promotion of Clean Energy Consumption through Establishment of an Energy Centre for Climate Resilience(CONSTRUCTION OF AN ENERGY CENTRE AND SOLARIZATION OF MUTEREMUKO VTC) | Climate Change | Awarded
458 | East Sang'alo |  | Integrated Community Resilience Project in water, agriculture and Environment at Sikata/Mwibale Water Spring Catchment | Climate Change | Awarded
459 | Mbakalo |  | Integrated Community Resilience Project in water, agriculture and Environment at Lutukayi Water Spring Catchment | Climate Change | Awarded
460 | Naitiri/ Kabuyefwe |  | Integrated Community Resilience Project through Promotion of Climate Smart Agriculture at Makhanga Water Pan Catchment | Climate Change | Awarded
461 | Ndalu/Tabani |  | Integrated Community Resilience Project in water, agriculture and Environment at Hezekiah Water Spring Catchment | Climate Change | Awarded
462 | Soysambu/ Mitua |  | Integrated Community Resilience Project in water, agriculture and Environment at Namunyiri Borehole Catchment | Climate Change | Awarded
463 | Tongaren |  | Integrated Community Resilience Project in water, agriculture and Environment at Jason Water Spring Catchment | Climate Change | Awarded
464 | Luuya Bwake |  | Integrated Community Resilience Project in water, agriculture and Environment at Lwanda Dispensary Borehole Catchment(UPGRADING OF LWANDA DISPENSARY BOREHOLE PROMOTION OF FRUIT TREE FARMING AND NATURE BASED ENTREPRISE IN LUUYA BWAKE WARD) | Climate Change | Awarded
465 | Chwele/ Kabuchai |  | Integrated Community Resilience Project through Promotion of Climate Smart Agriculture at Sikusi Borehole Catchment(PROTECTION AND UPGRADING OF MUNOKO WATER SPRING IN CHWELE KABUCHAI WARD) | Climate Change | Awarded
466 | Mukuyuni |  | Integrated Community Resilience Project in water, agriculture and Environment at Chebukaka Catchment | Climate Change | Awarded
467 | Namwela |  | Integrated Community Resilience Project in water, agriculture and Environment at Chebit Water Spring Catchment(UPGRADING OF MENU COFFEE FACTORY BOREHOLE IN NAMWELA WARD) | Climate Change | Awarded
468 | Malakisi Kulisiru |  | Integrated Community Resilience Project in water, agriculture and Environment at Nabuloli Borehole Catchment | Climate Change | Awarded
469 | Lwandanyi |  | Integrated Community Resilience Project in water, agriculture and Environment at Tisi River Catchment | Climate Change | Awarded
470 | Kimilili |  | Integrated Community Resilience Project in water, agriculture and Environment at Matili Water Pan Catchment | Climate Change | Awarded
471 | Kamukuywa |  | Integrated Community Resilience Project in water, agriculture and Environment at Chesamisi Catchment(PROTECTION AND UPGRADING OF MUKITANGA WATER SPRING AND ESTABLISHMENT OF ORCHARD IN KAMUKUYWA WARD) | Climate Change | Awarded
472 | Mihuu |  | Integrated Community Resilience Project in water, agriculture and Environment at Ngosia Water Spring Catchment | Climate Change | Awarded
473 | Maraka |  | Integrated Community Resilience Project in water, agriculture and Environment at Nzoia RC Primary Borehole Catchment | Climate Change | Awarded
474 | Matulo |  | Integrated Community Resilience Project in water, agriculture and Environment at Malaha FYM Borehole Catchment | Climate Change | Awarded
475 | Bokoli |  | Integrated Community Resilience Project in water, agriculture and Environment at Machakha VTC/Webuye TTI Boreholes Catchment | Climate Change | Awarded
476 | Sitikho |  | Integrated Community Resilience Project in water, agriculture and Environment at Milo/Maila Borehole Catchment | Climate Change | Awarded
477 | Misikhu |  | Integrated Community Resilience Project in water, agriculture and Environment at Lugulu Day Secondary Borehole Catchment | Climate Change | Awarded
478 | Siboti |  | Integrated Community Resilience Project in water, agriculture and Environment at Nandika Catholic Borehole Catchment(UPGRADING OF KISAWAYI PRIMARY BOREHOLE AND ESTABLISHMENT OF AN ORCHARD IN SIBOTI WARD) | Climate Change | Awarded
479 | West Bukusu |  | Integrated Community Resilience Project in water, agriculture and Environment at Nangèni Borehole Catchment | Climate Change | Awarded
480 | Kabula |  | Integrated Community Resilience Project in water, agriculture and Environment at Old Catholic Borehole Catchment | Climate Change | Awarded
481 | Kimaeti |  | Integrated Community Resilience Project in water, agriculture and Environment at Myanga Borehole Catchment | Climate Change | Awarded
482 | Bumula |  | Integrated Community Resilience Project in water, agriculture and Environment at Sindani Borehole Catchment(UPGRADING OF SINDANI BOREHOLE AND ESTABLISHMENT OF AN ORCHARD IN BUMULA WARD) | Climate Change | Awarded
483 | Elgon |  | Integrated Community Resilience Project in water, agriculture and Environment at Kitaban Water Catchment (AUGMENTATION AND EXTENSION OF KITABAN WATER PROJECT IN ELGON WARD) | Climate Change | Awarded
484 | Cheptais |  | Integrated Community Resilience Project in water, agriculture and Environment at Peresten Water Spring Catchment | Climate Change | Awarded
485 | Kapkateny |  | Integrated Community Resilience Project in water, agriculture and Environment at Chelebei Catchment(EXTENSION OF TOYIWONDET WATER PROJECT ) | Climate Change | Awarded
486 | Kaptama |  | Periodic Maintenance of kaptama-kaborom road | Roads & Infrastructure | Evaluation stage
487 | Kaptama |  | Periodic maintenance of Kimobo Kipkama | Roads & Infrastructure | Evaluation stage
488 | Elgon |  | Periodic Mintenance of Kipyeto - Kipkama Road in elgon ward(2.6KM) | Roads & Infrastructure | Ongoing
489 | Chesikaki |  | Periodic maintenance of Kiptii primary toroso polytechnic | Roads & Infrastructure | At Evaluation stage
490 | Cheptais |  | Periodic maintenance of Cheptais high scool Kapsesoi | Roads & Infrastructure | Evaluation stage
491 | Chepyuk |  | Periodic maintenance of Miti mbili Kapkisei | Roads & Infrastructure | Evaluation stage
492 | Kapkateny |  | Periodic maintenance of Kapkateny -Sacho Road | Roads & Infrastructure | Evaluation stage
493 | Lwandanyi |  | Periodic maintenance of Katomei Primary access road | Roads & Infrastructure | Evaluation stage
494 | Namwela |  | Periodic maintenance of Namwela-Kikai road | Roads & Infrastructure | Evaluation stage
495 | Malakisi Kulisiru | Lutaso | Periodic maintenance of Londo-Ndakaru Mkt road | Roads & Infrastructure | Evaluation stage
496 | Chwele/ Kabuchai |  | Periodic maintenance of Lwanda-Namilama-Sikusi | Roads & Infrastructure | Evaluation stage
497 | West Nalondo |  | Periodic maintenance of Chebukwa-Luucho | Roads & Infrastructure | Award
498 | Luuya Bwake |  | Periodic maintenance of Kiboochi-Bukembe | Roads & Infrastructure | Award
499 | West Bukusu |  | Periodic maintenance of Mwomo(Lukhanyu)- Lwanja(Wangokho) | Roads & Infrastructure | Evaluation stage
500 | South Bukusu |  | Periodic maintenance of Kibachenje-Mateka(Late Chief Wamalwa - Nabangi -Muchang'eni) | Roads & Infrastructure | At Award Stage
501 | Matulo |  | Periodic maintenance of Mwalimu House-malaha | Roads & Infrastructure | Evaluation stage
502 | Misikhu |  | Periodic maintenance of Lugulu - Lukusi | Roads & Infrastructure | Evaluation stage
503 | Kimaeti |  | Periodic maintenance of Myanga PTF ChurchMikokwe Primary School | Roads & Infrastructure | Evaluation stage
504 | Musikoma |  | Periodic maintenance of Namisi - Siritanyi | Roads & Infrastructure | Evaluation stage
505 | Khasoko |  | Periodic maintenance of Khasoko - Mundaa Primary | Roads & Infrastructure | At Evaluation stage
506 | Tuuti-Marakaru | Namikelo/Namawanga | Periodic maintenance of Bukananachi - R.khalaba - mayanja MarketC33 | Roads & Infrastructure | Evaluation stage
507 | Kimaeti |  | Periodic maintenance of Nambuchi - Nakalila - Napara - Kitabisi road | Roads & Infrastructure | Evaluation stage
508 | Sitikho |  | Periodic maintenance of Milo Secondary - Machakha | Roads & Infrastructure | Evaluation stage
509 | Soysambu/ Mitua |  | Periodic maintenance of Namunyiri Soysambu road R1,R2 | Roads & Infrastructure | At Award Stage
510 | Mukuyuni |  | Periodic maintenance of Teremi Primary School -Kuywa Girls High School | Roads & Infrastructure | Evaluation stage
511 | Kamukuywa |  | Upgrading of mapera juntion-kamukuywa ACK primary road in kamukuywa ward | Roads & Infrastructure | Award
512 | Cheptais | Cheptais | Purchase Of Medical Equipment For Cheptais Sub-County Hospital | Health & Sanitation | SUPPLIED
513 | Maraka | Webuye Sub County Hospital | Proposed Completion Of Icu/Renal Unit At Webuye Sub County Hospital | Health & Sanitation | Awarded
514 | Bokoli | Bokoli SunCounty Hospital | The Proposed Completion Works For Operation Theatre At Bokoli Sub County Hospital | Health & Sanitation | Ongoing
515 | Bumula | Bumula Sub County Hospital | Equipping Of 100 Bed Maternal Block At Bumula Sub-County Hospital | Health & Sanitation | Not supplied
516 | Mbakalo | across the ward | Construction of Mbakalo slaughter house | Livestock, Fisheries and Veterinary services | completed
517 | West Nalondo | Kisiwa | construction of 1 no ECDE classroom and 2 No door pit latrine at Kisiwa primary school in west Nalondo ward | Education & Vocational Training | Ongoing
518 | 45WARDS | 45WARDS | SUPPLY AND DISTRIBUTION OF CERTIFIED MAIZE SEED TO VULNARABLE FARMERS | AGRICULTURE/IRRIGATION | SUPPLIED
519 | 45WARDS | 45WARDS | SUPPLY AND DISTRIBUTION OF PLANTING FERTILIZER TO VULNARABLE FARMERS | AGRICULTURE/IRRIGATION | SUPPLIED
520 | 45WARDS | 45WARDS | SUPPLY AND DISTRIBUTION OF TOP DRESSING FERTILIZER TO VULNARABLE FARMERS | AGRICULTURE/IRRIGATION | SUPPLIED
521 | KAPKATENY |  | PROPOSED CONSTRUCTION OF FENCE AND GATE | Co-operatives | Ongoing
522 | Ndalu/Tabani |  | PROPOSED RENOVATION WORKS OF NADAFA MILK COOLER PLANT | CO-OPERATIVES | Ongoing
523 | Ndalu/Tabani |  | SUPPLY AND DELIVERY OF 1NO. MILK COOLER | CO-OPERATIVES | Yet to be supplied
524 | Bumula |  | Proposed Construction of musiya-wamuteke 2*4 box culvert on khayo river in bumula ward | Roads & Infrastructure | Awarded
525 | Ndalu/Tabani | Matisi, Machakha, Mitoto, Birunda and Milimani primary schools | The proposed consruction of 1no ECDE classroom at Matisi,Machakha,Mitoto,Birunda and Milimani primary schools in Tongaren ward | Education & Vocational Training | Complete and in use
526 | Bumula | Bumula | Proposed completion works construction of septic tank at bumula subcounty hospital | Health & Sanitation | complete
527 | Matulo | Matulo | Completion of ICU/renal unit at webuye sub-county hospital | Health & Sanitation | Ongoing
528 | Bukembe East | Navakholo market | Installation of 2No 12M solar lights | Trade & Industrialization | Site handed over
529 | Kimilili | Paspalam | Construction works of 12 NO. Doors exhastable pit latrine, 1 no door exhaustable pit latrine and urinal for teachers at paspalam ecde in bungoma county | Health & Sanitation | site handed over
530 | Ndalu/Tabani | Ndalu and muliro | Installation of 3No 12M Solar floodlights | Trade & Industrialization | Ongoing
531 | East Sang'alo |  | Periodic maintanance of Manga'le-Mayunga-Nyange road | Roads & Infrastructure
532 | Mihuu | Sipala | Periodic maintananace of Mwinami road 2km | Roads & Infrastructure | Complete
533 | Maraka | Sango pefa Primary | Proposed Construction works for 1 no ECDE Classroom and 3 no door pit latrine at Sango Pefa Primary school in Maraka ward | Education & Vocational Training | Complete
534 | South Bukusu | Lukhuna ECDE | Proposed Construction Works for 4no door Pit Latrine at Lukhuna ECDE in South Bukusu ward | Education & Vocational Training | Complete
535 | South Bukusu | Muanda primary | Proposed Construction Works for 1no ECDE Classroom at Muanda primary School in South Bukusu ward | Education & Vocational Training | Complete
536 | Malakisi Kulisiru | Namawanga,Lutaso,Namunyu,Butonge and Bukokholo primary | Proposed Renovation works for of 1 no ECDE Classrooms at Namawanga, Lutaso, Namunyu Butonge and Bukokholo primary School in Malakisi Kulisiru ward | Education & Vocational Training | Complete
537 | Tongaren | Kikwamet primary | Proposed Construction works for 1 no ECDE Classroom and 3no. Door pit latrine at Kikwamet Primary School in Tongaren Ward | Education & Vocational Training | Complete
538 | Kibingei | Khwiroro,Siuna,Kibingei FYM and Kibingei RC primary school in Kibingei ward | Proposed Renovation works for 1 no ECDE Classrooms at Khwiroro, Siuna, Kibingei FYM and Kibingei RC Primary School in Kibingei ward | Education & Vocational Training | Complete
539 | East Sang'alo | Nabutola and sango primary | Proposed Completion works for 1 no ECDE Classrooms and 2NO door Pit latrine at Nabutola and Sango Primary Schools in East Sang'alo ward | Education & Vocational Training | Complete
540 | Kimilili | Ngoli,Bituyu,Khamulati,Punda Misikhu main and Sango primary schools | Proposed Renovation works for 1 no ECDE Classrooms at Ng'oli, Bituyu,Khamulati,Punda Misikhu main, and Sango Primary School in Kimilili ward | Education & Vocational Training | Complete
541 | Elgon | Bugaa primary school | Erection end completion of 1 no ECDE classroom and 2 no door pit latrine at Bugaa primary school in Elgon ward | Education & Vocational Training | Complete
542 | Cheptais | Namatotoa primary school | Proposed construction works for 1 no ECDE classroom at Namatotoa primary school in Cheptais ward | Education & Vocational Training | Yet to start
543 | Bokoli | Chebini Pefa primary school | Construction of 1 no ECDE classroom at Chebini Pefa primary school in Bokoli ward | Education & Vocational Training | Ongoing
544 | Khalaba | Muteremko VTC | The proposed Renovation Works and Land scaping in Muteremko VTC and Tilling of Kanduyi DEB | Education & Vocational Training | Complete
545 | Milima | Hafo land and ICFEM | Proposed Construction works for 1 no ECDE Classroom at Hafo Land ICFEM Primary School in Milima Ward | Education & Vocational Training | Ongoing
546 | Bukembe East | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Bukembe East ward | Education & Vocational Training | Delivered
547 | Chesikaki | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Chesikaki ward | Education & Vocational Training | Delivered
548 | Khasoko | All ECDE centres | Equipping of 10 ECDE Classrooms with Plastic Chairs for ECDE Learners ,10 Tables and 20 Chairs for Teachers in Khasoko ward | Education & Vocational Training | Delivered
549 | Kimaeti | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Kimaeti ward | Education & Vocational Training | Delivered
550 | Misikhu | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Misikhu ward | Education & Vocational Training | Delivered
551 | Naitiri Kabuyefwe | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Naitiri Kabuyefwe ward | Education & Vocational Training | Delivered
552 | Namwela | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Namwela ward | Education & Vocational Training | Delivered
553 | Ndivisi | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Ndivisi ward | Education & Vocational Training | Delivered
554 | West Nalondo | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in West Nalondo ward | Education & Vocational Training | Delivered
555 | Matulo | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Matulo ward | Education & Vocational Training | Delivered
556 | Kamukuywa | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Kamukuywa ward | Education & Vocational Training | Delivered
557 | Ndalu/Tabani | All ECDE centres | Supply and delivery of no. 5000Ltrs water Tanks Equipping of ECDE Classrooms with Plastic Chairs in Ndalu Tabani ward | Education & Vocational Training | Delivered
558 | Luuya Bwake | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Luuya Bwake ward | Education & Vocational Training | Delivered
559 | Sitikho | All ECDE centres | Equipping of ECDE Classrooms with Plastic Chairs in Sitikho ward | Education & Vocational Training | Delivered
560 | WEST BUKUSU | All ECDE centres | Supply and delivery of ECDE plastic chairs for learners in West Bukusu ward | Education & Vocational Training | Delivered
561 | BOKOLI | All ECDE centres | Supply and delivery of ECDE plastic chairs for learners in Bokoli ward | Education & Vocational Training | Delivered
562 | MAENI | All ECDE centres | Supply and delivery of ECDE plastic chairs for learners in Maeni ward | Education & Vocational Training | Delivered
563 | Bukembe West | All ECDE centres | Supply and delivery of equipments for resource center in Bukembe West ward | Education & Vocational Training | Delivered
564 | LWANDANYI | All ECDE centres | Supply and delivery of tools and equipment for Lwandanyi ward | Education & Vocational Training | Delivered
565 | MBAKALO | Naitiri and Musembe VTCs | Supply and delivery of tools and equipment at Naitiri and Musembe VTC in Mbakalo ward | Education & Vocational Training | Delivered
566 | West Sang'alo | All ECDE centres | Supply and delivery of ECDE plastic chairs for learners in West Sang’alo ward | Education & Vocational Training | Delivered
567 | Township | Moi primary | Supply and delivery of building materials for Moi primary and 15 no tanks across the ward in Township ward | Education & Vocational Training | Delivered
568 | Mukuyuni | All ECDE centres | Supply and delivery of ECDE plastic chairs for learners in Mukuyuni ward | Education & Vocational Training | Delivered
569 | Mihuu | All ECDE centres | Supply and delivery of ECDE plastic chairs for learners in Mihuu ward | Education & Vocational Training | Delivered

## Sheet3
ydtyddfgh
lkhugugkgg
| WARD | LOCATION | NAME OF PROJECT | SECTOR | CONTRACTOR DETAILS | ALLOCATION | CONTRACT SUM | PROJECT STATUS | REMARKS
1 | Bokoli | Sirwa | Upgrading and piping of Sirwa borehole | Water & Natural Resources | M/S Albywood Agencies Limited | 2370000 | 3780185 | Awarded | WBP
2 | Bokoli |  | Drilling of Monyofwe Baptist church borehole | Water & Natural Resources | M/S Albywood Agencies Limited | 1480000 |  | Awarded | WBP
3 | Bokoli | Baptist church | Renovation of outpatient wing and completion of maternity wing in Machakha dispensary | Health & Sanitation | N/A | 800000 |  | To be retendered | WBP
4 | Bokoli | Machakha dispensary | Completion of maternity wing in Milani Dispensary | Health & Sanitation |  | 0 |  | At Evaluation stage | WBP
5 | Bokoli | Milani Dispensary | Completion of Bokoli sub county hospital theater | Health & Sanitation |  |  |  | At Evaluation stage | WBP
6 | Bokoli | Bokoli | Purchase of generator for power back up at Bokoli sub county hospital | Health & Sanitation |  | 0 |  | At Evaluation stage | WBP
7 | Bokoli | Mahanga Market | Openning ,Grading and Gravelling of Mahanga market- Sichei river road | Roads & Infrastructure | Ms Squina Investments & Supplies Ltd | 3600000 | 3452615.47 | At Procurement | WBP
8 | Bokoli | Kasembeli Watila Road | Periodic maintenance of Wafula Mukhebo- Kasembeli Watila road | Roads & Infrastructure | Bitro Construction Ltd | 3600000 | 10778026 | At Procurement | WBP
9 | Bokoli | Bruno road | Periodic maintenance of Kuywa-Lukuku-Bruno road | Roads & Infrastructure | Bitro Construction Ltd | 2700000 |  | At Procurement | WBP
10 | Bokoli | Bokoli Rc | Grading and gravelling of Wanyonyi- Mukhale- Kanuti- Moyokwe- Ben Kapten- Bokoli RC school | Roads & Infrastructure | Bitro Construction Ltd | 4500000 |  | At Procurement | WBP
11 | Bukembe East | Bunana | Periodic Maintenance of Martin Sindani Road | Roads & Infrastructure | N/A | 4500000 |  | Procurement stage | WBP
12 | Bukembe East | Misanga | Opening,grading and gravelling of Nyaranga Road | Roads & Infrastructure | N/A | 4500000 |  | Procurement stage | WBP
13 | Bukembe East | Tembelela | Opening grading and gravelling of Makunjo Road | Roads & Infrastructure | Ms Before Seven consulting Ltd | 3600000 | 3486251.47 | Ongoing | WBP
14 | Bukembe East | Tembelela | Drilling of borehole and solarization at BunanaVillage | Water & Natural Resources | M/S Jorajoh Ventures | 2880000 | 3188840 | Awarded | WBP
15 | Bukembe East | Bunana | Drilling of borehole and insolarization at Sipala Market | Water & Natural Resources | M/S Vitcy Company Limited | 2880000 | 2856732 | Awarded | WBP
| Bukembe East | Sudi/Sipala | Installation of high mast solar powred lights at Navakholo Market | Water & Natural Resources | Dutron Ltd | 2700000 | 2434726 | Awarded | WBP
16 | Bukembe East | Navakholo Market | Market lights at Kongoli Market | Trade & Industrialization | West link Ltd | 1800000 | 1543600 | Awarded | WBP
17 | Bukembe East | Kongoli | Installation of street lights at Misanga market lights | Trade & Industrialization | West link Ltd |  |  | At Award Stage | WBP
18 | Bukembe East | across the ward | Purchase and supply of dairy cows to farmers across the Ward | Agriculture, Livestock & Fisheries | Makheneidher ltd | 1270000 | 1270000 | supplied | WBP
19 | Bukembe East | Sudi/Misanga/tembelela/Kongoli/Bukembe | Purchase and supply of dairy goats across the ward | Agriculture, Livestock & Fisheries |  | 1540000 |  | At Award Stage | WBP
20 | Bukembe west | Kisuluni | Periodic maintenance of Maina Chengasia road | Roads & Infrastructure | N/A | 15300000 |  | Procurement stage | WBP | Framework contract
21 | Bukembe west | Ekitale/kisuluni | Periodic maintenance of Wakhisi road | Roads & Infrastructure | N/A |  |  | Procurement stage | WBP
22 | Bukembe west | Sichekereni/Ekitale | Periodic maintenance of Toko- Sichekereni- Mufuti road | Roads & Infrastructure | N/A |  |  | Procurement stage | WBP
23 | Bukembe west | Khaoya/Mutayi | Periodic maintenanceof Kanisa mbili- Chefunea- Makokha- MCA road | Roads & Infrastructure | N/A |  |  | Procurement stage | WBP
24 | Bukembe west | Chemche/Ekitale | Periodic maintenance of Chemche primary- Rodesha road | Roads & Infrastructure | N/A |  |  | Procurement stage | WBP
25 | Bukembe west | Ekitale | Periodic maintenance of Nachango- Mufuti road | Roads & Infrastructure | N/A |  |  | Procurement stage | WBP
26 | Bukembe west | Muyai/Khaoya | Periodic maintenance of SDA Church- Sibi- Misiko road | Roads & Infrastructure | N/A |  |  | Procurement stage | WBP
27 | Bukembe west | Nalutiri/Ndengelwa | Periodic maintenance of Ndengelwa primary - Misiko road | Roads & Infrastructure | N/A |  |  | Procurement stage | WBP
28 | Bukembe west | Nalutiri/Ndengelwa | Equipping of Bukembe west dairy cooperative sacco water project to include Installation of Hybrid pump, Solar system, Elevation of 12M high pressed steel tank, Extension of water pipeline up to 3kms, Construction of 3 water points and construction of 1 water kiosk | Water & Natural Resources | M/S Gresea Holdings Limited | 3000000 | 2950344 | Awarded | WBP
29 | Bukembe west | Bukembe West Cooperative | Construction of maternity wing at Namirembe dispensary | Health & Sanitation | N/A | 3000000 |  | At Opinion Stage | WBP
30 | Bukembe west | kisuluni, ekitale,muyai, khaoya & nalutiri | Supply and delivery of 10,000 grafted avocado seedling to farmers | Agriculture, Livestock & Fisheries | Lincolin Group Contractors ltd | 4300000 | 4099750 | Supplied awaiting payment | WBP
31 | Bukembe West | Kisuluni/Ekitale/Muyai/Khaoya/Nalutiri | Purchase of assorted sporting items | Youth & Sports | Swanstorm International Ltd | 900000 | 897204 | Awarded | WBP
32 | Bumula | Kisuluni/Ekitale/Muyai/Khaoya/Nalutiri | Protection of 5no water springs watamba kasi, Lutaso, Yakobo, Mukinga Kachala and wekesa mlima | Water & Natural Resources | M/S Sky End Investment Ltd | 1800000 | 1227860 | Awarded | WBP
33 | Bumula | watamba kasi, Lutaso, Yakobo, Mukinga Kachala and wekesa mlima | Drilling and equipping of Mukuyuni primary and Musia boreholes | Water & Natural Resources | M/S Qualmax Property Investments Company | 3600000 |  | Awarded | WBP